## % Progress
Milestone | Edition 66
| Total Slabs (includes mumty slabs, machine room slabs, mezzanine floors of penthouse) | Achieved Slabs | Achieved %
Bulk Excavation | _ |  | 99%
Local Excavation |  |  | 70%
PCC | _ |  | 70%
Tower Foundation/Raft | 6 | 6 | 100%
Retaining Wall | _ |  | 30%
3rd basement Floor Slab | 6 | 6 | 100%
2nd Basement Floor Slab | 6 | 6 | 100%
1st Basement Floor Slab | 6 | 6 | 100%
Ground Slab | 6 | 6 | 100%
1st Floor Slab | 6 | 6 | 100%
2nd Floor Slab | 6 | 6 | 100%
3rd Floor Slab | 6 | 6 | 100%
4th Floor Slab | 6 | 6 | 100%
5th Floor Slab | 6 | 6 | 100%
6th Floor Slab | 6 | 6 | 100%
7th Floor Slab | 6 | 6 | 100%
8th Floor Slab | 6 | 6 | 100%
9th Floor Slab | 6 | 6 | 100%
10th Floor Slab | 6 | 6 | 100%
11th Floor Slab | 6 | 5 | 83.33%
12th Floor Slab | 6 | 4 | 66.67%
13th Floor Slab | 6 | 3 | 50%
14th Floor Slab | 6 | 2 | 33.33%
15th Floor Slab | 6 | 2 | 33.33%
16th Floor Slab | 6 | 1 | 16.67%
17th Floor Slab | 6
18th Floor Slab | 6
19th Floor Slab | 6
20th Floor Slab | 6
21st Floor Slab | 6
22nd Floor Slab | 6
23rd Floor Slab | 6
24th Floor Slab | 6
25th Floor Slab | 6
26th Floor Slab | 6
27th Floor Slab | 6
28th Floor Slab | 6
29th Floor Slab | 6
30th Floor Slab | 6
31st Floor Slab | 6
32nd Floor Slab | 6
33rd Floor Slab | 6
34th Floor Slab | 6
35th Floor Slab | 6
36th Floor Slab | 6
37th Floor Slab | 6
38th Floor Slab | 6
39th Floor Slab | 6
40th Floor Slab | 6
41st Floor Slab | 2
Terrace Floor Slab | 6
Mummty | 6
Machine Room | 6
Total | 290 | 107

## 01.06.26 Revised
THE EDITION GROUP HOUSING SEC 66
START DATE | No. of days | END DATE |  | Structure Schedule_66
2024-08-07 | 1285 | 2028-02-13 |  | 42.1311
Tower 6 |  |  |  | Tower 5 |  |  |  | Tower 1 |  |  |  | Tower 2 |  |  |  | Tower 3 |  |  |  | Tower 4
| Actual /Anticipated Start | No. of days | Actual /Anticipated Finish |  | Actual /Anticipated Start | No. of days | Actual /Anticipated Finish |  | Actual /Anticipated Start | No. of days | Actual /Anticipated Finish |  | Actual /Anticipated Start | No. of days | Actual /Anticipated Finish |  | Actual /Anticipated Start | No. of days | Actual /Anticipated Finish |  | Actual /Anticipated Start | No. of days | Actual /Anticipated Finish
Surface Levelling & Dressing, Raft | 2024-08-07 | 75 | 2024-10-20 | Surface Levelling & Dressing, Raft | 2024-09-26 | 56 | 2024-11-20 | Surface Levelling & Dressing, Raft | 2024-10-10 | 83 | 2024-12-31 | Surface Levelling & Dressing, Raft | 2024-10-17 | 90 | 2025-01-14 | Surface Levelling & Dressing, Raft | 2024-10-24 | 117 | 2025-02-17 | Surface Levelling & Dressing, Raft | 2024-10-31 | 105 | 2025-02-12
Basement 3 | 2024-10-21 | 114 | 2025-02-11 | Basement 3 | 2024-11-21 | 81 | 2025-02-09 | Basement 3 | 2024-12-07 | 80 | 2025-02-24 | Basement 3 | 2024-12-16 | 80 | 2025-03-05 | Basement 3 | 2025-02-18 | 57 | 2025-04-15 | Basement 3 | 2025-02-13 | 52 | 2025-04-05
Basement 2 | 2025-02-12 | 44 | 2025-03-27 | Basement 2 | 2025-02-10 | 25 | 2025-03-06 | Basement 2 | 2025-02-13 | 51 | 2025-04-04 | Basement 2 | 2025-03-14 | 37 | 2025-04-19 | Basement 2 | 2025-03-23 | 70 | 2025-05-31 | Basement 2 | 2025-04-05 | 60 | 2025-06-03
Basement 1 | 2025-03-27 | 35 | 2025-04-30 | Basement 1 | 2025-03-06 | 34 | 2025-04-08 | Basement 1 | 2025-04-03 | 41 | 2025-05-13 | Basement 1 | 2025-04-19 | 44 | 2025-06-01 | Basement 1 | 2025-05-31 | 51 | 2025-07-21 | Basement 1 | 2025-06-03 | 56 | 2025-07-29
Stilt Floor | 2025-04-30 | 78 | 2025-07-17 | Stilt Floor | 2025-04-09 | 45 | 2025-05-23 | Stilt Floor | 2025-05-13 | 77 | 2025-07-29 | Stilt Floor | 2025-06-01 | 85 | 2025-08-25 | Stilt Floor | 2025-07-21 | 69 | 2025-09-28 | Stilt Floor | 2025-07-29 | 63 | 2025-09-30
1st Floor | 2025-07-17 | 75 | 2025-09-30 | 1st Floor | 2025-05-23 | 100 | 2025-08-31 | 1st Floor | 2025-07-29 | 74 | 2025-10-11 | 1st Floor | 2025-08-25 | 64 | 2025-10-28 | 1st Floor | 2025-09-28 | 65 | 2025-12-02 | 1st Floor | 2025-09-30 | 73 | 2025-12-12
2nd Floor | 2025-09-30 | 47 | 2025-11-21 | 2nd Floor | 2025-08-31 | 60 | 2025-10-04 | 2nd Floor | 2025-10-11 | 43 | 2025-11-23 | 2nd Floor | 2025-10-28 | 35 | 2025-12-02 | 2nd Floor | 2025-12-02 | 40 | 2026-01-11 | 2nd Floor | 2025-12-12 | 29 | 2026-01-10
3rd Floor | 2025-11-21 | 21 | 2025-12-12 | 3rd Floor | 2025-10-04 | 24 | 2025-10-28 | 3rd Floor | 2025-11-23 | 15 | 2025-12-08 | 3rd Floor | 2025-12-02 | 24 | 2025-12-26 | 3rd Floor | 2026-01-11 | 20 | 2026-01-31 | 3rd Floor | 2026-01-10 | 21 | 2026-01-31
4th Floor | 2025-12-12 | 24 | 2026-01-05 | 4th Floor | 2025-10-28 | 25 | 2025-11-22 | 4th Floor | 2025-12-08 | 22 | 2025-12-30 | 4th Floor | 2025-12-26 | 14 | 2026-01-09 | 4th Floor | 2026-01-31 | 14 | 2026-02-14 | 4th Floor | 2026-01-31 | 15 | 2026-02-15
5th Floor | 2026-01-05 | 14 | 2026-01-19 | 5th Floor | 2025-11-22 | 20 | 2025-12-12 | 5th Floor | 2025-12-30 | 18 | 2026-01-17 | 5th Floor | 2026-01-09 | 13 | 2026-01-22 | 5th Floor | 2026-02-14 | 14 | 2026-02-28 | 5th Floor | 2026-02-15 | 13 | 2026-02-28
6th Floor | 2026-01-19 | 12 | 2026-01-31 | 6th Floor | 2025-12-12 | 22 | 2026-01-03 | 6th Floor | 2026-01-17 | 14 | 2026-01-31 | 6th Floor | 2026-01-22 | 14 | 2026-02-05 | 6th Floor | 2026-02-28 | 22 | 2026-03-22 | 6th Floor | 2026-02-28 | 18 | 2026-03-18
7th Floor | 2026-01-31 | 14 | 2026-02-14 | 7th Floor | 2026-01-03 | 14 | 2026-01-17 | 7th Floor | 2026-01-31 | 13 | 2026-02-13 | 7th Floor | 2026-02-05 | 15 | 2026-02-20 | 7th Floor | 2026-03-22 | 14 | 2026-04-05 | 7th Floor | 2026-03-18 | 13 | 2026-03-31
8th Floor | 2026-02-14 | 12 | 2026-02-26 | 8th Floor | 2026-01-17 | 14 | 2026-01-31 | 8th Floor | 2026-02-13 | 15 | 2026-02-28 | 8th Floor | 2026-02-20 | 18 | 2026-03-10 | 8th Floor | 2026-04-05 | 15 | 2026-04-20 | 8th Floor | 2026-03-31 | 15 | 2026-04-15
9th Floor | 2026-02-26 | 13 | 2026-03-11 | 9th Floor | 2026-01-31 | 13 | 2026-02-13 | 9th Floor | 2026-02-28 | 19 | 2026-03-19 | 9th Floor | 2026-03-10 | 17 | 2026-03-27 | 9th Floor | 2026-04-20 | 13 | 2026-05-03 | 9th Floor | 2026-04-15 | 13 | 2026-04-28
10th Floor | 2026-03-11 | 11 | 2026-03-22 | 10th Floor | 2026-02-13 | 13 | 2026-02-26 | 10th Floor | 2026-03-19 | 12 | 2026-03-31 | 10th Floor | 2026-03-27 | 17 | 2026-04-13 | 10th Floor | 2026-05-03 | 28 | 2026-05-31 | 10th Floor | 2026-04-28 | 13 | 2026-05-11
11th Floor | 2026-03-22 | 9 | 2026-03-31 | 11th Floor | 2026-02-26 | 15 | 2026-03-13 | 11th Floor | 2026-03-31 | 20 | 2026-04-20 | 11th Floor | 2026-04-13 | 17 | 2026-04-30 | 11th Floor | 2026-05-31 | 12 | 2026-06-12 | 11th Floor | 2026-05-11 | 20 | 2026-05-31
12th Floor | 2026-03-31 | 13 | 2026-04-13 | 12th Floor | 2026-03-13 | 15 | 2026-03-28 | 12th Floor | 2026-04-20 | 12 | 2026-05-02 | 12th Floor | 2026-04-30 | 24 | 2026-05-24 | 12th Floor | 2026-06-12 | 12 | 2026-06-24 | 12th Floor | 2026-05-31 | 12 | 2026-06-12
13th Floor | 2026-04-13 | 12 | 2026-04-25 | 13th Floor | 2026-03-28 | 13 | 2026-04-10 | 13th Floor | 2026-05-02 | 29 | 2026-05-31 | 13th Floor | 2026-05-24 | 13 | 2026-06-06 | 13th Floor | 2026-06-24 | 12 | 2026-07-06 | 13th Floor | 2026-06-12 | 12 | 2026-06-24
14th Floor | 2026-04-25 | 15 | 2026-05-10 | 14th Floor | 2026-04-10 | 11 | 2026-04-21 | 14th Floor | 2026-05-31 | 13 | 2026-06-13 | 14th Floor | 2026-06-06 | 12 | 2026-06-18 | 14th Floor | 2026-07-06 | 12 | 2026-07-18 | 14th Floor | 2026-06-24 | 12 | 2026-07-06
15th Floor | 2026-05-10 | 18 | 2026-05-28 | 15th Floor | 2026-04-21 | 16 | 2026-05-07 | 15th Floor | 2026-06-13 | 12 | 2026-06-25 | 15th Floor | 2026-06-18 | 12 | 2026-06-30 | 15th Floor | 2026-07-18 | 12 | 2026-07-30 | 15th Floor | 2026-07-06 | 12 | 2026-07-18
16th Floor | 2026-05-28 | 13 | 2026-06-10 | 16th Floor | 2026-05-07 | 17 | 2026-05-24 | 16th Floor | 2026-06-25 | 12 | 2026-07-07 | 16th Floor | 2026-06-30 | 12 | 2026-07-12 | 16th Floor | 2026-07-30 | 12 | 2026-08-11 | 16th Floor | 2026-07-18 | 12 | 2026-07-30
17th Floor | 2026-06-10 | 13 | 2026-06-23 | 17th Floor | 2026-05-24 | 13 | 2026-06-06 | 17th Floor | 2026-07-07 | 12 | 2026-07-19 | 17th Floor | 2026-07-12 | 12 | 2026-07-24 | 17th Floor | 2026-08-11 | 12 | 2026-08-23 | 17th Floor | 2026-07-30 | 12 | 2026-08-11
18th Floor | 2026-06-23 | 14 | 2026-07-07 | 18th Floor | 2026-06-06 | 14 | 2026-06-20 | 18th Floor | 2026-07-19 | 14 | 2026-08-02 | 18th Floor | 2026-07-24 | 12 | 2026-08-05 | 18th Floor | 2026-08-23 | 12 | 2026-09-04 | 18th Floor | 2026-08-11 | 12 | 2026-08-23
19th Floor | 2026-07-07 | 13 | 2026-07-20 | 19th Floor | 2026-06-20 | 13 | 2026-07-03 | 19th Floor | 2026-08-02 | 12 | 2026-08-14 | 19th Floor | 2026-08-05 | 12 | 2026-08-17 | 19th Floor | 2026-09-04 | 12 | 2026-09-16 | 19th Floor | 2026-08-23 | 12 | 2026-09-04
20th Floor | 2026-07-20 | 13 | 2026-08-02 | 20th Floor | 2026-07-03 | 14 | 2026-07-17 | 20th Floor | 2026-08-14 | 12 | 2026-08-26 | 20th Floor | 2026-08-17 | 12 | 2026-08-29 | 20th Floor | 2026-09-16 | 12 | 2026-09-28 | 20th Floor | 2026-09-04 | 12 | 2026-09-16
21st Floor | 2026-08-02 | 13 | 2026-08-15 | 21st Floor | 2026-07-17 | 14 | 2026-07-31 | 21st Floor | 2026-08-26 | 12 | 2026-09-07 | 21st Floor | 2026-08-29 | 12 | 2026-09-10 | 21st Floor | 2026-09-28 | 11 | 2026-10-09 | 21st Floor | 2026-09-16 | 12 | 2026-09-28
22nd Floor | 2026-08-15 | 13 | 2026-08-28 | 22nd Floor | 2026-07-31 | 14 | 2026-08-14 | 22nd Floor | 2026-09-07 | 12 | 2026-09-19 | 22nd Floor | 2026-09-10 | 12 | 2026-09-22 | 22nd Floor | 2026-10-09 | 11 | 2026-10-20 | 22nd Floor | 2026-09-28 | 12 | 2026-10-10
23rd Floor | 2026-08-28 | 13 | 2026-09-10 | 23rd Floor | 2026-08-14 | 14 | 2026-08-28 | 23rd Floor | 2026-09-19 | 12 | 2026-10-01 | 23rd Floor | 2026-09-22 | 12 | 2026-10-04 | 23rd Floor | 2026-10-20 | 11 | 2026-10-31 | 23rd Floor | 2026-10-10 | 11 | 2026-10-21
24th Floor | 2026-09-10 | 13 | 2026-09-23 | 24th Floor | 2026-08-28 | 14 | 2026-09-11 | 24th Floor | 2026-10-01 | 12 | 2026-10-13 | 24th Floor | 2026-10-04 | 12 | 2026-10-16 | 24th Floor | 2026-10-31 | 11 | 2026-11-11 | 24th Floor | 2026-10-21 | 11 | 2026-11-01
25th Floor | 2026-09-23 | 13 | 2026-10-06 | 25th Floor | 2026-09-11 | 14 | 2026-09-25 | 25th Floor | 2026-10-13 | 12 | 2026-10-25 | 25th Floor | 2026-10-16 | 12 | 2026-10-28 | 25th Floor | 2026-11-11 | 12 | 2026-11-23 | 25th Floor | 2026-11-01 | 12 | 2026-11-13
26th Floor | 2026-10-06 | 13 | 2026-10-19 | 26th Floor | 2026-09-25 | 14 | 2026-10-09 | 26th Floor | 2026-10-25 | 12 | 2026-11-06 | 26th Floor | 2026-10-28 | 12 | 2026-11-09 | 26th Floor | 2026-11-23 | 11 | 2026-12-04 | 26th Floor | 2026-11-13 | 11 | 2026-11-24
27th Floor | 2026-10-19 | 15 | 2026-11-03 | 27th Floor | 2026-10-09 | 15 | 2026-10-24 | 27th Floor | 2026-11-06 | 13 | 2026-11-19 | 27th Floor | 2026-11-09 | 12 | 2026-11-21 | 27th Floor | 2026-12-04 | 11 | 2026-12-15 | 27th Floor | 2026-11-24 | 11 | 2026-12-05
28th Floor | 2026-11-03 | 13 | 2026-11-16 | 28th Floor | 2026-10-24 | 14 | 2026-11-07 | 28th Floor | 2026-11-19 | 12 | 2026-12-01 | 28th Floor | 2026-11-21 | 12 | 2026-12-03 | 28th Floor | 2026-12-15 | 11 | 2026-12-26 | 28th Floor | 2026-12-05 | 11 | 2026-12-16
29th Floor | 2026-11-16 | 12 | 2026-11-28 | 29th Floor | 2026-11-07 | 13 | 2026-11-20 | 29th Floor | 2026-12-01 | 12 | 2026-12-13 | 29th Floor | 2026-12-03 | 12 | 2026-12-15 | 29th Floor | 2026-12-26 | 11 | 2027-01-06 | 29th Floor | 2026-12-16 | 11 | 2026-12-27
30th Floor | 2026-11-28 | 12 | 2026-12-10 | 30th Floor | 2026-11-20 | 13 | 2026-12-03 | 30th Floor | 2026-12-13 | 12 | 2026-12-25 | 30th Floor | 2026-12-15 | 12 | 2026-12-27 | 30th Floor | 2027-01-06 | 11 | 2027-01-17 | 30th Floor | 2026-12-27 | 11 | 2027-01-07
31st Floor | 2026-12-10 | 12 | 2026-12-22 | 31st Floor | 2026-12-03 | 13 | 2026-12-16 | 31st Floor | 2026-12-25 | 12 | 2027-01-06 | 31st Floor | 2026-12-27 | 12 | 2027-01-08 | 31st Floor | 2027-01-17 | 11 | 2027-01-28 | 31st Floor | 2027-01-07 | 11 | 2027-01-18
32nd Floor | 2026-12-22 | 12 | 2027-01-03 | 32nd Floor | 2026-12-16 | 13 | 2026-12-29 | 32nd Floor | 2027-01-06 | 12 | 2027-01-18 | 32nd Floor | 2027-01-08 | 12 | 2027-01-20 | 32nd Floor | 2027-01-28 | 11 | 2027-02-08 | 32nd Floor | 2027-01-18 | 11 | 2027-01-29
33rd Floor | 2027-01-03 | 12 | 2027-01-15 | 33rd Floor | 2026-12-29 | 13 | 2027-01-11 | 33rd Floor | 2027-01-18 | 12 | 2027-01-30 | 33rd Floor | 2027-01-20 | 12 | 2027-02-01 | 33rd Floor | 2027-02-08 | 11 | 2027-02-19 | 33rd Floor | 2027-01-29 | 11 | 2027-02-09
34th Floor | 2027-01-15 | 12 | 2027-01-27 | 34th Floor | 2027-01-11 | 13 | 2027-01-24 | 34th Floor | 2027-01-30 | 12 | 2027-02-11 | 34th Floor | 2027-02-01 | 12 | 2027-02-13 | 34th Floor | 2027-02-19 | 11 | 2027-03-02 | 34th Floor | 2027-02-09 | 11 | 2027-02-20
35th Floor | 2027-01-27 | 12 | 2027-02-08 | 35th Floor | 2027-01-24 | 13 | 2027-02-06 | 35th Floor | 2027-02-11 | 12 | 2027-02-23 | 35th Floor | 2027-02-13 | 12 | 2027-02-25 | 35th Floor | 2027-03-02 | 11 | 2027-03-13 | 35th Floor | 2027-02-20 | 11 | 2027-03-03
36th Floor | 2027-02-08 | 14 | 2027-02-22 | 36th Floor | 2027-02-06 | 15 | 2027-02-21 | 36th Floor | 2027-02-23 | 12 | 2027-03-07 | 36th Floor | 2027-02-25 | 11 | 2027-03-08 | 36th Floor | 2027-03-13 | 11 | 2027-03-24 | 36th Floor | 2027-03-03 | 11 | 2027-03-14
37th Floor | 2027-02-22 | 12 | 2027-03-06 | 37th Floor | 2027-02-21 | 13 | 2027-03-06 | 37th Floor | 2027-03-07 | 12 | 2027-03-19 | 37th Floor | 2027-03-08 | 11 | 2027-03-19 | 37th Floor | 2027-03-24 | 11 | 2027-04-04 | 37th Floor | 2027-03-14 | 11 | 2027-03-25
38th Floor | 2027-03-06 | 12 | 2027-03-18 | 38th Floor | 2027-03-06 | 12 | 2027-03-18 | 38th Floor | 2027-03-19 | 12 | 2027-03-31 | 38th Floor | 2027-03-19 | 12 | 2027-03-31 | 38th Floor | 2027-04-04 | 11 | 2027-04-15 | 38th Floor | 2027-03-25 | 13 | 2027-04-07
39th Floor | 2027-03-18 | 13 | 2027-03-31 | 39th Floor | 2027-03-18 | 13 | 2027-03-31 | 39th Floor | 2027-03-31 | 14 | 2027-04-14 | 39th Floor | 2027-03-31 | 14 | 2027-04-14 | 39th Floor | 2027-04-15 | 24 | 2027-05-09 | 39th Floor | 2027-04-07 | 24 | 2027-05-01
40th Floor | 2027-03-31 | 14 | 2027-04-14 | 40th Floor | 2027-03-31 | 14 | 2027-04-14 | 40th Floor | 2027-04-14 | 24 | 2027-05-08 | 40th Floor | 2027-04-14 | 24 | 2027-05-08 | 40th Floor | 2027-05-09 | 26 | 2027-06-04 | 40th Floor | 2027-05-01 | 26 | 2027-05-27
41st Floor | 2027-04-14 | 24 | 2027-05-08 | 41st Floor | 2027-04-14 | 24 | 2027-05-08 | Terrace Floor | 2027-05-08 | 22 | 2027-05-30 | Terrace Floor | 2027-05-08 | 22 | 2027-05-30 | Terrace Floor | 2027-06-04 | 45 | 2027-07-19 | Terrace Floor | 2027-05-27 | 45 | 2027-07-11
Terrace Floor | 2027-05-08 | 22 | 2027-05-30 | Terrace Floor | 2027-05-08 | 22 | 2027-05-30 | Block Work | 2026-06-25 | 425 | 2027-08-24 | Block Work | 2026-07-12 | 453 | 2027-10-08 | Block Work | 2026-07-18 | 439 | 2027-09-30 | Block Work | 2026-06-24 | 425 | 2027-08-23
Block Works | 2026-07-07 | 430 | 2027-09-10 | Block Works | 2026-06-17 | 402 | 2027-06-29
Gypsum Plaster/ Plaster Works | 2026-07-15 | 650 | 2028-04-25 | Gypsum Plaster/ Plaster Works | 2026-07-15 | 650 | 2028-04-25 | Gypsum Plaster/ Plaster Works | 2026-07-15 | 650 | 2028-04-25 | Gypsum Plaster/ Plaster Works | 2026-07-15 | 650 | 2028-04-25 | Gypsum Plaster/ Plaster Works | 2026-07-15 | 650 | 2028-04-25 | Gypsum Plaster/ Plaster Works | 2026-07-15 | 650 | 2028-04-25
Tiling Works | 2026-08-29 | 640 | 2028-05-30 | Tiling Works | 2026-08-29 | 640 | 2028-05-30 | Tiling Works | 2026-08-29 | 640 | 2028-05-30 | Tiling Works | 2026-08-29 | 640 | 2028-05-30 | Tiling Works | 2026-08-29 | 640 | 2028-05-30 | Tiling Works | 2026-08-29 | 640 | 2028-05-30
Application of OC | 2028-05-30 |  | 2028-05-30 | Application of OC | 2028-05-30 |  | 2028-05-30 | Application of OC | 2028-05-30 |  | 2028-05-30 | Application of OC | 2028-05-30 |  | 2028-05-30 | Application of OC | 2028-05-30 |  | 2028-05-30 | Application of OC | 2028-05-30 |  | 2028-05-30
Start of Handover | 2028-08-28 |  |  | Start of Handover | 2028-08-28 |  |  | Start of Handover | 2028-08-28 |  |  | Start of Handover | 2028-08-28 |  |  | Start of Handover | 2028-08-28 |  |  | Start of Handover | 2028-08-28
Formulas:
END DATE = [START DATE]+[No. of days]
Actual /Anticipated Start = [Actual /Anticipated Finish, row above]
Actual /Anticipated Start = [No. of days]
Actual /Anticipated Finish = [No. of days]+[Actual /Anticipated Start]
Actual /Anticipated Finish = [END DATE]+[No. of days]
No. of days = [Actual /Anticipated Finish, row above]
No. of days = [No. of days, row above]+8

## Revised CRM milestones
Milestone | Tower 1 | Tower 2 | Tower 3 | Tower 4 | Tower 5 | Tower 6
On Application of Booking | As per customer booking
Within 30 days of Booking less : Booking amount | As per customer booking
Start of Excavation | 2024-02-01 | 2024-02-01 | 2024-02-01 | 2024-02-01 | 2024-01-01 | 2024-01-01
On Completion of Ground floor Slab | 2025-07-01 | 2025-07-01 | 2025-07-01 | 2025-07-01 | 2025-05-01 | 2025-05-01
|  | 2025-08-01 | 2025-09-01 | 2025-09-01 |  | 2025-07-01
On Completion of 5th floor Slab | 2025-11-01 | 2025-11-01 | 2025-12-01 | 2025-12-01 | 2025-10-01 | 2025-10-01
| 2026-01-01 | 2026-02-01 | 2026-03-01 | 2026-03-01 | 2026-12-01 | 2026-01-01
On Completion of 15th floor Slab | 2026-04-01 | 2026-05-01 | 2026-05-01 | 2026-05-01 | 2026-03-01 | 2026-03-01
| 2026-06-25 | 2026-06-30 | 2026-07-30 | 2026-07-18 | 2026-05-07 | 2026-05-28
On Completion of 25th floor Slab | 2026-08-01 | 2026-08-01 | 2026-09-01 | 2026-09-01 | 2026-07-01 | 2026-07-01
| 2026-10-25 | 2026-10-28 | 2026-12-01 | 2026-12-01 | 2026-10-01 | 2026-11-01
Completion Till Below Penthouse
| 2027-03-31 | 2027-03-31 | 2027-04-15 | 2027-04-07 | 2027-03-31 | 2027-03-31
On Completion of Structure | 2027-03-01 | 2027-03-01 | 2027-03-01 | 2027-03-01 | 2027-02-01 | 2027-02-01
| 2027-05-30 | 2027-05-30 | 2027-07-19 | 2027-07-11 | 2027-05-30 | 2027-05-30
On Application of Occupation Certificate | 2027-12-01
2028-05-30
Projected Completion | 0
On Offer of Possession | After OC
Formulas:
Tower 4 = [Tower 3]