## Sheet1
WBS | WBS Description | Profit Center | Business Area | Plant_WBS | Plant Name | Vendor Name | Purchasing Document | Item No. | GL Code | GL Code Description | Document Date | Short Text | UOM | Quantity | Net Price | Ordered Value | Ordered with GST | Delivered Value | Delivered Value with GST | Still to be Delivered Value | Invoiced Value | Invoiced Value with GST | Document Type | Validity Start Date | Validity End Date
RE/0066-CQL-01 | Quality Lab Expenses_Old | 2011 | GR01 | 2011 |  |  |  | 0 | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
RE/0066-CQL-02 | Central Quality Lab 2010_New | 2010 | GR01 | 2010 | SWD Central office-75 | Ametek Instruments India Private Li | 9110000497 | 10 |  |  | 2024-02-28 | OES Spectrometer (Spectrometer Ametek, L | NO | 1 | 2276000 | 2276000 | 2685680 | 2276000 | 2685680 | 0 | 2276000 | 2685680 | ZMAT | 2024-02-28 | 2024-03-28
RE/0066-CQL-02 | Central Quality Lab 2010_New | 2010 | GR01 | 2010 | SWD Central office-75 | Ametek Instruments India Private Li | 9110000497 | 20 |  |  | 2024-02-28 | Argon Gas Cylinder with XL Grade Argon | NO | 2 | 27300 | 54600 | 64428 | 54600 | 64428 | 0 | 54600 | 64428 | ZMAT | 2024-02-28 | 2024-03-28
RE/0066-CQL-02 | Central Quality Lab 2010_New | 2010 | GR01 | 2010 | SWD Central office-75 | Ametek Instruments India Private Li | 9110000497 | 30 |  |  | 2024-02-28 | Double Stage Argon Gas Regulator | NO | 1 | 29400 | 29400 | 34692 | 29400 | 34692 | 0 | 29400 | 34692 | ZMAT | 2024-02-28 | 2024-03-28
RE/0066-CQL-02 | Central Quality Lab 2010_New | 2010 | GR01 | 2010 | SWD Central office-75 | Ametek Instruments India Private Li | 9110000497 | 40 |  |  | 2024-02-28 | High Speed Grinding Machine | NO | 1 | 75000 | 75000 | 88500 | 75000 | 88500 | 0 | 75000 | 88500 | ZMAT | 2024-02-28 | 2024-03-28
RE/0066-CQL-02 | Central Quality Lab 2010_New | 2010 | GR01 | 2010 | SWD Central office-75 | Ametek Instruments India Private Li | 9110000497 | 50 |  |  | 2024-02-28 | Certified Reference Material Samples | NO | 6 | 53883.33 | 323299.98 | 381493.98 | 323299.98 | 381493.98 | 0 | 323299.98 | 381493.98 | ZMAT | 2024-02-28 | 2024-03-28
RE/0066-CQL-02 | Central Quality Lab 2010_New | 2010 | GR01 | 2010 | SWD Central office-75 | Testwel Instruments Company | 9110000621 | 10 |  |  | 2024-07-12 | CRM (OPC, PPC, FLY Ash) Fineness Test , | NO | 1 | 22500 | 22500 | 26550 | 22500 | 26550 | 0 | 22500 | 26548.99 | ZMAT | 2024-05-13 | 2024-06-13
RE/0066-CQL-02 | Central Quality Lab 2010_New | 2010 | GR01 | 2010 | SWD Central office-75 | Testwel Instruments Company | 9110000621 | 20 |  |  | 2024-07-12 | Glass Hydrometer, 0.7-1.0 With calibrati | NO | 1 | 650 | 650 | 767 | 650 | 767 | 0 | 650 | 766.97 | ZMAT | 2024-05-13 | 2024-06-13
RE/0066-CQL-02 | Central Quality Lab 2010_New | 2010 | GR01 | 2010 | SWD Central office-75 | Testwel Instruments Company | 9110000621 | 30 |  |  | 2024-07-12 | Glass Hydrometer, 1.0-1.5 with Calibrati | NO | 1 | 650 | 650 | 767 | 650 | 767 | 0 | 650 | 766.97 | ZMAT | 2024-05-13 | 2024-06-13
RE/0066-CQL-02 | Central Quality Lab 2010_New | 2010 | GR01 | 2010 | SWD Central office-75 | Testwel Instruments Company | 9110000621 | 40 |  |  | 2024-07-12 | Glass Petri Dish, 50 X 17 w/o Calibratio | NO | 4 | 550 | 2200 | 2596 | 2200 | 2596 | 0 | 2200 | 2595.9 | ZMAT | 2024-05-13 | 2024-06-13
RE/0066-CQL-02 | Central Quality Lab 2010_New | 2010 | GR01 | 2010 | SWD Central office-75 | Testwel Instruments Company | 9110000621 | 50 |  |  | 2024-07-12 | Glass Rod 6mm dia x 600mm long w/o Cali | NO | 4 | 100 | 400 | 472 | 400 | 472 | 0 | 400 | 471.98 | ZMAT | 2024-05-13 | 2024-06-13
RE/0066-CQL-02 | Central Quality Lab 2010_New | 2010 | GR01 | 2010 | SWD Central office-75 | Testwel Instruments Company | 9110000621 | 60 |  |  | 2024-07-12 | Sieve Brass Frame 20cm dia x 10mm w/o Ca | NO | 1 | 625 | 625 | 737.5 | 625 | 737.5 | 0 | 625 | 737.97 | ZMAT | 2024-05-13 | 2024-06-13
RE/0066-CQL-02 | Central Quality Lab 2010_New | 2010 | GR01 | 2010 | SWD Central office-75 | Testwel Instruments Company | 9110000621 | 70 |  |  | 2024-07-12 | Sieve Brass Frame 20cm dia x 4.75mm w/o | NO | 1 | 625 | 625 | 737.5 | 625 | 737.5 | 0 | 625 | 737.97 | ZMAT | 2024-05-13 | 2024-06-13
RE/0066-CQL-02 | Central Quality Lab 2010_New | 2010 | GR01 | 2010 | SWD Central office-75 | Testwel Instruments Company | 9110000621 | 80 |  |  | 2024-07-12 | Sieve Brass Frame 20cm dia x 2.36mm w/o | NO | 1 | 625 | 625 | 737.5 | 625 | 737.5 | 0 | 625 | 737.97 | ZMAT | 2024-05-13 | 2024-06-13
RE/0066-CQL-02 | Central Quality Lab 2010_New | 2010 | GR01 | 2010 | SWD Central office-75 | Testwel Instruments Company | 9110000621 | 90 |  |  | 2024-07-12 | Sieve Brass Frame 20cm dia x 2.00mm w/o | NO | 1 | 625 | 625 | 737.5 | 625 | 737.5 | 0 | 625 | 737.97 | ZMAT | 2024-05-13 | 2024-06-13
RE/0066-CQL-02 | Central Quality Lab 2010_New | 2010 | GR01 | 2010 | SWD Central office-75 | Testwel Instruments Company | 9110000621 | 100 |  |  | 2024-07-12 | Sieve Brass Frame 20cm dia x 1.00mm w/o | NO | 1 | 625 | 625 | 737.5 | 625 | 737.5 | 0 | 625 | 737.97 | ZMAT | 2024-05-13 | 2024-06-13
RE/0066-CQL-02 | Central Quality Lab 2010_New | 2010 | GR01 | 2010 | SWD Central office-75 | Testwel Instruments Company | 9110000621 | 110 |  |  | 2024-07-12 | Sieve Brass Frame 20cm dia x 500 microns | NO | 1 | 625 | 625 | 737.5 | 625 | 737.5 | 0 | 625 | 737.97 | ZMAT | 2024-05-13 | 2024-06-13
RE/0066-CQL-02 | Central Quality Lab 2010_New | 2010 | GR01 | 2010 | SWD Central office-75 | Testwel Instruments Company | 9110000621 | 120 |  |  | 2024-07-12 | Sieve G.I. Frame 45cm dia x 80mm w/o Cal | NO | 1 | 550 | 550 | 649 | 550 | 649 | 0 | 550 | 648.98 | ZMAT | 2024-05-13 | 2024-06-13
RE/0066-CQL-02 | Central Quality Lab 2010_New | 2010 | GR01 | 2010 | SWD Central office-75 | Testwel Instruments Company | 9110000621 | 130 |  |  | 2024-07-12 | Sieve G.I. Frame 45cm dia x 75mm w/o Ca | NO | 1 | 550 | 550 | 649 | 550 | 649 | 0 | 550 | 648.98 | ZMAT | 2024-05-13 | 2024-06-13
RE/0066-CQL-02 | Central Quality Lab 2010_New | 2010 | GR01 | 2010 | SWD Central office-75 | Testwel Instruments Company | 9110000621 | 140 |  |  | 2024-07-12 | Sieve G.I. Frame 45cm dia x 63mm w/o Cal | NO | 1 | 550 | 550 | 649 | 550 | 649 | 0 | 550 | 648.98 | ZMAT | 2024-05-13 | 2024-06-13
RE/0066-CQL-02 | Central Quality Lab 2010_New | 2010 | GR01 | 2010 | SWD Central office-75 | Testwel Instruments Company | 9110000621 | 150 |  |  | 2024-07-12 | Sieve G.I. Frame 45cm dia x 53mm w/o Cal | NO | 1 | 550 | 550 | 649 | 550 | 649 | 0 | 550 | 648.98 | ZMAT | 2024-05-13 | 2024-06-13
RE/0066-CQL-02 | Central Quality Lab 2010_New | 2010 | GR01 | 2010 | SWD Central office-75 | Testwel Instruments Company | 9110000621 | 160 |  |  | 2024-07-12 | Sieve G.I. Frame 45cm dia x 50mm w/o Cal | NO | 1 | 550 | 550 | 649 | 550 | 649 | 0 | 550 | 648.98 | ZMAT | 2024-05-13 | 2024-06-13
RE/0066-CQL-02 | Central Quality Lab 2010_New | 2010 | GR01 | 2010 | SWD Central office-75 | Testwel Instruments Company | 9110000621 | 170 |  |  | 2024-07-12 | Sieve G.I. Frame 45cm dia x 45mm w/o Cal | NO | 1 | 550 | 550 | 649 | 550 | 649 | 0 | 550 | 648.98 | ZMAT | 2024-05-13 | 2024-06-13
RE/0066-CQL-02 | Central Quality Lab 2010_New | 2010 | GR01 | 2010 | SWD Central office-75 | Testwel Instruments Company | 9110000621 | 180 |  |  | 2024-07-12 | Sieve G.I. Frame 45cm dia x 37.5mm w/o C | NO | 1 | 550 | 550 | 649 | 550 | 649 | 0 | 550 | 648.98 | ZMAT | 2024-05-13 | 2024-06-13
RE/0066-CQL-02 | Central Quality Lab 2010_New | 2010 | GR01 | 2010 | SWD Central office-75 | Testwel Instruments Company | 9110000621 | 190 |  |  | 2024-07-12 | Sieve G.I. Frame 45cm dia x 26.5mm w/o C | NO | 1 | 550 | 550 | 649 | 550 | 649 | 0 | 550 | 648.98 | ZMAT | 2024-05-13 | 2024-06-13
RE/0066-CQL-02 | Central Quality Lab 2010_New | 2010 | GR01 | 2010 | SWD Central office-75 | Testwel Instruments Company | 9110000621 | 200 |  |  | 2024-07-12 | Sieve G.I. Frame 45cm dia x 25mm w/o Cal | NO | 1 | 550 | 550 | 649 | 550 | 649 | 0 | 550 | 648.98 | ZMAT | 2024-05-13 | 2024-06-13
RE/0066-CQL-02 | Central Quality Lab 2010_New | 2010 | GR01 | 2010 | SWD Central office-75 | Testwel Instruments Company | 9110000621 | 210 |  |  | 2024-07-12 | Sieve G.I. Frame 45cm dia x 22.4mm w/o C | NO | 1 | 550 | 550 | 649 | 550 | 649 | 0 | 550 | 648.98 | ZMAT | 2024-05-13 | 2024-06-13
RE/0066-CQL-02 | Central Quality Lab 2010_New | 2010 | GR01 | 2010 | SWD Central office-75 | Testwel Instruments Company | 9110000621 | 220 |  |  | 2024-07-12 | Sieve G.I. Frame 45cm dia x 19mm w/o Cal | NO | 1 | 550 | 550 | 649 | 550 | 649 | 0 | 550 | 648.98 | ZMAT | 2024-05-13 | 2024-06-13
RE/0066-CQL-02 | Central Quality Lab 2010_New | 2010 | GR01 | 2010 | SWD Central office-75 | Testwel Instruments Company | 9110000621 | 230 |  |  | 2024-07-12 | Sieve G.I. Frame 45cm dia x 13.2mm w/o C | NO | 1 | 550 | 550 | 649 | 550 | 649 | 0 | 550 | 648.98 | ZMAT | 2024-05-13 | 2024-06-13
RE/0066-CQL-02 | Central Quality Lab 2010_New | 2010 | GR01 | 2010 | SWD Central office-75 | Testwel Instruments Company | 9110000621 | 240 |  |  | 2024-07-12 | Sieve G.I. Frame 45cm dia x 11.2mm w/o C | NO | 1 | 550 | 550 | 649 | 550 | 649 | 0 | 550 | 648.98 | ZMAT | 2024-05-13 | 2024-06-13
RE/0066-CQL-02 | Central Quality Lab 2010_New | 2010 | GR01 | 2010 | SWD Central office-75 | Testwel Instruments Company | 9110000621 | 250 |  |  | 2024-07-12 | Sieve G.I. Frame 45cm dia x 9.5mm w/o Ca | NO | 1 | 550 | 550 | 649 | 550 | 649 | 0 | 550 | 648.98 | ZMAT | 2024-05-13 | 2024-06-13
RE/0066-CQL-02 | Central Quality Lab 2010_New | 2010 | GR01 | 2010 | SWD Central office-75 | Testwel Instruments Company | 9110000621 | 260 |  |  | 2024-07-12 | Sieve G.I. Frame 45cm dia x 6.3mm w/o Ca | NO | 1 | 550 | 550 | 649 | 550 | 649 | 0 | 550 | 648.98 | ZMAT | 2024-05-13 | 2024-06-13
RE/0066-CQL-02 | Central Quality Lab 2010_New | 2010 | GR01 | 2010 | SWD Central office-75 | Testwel Instruments Company | 9110000621 | 270 |  |  | 2024-07-12 | Sieve G.I. Frame 45cm dia x 5.6mm w/o Ca | NO | 1 | 550 | 550 | 649 | 550 | 649 | 0 | 550 | 648.98 | ZMAT | 2024-05-13 | 2024-06-13
RE/0066-CQL-02 | Central Quality Lab 2010_New | 2010 | GR01 | 2010 | SWD Central office-75 | Testwel Instruments Company | 9110000621 | 280 |  |  | 2024-07-12 | Sieve G.I. Frame 45cm dia x 4.75mm w/o C | NO | 1 | 550 | 550 | 649 | 550 | 649 | 0 | 550 | 648.98 | ZMAT | 2024-05-13 | 2024-06-13
RE/0066-CQL-02 | Central Quality Lab 2010_New | 2010 | GR01 | 2010 | SWD Central office-75 | Testwel Instruments Company | 9110000621 | 290 |  |  | 2024-07-12 | Sieve G.I. Frame 45cm dia x 2.36mm w/o C | NO | 1 | 550 | 550 | 649 | 550 | 649 | 0 | 550 | 648.98 | ZMAT | 2024-05-13 | 2024-06-13
RE/0066-CQL-02 | Central Quality Lab 2010_New | 2010 | GR01 | 2010 | SWD Central office-75 | Testwel Instruments Company | 9110000621 | 300 |  |  | 2024-07-12 | Sieve Brass Frame 20cm dia x 850 microns | NO | 1 | 625 | 625 | 737.5 | 625 | 737.5 | 0 | 625 | 737.97 | ZMAT | 2024-05-13 | 2024-06-13
RE/0066-CQL-02 | Central Quality Lab 2010_New | 2010 | GR01 | 2010 | SWD Central office-75 | Testwel Instruments Company | 9110000621 | 310 |  |  | 2024-07-12 | Sieve Brass Frame 20cm dia x 600 microns | NO | 1 | 625 | 625 | 737.5 | 625 | 737.5 | 0 | 625 | 737.97 | ZMAT | 2024-05-13 | 2024-06-13
RE/0066-CQL-02 | Central Quality Lab 2010_New | 2010 | GR01 | 2010 | SWD Central office-75 | Testwel Instruments Company | 9110000621 | 320 |  |  | 2024-07-12 | Sieve Brass Frame 20cm dia x 425 microns | NO | 1 | 625 | 625 | 737.5 | 625 | 737.5 | 0 | 625 | 737.97 | ZMAT | 2024-05-13 | 2024-06-13
RE/0066-CQL-02 | Central Quality Lab 2010_New | 2010 | GR01 | 2010 | SWD Central office-75 | Testwel Instruments Company | 9110000621 | 330 |  |  | 2024-07-12 | Sieve Brass Frame 20cm dia x 75 microns | NO | 1 | 725 | 725 | 855.5 | 725 | 855.5 | 0 | 725 | 855.97 | ZMAT | 2024-05-13 | 2024-06-13
RE/0066-CQL-02 | Central Quality Lab 2010_New | 2010 | GR01 | 2010 | SWD Central office-75 | Testwel Instruments Company | 9110000621 | 340 |  |  | 2024-07-12 | Sieve G.I. Frame 30cm dia x 31.5mm w/o C | NO | 1 | 550 | 550 | 649 | 550 | 649 | 0 | 550 | 648.98 | ZMAT | 2024-05-13 | 2024-06-13
RE/0066-CQL-02 | Central Quality Lab 2010_New | 2010 | GR01 | 2010 | SWD Central office-75 | Testwel Instruments Company | 9110000621 | 350 |  |  | 2024-07-12 | Sieve G.I. Frame 30cm dia x 3.35mm w/o C | NO | 1 | 550 | 550 | 649 | 550 | 649 | 0 | 550 | 648.98 | ZMAT | 2024-05-13 | 2024-06-13
RE/0066-CQL-02 | Central Quality Lab 2010_New | 2010 | GR01 | 2010 | SWD Central office-75 | Testwel Instruments Company | 9110000621 | 360 |  |  | 2024-07-12 | Sieve Brass Frame 20cm dia x 1.70mm w/o | NO | 1 | 625 | 625 | 737.5 | 625 | 737.5 | 0 | 625 | 737.97 | ZMAT | 2024-05-13 | 2024-06-13
RE/0066-CQL-02 | Central Quality Lab 2010_New | 2010 | GR01 | 2010 | SWD Central office-75 | Testwel Instruments Company | 9110000621 | 370 |  |  | 2024-07-12 | Pan and Cover for 45cm dia sieves w/o Ca | NO | 1 | 550 | 550 | 649 | 550 | 649 | 0 | 550 | 648.98 | ZMAT | 2024-05-13 | 2024-06-13
RE/0066-CQL-02 | Central Quality Lab 2010_New | 2010 | GR01 | 2010 | SWD Central office-75 | Testwel Instruments Company | 9110000621 | 380 |  |  | 2024-07-12 | Filter Paper Discs, Set of 100 numbers f | NO | 1 | 900 | 900 | 1062 | 900 | 1062 | 0 | 900 | 1061.96 | ZMAT | 2024-05-13 | 2024-06-13
RE/0066-CQL-02 | Central Quality Lab 2010_New | 2010 | GR01 | 2010 | SWD Central office-75 | Testwel Instruments Company | 9110000621 | 390 |  |  | 2024-07-12 | Hyderated Lime CALCIUM HYDROXIDE special | NO | 15 | 300 | 4500 | 5310 | 0 | 0 | 4500 | 0 | 0 | ZMAT | 2024-05-13 | 2024-06-13
RE/0066-CQL-02 | Central Quality Lab 2010_New | 2010 | GR01 | 2010 | SWD Central office-75 | Testwel Instruments Company | 9110000621 | 400 |  |  | 2024-07-12 | Stainless Steel Spatula with wooden Hand | NO | 2 | 100 | 200 | 236 | 200 | 236 | 0 | 200 | 235.99 | ZMAT | 2024-05-13 | 2024-06-13
RE/0066-CQL-02 | Central Quality Lab 2010_New | 2010 | GR01 | 2010 | SWD Central office-75 | Testwel Instruments Company | 9110000621 | 410 |  |  | 2024-07-12 | Stainless Steel Spatula with wooden Hand | NO | 2 | 125 | 250 | 295 | 250 | 295 | 0 | 250 | 294.99 | ZMAT | 2024-05-13 | 2024-06-13
RE/0066-CQL-02 | Central Quality Lab 2010_New | 2010 | GR01 | 2010 | SWD Central office-75 | Testwel Instruments Company | 9110000621 | 420 |  |  | 2024-07-12 | Stainless Steel Spatula with wooden Hand | NO | 2 | 150 | 300 | 354 | 300 | 354 | 0 | 300 | 353.99 | ZMAT | 2024-05-13 | 2024-06-13
RE/0066-CQL-02 | Central Quality Lab 2010_New | 2010 | GR01 | 2010 | SWD Central office-75 | Testwel Instruments Company | 9110000621 | 430 |  |  | 2024-07-12 | Stainless Steel Spatula with wooden Hand | NO | 2 | 250 | 500 | 590 | 500 | 590 | 0 | 500 | 589.98 | ZMAT | 2024-05-13 | 2024-06-13
RE/0066-CQL-02 | Central Quality Lab 2010_New | 2010 | GR01 | 2010 | SWD Central office-75 | Testwel Instruments Company | 9110000621 | 440 |  |  | 2024-07-12 | Rubber Mallet. w/o Calibration Certific | NO | 2 | 100 | 200 | 236 | 200 | 236 | 0 | 200 | 235.99 | ZMAT | 2024-05-13 | 2024-06-13
RE/0066-CQL-02 | Central Quality Lab 2010_New | 2010 | GR01 | 2010 | SWD Central office-75 | Testwel Instruments Company | 9110000621 | 450 |  |  | 2024-07-12 | Aluminum Container with Lid, 45 x 50mm w | NO | 20 | 50 | 1000 | 1180 | 1000 | 1180 | 0 | 1000 | 1179.95 | ZMAT | 2024-05-13 | 2024-06-13
RE/0066-CQL-02 | Central Quality Lab 2010_New | 2010 | GR01 | 2010 | SWD Central office-75 | Testwel Instruments Company | 9110000621 | 460 |  |  | 2024-07-12 | Digital Hand Held Thermometer with 300mm | NO | 2 | 3300 | 6600 | 7788 | 0 | 0 | 6600 | 0 | 0 | ZMAT | 2024-05-13 | 2024-06-13
RE/0066-CQL-02 | Central Quality Lab 2010_New | 2010 | GR01 | 2010 | SWD Central office-75 | Testwel Instruments Company | 9110000621 | 470 |  |  | 2024-07-12 | Plastic Wash Bottle, Cap.: 500ml w/o Cal | NO | 5 | 450 | 2250 | 2655 | 2250 | 2655 | 0 | 2250 | 2654.9 | ZMAT | 2024-05-13 | 2024-06-13
RE/0066-CQL-02 | Central Quality Lab 2010_New | 2010 | GR01 | 2010 | SWD Central office-75 | Testwel Instruments Company | 9110000621 | 480 |  |  | 2024-07-12 | Plastic Wash Bottle, Cap.: 1000ml w/o Ca | NO | 5 | 600 | 3000 | 3540 | 3000 | 3540 | 0 | 3000 | 3539.86 | ZMAT | 2024-05-13 | 2024-06-13
RE/0066-CQL-02 | Central Quality Lab 2010_New | 2010 | GR01 | 2010 | SWD Central office-75 | Testwel Instruments Company | 9110000621 | 490 |  |  | 2024-07-12 | Plastic Air Tight Container, Cap 5Kgs w/ | NO | 10 | 550 | 5500 | 6490 | 5500 | 6490 | 0 | 5500 | 6489.75 | ZMAT | 2024-05-13 | 2024-06-13
RE/0066-CQL-02 | Central Quality Lab 2010_New | 2010 | GR01 | 2010 | SWD Central office-75 | Testwel Instruments Company | 9110000621 | 500 |  |  | 2024-07-12 | Enamel Tray, Size : 600 x 450 x 50mm w/o | NO | 5 | 950 | 4750 | 5605 | 4750 | 5605 | 0 | 4750 | 5604.79 | ZMAT | 2024-05-13 | 2024-06-13
RE/0066-CQL-02 | Central Quality Lab 2010_New | 2010 | GR01 | 2010 | SWD Central office-75 | Testwel Instruments Company | 9110000621 | 510 |  |  | 2024-07-12 | Enamel Tray, Size: 450 x 300 x 40mm w/o | NO | 5 | 675 | 3375 | 3982.5 | 3375 | 3982.5 | 0 | 3375 | 3982.85 | ZMAT | 2024-05-13 | 2024-06-13
RE/0066-CQL-02 | Central Quality Lab 2010_New | 2010 | GR01 | 2010 | SWD Central office-75 | Testwel Instruments Company | 9110000621 | 520 |  |  | 2024-07-12 | Enamel Tray, Size: 300 x 250 x 40mm w/o | NO | 5 | 375 | 1875 | 2212.5 | 1875 | 2212.5 | 0 | 1875 | 2212.92 | ZMAT | 2024-05-13 | 2024-06-13
RE/0066-CQL-02 | Central Quality Lab 2010_New | 2010 | GR01 | 2010 | SWD Central office-75 | Testwel Instruments Company | 9110000621 | 530 |  |  | 2024-07-12 | Enamel Tray, Circular Plate of 250mm di | NO | 5 | 225 | 1125 | 1327.5 | 1125 | 1327.5 | 0 | 1125 | 1327.95 | ZMAT | 2024-05-13 | 2024-06-13
RE/0066-CQL-02 | Central Quality Lab 2010_New | 2010 | GR01 | 2010 | SWD Central office-75 | Testwel Instruments Company | 9110000621 | 540 |  |  | 2024-07-12 | Stainless Steel Scoop with Handle, Cap.: | NO | 2 | 575 | 1150 | 1357 | 1150 | 1357 | 0 | 1150 | 1356.95 | ZMAT | 2024-05-13 | 2024-06-13
RE/0066-CQL-02 | Central Quality Lab 2010_New | 2010 | GR01 | 2010 | SWD Central office-75 | Testwel Instruments Company | 9110000621 | 550 |  |  | 2024-07-12 | Stainless Steel Scoop with Handle, Cap.: | NO | 3 | 675 | 2025 | 2389.5 | 2025 | 2389.5 | 0 | 2025 | 2389.91 | ZMAT | 2024-05-13 | 2024-06-13
RE/0066-CQL-02 | Central Quality Lab 2010_New | 2010 | GR01 | 2010 | SWD Central office-75 | Testwel Instruments Company | 9110000621 | 560 |  |  | 2024-07-12 | CRM (OPC, PPC, Fly Ash) Chemical | NO | 1 | 22500 | 22500 | 26550 | 22500 | 26550 | 0 | 22500 | 26548.99 | ZMAT | 2024-05-13 | 2024-06-13
RE/0066-CQL-02 | Central Quality Lab 2010_New | 2010 | GR01 | 2010 | SWD Central office-75 | Testwel Instruments Company | 9110000621 | 570 |  |  | 2024-07-12 | POTASSIUM HYDROGEN PHTHALATE, 500gm, Gra | NO | 1 | 760 | 760 | 896.8 | 760 | 896.8 | 0 | 760 | 896.97 | ZMAT | 2024-05-13 | 2024-06-13
RE/0066-CQL-02 | Central Quality Lab 2010_New | 2010 | GR01 | 2010 | SWD Central office-75 | Testwel Instruments Company | 9110000621 | 580 |  |  | 2024-07-12 | CALCIUM CARBONATE, 500gm Grade LR w/o C | NO | 1 | 360 | 360 | 424.8 | 360 | 424.8 | 0 | 360 | 424.98 | ZMAT | 2024-05-13 | 2024-06-13
RE/0066-CQL-02 | Central Quality Lab 2010_New | 2010 | GR01 | 2010 | SWD Central office-75 | Testwel Instruments Company | 9110000621 | 590 |  |  | 2024-07-12 | SODIUM CHLORIDE, 500gm Grade LR w/o Cali | NO | 1 | 260 | 260 | 306.8 | 260 | 306.8 | 0 | 260 | 306.99 | ZMAT | 2024-05-13 | 2024-06-13
RE/0066-CQL-02 | Central Quality Lab 2010_New | 2010 | GR01 | 2010 | SWD Central office-75 | Testwel Instruments Company | 9110000621 | 600 |  |  | 2024-07-12 | Reagent Bottle, Amber 500ml w/o Calibrat | NO | 6 | 450 | 2700 | 3186 | 2700 | 3186 | 0 | 2700 | 3185.88 | ZMAT | 2024-05-13 | 2024-06-13
RE/0066-CQL-02 | Central Quality Lab 2010_New | 2010 | GR01 | 2010 | SWD Central office-75 | Testwel Instruments Company | 9110000621 | 610 |  |  | 2024-07-12 | Reagent Bottle Plastic, Cap. 100ml w/o C | NO | 6 | 100 | 600 | 708 | 600 | 708 | 0 | 600 | 707.97 | ZMAT | 2024-05-13 | 2024-06-13
RE/0066-CQL-02 | Central Quality Lab 2010_New | 2010 | GR01 | 2010 | SWD Central office-75 | Testwel Instruments Company | 9110000621 | 620 |  |  | 2024-07-12 | Reagent Bottle Plastic, Cap. 500ml w/o C | NO | 6 | 20 | 120 | 141.6 | 120 | 141.6 | 0 | 120 | 141.99 | ZMAT | 2024-05-13 | 2024-06-13
RE/0066-CQL-02 | Central Quality Lab 2010_New | 2010 | GR01 | 2010 | SWD Central office-75 | Testwel Instruments Company | 9110000621 | 630 |  |  | 2024-07-12 | Reagent Bootle, Transparent, 500ml w/o C | NO | 6 | 1000 | 6000 | 7080 | 6000 | 7080 | 0 | 6000 | 7079.73 | ZMAT | 2024-05-13 | 2024-06-13
RE/0066-CQL-02 | Central Quality Lab 2010_New | 2010 | GR01 | 2010 | SWD Central office-75 | Testwel Instruments Company | 9110000621 | 640 |  |  | 2024-07-12 | Volumetric Flask, Cap.: 100ml w/o Calibr | NO | 2 | 340 | 680 | 802.4 | 680 | 802.4 | 0 | 680 | 801.97 | ZMAT | 2024-05-13 | 2024-06-13
RE/0066-CQL-02 | Central Quality Lab 2010_New | 2010 | GR01 | 2010 | SWD Central office-75 | Testwel Instruments Company | 9110000621 | 650 |  |  | 2024-07-12 | Volumetric Flask, Cap.: 250ml w/o Calibr | NO | 2 | 415 | 830 | 979.4 | 830 | 979.4 | 0 | 830 | 978.96 | ZMAT | 2024-05-13 | 2024-06-13
RE/0066-CQL-02 | Central Quality Lab 2010_New | 2010 | GR01 | 2010 | SWD Central office-75 | Testwel Instruments Company | 9110000621 | 660 |  |  | 2024-07-12 | Volumetric Flask, Cap.: 500ml w/o Calibr | NO | 2 | 580 | 1160 | 1368.8 | 1160 | 1368.8 | 0 | 1160 | 1368.95 | ZMAT | 2024-05-13 | 2024-06-13
RE/0066-CQL-02 | Central Quality Lab 2010_New | 2010 | GR01 | 2010 | SWD Central office-75 | Testwel Instruments Company | 9110000621 | 670 |  |  | 2024-07-12 | Volumetric Flask, Cap.: 1000ml w/o Calib | NO | 2 | 950 | 1900 | 2242 | 1900 | 2242 | 0 | 1900 | 2241.91 | ZMAT | 2024-05-13 | 2024-06-13
RE/0066-CQL-02 | Central Quality Lab 2010_New | 2010 | GR01 | 2010 | SWD Central office-75 | Testwel Instruments Company | 9110000621 | 680 |  |  | 2024-07-12 | Conical Flask, Cap. 250ml w/o Calibratio | NO | 3 | 175 | 525 | 619.5 | 525 | 619.5 | 0 | 525 | 619.98 | ZMAT | 2024-05-13 | 2024-06-13
RE/0066-CQL-02 | Central Quality Lab 2010_New | 2010 | GR01 | 2010 | SWD Central office-75 | Testwel Instruments Company | 9110000621 | 690 |  |  | 2024-07-12 | Conical Flask, Cap. 500ml w/o Calibratio | NO | 3 | 245 | 735 | 867.3 | 735 | 867.3 | 0 | 735 | 866.97 | ZMAT | 2024-05-13 | 2024-06-13
RE/0066-CQL-02 | Central Quality Lab 2010_New | 2010 | GR01 | 2010 | SWD Central office-75 | Testwel Instruments Company | 9110000621 | 700 |  |  | 2024-07-12 | Glass Beaker, Cap. 100ml w/o Calibration | NO | 2 | 100 | 200 | 236 | 200 | 236 | 0 | 200 | 235.99 | ZMAT | 2024-05-13 | 2024-06-13
RE/0066-CQL-02 | Central Quality Lab 2010_New | 2010 | GR01 | 2010 | SWD Central office-75 | Testwel Instruments Company | 9110000621 | 710 |  |  | 2024-07-12 | Glass Beaker, Cap. 250ml w/o Calibration | NO | 2 | 110 | 220 | 259.6 | 220 | 259.6 | 0 | 220 | 259.99 | ZMAT | 2024-05-13 | 2024-06-13
RE/0066-CQL-02 | Central Quality Lab 2010_New | 2010 | GR01 | 2010 | SWD Central office-75 | Testwel Instruments Company | 9110000621 | 720 |  |  | 2024-07-12 | Glass Beaker, Cap. 500ml w/o Calibration | NO | 2 | 175 | 350 | 413 | 350 | 413 | 0 | 350 | 412.98 | ZMAT | 2024-05-13 | 2024-06-13
RE/0066-CQL-02 | Central Quality Lab 2010_New | 2010 | GR01 | 2010 | SWD Central office-75 | Testwel Instruments Company | 9110000621 | 730 |  |  | 2024-07-12 | Glass Beaker, Cap. 1000ml w/o Calibratio | NO | 1 | 355 | 355 | 418.9 | 355 | 418.9 | 0 | 355 | 418.98 | ZMAT | 2024-05-13 | 2024-06-13
RE/0066-CQL-02 | Central Quality Lab 2010_New | 2010 | GR01 | 2010 | SWD Central office-75 | Testwel Instruments Company | 9110000621 | 740 |  |  | 2024-07-12 | Glass Beaker, Cap. 2000ml w/o Calibratio | NO | 1 | 720 | 720 | 849.6 | 720 | 849.6 | 0 | 720 | 849.97 | ZMAT | 2024-05-13 | 2024-06-13
RE/0066-CQL-02 | Central Quality Lab 2010_New | 2010 | GR01 | 2010 | SWD Central office-75 | Testwel Instruments Company | 9110000621 | 750 |  |  | 2024-07-12 | Glass Measuring Cylinder, Cap. 10ml w/o | NO | 1 | 440 | 440 | 519.2 | 440 | 519.2 | 0 | 440 | 518.98 | ZMAT | 2024-05-13 | 2024-06-13
RE/0066-CQL-02 | Central Quality Lab 2010_New | 2010 | GR01 | 2010 | SWD Central office-75 | Testwel Instruments Company | 9110000621 | 760 |  |  | 2024-07-12 | Glass Measuring Cylinder, Cap. 50ml w/o | NO | 1 | 580 | 580 | 684.4 | 580 | 684.4 | 0 | 580 | 683.97 | ZMAT | 2024-05-13 | 2024-06-13
RE/0066-CQL-02 | Central Quality Lab 2010_New | 2010 | GR01 | 2010 | SWD Central office-75 | Testwel Instruments Company | 9110000621 | 770 |  |  | 2024-07-12 | Glass Measuring Cylinder, Cap. 100ml w/o | NO | 1 | 450 | 450 | 531 | 450 | 531 | 0 | 450 | 530.98 | ZMAT | 2024-05-13 | 2024-06-13
RE/0066-CQL-02 | Central Quality Lab 2010_New | 2010 | GR01 | 2010 | SWD Central office-75 | Testwel Instruments Company | 9110000621 | 780 |  |  | 2024-07-12 | Glass Measuring Cylinder, Cap. 250ml w/o | NO | 1 | 750 | 750 | 885 | 750 | 885 | 0 | 750 | 884.97 | ZMAT | 2024-05-13 | 2024-06-13
RE/0066-CQL-02 | Central Quality Lab 2010_New | 2010 | GR01 | 2010 | SWD Central office-75 | Testwel Instruments Company | 9110000621 | 790 |  |  | 2024-07-12 | Glass Measuring Cylinder, Cap. 500ml w/o | NO | 1 | 1100 | 1100 | 1298 | 1100 | 1298 | 0 | 1100 | 1297.95 | ZMAT | 2024-05-13 | 2024-06-13
RE/0066-CQL-02 | Central Quality Lab 2010_New | 2010 | GR01 | 2010 | SWD Central office-75 | Testwel Instruments Company | 9110000621 | 800 |  |  | 2024-07-12 | Glass Measuring Cylinder, Cap. 1000ml w/ | NO | 1 | 1450 | 1450 | 1711 | 1450 | 1711 | 0 | 1450 | 1710.93 | ZMAT | 2024-05-13 | 2024-06-13
RE/0066-CQL-02 | Central Quality Lab 2010_New | 2010 | GR01 | 2010 | SWD Central office-75 | Testwel Instruments Company | 9110000621 | 810 |  |  | 2024-07-12 | Glass Measuring Cylinder with Stopper, C | NO | 2 | 1360 | 2720 | 3209.6 | 2720 | 3209.6 | 0 | 2720 | 3209.88 | ZMAT | 2024-05-13 | 2024-06-13
RE/0066-CQL-02 | Central Quality Lab 2010_New | 2010 | GR01 | 2010 | SWD Central office-75 | Testwel Instruments Company | 9110000621 | 820 |  |  | 2024-07-12 | Glass Burette, Cap. 5ml w/o Calibration | NO | 1 | 975 | 975 | 1150.5 | 975 | 1150.5 | 0 | 975 | 1150.96 | ZMAT | 2024-05-13 | 2024-06-13
RE/0066-CQL-02 | Central Quality Lab 2010_New | 2010 | GR01 | 2010 | SWD Central office-75 | Testwel Instruments Company | 9110000621 | 830 |  |  | 2024-07-12 | Glass Burette, Cap. 10ml w/o Calibration | NO | 1 | 830 | 830 | 979.4 | 830 | 979.4 | 0 | 830 | 978.96 | ZMAT | 2024-05-13 | 2024-06-13
RE/0066-CQL-02 | Central Quality Lab 2010_New | 2010 | GR01 | 2010 | SWD Central office-75 | Testwel Instruments Company | 9110000621 | 840 |  |  | 2024-07-12 | Glass Burette, Cap. 25ml w/o Calibration | NO | 1 | 810 | 810 | 955.8 | 810 | 955.8 | 0 | 810 | 955.96 | ZMAT | 2024-05-13 | 2024-06-13
RE/0066-CQL-02 | Central Quality Lab 2010_New | 2010 | GR01 | 2010 | SWD Central office-75 | Testwel Instruments Company | 9110000621 | 850 |  |  | 2024-07-12 | Glass Burette, Cap. 50ml w/o Calibration | NO | 1 | 880 | 880 | 1038.4 | 880 | 1038.4 | 0 | 880 | 1037.96 | ZMAT | 2024-05-13 | 2024-06-13
RE/0066-CQL-02 | Central Quality Lab 2010_New | 2010 | GR01 | 2010 | SWD Central office-75 | Testwel Instruments Company | 9110000621 | 860 |  |  | 2024-07-12 | Graduated Pipette, Cap. 1ml w/o Calibrat | NO | 1 | 200 | 200 | 236 | 200 | 236 | 0 | 200 | 235.99 | ZMAT | 2024-05-13 | 2024-06-13
RE/0066-CQL-02 | Central Quality Lab 2010_New | 2010 | GR01 | 2010 | SWD Central office-75 | Testwel Instruments Company | 9110000621 | 870 |  |  | 2024-07-12 | Graduated Pipette, Cap. 2ml w/o Calibrat | NO | 1 | 210 | 210 | 247.8 | 210 | 247.8 | 0 | 210 | 247.99 | ZMAT | 2024-05-13 | 2024-06-13
RE/0066-CQL-02 | Central Quality Lab 2010_New | 2010 | GR01 | 2010 | SWD Central office-75 | Testwel Instruments Company | 9110000621 | 880 |  |  | 2024-07-12 | Graduated Pipette, Cap. 5ml w/o Calibrat | NO | 1 | 220 | 220 | 259.6 | 220 | 259.6 | 0 | 220 | 259.99 | ZMAT | 2024-05-13 | 2024-06-13
RE/0066-CQL-02 | Central Quality Lab 2010_New | 2010 | GR01 | 2010 | SWD Central office-75 | Testwel Instruments Company | 9110000621 | 890 |  |  | 2024-07-12 | Graduated Pipette, Cap. 10ml w/o Calibra | NO | 1 | 240 | 240 | 283.2 | 240 | 283.2 | 0 | 240 | 282.99 | ZMAT | 2024-05-13 | 2024-06-13
RE/0066-CQL-02 | Central Quality Lab 2010_New | 2010 | GR01 | 2010 | SWD Central office-75 | Testwel Instruments Company | 9110000621 | 900 |  |  | 2024-07-12 | Graduated Pipette, Cap. 25ml w/o Calibra | NO | 1 | 375 | 375 | 442.5 | 375 | 442.5 | 0 | 375 | 442.98 | ZMAT | 2024-05-13 | 2024-06-13
RE/0066-CQL-02 | Central Quality Lab 2010_New | 2010 | GR01 | 2010 | SWD Central office-75 | Testwel Instruments Company | 9110000621 | 910 |  |  | 2024-07-12 | Bulb Pipette, Cap. 5ml w/o Calibration C | NO | 1 | 220 | 220 | 259.6 | 220 | 259.6 | 0 | 220 | 259.99 | ZMAT | 2024-05-13 | 2024-06-13
RE/0066-CQL-02 | Central Quality Lab 2010_New | 2010 | GR01 | 2010 | SWD Central office-75 | Testwel Instruments Company | 9110000621 | 920 |  |  | 2024-07-12 | Bulb Pipette, Cap. 10ml w/o Calibration | NO | 1 | 255 | 255 | 300.9 | 255 | 300.9 | 0 | 255 | 300.99 | ZMAT | 2024-05-13 | 2024-06-13
RE/0066-CQL-02 | Central Quality Lab 2010_New | 2010 | GR01 | 2010 | SWD Central office-75 | Testwel Instruments Company | 9110000621 | 930 |  |  | 2024-07-12 | Bulb Pipette, Cap. 20ml w/o Calibration | NO | 1 | 295 | 295 | 348.1 | 295 | 348.1 | 0 | 295 | 347.99 | ZMAT | 2024-05-13 | 2024-06-13
RE/0066-CQL-02 | Central Quality Lab 2010_New | 2010 | GR01 | 2010 | SWD Central office-75 | Testwel Instruments Company | 9110000621 | 940 |  |  | 2024-07-12 | Bulb Pipette, Cap. 25ml w/o Calibration | NO | 1 | 310 | 310 | 365.8 | 310 | 365.8 | 0 | 310 | 365.99 | ZMAT | 2024-05-13 | 2024-06-13
RE/0066-CQL-02 | Central Quality Lab 2010_New | 2010 | GR01 | 2010 | SWD Central office-75 | Testwel Instruments Company | 9110000621 | 950 |  |  | 2024-07-12 | Bulb Pipette, Cap. 50ml w/o Calibration | NO | 1 | 360 | 360 | 424.8 | 360 | 424.8 | 0 | 360 | 424.98 | ZMAT | 2024-05-13 | 2024-06-13
RE/0066-CQL-02 | Central Quality Lab 2010_New | 2010 | GR01 | 2010 | SWD Central office-75 | Testwel Instruments Company | 9110000621 | 960 |  |  | 2024-07-12 | Test Tube Big Size, 25 x 150mm w/o Calib | NO | 12 | 50 | 600 | 708 | 600 | 708 | 0 | 600 | 707.97 | ZMAT | 2024-05-13 | 2024-06-13
RE/0066-CQL-02 | Central Quality Lab 2010_New | 2010 | GR01 | 2010 | SWD Central office-75 | Testwel Instruments Company | 9110000621 | 970 |  |  | 2024-07-12 | Test Tube Stand w/o Calibration Certific | NO | 1 | 140 | 140 | 165.2 | 140 | 165.2 | 0 | 140 | 164.99 | ZMAT | 2024-05-13 | 2024-06-13
RE/0066-CQL-02 | Central Quality Lab 2010_New | 2010 | GR01 | 2010 | SWD Central office-75 | Testwel Instruments Company | 9110000621 | 980 |  |  | 2024-07-12 | Oxygen Cylinder | NO | 1 | 3300 | 3300 | 3894 | 0 | 0 | 3300 | 0 | 0 | ZMAT | 2024-05-13 | 2024-06-13
RE/0066-CQL-02 | Central Quality Lab 2010_New | 2010 | GR01 | 2010 | SWD Central office-75 | Testwel Instruments Company | 9110000621 | 990 |  |  | 2024-07-12 | Writing Brush 50mm and 100mm w/o Calibra | NO | 3 | 150 | 450 | 531 | 450 | 531 | 0 | 450 | 530.98 | ZMAT | 2024-05-13 | 2024-06-13
RE/0066-CQL-02 | Central Quality Lab 2010_New | 2010 | GR01 | 2010 | SWD Central office-75 | Testwel Instruments Company | 9110000621 | 1000 |  |  | 2024-07-12 | Heating Mantle, Cap.: 2 Liter fitted wit | NO | 2 | 1200 | 2400 | 2832 | 2400 | 2832 | 0 | 2400 | 2831.89 | ZMAT | 2024-05-13 | 2024-06-13
RE/0066-CQL-02 | Central Quality Lab 2010_New | 2010 | GR01 | 2010 | SWD Central office-75 | Testwel Instruments Company | 9110000621 | 1010 |  |  | 2024-07-12 | Digital Barometer Hand Held w/o Calibrat | NO | 1 | 3500 | 3500 | 4130 | 3500 | 4130 | 0 | 3500 | 4129.84 | ZMAT | 2024-05-13 | 2024-06-13
RE/0066-CQL-02 | Central Quality Lab 2010_New | 2010 | GR01 | 2010 | SWD Central office-75 | Testwel Instruments Company | 9110000621 | 1020 |  |  | 2024-07-12 | Porcelain Dish, 125mm dia. w/o Calibrati | NO | 4 | 550 | 2200 | 2596 | 2200 | 2596 | 0 | 2200 | 2595.9 | ZMAT | 2024-05-13 | 2024-06-13
RE/0066-CQL-02 | Central Quality Lab 2010_New | 2010 | GR01 | 2010 | SWD Central office-75 | Testwel Instruments Company | 9110000621 | 1030 |  |  | 2024-07-12 | Filter Flask, Cap. 1000ml w/o Calibratio | NO | 1 | 2200 | 2200 | 2596 | 2200 | 2596 | 0 | 2200 | 2595.9 | ZMAT | 2024-05-13 | 2024-06-13
RE/0066-CQL-02 | Central Quality Lab 2010_New | 2010 | GR01 | 2010 | SWD Central office-75 | Testwel Instruments Company | 9110000621 | 1040 |  |  | 2024-07-12 | Burette Stand w/o Calibration Certificat | NO | 2 | 250 | 500 | 590 | 500 | 590 | 0 | 500 | 589.98 | ZMAT | 2024-05-13 | 2024-06-13
RE/0066-CQL-02 | Central Quality Lab 2010_New | 2010 | GR01 | 2010 | SWD Central office-75 | Testwel Instruments Company | 9110000621 | 1050 |  |  | 2024-07-12 | Filter Paper (40, 41 and 42), of Size 12 | NO | 1 | 18000 | 18000 | 21240 | 18000 | 21240 | 0 | 18000 | 21239.19 | ZMAT | 2024-05-13 | 2024-06-13
RE/0066-CQL-02 | Central Quality Lab 2010_New | 2010 | GR01 | 2010 | SWD Central office-75 | Testwel Instruments Company | 9110000621 | 1060 |  |  | 2024-07-12 | Standard Bubbler for Lab Use w/o Calibra | NO | 6 | 100 | 600 | 708 | 600 | 708 | 0 | 600 | 707.97 | ZMAT | 2024-05-13 | 2024-06-13
RE/0066-CQL-02 | Central Quality Lab 2010_New | 2010 | GR01 | 2010 | SWD Central office-75 | Testwel Instruments Company | 9110000621 | 1070 |  |  | 2024-07-12 | Stainless Steel Tong, 6" w/o Calibratio | NO | 1 | 50 | 50 | 59 | 50 | 59 | 0 | 50 | 59 | ZMAT | 2024-05-13 | 2024-06-13
RE/0066-CQL-02 | Central Quality Lab 2010_New | 2010 | GR01 | 2010 | SWD Central office-75 | Testwel Instruments Company | 9110000621 | 1080 |  |  | 2024-07-12 | Stainless Steel Tong, 8" w/o Calibration | NO | 1 | 75 | 75 | 88.5 | 75 | 88.5 | 0 | 75 | 89 | ZMAT | 2024-05-13 | 2024-06-13
RE/0066-CQL-02 | Central Quality Lab 2010_New | 2010 | GR01 | 2010 | SWD Central office-75 | Testwel Instruments Company | 9110000621 | 1090 |  |  | 2024-07-12 | Stainless Steel Tong, 12" w/o Calibratio | NO | 1 | 150 | 150 | 177 | 150 | 177 | 0 | 150 | 176.99 | ZMAT | 2024-05-13 | 2024-06-13
RE/0066-CQL-02 | Central Quality Lab 2010_New | 2010 | GR01 | 2010 | SWD Central office-75 | Testwel Instruments Company | 9110000621 | 1100 |  |  | 2024-07-12 | Stainless Steel Tong, 24" w/o Calibratio | NO | 1 | 350 | 350 | 413 | 350 | 413 | 0 | 350 | 412.98 | ZMAT | 2024-05-13 | 2024-06-13
RE/0066-CQL-02 | Central Quality Lab 2010_New | 2010 | GR01 | 2010 | SWD Central office-75 | Testwel Instruments Company | 9110000621 | 1110 |  |  | 2024-07-12 | AMMONIUM ACETATE AR, 500gm Grade LR w/o | NO | 1 | 640 | 640 | 755.2 | 640 | 755.2 | 0 | 640 | 754.97 | ZMAT | 2024-05-13 | 2024-06-13
RE/0066-CQL-02 | Central Quality Lab 2010_New | 2010 | GR01 | 2010 | SWD Central office-75 | Testwel Instruments Company | 9110000621 | 1120 |  |  | 2024-07-12 | ACETIC ACID GLACIAL AR, 500ml w/o Calibr | NO | 1 | 410 | 410 | 483.8 | 410 | 483.8 | 0 | 410 | 483.98 | ZMAT | 2024-05-13 | 2024-06-13
RE/0066-CQL-02 | Central Quality Lab 2010_New | 2010 | GR01 | 2010 | SWD Central office-75 | Testwel Instruments Company | 9110000621 | 1130 |  |  | 2024-07-12 | BARIUM CHLORIDE AR, 500ml Grade LR w/o | NO | 1 | 415 | 415 | 489.7 | 0 | 0 | 415 | 0 | 0 | ZMAT | 2024-05-13 | 2024-06-13
RE/0066-CQL-02 | Central Quality Lab 2010_New | 2010 | GR01 | 2010 | SWD Central office-75 | Testwel Instruments Company | 9110000621 | 1140 |  |  | 2024-07-12 | ErichromE Black T, 25gm Grade LR w/o Ca | NO | 1 | 495 | 495 | 584.1 | 495 | 584.1 | 0 | 495 | 583.98 | ZMAT | 2024-05-13 | 2024-06-13
RE/0066-CQL-02 | Central Quality Lab 2010_New | 2010 | GR01 | 2010 | SWD Central office-75 | Testwel Instruments Company | 9110000621 | 1150 |  |  | 2024-07-12 | MAGNESIUM CHLORIDE AR, 500gm Grade LR w | NO | 1 | 400 | 400 | 472 | 400 | 472 | 0 | 400 | 471.98 | ZMAT | 2024-05-13 | 2024-06-13
RE/0066-CQL-02 | Central Quality Lab 2010_New | 2010 | GR01 | 2010 | SWD Central office-75 | Testwel Instruments Company | 9110000621 | 1160 |  |  | 2024-07-12 | POTASSIUM CHLORIDE AR, 500gm Grade LR w | NO | 1 | 540 | 540 | 637.2 | 540 | 637.2 | 0 | 540 | 636.98 | ZMAT | 2024-05-13 | 2024-06-13
RE/0066-CQL-02 | Central Quality Lab 2010_New | 2010 | GR01 | 2010 | SWD Central office-75 | Testwel Instruments Company | 9110000621 | 1170 |  |  | 2024-07-12 | SODIUM CHLORIDE, 500gm Grade LR w/o Cal | NO | 1 | 295 | 295 | 348.1 | 295 | 348.1 | 0 | 295 | 347.99 | ZMAT | 2024-05-13 | 2024-06-13
RE/0066-CQL-02 | Central Quality Lab 2010_New | 2010 | GR01 | 2010 | SWD Central office-75 | Testwel Instruments Company | 9110000621 | 1180 |  |  | 2024-07-12 | SODIUM ACETATE anhydrous AR, 500gm w/o C | NO | 1 | 630 | 630 | 743.4 | 630 | 743.4 | 0 | 630 | 742.97 | ZMAT | 2024-05-13 | 2024-06-13
RE/0066-CQL-02 | Central Quality Lab 2010_New | 2010 | GR01 | 2010 | SWD Central office-75 | Testwel Instruments Company | 9110000621 | 1190 |  |  | 2024-07-12 | STARCH SOLUBLE (potato), 500gm Grade LR | NO | 1 | 2370 | 2370 | 2796.6 | 0 | 0 | 2370 | 0 | 0 | ZMAT | 2024-05-13 | 2024-06-13
RE/0066-CQL-02 | Central Quality Lab 2010_New | 2010 | GR01 | 2010 | SWD Central office-75 | Testwel Instruments Company | 9110000621 | 1200 |  |  | 2024-07-12 | MAGNESIUM SULPHATE AR, 500gm Grade LR w | NO | 1 | 335 | 335 | 395.3 | 335 | 395.3 | 0 | 335 | 394.99 | ZMAT | 2024-05-13 | 2024-06-13
RE/0066-CQL-02 | Central Quality Lab 2010_New | 2010 | GR01 | 2010 | SWD Central office-75 | Testwel Instruments Company | 9110000621 | 1210 |  |  | 2024-07-12 | METHYL RED SOLUTION, 125ml Grade LR w/o | NO | 1 | 335 | 335 | 395.3 | 0 | 0 | 335 | 0 | 0 | ZMAT | 2024-05-13 | 2024-06-13
RE/0066-CQL-02 | Central Quality Lab 2010_New | 2010 | GR01 | 2010 | SWD Central office-75 | Testwel Instruments Company | 9110000621 | 1220 |  |  | 2024-07-12 | Cadmium chloride monohydrate, 100gm, AR | NO | 1 | 660 | 660 | 778.8 | 660 | 778.8 | 0 | 660 | 778.97 | ZMAT | 2024-05-13 | 2024-06-13
RE/0066-CQL-02 | Central Quality Lab 2010_New | 2010 | GR01 | 2010 | SWD Central office-75 | Testwel Instruments Company | 9110000621 | 1230 |  |  | 2024-07-12 | AMMONIUM MOLYBDATE AR, 100gm w/o Calibra | NO | 1 | 1910 | 1910 | 2253.8 | 1910 | 2253.8 | 0 | 1910 | 2253.91 | ZMAT | 2024-05-13 | 2024-06-13
RE/0066-CQL-02 | Central Quality Lab 2010_New | 2010 | GR01 | 2010 | SWD Central office-75 | Testwel Instruments Company | 9110000621 | 1240 |  |  | 2024-07-12 | POTASSIUM NITRATE, 500gm Grade LR w/o C | NO | 1 | 660 | 660 | 778.8 | 660 | 778.8 | 0 | 660 | 778.97 | ZMAT | 2024-05-13 | 2024-06-13
RE/0066-CQL-02 | Central Quality Lab 2010_New | 2010 | GR01 | 2010 | SWD Central office-75 | Testwel Instruments Company | 9110000621 | 1250 |  |  | 2024-07-12 | SODIUM CARBONATE ANHYDROUS AR, 500gm w/o | NO | 1 | 515 | 515 | 607.7 | 515 | 607.7 | 0 | 515 | 607.98 | ZMAT | 2024-05-13 | 2024-06-13
RE/0066-CQL-02 | Central Quality Lab 2010_New | 2010 | GR01 | 2010 | SWD Central office-75 | Testwel Instruments Company | 9110000621 | 1260 |  |  | 2024-07-12 | METHYL ORANGE (pH indicator), 100gm Gra | NO | 1 | 215 | 215 | 253.7 | 0 | 0 | 215 | 0 | 0 | ZMAT | 2024-05-13 | 2024-06-13
RE/0066-CQL-02 | Central Quality Lab 2010_New | 2010 | GR01 | 2010 | SWD Central office-75 | Testwel Instruments Company | 9110000621 | 1270 |  |  | 2024-07-12 | OXALIC ACID AR, 500gm w/o Calibration Ce | NO | 1 | 530 | 530 | 625.4 | 530 | 625.4 | 0 | 530 | 624.98 | ZMAT | 2024-05-13 | 2024-06-13
RE/0066-CQL-02 | Central Quality Lab 2010_New | 2010 | GR01 | 2010 | SWD Central office-75 | Testwel Instruments Company | 9110000621 | 1280 |  |  | 2024-07-12 | PHENOLPHTHALEIN powder (pH indicator), 1 | NO | 1 | 850 | 850 | 1003 | 850 | 1003 | 0 | 850 | 1002.96 | ZMAT | 2024-05-13 | 2024-06-13
RE/0066-CQL-02 | Central Quality Lab 2010_New | 2010 | GR01 | 2010 | SWD Central office-75 | Testwel Instruments Company | 9110000621 | 1290 |  |  | 2024-07-12 | POTASSIUM CHROMATE, 500gm Grade LR w/o | NO | 1 | 1410 | 1410 | 1663.8 | 1410 | 1663.8 | 0 | 1410 | 1663.94 | ZMAT | 2024-05-13 | 2024-06-13
RE/0066-CQL-02 | Central Quality Lab 2010_New | 2010 | GR01 | 2010 | SWD Central office-75 | Testwel Instruments Company | 9110000621 | 1300 |  |  | 2024-07-12 | THYMOLPHTHALEIN powder, 25gm Grade LR w | NO | 1 | 1210 | 1210 | 1427.8 | 1210 | 1427.8 | 0 | 1210 | 1427.95 | ZMAT | 2024-05-13 | 2024-06-13
RE/0066-CQL-02 | Central Quality Lab 2010_New | 2010 | GR01 | 2010 | SWD Central office-75 | Testwel Instruments Company | 9110000621 | 1310 |  |  | 2024-07-12 | SILICA GEL 60-120 mesh, 500gm Grade LR | NO | 2 | 585 | 1170 | 1380.6 | 1170 | 1380.6 | 0 | 1170 | 1380.95 | ZMAT | 2024-05-13 | 2024-06-13
RE/0066-CQL-02 | Central Quality Lab 2010_New | 2010 | GR01 | 2010 | SWD Central office-75 | Testwel Instruments Company | 9110000621 | 1320 |  |  | 2024-07-12 | di-AMMONIUM HYDROGEN ORTHOPHOSPHATE, 500 | NO | 1 | 1150 | 1150 | 1357 | 1150 | 1357 | 0 | 1150 | 1356.95 | ZMAT | 2024-05-13 | 2024-06-13
RE/0066-CQL-02 | Central Quality Lab 2010_New | 2010 | GR01 | 2010 | SWD Central office-75 | Testwel Instruments Company | 9110000621 | 1330 |  |  | 2024-07-12 | CALCIUM CHLORIDE dihydrate, 500gm Grade | NO | 1 | 650 | 650 | 767 | 650 | 767 | 0 | 650 | 766.97 | ZMAT | 2024-05-13 | 2024-06-13
RE/0066-CQL-02 | Central Quality Lab 2010_New | 2010 | GR01 | 2010 | SWD Central office-75 | Testwel Instruments Company | 9110000621 | 1340 |  |  | 2024-07-12 | MAGNESIUM CHLORIDE AR, 500gm w/o Calibr | NO | 1 | 400 | 400 | 472 | 400 | 472 | 0 | 400 | 471.98 | ZMAT | 2024-05-13 | 2024-06-13
RE/0066-CQL-02 | Central Quality Lab 2010_New | 2010 | GR01 | 2010 | SWD Central office-75 | Testwel Instruments Company | 9110000621 | 1350 |  |  | 2024-07-12 | POTASSIUM DIHYDROGEN o-PHOSPHATE anhy. ( | NO | 1 | 960 | 960 | 1132.8 | 960 | 1132.8 | 0 | 960 | 1132.96 | ZMAT | 2024-05-13 | 2024-06-13
RE/0066-CQL-02 | Central Quality Lab 2010_New | 2010 | GR01 | 2010 | SWD Central office-75 | Testwel Instruments Company | 9110000621 | 1360 |  |  | 2024-07-12 | DI-SODIUM HYDROGEN-o-PHOSPHATE ANHYDROUS | NO | 1 | 885 | 885 | 1044.3 | 885 | 1044.3 | 0 | 885 | 1043.96 | ZMAT | 2024-05-13 | 2024-06-13
RE/0066-CQL-02 | Central Quality Lab 2010_New | 2010 | GR01 | 2010 | SWD Central office-75 | Testwel Instruments Company | 9110000621 | 1370 |  |  | 2024-07-12 | LITMUS PAPER BLUE, 200lvs Grade LR w/o | NO | 10 | 420 | 4200 | 4956 | 4200 | 4956 | 0 | 4200 | 4955.81 | ZMAT | 2024-05-13 | 2024-06-13
RE/0066-CQL-02 | Central Quality Lab 2010_New | 2010 | GR01 | 2010 | SWD Central office-75 | Testwel Instruments Company | 9110000621 | 1380 |  |  | 2024-07-12 | SODIUM SULPHATE ANHYDROUS, 500gm Grade L | NO | 1 | 305 | 305 | 359.9 | 305 | 359.9 | 0 | 305 | 359.99 | ZMAT | 2024-05-13 | 2024-06-13
RE/0066-CQL-02 | Central Quality Lab 2010_New | 2010 | GR01 | 2010 | SWD Central office-75 | Testwel Instruments Company | 9110000621 | 1390 |  |  | 2024-07-12 | SODIUM NITRATE AR, 500gm w/o Calibration | NO | 1 | 505 | 505 | 595.9 | 0 | 0 | 505 | 0 | 0 | ZMAT | 2024-05-13 | 2024-06-13
RE/0066-CQL-02 | Central Quality Lab 2010_New | 2010 | GR01 | 2010 | SWD Central office-75 | Testwel Instruments Company | 9110000621 | 1400 |  |  | 2024-07-12 | AMMONIA SOLUTION 0.89 (Ammonium Hydroxid | NO | 1 | 685 | 685 | 808.3 | 0 | 0 | 685 | 0 | 0 | ZMAT | 2024-05-13 | 2024-06-13
RE/0066-CQL-02 | Central Quality Lab 2010_New | 2010 | GR01 | 2010 | SWD Central office-75 | Testwel Instruments Company | 9110000621 | 1410 |  |  | 2024-07-12 | CALCIUM CARBONATE precipitated, 500gm Gr | NO | 1 | 420 | 420 | 495.6 | 420 | 495.6 | 0 | 420 | 495.98 | ZMAT | 2024-05-13 | 2024-06-13
RE/0066-CQL-02 | Central Quality Lab 2010_New | 2010 | GR01 | 2010 | SWD Central office-75 | Testwel Instruments Company | 9110000621 | 1420 |  |  | 2024-07-12 | ACETONE, 500ml Grade LR w/o Calibration | NO | 1 | 525 | 525 | 619.5 | 525 | 619.5 | 0 | 525 | 619.98 | ZMAT | 2024-05-13 | 2024-06-13
RE/0066-CQL-02 | Central Quality Lab 2010_New | 2010 | GR01 | 2010 | SWD Central office-75 | Testwel Instruments Company | 9110000621 | 1430 |  |  | 2024-07-12 | Magnesium Salt EDTA, 500GM Grade LR w/o | NO | 1 | 1130 | 1130 | 1333.4 | 1130 | 1333.4 | 0 | 1130 | 1332.95 | ZMAT | 2024-05-13 | 2024-06-13
RE/0066-CQL-02 | Central Quality Lab 2010_New | 2010 | GR01 | 2010 | SWD Central office-75 | Testwel Instruments Company | 9110000621 | 1440 |  |  | 2024-07-12 | Tannic Acid, 500gm w/o Calibration Certi | NO | 1 | 1050 | 1050 | 1239 | 1050 | 1239 | 0 | 1050 | 1238.95 | ZMAT | 2024-05-13 | 2024-06-13
RE/0066-CQL-02 | Central Quality Lab 2010_New | 2010 | GR01 | 2010 | SWD Central office-75 | Testwel Instruments Company | 9110000621 | 1450 |  |  | 2024-07-12 | Alcohol 99%, 500ml w/o Calibration Certi | NO | 1 | 750 | 750 | 885 | 750 | 885 | 0 | 750 | 884.97 | ZMAT | 2024-05-13 | 2024-06-13
RE/0066-CQL-02 | Central Quality Lab 2010_New | 2010 | GR01 | 2010 | SWD Central office-75 | Testwel Instruments Company | 9110000621 | 1460 |  |  | 2024-07-12 | Wired Brush for Cleaning Jaws w/o Calibr | NO | 2 | 1504 | 3008 | 3549.44 | 3007.97 | 3549.4 | 0.03 | 3008 | 3548.86 | ZMAT | 2024-05-13 | 2024-06-13
RE/0066-CQL-02 | Central Quality Lab 2010_New | 2010 | GR01 | 2010 | SWD Central office-75 | Testwel Instruments Company | 9110000621 | 1470 |  |  | 2024-07-12 | Hammer Cap.: 2 Kg w/o Calibration Certi | NO | 1 | 350 | 350 | 413 | 350 | 413 | 0 | 350 | 412.98 | ZMAT | 2024-05-13 | 2024-06-13
RE/0066-CQL-02 | Central Quality Lab 2010_New | 2010 | GR01 | 2010 | SWD Central office-75 | Testwel Instruments Company | 9110000621 | 1480 |  |  | 2024-07-12 | Spanner set for Moulds for 50mm, 70.mm | NO | 1 | 750 | 750 | 885 | 750 | 885 | 0 | 750 | 884.97 | ZMAT | 2024-05-13 | 2024-06-13
RE/0066-CQL-02 | Central Quality Lab 2010_New | 2010 | GR01 | 2010 | SWD Central office-75 | Testwel Instruments Company | 9110000621 | 1490 |  |  | 2024-07-12 | Basic Tool Kit and Allen Key w/o Calibra | NO | 1 | 900 | 900 | 1062 | 900 | 1062 | 0 | 900 | 1061.96 | ZMAT | 2024-05-13 | 2024-06-13
RE/0066-CQL-02 | Central Quality Lab 2010_New | 2010 | GR01 | 2010 | SWD Central office-75 | Testwel Instruments Company | 9110000621 | 1500 |  |  | 2024-07-12 | Mobile Oil per ltr w/o Calibration Certi | NO | 2 | 225 | 450 | 531 | 450 | 531 | 0 | 450 | 530.98 | ZMAT | 2024-05-13 | 2024-06-13
RE/0066-CQL-02 | Central Quality Lab 2010_New | 2010 | GR01 | 2010 | SWD Central office-75 | Testwel Instruments Company | 9110000621 | 1510 |  |  | 2024-07-12 | Grease 500gm w/o Calibration Certificate | NO | 4 | 1050 | 4200 | 4956 | 4200 | 4956 | 0 | 4200 | 4955.81 | ZMAT | 2024-05-13 | 2024-06-13
RE/0066-CQL-02 | Central Quality Lab 2010_New | 2010 | GR01 | 2010 | SWD Central office-75 | Testwel Instruments Company | 9110000621 | 1520 |  |  | 2024-07-12 | Benzene, per ltr w/o Calibration Certifi | NO | 15 | 185 | 2775 | 3274.5 | 2775 | 3274.5 | 0 | 2775 | 3274.87 | ZMAT | 2024-05-13 | 2024-06-13
RE/0066-CQL-02 | Central Quality Lab 2010_New | 2010 | GR01 | 2010 | SWD Central office-75 | Testwel Instruments Company | 9110000621 | 1530 |  |  | 2024-07-12 | Filter Paper No. 1, Size 12.5cm w/o Cal | NO | 1 | 5700 | 5700 | 6726 | 5700 | 6726 | 0 | 5700 | 6725.74 | ZMAT | 2024-05-13 | 2024-06-13
RE/0066-CQL-02 | Central Quality Lab 2010_New | 2010 | GR01 | 2010 | SWD Central office-75 | Testwel Instruments Company | 9110000621 | 1540 |  |  | 2024-07-12 | Immersion Rod 2000watt (Simple) w/o Cali | NO | 2 | 3500 | 7000 | 8260 | 7000 | 8260 | 0 | 7000 | 8259.68 | ZMAT | 2024-05-13 | 2024-06-13
RE/0066-CQL-02 | Central Quality Lab 2010_New | 2010 | GR01 | 2010 | SWD Central office-75 | Testwel Instruments Company | 9110000621 | 1550 |  |  | 2024-07-12 | POTASSIUM HYDROGEN PHTHALATE AR, 500gm w | NO | 1 | 760 | 760 | 896.8 | 0 | 0 | 760 | 0 | 0 | ZMAT | 2024-05-13 | 2024-06-13
RE/0066-CQL-02 | Central Quality Lab 2010_New | 2010 | GR01 | 2010 | SWD Central office-75 | Testwel Instruments Company | 9110000621 | 1560 |  |  | 2024-07-12 | Potassium periodate, 100gm w/o Calibrati | NO | 1 | 2770 | 2770 | 3268.6 | 2770 | 3268.6 | 0 | 2770 | 3268.88 | ZMAT | 2024-05-13 | 2024-06-13
RE/0066-CQL-02 | Central Quality Lab 2010_New | 2010 | GR01 | 2010 | SWD Central office-75 | Testwel Instruments Company | 9110000621 | 1570 |  |  | 2024-07-12 | STANNOUS CHLORIDE AR, 100gm w/o Calibrat | NO | 1 | 2850 | 2850 | 3363 | 0 | 0 | 2850 | 0 | 0 | ZMAT | 2024-05-13 | 2024-06-13
RE/0066-CQL-02 | Central Quality Lab 2010_New | 2010 | GR01 | 2010 | SWD Central office-75 | Testwel Instruments Company | 9110000621 | 1580 |  |  | 2024-07-12 | MERCURIC CHLORIDE AR, 100gm w/o Calibrat | NO | 1 | 5990 | 5990 | 7068.2 | 5990 | 7068.2 | 0 | 5990 | 7067.73 | ZMAT | 2024-05-13 | 2024-06-13
RE/0066-CQL-02 | Central Quality Lab 2010_New | 2010 | GR01 | 2010 | SWD Central office-75 | Testwel Instruments Company | 9110000621 | 1590 |  |  | 2024-07-12 | MAGNESIUM SULPHATE AR, 500gm w/o Calibra | NO | 1 | 670 | 670 | 790.6 | 0 | 0 | 670 | 0 | 0 | ZMAT | 2024-05-13 | 2024-06-13
RE/0066-CQL-02 | Central Quality Lab 2010_New | 2010 | GR01 | 2010 | SWD Central office-75 | Testwel Instruments Company | 9110000621 | 1600 |  |  | 2024-07-12 | AMMONIUM ACETATE AR, 500gm w/o Calibrati | NO | 1 | 640 | 640 | 755.2 | 0 | 0 | 640 | 0 | 0 | ZMAT | 2024-05-13 | 2024-06-13
RE/0066-CQL-02 | Central Quality Lab 2010_New | 2010 | GR01 | 2010 | SWD Central office-75 | Testwel Instruments Company | 9110000621 | 1610 |  |  | 2024-07-12 | AMMONIA SOLUTION 0.91 AR(Ammonium Hydrox | NO | 1 | 500 | 500 | 590 | 500 | 590 | 0 | 500 | 589.98 | ZMAT | 2024-05-13 | 2024-06-13
RE/0066-CQL-02 | Central Quality Lab 2010_New | 2010 | GR01 | 2010 | SWD Central office-75 | Testwel Instruments Company | 9110000621 | 1620 |  |  | 2024-07-12 | di-AMMONIUM HYDROGEN ORTHOPHOSPHATE AR, | NO | 1 | 980 | 980 | 1156.4 | 0 | 0 | 980 | 0 | 0 | ZMAT | 2024-05-13 | 2024-06-13
RE/0066-CQL-02 | Central Quality Lab 2010_New | 2010 | GR01 | 2010 | SWD Central office-75 | Testwel Instruments Company | 9110000621 | 1630 |  |  | 2024-07-12 | BISMUTH NITRATE AR, 100gm w/o Calibratio | NO | 1 | 975 | 975 | 1150.5 | 975 | 1150.5 | 0 | 975 | 1150.96 | ZMAT | 2024-05-13 | 2024-06-13
RE/0066-CQL-02 | Central Quality Lab 2010_New | 2010 | GR01 | 2010 | SWD Central office-75 | Testwel Instruments Company | 9110000621 | 1640 |  |  | 2024-07-12 | ZINC (METAL) DUST (325 mesh) AR, 500gm w | NO | 1 | 1360 | 1360 | 1604.8 | 0 | 0 | 1360 | 0 | 0 | ZMAT | 2024-05-13 | 2024-06-13
RE/0066-CQL-02 | Central Quality Lab 2010_New | 2010 | GR01 | 2010 | SWD Central office-75 | Testwel Instruments Company | 9110000621 | 1650 |  |  | 2024-07-12 | XYLENOL ORANGE AR, 5gm w/o Calibration C | NO | 1 | 605 | 605 | 713.9 | 605 | 713.9 | 0 | 605 | 713.97 | ZMAT | 2024-05-13 | 2024-06-13
RE/0066-CQL-02 | Central Quality Lab 2010_New | 2010 | GR01 | 2010 | SWD Central office-75 | Testwel Instruments Company | 9110000621 | 1660 |  |  | 2024-07-12 | PERCHLORIC ACID 70% AR, 500ml w/o Calibr | NO | 1 | 1920 | 1920 | 2265.6 | 0 | 0 | 1920 | 0 | 0 | ZMAT | 2024-05-13 | 2024-06-13
RE/0066-CQL-02 | Central Quality Lab 2010_New | 2010 | GR01 | 2010 | SWD Central office-75 | Testwel Instruments Company | 9110000621 | 1670 |  |  | 2024-07-12 | MOLYBDIC ACID 85%, 100gm w/o Calibration | NO | 1 | 1705 | 1705 | 2011.9 | 1705 | 2011.9 | 0 | 1705 | 2011.92 | ZMAT | 2024-05-13 | 2024-06-13
RE/0066-CQL-02 | Central Quality Lab 2010_New | 2010 | GR01 | 2010 | SWD Central office-75 | Testwel Instruments Company | 9110000621 | 1680 |  |  | 2024-07-12 | AMMONIUM FERROUS SULPHATE AR, 500gm w/o | NO | 1 | 500 | 500 | 590 | 0 | 0 | 500 | 0 | 0 | ZMAT | 2024-05-13 | 2024-06-13
RE/0066-CQL-02 | Central Quality Lab 2010_New | 2010 | GR01 | 2010 | SWD Central office-75 | Testwel Instruments Company | 9110000621 | 1690 |  |  | 2024-07-12 | POTASSIUM IODIDE AR, 100gm w/o Calibrati | NO | 1 | 3000 | 3000 | 3540 | 3000 | 3540 | 0 | 3000 | 3539.86 | ZMAT | 2024-05-13 | 2024-06-13
RE/0066-CQL-02 | Central Quality Lab 2010_New | 2010 | GR01 | 2010 | SWD Central office-75 | Testwel Instruments Company | 9110000621 | 1700 |  |  | 2024-07-12 | STARCH SOLUBLE (potato), 500gm w/o Calib | NO | 1 | 2370 | 2370 | 2796.6 | 2370 | 2796.6 | 0 | 2370 | 2796.89 | ZMAT | 2024-05-13 | 2024-06-13
RE/0066-CQL-02 | Central Quality Lab 2010_New | 2010 | GR01 | 2010 | SWD Central office-75 | Testwel Instruments Company | 9110000621 | 1710 |  |  | 2024-07-12 | PHENOLPHTHALEIN powder (pH indicator), 2 | NO | 1 | 225 | 225 | 265.5 | 0 | 0 | 225 | 0 | 0 | ZMAT | 2024-05-13 | 2024-06-13
RE/0066-CQL-02 | Central Quality Lab 2010_New | 2010 | GR01 | 2010 | SWD Central office-75 | Testwel Instruments Company | 9110000621 | 1720 |  |  | 2024-07-12 | WATER D.M. 5ltr w/o Calibration Certifi | NO | 2 | 1900 | 3800 | 4484 | 3800 | 4484 | 0 | 3800 | 4483.83 | ZMAT | 2024-05-13 | 2024-06-13
RE/0066-CQL-02 | Central Quality Lab 2010_New | 2010 | GR01 | 2010 | SWD Central office-75 | Testwel Instruments Company | 9110000621 | 1730 |  |  | 2024-07-12 | TIN MEAL GRANULATED AR, 100gm w/o Calibr | NO | 1 | 2245 | 2245 | 2649.1 | 0 | 0 | 2245 | 0 | 0 | ZMAT | 2024-05-13 | 2024-06-13
RE/0066-CQL-02 | Central Quality Lab 2010_New | 2010 | GR01 | 2010 | SWD Central office-75 | Testwel Instruments Company | 9110000621 | 1740 |  |  | 2024-07-12 | TIN METAL AR powder, 100gm w/o Calibrati | NO | 1 | 1600 | 1600 | 1888 | 1600 | 1888 | 0 | 1600 | 1887.93 | ZMAT | 2024-05-13 | 2024-06-13
RE/0066-CQL-02 | Central Quality Lab 2010_New | 2010 | GR01 | 2010 | SWD Central office-75 | Testwel Instruments Company | 9110000621 | 1750 |  |  | 2024-07-12 | THYMOL BLUE indicator solution, 125ml w/ | NO | 1 | 410 | 410 | 483.8 | 410 | 483.8 | 0 | 410 | 483.98 | ZMAT | 2024-05-13 | 2024-06-13
RE/0066-CQL-02 | Central Quality Lab 2010_New | 2010 | GR01 | 2010 | SWD Central office-75 | Testwel Instruments Company | 9110000621 | 1760 |  |  | 2024-07-12 | Googles for Lab w/o Calibration Certific | NO | 10 | 65 | 650 | 767 | 650 | 767 | 0 | 650 | 766.97 | ZMAT | 2024-05-13 | 2024-06-13
RE/0066-CQL-02 | Central Quality Lab 2010_New | 2010 | GR01 | 2010 | SWD Central office-75 | Testwel Instruments Company | 9110000621 | 1770 |  |  | 2024-07-12 | Mask Box (General Purpose), Pack of 100 | NO | 0.1 | 0.1 | 0.01 | 0.01 | 0 | 0 | 0.01 | 0 | 0 | ZMAT | 2024-05-13 | 2024-06-13
RE/0066-CQL-02 | Central Quality Lab 2010_New | 2010 | GR01 | 2010 | SWD Central office-75 | Testwel Instruments Company | 9110000621 | 1780 |  |  | 2024-07-12 | Asbestos Gloves. (Pair) w/o Calibration | NO | 2 | 550 | 1100 | 1298 | 1100 | 1298 | 0 | 1100 | 1297.95 | ZMAT | 2024-05-13 | 2024-06-13
RE/0066-CQL-02 | Central Quality Lab 2010_New | 2010 | GR01 | 2010 | SWD Central office-75 | Testwel Instruments Company | 9110000621 | 1790 |  |  | 2024-07-12 | Ear Plug w/o Calibration Certificate | NO | 50 | 50 | 2500 | 2950 | 2500 | 2950 | 0 | 2500 | 2949.89 | ZMAT | 2024-05-13 | 2024-06-13
RE/0066-CQL-02 | Central Quality Lab 2010_New | 2010 | GR01 | 2010 | SWD Central office-75 | Testwel Instruments Company | 9110000621 | 1800 |  |  | 2024-07-12 | Hand Surgical Gloves (Pack of 100) w/o C | NO | 3 | 100 | 300 | 354 | 300 | 354 | 0 | 300 | 353.99 | ZMAT | 2024-05-13 | 2024-06-13
RE/0066-CQL-02 | Central Quality Lab 2010_New | 2010 | GR01 | 2010 | SWD Central office-75 | Testwel Instruments Company | 9110000621 | 1810 |  |  | 2024-07-12 | Rubber Gloves. (Pair) w/o Calibration Ce | NO | 2 | 125 | 250 | 295 | 250 | 295 | 0 | 250 | 294.99 | ZMAT | 2024-05-13 | 2024-06-13
RE/0066-CQL-02 | Central Quality Lab 2010_New | 2010 | GR01 | 2010 | SWD Central office-75 | Testwel Instruments Company | 9110000621 | 1820 |  |  | 2024-07-12 | ABC Type Fire Extengushier, 6kgs w/o Cal | NO | 6 | 1000 | 6000 | 7080 | 6000 | 7080 | 0 | 6000 | 7079.73 | ZMAT | 2024-05-13 | 2024-06-13
RE/0066-CQL-02 | Central Quality Lab 2010_New | 2010 | GR01 | 2010 | SWD Central office-75 | Testwel Instruments Company | 9110000621 | 1830 |  |  | 2024-07-12 | Wood Saw, 18 inches w/o Calibration Cert | NO | 2 | 850 | 1700 | 2006 | 1700 | 2006 | 0 | 1700 | 2005.92 | ZMAT | 2024-05-13 | 2024-06-13
RE/0066-CQL-02 | Central Quality Lab 2010_New | 2010 | GR01 | 2010 | SWD Central office-75 | Testwel Instruments Company | 9110000621 | 1840 |  |  | 2024-07-12 | Cube Mould Clipper to pick Cubes of 150m | NO | 1 | 1900 | 1900 | 2242 | 1900 | 2242 | 0 | 1900 | 2241.91 | ZMAT | 2024-05-13 | 2024-06-13
RE/0066-CQL-02 | Central Quality Lab 2010_New | 2010 | GR01 | 2010 | SWD Central office-75 | Testwel Instruments Company | 9110000621 | 1850 |  |  | 2024-07-12 | Pocket pH Meter with Calibration Certifi | NO | 1 | 1250 | 1250 | 1475 | 1250 | 1475 | 0 | 1250 | 1474.94 | ZMAT | 2024-05-13 | 2024-06-13
RE/0066-CQL-02 | Central Quality Lab 2010_New | 2010 | GR01 | 2010 | SWD Central office-75 | Testwel Instruments Company | 9110000621 | 1860 |  |  | 2024-07-12 | TDS Meter, Pocket, Digital with Calibrat | NO | 1 | 950 | 950 | 1121 | 950 | 1121 | 0 | 950 | 1120.96 | ZMAT | 2024-05-13 | 2024-06-13
RE/0066-CQL-02 | Central Quality Lab 2010_New | 2010 | GR01 | 2010 | SWD Central office-75 | Testwel Instruments Company | 9110000621 | 1870 |  |  | 2024-07-12 | Plastic Measuring Cylinder, Cap.: 100ml | NO | 1 | 100 | 100 | 118 | 100 | 118 | 0 | 100 | 118 | ZMAT | 2024-05-13 | 2024-06-13
RE/0066-CQL-02 | Central Quality Lab 2010_New | 2010 | GR01 | 2010 | SWD Central office-75 | Testwel Instruments Company | 9110000621 | 1880 |  |  | 2024-07-12 | Plastic Measuring Cylinder, Cap.: 250ml | NO | 1 | 150 | 150 | 177 | 150 | 177 | 0 | 150 | 176.99 | ZMAT | 2024-05-13 | 2024-06-13
RE/0066-CQL-02 | Central Quality Lab 2010_New | 2010 | GR01 | 2010 | SWD Central office-75 | Testwel Instruments Company | 9110000621 | 1890 |  |  | 2024-07-12 | Plastic Measuring Cylinder, Cap.: 500ml | NO | 1 | 200 | 200 | 236 | 200 | 236 | 0 | 200 | 235.99 | ZMAT | 2024-05-13 | 2024-06-13
RE/0066-CQL-02 | Central Quality Lab 2010_New | 2010 | GR01 | 2010 | SWD Central office-75 | Testwel Instruments Company | 9110000621 | 1900 |  |  | 2024-07-12 | Plastic Beaker, Cap. 250ml w/o Calibrati | NO | 1 | 50 | 50 | 59 | 50 | 59 | 0 | 50 | 59 | ZMAT | 2024-05-13 | 2024-06-13
RE/0066-CQL-02 | Central Quality Lab 2010_New | 2010 | GR01 | 2010 | SWD Central office-75 | Testwel Instruments Company | 9110000621 | 1910 |  |  | 2024-07-12 | Plastic Beaker, Cap. 500ml w/o Calibrati | NO | 1 | 75 | 75 | 88.5 | 75 | 88.5 | 0 | 75 | 89 | ZMAT | 2024-05-13 | 2024-06-13
RE/0066-CQL-02 | Central Quality Lab 2010_New | 2010 | GR01 | 2010 | SWD Central office-75 | Testwel Instruments Company | 9110000621 | 1920 |  |  | 2024-07-12 | Wet and Dry Thermometer with Calibration | NO | 1 | 950 | 950 | 1121 | 950 | 1121 | 0 | 950 | 1120.96 | ZMAT | 2024-05-13 | 2024-06-13
RE/0066-CQL-02 | Central Quality Lab 2010_New | 2010 | GR01 | 2010 | SWD Central office-75 | Testwel Instruments Company | 9110000621 | 1930 |  |  | 2024-07-12 | Chloride Test Kit (Disposable Type) Rang | NO | 3 | 1850 | 5550 | 6549 | 5550 | 6549 | 0 | 5550 | 6548.75 | ZMAT | 2024-05-13 | 2024-06-13
RE/0066-CQL-02 | Central Quality Lab 2010_New | 2010 | GR01 | 2010 | SWD Central office-75 | Testwel Instruments Company | 9110000621 | 1940 |  |  | 2024-07-12 | Mould, Cast Iron, for 100mm Cube with IS | NO | 12 | 1850 | 22200 | 26196 | 22200 | 26196 | 0 | 22200 | 26195 | ZMAT | 2024-05-13 | 2024-06-13
RE/0066-CQL-02 | Central Quality Lab 2010_New | 2010 | GR01 | 2010 | SWD Central office-75 | Testwel Instruments Company | 9110000621 | 1950 |  |  | 2024-07-12 | Reaction Container as per IS:2386 (Part- | NO | 2 | 3000 | 6000 | 7080 | 6000 | 7080 | 0 | 6000 | 7079.73 | ZMAT | 2024-05-13 | 2024-06-13
RE/0066-CQL-02 | Central Quality Lab 2010_New | 2010 | GR01 | 2010 | SWD Central office-75 | Commercial Equipment | 9110000635 | 280 |  |  | 2024-05-13 | Mandril for UTM 32mm DIA w/o Calibration | NO | 1 | 3320 | 3320 | 3917.6 | 3320 | 3917.6 | 0 | 3320 | 3917.61 | ZMAT | 2024-05-13 | 2024-06-13
RE/0066-CQL-02 | Central Quality Lab 2010_New | 2010 | GR01 | 2010 | SWD Central office-75 | Commercial Equipment | 9110000635 | 290 |  |  | 2024-05-13 | Mandril for UTM 40mm DIA w/o Calibration | NO | 1 | 3320 | 3320 | 3917.6 | 3320 | 3917.6 | 0 | 3320 | 3917.61 | ZMAT | 2024-05-13 | 2024-06-13
RE/0066-CQL-02 | Central Quality Lab 2010_New | 2010 | GR01 | 2010 | SWD Central office-75 | Commercial Equipment | 9110000635 | 300 |  |  | 2024-05-13 | Mandril for UTM 64mm DIA w/o Calibration | NO | 1 | 3320 | 3320 | 3917.6 | 3320 | 3917.6 | 0 | 3320 | 3917.61 | ZMAT | 2024-05-13 | 2024-06-13
RE/0066-CQL-02 | Central Quality Lab 2010_New | 2010 | GR01 | 2010 | SWD Central office-75 | Commercial Equipment | 9110000635 | 310 |  |  | 2024-05-13 | Abrasive Powder (PER KG) w/o Calibration | NO | 5 | 504 | 2520 | 2973.6 | 2520 | 2973.6 | 0 | 2520 | 2973.61 | ZMAT | 2024-05-13 | 2024-06-13
RE/0066-CQL-02 | Central Quality Lab 2010_New | 2010 | GR01 | 2010 | SWD Central office-75 | Commercial Equipment | 9110000635 | 320 |  |  | 2024-05-13 | Capping Compound, Pack of 5kg | NO | 2 | 647 | 1294 | 1526.92 | 1294 | 1526.92 | 0 | 1294 | 1526.92 | ZMAT | 2024-05-13 | 2024-06-13
RE/0066-CQL-02 | Central Quality Lab 2010_New | 2010 | GR01 | 2010 | SWD Central office-75 | Commercial Equipment | 9110000636 | 10 |  |  | 2024-05-13 | Steel Cutting Machine up size 355 mm w/o | NO | 1 | 17200 | 17200 | 20296 | 17200 | 20296 | 0 | 17200.52 | 20296.59 | ZMAT | 2024-05-13 | 2024-06-13
RE/0066-CQL-02 | Central Quality Lab 2010_New | 2010 | GR01 | 2010 | SWD Central office-75 | Commercial Equipment | 9110000636 | 40 |  |  | 2024-05-13 | Kerosene Oil, per ltr w/o Calibration Ce | NO | 5 | 304 | 1520 | 1793.6 | 1520 | 1793.6 | 0 | 1520 | 1793.6 | ZMAT | 2024-05-13 | 2024-06-13
RE/0066-CQL-02 | Central Quality Lab 2010_New | 2010 | GR01 | 2010 | SWD Central office-75 | Commercial Equipment | 9110000636 | 50 |  |  | 2024-05-13 | File Set / Punch for Gauge Length Length | NO | 1 | 1000 | 1000 | 1180 | 1000 | 1180 | 0 | 1000 | 1180 | ZMAT | 2024-05-13 | 2024-06-13
RE/0066-CQL-02 | Central Quality Lab 2010_New | 2010 | GR01 | 2010 | SWD Central office-75 | Commercial Equipment | 9110000636 | 60 |  |  | 2024-05-13 | Lab Apron w/o Calibration Certificate | NO | 6 | 680 | 4080 | 4814.4 | 4080 | 4814.4 | 0 | 4080 | 4814.39 | ZMAT | 2024-05-13 | 2024-06-13
RE/0066-CQL-02 | Central Quality Lab 2010_New | 2010 | GR01 | 2010 | SWD Central office-75 | Commercial Equipment | 9110000636 | 70 |  |  | 2024-05-13 | Lab Head Cover Mask (Pack of 100) w/o Ca | NO | 1 | 1000 | 1000 | 1180 | 1000 | 1180 | 0 | 1000 | 1180 | ZMAT | 2024-05-13 | 2024-06-13
RE/0066-CQL-02 | Central Quality Lab 2010_New | 2010 | GR01 | 2010 | SWD Central office-75 | Commercial Equipment | 9110000636 | 80 |  |  | 2024-05-13 | 3-ply plywood sheet of 3mm for brick, 24 | NO | 10 | 240 | 2400 | 2832 | 2400 | 2832 | 0 | 2400 | 2832 | ZMAT | 2024-05-13 | 2024-06-13
RE/0066-CQL-02 | Central Quality Lab 2010_New | 2010 | GR01 | 2010 | SWD Central office-75 | Commercial Equipment | 9110000636 | 90 |  |  | 2024-05-13 | 4mm thick plywood for paver block, (Pai | NO | 10 | 360 | 3600 | 4248 | 3600 | 4248 | 0 | 3600 | 4247.99 | ZMAT | 2024-05-13 | 2024-06-13
RE/0066-CQL-02 | Central Quality Lab 2010_New | 2010 | GR01 | 2010 | SWD Central office-75 | Commercial Equipment | 9110000636 | 100 |  |  | 2024-05-13 | Wood Chisesl not as per IS 4020 w/o Cali | NO | 1 | 440 | 440 | 519.2 | 0 | 0 | 440 | 0 | 0 | ZMAT | 2024-05-13 | 2024-06-13
RE/0066-CQL-02 | Central Quality Lab 2010_New | 2010 | GR01 | 2010 | SWD Central office-75 | Commercial Equipment | 9110000636 | 110 |  |  | 2024-05-13 | Sieve Openor (for opening sieve from sie | NO | 1 | 360 | 360 | 424.8 | 360 | 424.8 | 0 | 360 | 424.8 | ZMAT | 2024-05-13 | 2024-06-13
RE/0066-CQL-02 | Central Quality Lab 2010_New | 2010 | GR01 | 2010 | SWD Central office-75 | Commercial Equipment | 9110000636 | 120 |  |  | 2024-05-13 | Sand Pouring Cylinder Apparatus, large | NO | 1 | 12496 | 12496 | 14745.28 | 12496 | 14745.28 | 0 | 12496 | 14745.26 | ZMAT | 2024-05-13 | 2024-06-13
RE/0066-CQL-02 | Central Quality Lab 2010_New | 2010 | GR01 | 2010 | SWD Central office-75 | Commercial Equipment | 9110000636 | 130 |  |  | 2024-05-13 | Hand Tile Cutting Machine with spare bla | NO | 1 | 10240 | 10240 | 12083.2 | 10240 | 12083.2 | 0 | 10240 | 12083.19 | ZMAT | 2024-05-13 | 2024-06-13
RE/0066-CQL-02 | Central Quality Lab 2010_New | 2010 | GR01 | 2010 | SWD Central office-75 | Commercial Equipment | 9110000636 | 140 |  |  | 2024-05-13 | Mecury 500gm "Ordinary" | NO | 1 | 11840 | 11840 | 13971.2 | 11840 | 13971.2 | 0 | 11840 | 13971.18 | ZMAT | 2024-05-13 | 2024-06-13
RE/0066-CQL-02 | Central Quality Lab 2010_New | 2010 | GR01 | 2010 | SWD Central office-75 | M/s Satyam Gases | 9110000684 | 20 |  |  | 2024-08-28 | Oxygen Cylinder | NO | 1 | 7350 | 7350 | 8673 | 7350 | 8673 | 0 | 7350 | 8673 | ZMAT | 2024-08-28 | 2025-02-27
RE/0066-CQL-02 | Central Quality Lab 2010_New | 2010 | GR01 | 2010 | SWD Central office-75 | G K Industries | 9110000839 | 10 |  |  | 2024-12-18 | Refilling of Argon Gas Cylinder | NO | 60 | 3250 | 195000 | 230100 | 107250 | 126555 | 87750 | 107250 | 126555 | ZMAT | 2024-12-18 | 2025-12-18
RE/0066-CQL-02 | Central Quality Lab 2010_New | 2010 | GR01 | 2010 | SMARTWORLD THE EDITION | Commercial Equipment | 9110001339 | 10 |  |  | 2025-10-25 | Indian Heavy Duty Blade for AAC Block | NO | 5 | 7020 | 35100 | 41418 | 35100 | 41418 | 0 | 35100 | 41418 | ZMAT
RE/0066-CQL-02 | Central Quality Lab 2010_New | 2010 | GR01 | 2010 | SMARTWORLD THE EDITION | Frontline Construction | 9140000184 | 20 |  |  | 2023-07-21 | Civil foundation works at Central Lab | AU | 1 | 84317.3 | 84317.3 | 99494.41 | 0 | 0 | 84317.3 | 0 | 0 | ZSER | 2023-07-19 | 2023-08-03
RE/0066-CQL-02 | Central Quality Lab 2010_New | 2010 | GR01 | 2010 | SWD Central office-75 | SSS Services Private Limited | 9140000323 | 10 |  |  | 2024-07-26 | Rental Of Vehicle for Quality lab | AU | 1 | 560000 | 560000 | 627200 | 560000 | 627200 | 0 | 560000 | 627200 | ZSER | 2024-07-27 | 2026-03-25
RE/0066-CQL-02 | Central Quality Lab 2010_New | 2010 | GR01 | 2010 | SWD Central office-75 | SSS Services Private Limited | 9140000323 | 20 |  |  | 2024-07-26 | Rental Of Vehicle for Quality lab | AU | 1 | 840000 | 350000 | 413000 | 818644.07 | 966000 | 468644.07 | 815084.75 | 961800 | ZSER | 2024-07-27 | 2026-03-25
RE/0066-CQL-02 | Central Quality Lab 2010_New | 2010 | GR01 | 2010 | SWD Central office-75 | SSS Services Private Limited | 9140000323 | 20 |  |  | 2024-07-26 | Rental Of Vehicle for Quality lab | AU | 1 | 0 | 490000 | 548800 | 862500 | 966000 | 372500 | 858750 | 961800 | ZSER | 2024-07-27 | 2026-03-25
RE/0066-CQL-02 | Central Quality Lab 2010_New | 2010 | GR01 | 2010 | SWD Central office-75 | SSS Services Private Limited | 9140000323 | 30 |  |  | 2024-07-26 | Rental of vehicle for Quality lab | AU | 1 | 45000 | 45000 | 53100 | 45000 | 53100 | 0 | 45000 | 53100 | ZSER | 2024-07-27 | 2026-03-25
RE/0066-CQL-02 | Central Quality Lab 2010_New | 2010 | GR01 | 2010 | SWD Central office-75 | Pahuja Aircon Pvt LtdVinay Malik | 9140000359 | 10 |  |  | 2024-09-02 | Installation, Testing & Comm. of AC'S | AU | 1 | 81300 | 81300 | 95934 | 0 | 0 | 81300 | 0 | 0 | ZSER | 2024-09-02 | 2024-09-02
RE/0066-CQL-02 | Central Quality Lab 2010_New | 2010 | GR01 | 2010 | SWD Central office-75 | Jaibir Enterprises | 9140000380 | 10 |  |  | 2024-11-06 | Removal of Debris from Central Quality L | AU | 1 | 84000 | 84000 | 99120 | 37800 | 44604 | 46200 | 37800 | 44604 | ZSER | 2024-11-06 | 2025-12-31
RE/0066-CQL-02 | Central Quality Lab 2010_New | 2010 | GR01 | 2010 | SWD Central office-75 | Maanak Callab Private Limited | 9140000388 | 10 |  |  | 2024-10-25 | Calibration of Lab Equipments at Central | AU | 1 | 67735 | 67735 | 79927.3 | 21428.26 | 25285.35 | 46306.74 | 21428.3 | 25285.39 | ZSER | 2024-10-25 | 2025-10-24
RE/0066-CQL-02 | Central Quality Lab 2010_New | 2010 | GR01 | 2010 | SWD Central office-75 | Maanak Callab Private Limited | 9140000388 | 20 |  |  | 2024-10-25 | Calibration of CTM at Central Quality la | AU | 1 | 6650 | 6650 | 7847 | 0 | 0 | 6650 | 0 | 0 | ZSER | 2024-10-25 | 2025-10-24
RE/0066-CQL-02 | Central Quality Lab 2010_New | 2010 | GR01 | 2010 | SWD Central office-75 | Commercial Equipment | 9140000401 | 10 |  |  | 2024-12-31 | AMC for Lab Equipments at Central Qualit | AU | 1 | 316635 | 316635 | 373629.3 | 158317.5 | 186814.65 | 158317.5 | 158317.5 | 186814.65 | ZSER | 2024-12-31 | 2025-12-31
RE/0066-CQL-02 | Central Quality Lab 2010_New | 2010 | GR01 | 2010 | SWD Central office-75 | Commercial Equipment | 9140000401 | 20 |  |  | 2024-12-31 | cost of Consumable Materials | AU | 1 | 18677 | 18677 | 22038.86 | 18677 | 22038.86 | 0 | 18677 | 22038.86 | ZSER | 2024-12-31 | 2025-12-31
RE/0066-CQL-02 | Central Quality Lab 2010_New | 2010 | GR01 | 2010 | SWD Central office-75 | Commercial Equipment | 9140000401 | 30 |  |  | 2024-12-31 | cost of Consumable Materials | AU | 1 | 78189.75 | 78189.75 | 92263.91 | 78189.75 | 92263.91 | 0 | 78189.75 | 92263.91 | ZSER | 2024-12-31 | 2025-12-31
RE/0066-CQL-02 | Central Quality Lab 2010_New | 2010 | GR01 | 2010 | SWD Central office-75 | Commercial Equipment | 9140000401 | 50 |  |  | 2024-12-31 | Amendment-1 for AMC for Lab Equipmnet | AU | 1 | 37335 | 37335 | 44055.3 | 37335 | 44055.3 | 0 | 37335 | 44055.3 | ZSER | 2024-12-31 | 2025-12-31
RE/0066-CQL-02 | Central Quality Lab 2010_New | 2010 | GR01 | 2010 | SWD Central office-75 | DRS ENGINEERING & CALIBRATION SERVI | 9140000484 | 10 |  |  | 2025-08-06 | Calibration of Lab Equipments at Central | AU | 1 | 69360 | 69360 | 81844.8 | 68935 | 81343.3 | 425 | 68935 | 81343.3 | ZSER | 2025-07-31 | 2025-08-30
RE/0066-CQL-02 | Central Quality Lab 2010_New | 2010 | GR01 | 2010 | SMARTWORLD THE EDITION | Ametek Instruments India Private Li | 9140000515 | 10 |  |  | 2025-10-17 | AMC and Calibration charge for SPECTROCH | AU | 1 | 100000 | 100000 | 118000 | 100000 | 118000 | 0 | 100000 | 118000 | ZSER | 2025-10-16 | 2026-10-16
RE/0066-CQL-02 | Central Quality Lab 2010_New | 2010 | GR01 | 2010 | SMARTWORLD THE EDITION | SHIVATMIKA PROJECTSBIJENDER SINGH | 9140000576 | 10 |  |  | 2026-02-17 | Repairing Work for Sec-75 Lab | AU | 1 | 768373.86 | 768373.86 | 906681.15 | 0 | 0 | 768373.86 | 0 | 0 | ZSER | 2026-02-16 | 2026-04-16
RE/0066-CQL-02 | Central Quality Lab 2010_New | 2010 | GR01 | 2010 | SMARTWORLD THE EDITION | ACCUTECH TECHNICAL SERVICES PRIVATELIMITED | 9160002645 | 10 |  |  | 2026-01-16 | Calibration of lab equipments | AU | 1 | 37800 | 37800 | 44604 | 37800 | 44604 | 0 | 37800 | 44604 | ZGEN | 2026-01-14 | 2026-02-14
RE/0066-CQL-02 | Central Quality Lab 2010_New | 2010 | GR01 | 2010 | SMARTWORLD THE EDITION | AIMIL LTDMr. Madan Sharma | 9160002778 | 10 |  |  | 2026-02-24 | AMC for lab equipment at central quality | AU | 1 | 283575 | 283575 | 334618.5 | 283575 | 334618.5 | 0 | 283575 | 334618.5 | ZGEN | 2026-02-19 | 2027-02-19
RE/0066-NPE-AD-01 | House Keeping Expenses | 2010 |  | 2010 | SMARTWORLD THE EDITION | Updater Services limited | 9110000231 | 10 |  |  | 2023-08-01 | Consumables/Cleaning Material | NO | 85000 | 1 | 85000 | 85000 | 0 | 0 | 85000 | 0 | 0 | ZMAT | 2025-01-20 | 2025-03-20
RE/0066-NPE-AD-01 | House Keeping Expenses | 2010 |  | 2010 | SMARTWORLD THE EDITION | Updater Services limited | 9110000231 | 20 |  |  | 2023-08-01 | Consumables/Cleaning Material | NO | 7500 | 1 | 7500 | 8850 | 0 | 0 | 7500 | 0 | 0 | ZMAT | 2025-01-20 | 2025-03-20
RE/0066-NPE-AD-01 | House Keeping Expenses | 2010 |  | 2010 | SMARTWORLD THE EDITION | Updater Services limited | 9110000231 | 30 |  |  | 2023-08-01 | Consumables/Cleaning Material | NO | 4177.11 | 1 | 4177.11 | 4928.99 | 0 | 0 | 4177.11 | 0 | 0 | ZMAT | 2025-01-20 | 2025-03-20
RE/0066-NPE-AD-01 | House Keeping Expenses | 2010 |  | 2010 | SMARTWORLD THE EDITION | Updater Services limited | 9110000231 | 40 |  |  | 2023-08-01 | SCOTCH BRIGHT 3M | NO | 2 | 27.77 | 55.54 | 65.54 | 0 | 0 | 55.54 | 0 | 0 | ZMAT | 2025-01-20 | 2025-03-20
RE/0066-NPE-AD-01 | House Keeping Expenses | 2010 |  | 2010 | SMARTWORLD THE EDITION | Updater Services limited | 9110000231 | 50 |  |  | 2023-08-01 | COLIN 500 ML | NO | 3 | 100.8 | 302.4 | 356.83 | 0 | 0 | 302.4 | 0 | 0 | ZMAT | 2025-01-20 | 2025-03-20
RE/0066-NPE-AD-01 | House Keeping Expenses | 2010 |  | 2010 | SMARTWORLD THE EDITION | Updater Services limited | 9110000231 | 60 |  |  | 2023-08-01 | ODONIL 75 GMS | NO | 2 | 71.4 | 142.8 | 168.5 | 0 | 0 | 142.8 | 0 | 0 | ZMAT | 2025-01-20 | 2025-03-20
RE/0066-NPE-AD-01 | House Keeping Expenses | 2010 |  | 2010 | SMARTWORLD THE EDITION | Updater Services limited | 9110000231 | 70 |  |  | 2023-08-01 | HARD BROOM (BIG) | NO | 2 | 54.34 | 108.68 | 108.68 | 0 | 0 | 108.68 | 0 | 0 | ZMAT | 2025-01-20 | 2025-03-20
RE/0066-NPE-AD-01 | House Keeping Expenses | 2010 |  | 2010 | SMARTWORLD THE EDITION | Updater Services limited | 9110000231 | 80 |  |  | 2023-08-01 | FEM HAND WASH 5 LITS | NO | 1 | 760.63 | 760.63 | 897.54 | 0 | 0 | 760.63 | 0 | 0 | ZMAT | 2025-01-20 | 2025-03-20
RE/0066-NPE-AD-01 | House Keeping Expenses | 2010 |  | 2010 | SMARTWORLD THE EDITION | Updater Services limited | 9110000231 | 90 |  |  | 2023-08-01 | PRILL 425 ML | NO | 2 | 99.02 | 198.04 | 233.69 | 0 | 0 | 198.04 | 0 | 0 | ZMAT | 2025-01-20 | 2025-03-20
RE/0066-NPE-AD-01 | House Keeping Expenses | 2010 |  | 2010 | SMARTWORLD THE EDITION | Updater Services limited | 9110000231 | 100 |  |  | 2023-08-01 | TASKI - R2 | NO | 5 | 236.25 | 1181.25 | 1393.88 | 0 | 0 | 1181.25 | 0 | 0 | ZMAT | 2025-01-20 | 2025-03-20
RE/0066-NPE-AD-01 | House Keeping Expenses | 2010 |  | 2010 | SMARTWORLD THE EDITION | Updater Services limited | 9110000231 | 110 |  |  | 2023-08-01 | COMPOSTABLE GARBAGE BAG 20 x20 | NO | 5 | 114.71 | 573.55 | 676.79 | 0 | 0 | 573.55 | 0 | 0 | ZMAT | 2025-01-20 | 2025-03-20
RE/0066-NPE-AD-01 | House Keeping Expenses | 2010 |  | 2010 | SMARTWORLD THE EDITION | Deskbasket office SuppliesVandana | 9110000560 | 190 |  |  | 2024-05-28 | BIO URINAL SCREEN - Multiple color (6" r | NO | 10 | 55 | 550 | 649 | 110 | 129.8 | 440 | 110 | 129.8 | ZMAT | 2024-04-01 | 2025-03-31
RE/0066-NPE-AD-01 | House Keeping Expenses | 2010 |  | 2010 | SMARTWORLD THE EDITION | Deskbasket office SuppliesVandana | 9110000560 | 200 |  |  | 2024-05-28 | Blue Dust controller set (24 inch) | NO | 2 | 178 | 356 | 420.08 | 356 | 420.08 | 0 | 356.37 | 420.52 | ZMAT | 2024-04-01 | 2025-03-31
RE/0066-NPE-AD-01 | House Keeping Expenses | 2010 |  | 2010 | SMARTWORLD THE EDITION | Deskbasket office SuppliesVandana | 9110000560 | 210 |  |  | 2024-05-28 | Bucket (comes in 5Ltr) | NO | 2 | 60 | 120 | 141.6 | 0 | 0 | 120 | 0 | 0 | ZMAT | 2024-04-01 | 2025-03-31
RE/0066-NPE-AD-01 | House Keeping Expenses | 2010 |  | 2010 | SMARTWORLD THE EDITION | Deskbasket office SuppliesVandana | 9110000560 | 220 |  |  | 2024-05-28 | Carpet brush (Hard) - Plastic | NO | 3 | 40 | 120 | 141.6 | 120 | 141.6 | 0 | 120 | 141.6 | ZMAT | 2024-04-01 | 2025-03-31
RE/0066-NPE-AD-01 | House Keeping Expenses | 2010 |  | 2010 | SMARTWORLD THE EDITION | Deskbasket office SuppliesVandana | 9110000560 | 230 |  |  | 2024-05-28 | Cobweb brush (Jala brush), good quality | NO | 2 | 88 | 176 | 207.68 | 0 | 0 | 176 | 0 | 0 | ZMAT | 2024-04-01 | 2025-03-31
RE/0066-NPE-AD-01 | House Keeping Expenses | 2010 |  | 2010 | SMARTWORLD THE EDITION | Deskbasket office SuppliesVandana | 9110000560 | 240 |  |  | 2024-05-28 | DISPOSABLE BAG BIG BLACK 36x44, 120 micr | NO | 20 | 82 | 1640 | 1935.2 | 410 | 483.8 | 1230 | 410 | 483.8 | ZMAT | 2024-04-01 | 2025-03-31
RE/0066-NPE-AD-01 | House Keeping Expenses | 2010 |  | 2010 | SMARTWORLD THE EDITION | Deskbasket office SuppliesVandana | 9110000560 | 250 |  |  | 2024-05-28 | DISPOSABLE BAG SMALL BLACK (20x24), 120 | NO | 10 | 82 | 820 | 967.6 | 410 | 483.8 | 410 | 410 | 483.8 | ZMAT | 2024-04-01 | 2025-03-31
RE/0066-NPE-AD-01 | House Keeping Expenses | 2010 |  | 2010 | SMARTWORLD THE EDITION | Deskbasket office SuppliesVandana | 9110000560 | 260 |  |  | 2024-05-28 | Dusting cloth (20x20 cm) - check | NO | 2 | 10 | 20 | 23.6 | 10 | 11.8 | 10 | 10 | 10.5 | ZMAT | 2024-04-01 | 2025-03-31
RE/0066-NPE-AD-01 | House Keeping Expenses | 2010 |  | 2010 | SMARTWORLD THE EDITION | Deskbasket office SuppliesVandana | 9110000560 | 270 |  |  | 2024-05-28 | Fem Hand Wash ( 5Ltr) | NO | 3 | 550 | 1650 | 1947 | 550 | 649 | 1100 | 550 | 649 | ZMAT | 2024-04-01 | 2025-03-31
RE/0066-NPE-AD-01 | House Keeping Expenses | 2010 |  | 2010 | SMARTWORLD THE EDITION | Deskbasket office SuppliesVandana | 9110000560 | 280 |  |  | 2024-05-28 | FLOOR CLEANING CLOTH MEDIUM | NO | 8 | 17 | 136 | 160.48 | 51 | 60.18 | 85 | 51 | 53.56 | ZMAT | 2024-04-01 | 2025-03-31
RE/0066-NPE-AD-01 | House Keeping Expenses | 2010 |  | 2010 | SMARTWORLD THE EDITION | Deskbasket office SuppliesVandana | 9110000560 | 290 |  |  | 2024-05-28 | HIT Spray (Red/Black) (200 ML) | NO | 8 | 82 | 656 | 774.08 | 410 | 483.8 | 246 | 410 | 483.8 | ZMAT | 2024-04-01 | 2025-03-31
RE/0066-NPE-AD-01 | House Keeping Expenses | 2010 |  | 2010 | SMARTWORLD THE EDITION | Deskbasket office SuppliesVandana | 9110000560 | 300 |  |  | 2024-05-28 | HIT Spray (Red/Black) (200 ML) | NO | 3 | 82 | 246 | 290.28 | 164 | 193.52 | 82 | 164 | 193.52 | ZMAT | 2024-04-01 | 2025-03-31
RE/0066-NPE-AD-01 | House Keeping Expenses | 2010 |  | 2010 | SMARTWORLD THE EDITION | Deskbasket office SuppliesVandana | 9110000560 | 310 |  |  | 2024-05-28 | Micro fiber cloth - blue (10x10 inches) | NO | 15 | 42 | 630 | 743.4 | 210 | 247.8 | 420 | 210 | 220.5 | ZMAT | 2024-04-01 | 2025-03-31
RE/0066-NPE-AD-01 | House Keeping Expenses | 2010 |  | 2010 | SMARTWORLD THE EDITION | Deskbasket office SuppliesVandana | 9110000560 | 320 |  |  | 2024-05-28 | Prill (425 ml) | NO | 20 | 89 | 1780 | 2100.4 | 890 | 1050.2 | 890 | 890 | 1050.2 | ZMAT | 2024-04-01 | 2025-03-31
RE/0066-NPE-AD-01 | House Keeping Expenses | 2010 |  | 2010 | SMARTWORLD THE EDITION | Deskbasket office SuppliesVandana | 9110000560 | 330 |  |  | 2024-05-28 | Room Freshner 220 ML | NO | 25 | 88 | 2200 | 2596 | 880 | 1038.4 | 1320 | 880 | 1038.4 | ZMAT | 2024-04-01 | 2025-03-31
RE/0066-NPE-AD-01 | House Keeping Expenses | 2010 |  | 2010 | SMARTWORLD THE EDITION | Deskbasket office SuppliesVandana | 9110000560 | 340 |  |  | 2024-05-28 | Soft broom with big pipe | NO | 3 | 66 | 198 | 233.64 | 0 | 0 | 198 | 0 | 0 | ZMAT | 2024-04-01 | 2025-03-31
RE/0066-NPE-AD-01 | House Keeping Expenses | 2010 |  | 2010 | SMARTWORLD THE EDITION | Deskbasket office SuppliesVandana | 9110000560 | 350 |  |  | 2024-05-28 | Tile Cleaner (1 Ltr) | NO | 10 | 120 | 1200 | 1416 | 0 | 0 | 1200 | 0 | 0 | ZMAT | 2024-04-01 | 2025-03-31
RE/0066-NPE-AD-01 | House Keeping Expenses | 2010 |  | 2010 | SMARTWORLD THE EDITION | Deskbasket office SuppliesVandana | 9110000560 | 360 |  |  | 2024-05-28 | Wiper Large - 3ft | NO | 6 | 87 | 522 | 615.96 | 0 | 0 | 522 | 0 | 0 | ZMAT | 2024-04-01 | 2025-03-31
RE/0066-NPE-AD-01 | House Keeping Expenses | 2010 |  | 2010 | SMARTWORLD THE EDITION | Updater Services limited | 9160000285 | 20 |  |  | 2023-08-01 | Additional Housekeeping Manpower | AU | 1 | 30099.24 | 30099.24 | 35517.1 | 30099.19 | 35517.05 | 0.05 | 30099.19 | 35517.04 | ZGEN | 2023-07-12 | 2024-03-31
RE/0066-NPE-AD-02 | Pantry Expenses | 2010 |  | 2010 | SMARTWORLD THE EDITION | Luck Aqua | 9110000209 | 20 |  |  | 2023-07-24 | Drinking Water | NO | 2858 | 15 | 42870 | 48014.4 | 15404.87 | 17253.45 | 27465.13 | 15405 | 17254 | ZMAT | 2025-01-20 | 2025-03-20
RE/0066-NPE-AD-02 | Pantry Expenses | 2010 |  | 2010 | SMARTWORLD THE EDITION | Wings BeveragesCharanpreet | 9110000260 | 10 |  |  | 2023-09-02 | Tea | PC | 120 | 4.5 | 540 | 567 | 0 | 0 | 540 | 0 | 0 | ZMAT | 2025-01-20 | 2025-03-20
RE/0066-NPE-AD-02 | Pantry Expenses | 2010 |  | 2010 | SMARTWORLD THE EDITION | Wings BeveragesCharanpreet | 9110000260 | 20 |  |  | 2023-09-02 | Masala Tea -CCD (100 Dip) | BOX | 100 | 248 | 24800 | 26040 | 0 | 0 | 24800 | 0 | 0 | ZMAT | 2025-01-20 | 2025-03-20
RE/0066-NPE-AD-02 | Pantry Expenses | 2010 |  | 2010 | SMARTWORLD THE EDITION | Wings BeveragesCharanpreet | 9110000260 | 30 |  |  | 2023-09-02 | Ginger Tea - CCD (100 Dip) | BOX | 100 | 248 | 24800 | 26040 | 0 | 0 | 24800 | 0 | 0 | ZMAT | 2025-01-20 | 2025-03-20
RE/0066-NPE-AD-02 | Pantry Expenses | 2010 |  | 2010 | SMARTWORLD THE EDITION | Wings BeveragesCharanpreet | 9110000260 | 40 |  |  | 2023-09-02 | Elaichi Tea - CCD (100 Dip) | BOX | 100 | 248 | 24800 | 26040 | 0 | 0 | 24800 | 0 | 0 | ZMAT | 2025-01-20 | 2025-03-20
RE/0066-NPE-AD-02 | Pantry Expenses | 2010 |  | 2010 | SMARTWORLD THE EDITION | Wings BeveragesCharanpreet | 9110000260 | 50 |  |  | 2023-09-02 | Green Tea - CCD | PC | 3777.777 | 4.5 | 17000 | 17850 | 0 | 0 | 17000 | 0 | 0 | ZMAT | 2025-01-20 | 2025-03-20
RE/0066-NPE-AD-02 | Pantry Expenses | 2010 |  | 2010 | SMARTWORLD THE EDITION | Wings BeveragesCharanpreet | 9110000260 | 60 |  |  | 2023-09-02 | Coffee Beans - CCD | KG | 100 | 623 | 62300 | 65415 | 0 | 0 | 62300 | 0 | 0 | ZMAT | 2025-01-20 | 2025-03-20
RE/0066-NPE-AD-02 | Pantry Expenses | 2010 |  | 2010 | SMARTWORLD THE EDITION | Wings BeveragesCharanpreet | 9110000260 | 70 |  |  | 2023-09-02 | Assam/ Classic/ Plain Tea - CCD | BOX | 100 | 150 | 15000 | 15750 | 0 | 0 | 15000 | 0 | 0 | ZMAT | 2025-01-20 | 2025-03-20
RE/0066-NPE-AD-02 | Pantry Expenses | 2010 |  | 2010 | SMARTWORLD THE EDITION | Wings BeveragesCharanpreet | 9110000260 | 80 |  |  | 2023-09-02 | Sugar Crystal Branded | KG | 800 | 58 | 46400 | 48720 | 0 | 0 | 46400 | 0 | 0 | ZMAT | 2025-01-20 | 2025-03-20
RE/0066-NPE-AD-02 | Pantry Expenses | 2010 |  | 2010 | SMARTWORLD THE EDITION | Wings BeveragesCharanpreet | 9110000260 | 90 |  |  | 2023-09-02 | Sugar Cube branded | KG | 24 | 90 | 2160 | 2419.2 | 0 | 0 | 2160 | 0 | 0 | ZMAT | 2025-01-20 | 2025-03-20
RE/0066-NPE-AD-02 | Pantry Expenses | 2010 |  | 2010 | SMARTWORLD THE EDITION | Wings BeveragesCharanpreet | 9110000260 | 100 |  |  | 2023-09-02 | Flavor GreenTea(Tulsi/Mint/Honey/lemon) | PC | 3600 | 5 | 18000 | 18900 | 0 | 0 | 18000 | 0 | 0 | ZMAT | 2025-01-20 | 2025-03-20
RE/0066-NPE-AD-03 | Electricity Expenses | 2010 |  | 2010 | SMARTWORLD THE EDITION | Luck Aqua | 9110000209 | 10 |  |  | 2023-07-24 | Drinking Water | NO | 117 | 15 | 1755 | 1965.6 | 1755 | 1965.6 | 0 | 1755 | 1965 | ZMAT | 2025-01-20 | 2025-03-20
RE/0066-NPE-AD-04 | Office Expenses | 2010 |  | 2010 | SMARTWORLD THE EDITION | HansrajHansraj | 9110000264 | 10 |  |  | 2023-09-06 | Horticulture Water Tanker | L | 77 | 325 | 25025 | 25025 | 25025 | 25025 | 0 | 25025 | 25025 | ZMAT | 2025-01-20 | 2025-03-20
RE/0066-NPE-AD-04 | Office Expenses | 2010 |  | 2010 | SMARTWORLD THE EDITION | HansrajHansraj | 9110000264 | 20 |  |  | 2023-09-06 | Washroom Water Tanker | L | 198 | 650 | 128700 | 128700 | 128700 | 128700 | 0 | 128700 | 128700 | ZMAT | 2025-01-20 | 2025-03-20
RE/0066-NPE-AD-04 | Office Expenses | 2010 |  | 2010 | SMARTWORLD THE EDITION | Max ComMayank | 9160000367 | 10 |  |  | 2023-09-08 | Walky Talky on Rent (Sep'23 to Mar'24) | AU | 1 | 5220 | 5220 | 6159.6 | 5220.34 | 6160 | 0.34 | 5219.66 | 6159.2 | ZGEN | 2023-09-01 | 2024-03-31
RE/0066-NPE-AD-04 | Office Expenses | 2010 |  | 2010 | SMARTWORLD THE EDITION | Max ComMayank | 9160000367 | 20 |  |  | 2023-09-08 | Walky Talky on Rent (Sep'23 to Mar'24) | AU | 1 | 5220 | 1740 | 2053.2 | 1740.68 | 2054 | 0.68 | 1740 | 2053.2 | ZGEN | 2023-09-01 | 2024-03-31
RE/0066-NPE-AD-05 | Power & Fuel Expenses | 2010 |  | 2010 | SMARTWORLD THE EDITION | Treis Solutions LLP | 9110000191 | 10 |  |  | 2023-07-11 | Diesel | L | 5000 | 99.5 | 497500 | 497500 | 0 | 0 | 497500 | 0 | 0 | ZMAT | 2025-01-20 | 2025-03-20
RE/0066-NPE-AD-05 | Power & Fuel Expenses | 2010 |  | 2010 | SMARTWORLD THE EDITION | Treis Solutions LLP | 9110000191 | 20 |  |  | 2023-07-11 | Freight Charges | L | 10 | 199 | 1990 | 2348.2 | 0 | 0 | 1990 | 0 | 0 | ZMAT | 2025-01-20 | 2025-03-20
RE/0066-NPE-AD-06 | Asset | 2010 | GR01 | 2010 |  |  |  | 0 | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
RE/0066-NPE-AD-07 | Vehicle repair & Maintenance | 2010 | GR01 | 2010 |  |  |  | 0 | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
RE/0066-NPE-AD-08 | Printing & Stationery Expenses | 2010 |  | 2010 | SMARTWORLD THE EDITION | Book Mark Office AutomationPreeti Shivhare | 9110000370 | 10 |  |  | 2024-01-31 | Cobra File | NO | 100 | 11 | 1100 | 1298 | 220 | 259.6 | 880 | 220.39 | 259.79 | ZMAT | 2025-01-20 | 2025-03-20
RE/0066-NPE-AD-08 | Printing & Stationery Expenses | 2010 |  | 2010 | SMARTWORLD THE EDITION | Book Mark Office AutomationPreeti Shivhare | 9110000370 | 20 |  |  | 2024-01-31 | Index File | NO | 100 | 75 | 7500 | 8850 | 1500 | 1770 | 6000 | 1500 | 1768.61 | ZMAT | 2025-01-20 | 2025-03-20
RE/0066-NPE-AD-08 | Printing & Stationery Expenses | 2010 |  | 2010 | SMARTWORLD THE EDITION | Book Mark Office AutomationPreeti Shivhare | 9110000370 | 30 |  |  | 2024-01-31 | Box File | NO | 100 | 110 | 11000 | 12980 | 550 | 649 | 10450 | 550 | 648.49 | ZMAT | 2025-01-20 | 2025-03-20
RE/0066-NPE-AD-08 | Printing & Stationery Expenses | 2010 |  | 2010 | SMARTWORLD THE EDITION | Book Mark Office AutomationPreeti Shivhare | 9110000370 | 40 |  |  | 2024-01-31 | Stapler Big | NO | 20 | 181 | 3620 | 4271.6 | 181 | 213.58 | 3439 | 181 | 213.43 | ZMAT | 2025-01-20 | 2025-03-20
RE/0066-NPE-AD-08 | Printing & Stationery Expenses | 2010 |  | 2010 | SMARTWORLD THE EDITION | Book Mark Office AutomationPreeti Shivhare | 9110000370 | 50 |  |  | 2024-01-31 | Stapler | NO | 20 | 66 | 1320 | 1557.6 | 660 | 778.8 | 660 | 660 | 778.19 | ZMAT | 2025-01-20 | 2025-03-20
RE/0066-NPE-AD-08 | Printing & Stationery Expenses | 2010 |  | 2010 | SMARTWORLD THE EDITION | Book Mark Office AutomationPreeti Shivhare | 9110000370 | 60 |  |  | 2024-01-31 | Stapler Pin Big | NO | 20 | 13.9 | 278 | 328.04 | 277.97 | 328 | 0.03 | 278 | 327.74 | ZMAT | 2025-01-20 | 2025-03-20
RE/0066-NPE-AD-08 | Printing & Stationery Expenses | 2010 |  | 2010 | SMARTWORLD THE EDITION | Book Mark Office AutomationPreeti Shivhare | 9110000370 | 70 |  |  | 2024-01-31 | Stapler Pin Small | NO | 20 | 6 | 120 | 141.6 | 120 | 141.6 | 0 | 120 | 141.49 | ZMAT | 2025-01-20 | 2025-03-20
RE/0066-NPE-AD-08 | Printing & Stationery Expenses | 2010 |  | 2010 | SMARTWORLD THE EDITION | Book Mark Office AutomationPreeti Shivhare | 9110000370 | 80 |  |  | 2024-01-31 | Calculator | NO | 50 | 382 | 19100 | 22538 | 2292 | 2704.56 | 16808 | 2292 | 2702.48 | ZMAT | 2025-01-20 | 2025-03-20
RE/0066-NPE-AD-08 | Printing & Stationery Expenses | 2010 |  | 2010 | SMARTWORLD THE EDITION | Book Mark Office AutomationPreeti Shivhare | 9110000370 | 90 |  |  | 2024-01-31 | Register @12% | NO | 10 | 110 | 1100 | 1232 | 1100 | 1232 | 0 | 1100 | 1232 | ZMAT | 2025-01-20 | 2025-03-20
RE/0066-NPE-AD-08 | Printing & Stationery Expenses | 2010 |  | 2010 | SMARTWORLD THE EDITION | Book Mark Office AutomationPreeti Shivhare | 9110000370 | 100 |  |  | 2024-01-31 | Register 144pgs | NO | 10 | 79 | 790 | 884.8 | 790 | 884.8 | 0 | 790 | 884.8 | ZMAT | 2025-01-20 | 2025-03-20
RE/0066-NPE-AD-08 | Printing & Stationery Expenses | 2010 |  | 2010 | SMARTWORLD THE EDITION | Book Mark Office AutomationPreeti Shivhare | 9110000370 | 110 |  |  | 2024-01-31 | Measurement Tape 5mtr | NO | 5 | 106 | 530 | 625.4 | 530 | 625.4 | 0 | 530 | 624.91 | ZMAT | 2025-01-20 | 2025-03-20
RE/0066-NPE-AD-08 | Printing & Stationery Expenses | 2010 |  | 2010 | SMARTWORLD THE EDITION | Book Mark Office AutomationPreeti Shivhare | 9110000370 | 120 |  |  | 2024-01-31 | Measurement Tape Big | NO | 1 | 289 | 289 | 341.02 | 288.98 | 341 | 0.02 | 289 | 340.73 | ZMAT | 2025-01-20 | 2025-03-20
RE/0066-NPE-AD-08 | Printing & Stationery Expenses | 2010 |  | 2010 | SMARTWORLD THE EDITION | Book Mark Office AutomationPreeti Shivhare | 9110000370 | 130 |  |  | 2024-01-31 | Tape Dispenser | NO | 5 | 60 | 300 | 354 | 300 | 354 | 0 | 300 | 353.72 | ZMAT | 2025-01-20 | 2025-03-20
RE/0066-NPE-AD-08 | Printing & Stationery Expenses | 2010 |  | 2010 | SMARTWORLD THE EDITION | Book Mark Office AutomationPreeti Shivhare | 9110000370 | 140 |  |  | 2024-01-31 | Brown Tape 2 Inch | NO | 12 | 32 | 384 | 453.12 | 384.07 | 453.2 | 0.07 | 384 | 452.84 | ZMAT | 2025-01-20 | 2025-03-20
RE/0066-NPE-AD-08 | Printing & Stationery Expenses | 2010 |  | 2010 | SMARTWORLD THE EDITION | Book Mark Office AutomationPreeti Shivhare | 9110000370 | 150 |  |  | 2024-01-31 | Cello Tape 2 Inch | NO | 12 | 32 | 384 | 453.12 | 384.07 | 453.2 | 0.07 | 384 | 452.84 | ZMAT | 2025-01-20 | 2025-03-20
RE/0066-NPE-AD-08 | Printing & Stationery Expenses | 2010 |  | 2010 | SMARTWORLD THE EDITION | Book Mark Office AutomationPreeti Shivhare | 9110000370 | 160 |  |  | 2024-01-31 | Cello Tape 1 Inch | NO | 12 | 14 | 168 | 198.24 | 167.97 | 198.2 | 0.03 | 168 | 198.05 | ZMAT | 2025-01-20 | 2025-03-20
RE/0066-NPE-AD-08 | Printing & Stationery Expenses | 2010 |  | 2010 | SMARTWORLD THE EDITION | Book Mark Office AutomationPreeti Shivhare | 9110000370 | 170 |  |  | 2024-01-31 | Permanent Marker | NO | 10 | 13 | 130 | 153.4 | 130 | 153.4 | 0 | 130 | 153.28 | ZMAT | 2025-01-20 | 2025-03-20
RE/0066-NPE-AD-08 | Printing & Stationery Expenses | 2010 |  | 2010 | SMARTWORLD THE EDITION | Book Mark Office AutomationPreeti Shivhare | 9110000370 | 180 |  |  | 2024-01-31 | Highlighter | NO | 5 | 12.5 | 62.5 | 73.75 | 62.46 | 73.7 | 0.04 | 62.5 | 73.64 | ZMAT | 2025-01-20 | 2025-03-20
RE/0066-NPE-AD-08 | Printing & Stationery Expenses | 2010 |  | 2010 | SMARTWORLD THE EDITION | Book Mark Office AutomationPreeti Shivhare | 9110000370 | 190 |  |  | 2024-01-31 | Pencil (12%) | NO | 5 | 48 | 240 | 283.2 | 240 | 283.2 | 0 | 240 | 282.98 | ZMAT | 2025-01-20 | 2025-03-20
RE/0066-NPE-AD-08 | Printing & Stationery Expenses | 2010 |  | 2010 | SMARTWORLD THE EDITION | Book Mark Office AutomationPreeti Shivhare | 9110000370 | 200 |  |  | 2024-01-31 | Ball Pen Blue | NO | 100 | 6 | 600 | 708 | 600 | 708 | 0 | 600 | 707.45 | ZMAT | 2025-01-20 | 2025-03-20
RE/0066-NPE-AD-08 | Printing & Stationery Expenses | 2010 |  | 2010 | SMARTWORLD THE EDITION | Book Mark Office AutomationPreeti Shivhare | 9110000370 | 210 |  |  | 2024-01-31 | Ball Pen Black | NO | 40 | 6 | 240 | 283.2 | 60 | 70.8 | 180 | 60 | 70.74 | ZMAT | 2025-01-20 | 2025-03-20
RE/0066-NPE-AD-08 | Printing & Stationery Expenses | 2010 |  | 2010 | SMARTWORLD THE EDITION | Book Mark Office AutomationPreeti Shivhare | 9110000370 | 220 |  |  | 2024-01-31 | Gel Pen Blue | NO | 40 | 9 | 360 | 424.8 | 225 | 265.5 | 135 | 225 | 265.39 | ZMAT | 2025-01-20 | 2025-03-20
RE/0066-NPE-AD-08 | Printing & Stationery Expenses | 2010 |  | 2010 | SMARTWORLD THE EDITION | Book Mark Office AutomationPreeti Shivhare | 9110000370 | 230 |  |  | 2024-01-31 | GEL PEN RED | NO | 20 | 9 | 180 | 212.4 | 90 | 106.2 | 90 | 90 | 106.12 | ZMAT | 2025-01-20 | 2025-03-20
RE/0066-NPE-AD-08 | Printing & Stationery Expenses | 2010 |  | 2010 | SMARTWORLD THE EDITION | Book Mark Office AutomationPreeti Shivhare | 9110000370 | 240 |  |  | 2024-01-31 | Glue Stick | NO | 20 | 27 | 540 | 637.2 | 135 | 159.3 | 405 | 135 | 159.27 | ZMAT | 2025-01-20 | 2025-03-20
RE/0066-NPE-AD-08 | Printing & Stationery Expenses | 2010 |  | 2010 | SMARTWORLD THE EDITION | Book Mark Office AutomationPreeti Shivhare | 9110000370 | 250 |  |  | 2024-01-31 | Steel Scale | NO | 20 | 19 | 380 | 448.4 | 228 | 269.04 | 152 | 228 | 268.79 | ZMAT | 2025-01-20 | 2025-03-20
RE/0066-NPE-AD-08 | Printing & Stationery Expenses | 2010 |  | 2010 | SMARTWORLD THE EDITION | Book Mark Office AutomationPreeti Shivhare | 9110000370 | 260 |  |  | 2024-01-31 | Correction Pen | NO | 20 | 17.6 | 352 | 415.36 | 35.2 | 41.54 | 316.8 | 35.2 | 41.57 | ZMAT | 2025-01-20 | 2025-03-20
RE/0066-NPE-AD-08 | Printing & Stationery Expenses | 2010 |  | 2010 | SMARTWORLD THE EDITION | Book Mark Office AutomationPreeti Shivhare | 9110000370 | 270 |  |  | 2024-01-31 | Binder Clip 25 MM | NO | 50 | 32 | 1600 | 1888 | 384 | 453.12 | 1216 | 384 | 452.84 | ZMAT | 2025-01-20 | 2025-03-20
RE/0066-NPE-AD-08 | Printing & Stationery Expenses | 2010 |  | 2010 | SMARTWORLD THE EDITION | Book Mark Office AutomationPreeti Shivhare | 9110000370 | 280 |  |  | 2024-01-31 | Envelope A3 Yellow | NO | 100 | 4.88 | 488 | 575.84 | 243.98 | 287.9 | 244.02 | 244 | 287.77 | ZMAT | 2025-01-20 | 2025-03-20
RE/0066-NPE-AD-08 | Printing & Stationery Expenses | 2010 |  | 2010 | SMARTWORLD THE EDITION | Book Mark Office AutomationPreeti Shivhare | 9110000370 | 290 |  |  | 2024-01-31 | Envelope A4 Yellow | NO | 100 | 3.25 | 325 | 383.5 | 162.54 | 191.8 | 162.46 | 162.5 | 191.55 | ZMAT | 2025-01-20 | 2025-03-20
RE/0066-NPE-AD-08 | Printing & Stationery Expenses | 2010 |  | 2010 | SMARTWORLD THE EDITION | Book Mark Office AutomationPreeti Shivhare | 9110000370 | 300 |  |  | 2024-01-31 | Punching Machine Big | NO | 5 | 962 | 4810 | 5675.8 | 962 | 1135.16 | 3848 | 962 | 1134.31 | ZMAT | 2025-01-20 | 2025-03-20
RE/0066-NPE-AD-08 | Printing & Stationery Expenses | 2010 |  | 2010 | SMARTWORLD THE EDITION | Book Mark Office AutomationPreeti Shivhare | 9110000370 | 310 |  |  | 2024-01-31 | Punching Machine | NO | 10 | 108 | 1080 | 1274.4 | 540 | 637.2 | 540 | 540 | 636.7 | ZMAT | 2025-01-20 | 2025-03-20
RE/0066-NPE-AD-08 | Printing & Stationery Expenses | 2010 |  | 2010 | SMARTWORLD THE EDITION | Book Mark Office AutomationPreeti Shivhare | 9110000370 | 320 |  |  | 2024-01-31 | Copier Paper A/4 | NO | 500 | 238 | 119000 | 133280 | 4760 | 5331.2 | 114240 | 4760 | 5331.2 | ZMAT | 2025-01-20 | 2025-03-20
RE/0066-NPE-AD-08 | Printing & Stationery Expenses | 2010 |  | 2010 | SMARTWORLD THE EDITION | Book Mark Office AutomationPreeti Shivhare | 9110000370 | 330 |  |  | 2024-01-31 | Note Pad | NO | 30 | 23.9 | 717 | 846.06 | 238.98 | 282 | 478.02 | 239 | 281.78 | ZMAT | 2025-01-20 | 2025-03-20
RE/0066-NPE-AD-08 | Printing & Stationery Expenses | 2010 |  | 2010 | SMARTWORLD THE EDITION | Book Mark Office AutomationPreeti Shivhare | 9110000370 | 340 |  |  | 2024-01-31 | Post It Flags | NO | 30 | 30 | 900 | 1062 | 150 | 177 | 750 | 150 | 176.86 | ZMAT | 2025-01-20 | 2025-03-20
RE/0066-NPE-AD-08 | Printing & Stationery Expenses | 2010 |  | 2010 | SMARTWORLD THE EDITION | Book Mark Office AutomationPreeti Shivhare | 9110000370 | 350 |  |  | 2024-01-31 | Sticky Pad | NO | 30 | 39.35 | 1180.5 | 1392.99 | 196.76 | 232.18 | 983.74 | 196.75 | 231.97 | ZMAT | 2025-01-20 | 2025-03-20
RE/0066-NPE-AD-08 | Printing & Stationery Expenses | 2010 |  | 2010 | SMARTWORLD THE EDITION | Book Mark Office AutomationPreeti Shivhare | 9110000370 | 360 |  |  | 2024-01-31 | Pen Holder | NO | 30 | 116 | 3480 | 4106.4 | 1160 | 1368.8 | 2320 | 1160 | 1367.73 | ZMAT | 2025-01-20 | 2025-03-20
RE/0066-NPE-AD-08 | Printing & Stationery Expenses | 2010 |  | 2010 | SMARTWORLD THE EDITION | Book Mark Office AutomationPreeti Shivhare | 9110000370 | 370 |  |  | 2024-01-31 | Notice Board 2 *3 Inch | NO | 7 | 856 | 5992 | 7070.56 | 1712.01 | 2020.17 | 4279.99 | 1712 | 2018.62 | ZMAT | 2025-01-20 | 2025-03-20
RE/0066-NPE-AD-08 | Printing & Stationery Expenses | 2010 |  | 2010 | SMARTWORLD THE EDITION | Book Mark Office AutomationPreeti Shivhare | 9110000370 | 380 |  |  | 2024-01-31 | Binder Clip 15 MM | NO | 21 | 20 | 420 | 495.6 | 240 | 283.2 | 180 | 240 | 282.98 | ZMAT | 2025-01-20 | 2025-03-20
RE/0066-NPE-AD-08 | Printing & Stationery Expenses | 2010 |  | 2010 | SMARTWORLD THE EDITION | Book Mark Office AutomationPreeti Shivhare | 9110000370 | 390 |  |  | 2024-01-31 | Binder Clip 19 MM | NO | 277 | 23 | 6371 | 7517.78 | 276 | 325.68 | 6095 | 276 | 325.35 | ZMAT | 2025-01-20 | 2025-03-20
RE/0066-NPE-AD-09 | Repair & Maintenance Expenses | 2010 | GR01 | 2010 |  |  |  | 0 | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
RE/0066-NPE-AD-10 | Travel Expenses | 2010 |  | 2010 |  |  |  | 0 | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
RE/0066-NPE-AD-11 | Security Manpower Expenses | 2010 |  | 2010 | SMARTWORLD THE EDITION | G4S SECURE SOLUTIONS (INDIA) PVT LT | 9160000272 | 10 |  |  | 2023-07-29 | Hiring of Manpower for Security | AU | 1 | 1910855.94 | 1910855.94 | 2254810.01 | 1910003.22 | 2253803.8 | 852.72 | 1910862.96 | 2254818.29 | ZGEN | 2023-06-29 | 2024-06-30
RE/0066-NPE-AD-11 | Security Manpower Expenses | 2010 |  | 2010 | SMARTWORLD THE EDITION | G4S SECURE SOLUTIONS (INDIA) PVT LT | 9160000272 | 20 |  |  | 2023-07-29 | Security Guard | AU | 1 | 258446.75 | 258446.75 | 304967.17 | 258442.23 | 304961.83 | 4.52 | 258447.08 | 304967.56 | ZGEN | 2023-06-29 | 2024-06-30
RE/0066-NPE-AD-11 | Security Manpower Expenses | 2010 |  | 2010 | SMARTWORLD THE EDITION | Max ComMayank | 9160000367 | 20 |  |  | 2023-09-08 | Walky Talky on Rent (Sep'23 to Mar'24) | AU | 1 | 0 | 3480 | 4106.4 | 3481.36 | 4108 | 1.36 | 3480 | 4106.4 | ZGEN | 2023-09-01 | 2024-03-31
RE/0066-NPE-BD-01 | Business development & Strategy Expenses | 2010 | GR01 | 2010 |  |  |  | 0 | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
RE/0066-NPE-BR-01 | Brokerage Expenses | 2010 | GR01 | 2010 |  |  |  | 0 | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
RE/0066-NPE-CR-01 | CRM Expenses | 2010 |  | 2010 | SMARTWORLD THE EDITION | Beli Ram ExclusivesAshish | 9110000333 | 10 |  |  | 2023-12-21 | silver articles for "The Edition" | NO | 250 | 2450 | 612500 | 630875 | 612500 | 630875 | 0 | 612500 | 630875 | ZMAT | 2025-01-20 | 2025-03-20
RE/0066-NPE-CR-01 | CRM Expenses | 2010 |  | 2010 | SMARTWORLD THE EDITION | Ipack Ind | 9110000342 | 10 |  |  | 2024-01-03 | Letter Heads For Edition | NO | 10000 | 3.25 | 32500 | 38350 | 30847.46 | 36400 | 1652.54 | 32500 | 38350 | ZMAT | 2025-01-20 | 2025-03-20
RE/0066-NPE-CR-01 | CRM Expenses | 2010 |  | 2010 | SMARTWORLD THE EDITION | Beli Ram ExclusivesAshish | 9110000391 | 10 |  |  | 2024-02-20 | Procurement of silver articles | NO | 350 | 2450 | 857500 | 883225 | 857500 | 883225 | 0 | 857500 | 883225 | ZMAT | 2025-01-20 | 2025-03-20
RE/0066-NPE-DA-01 | Design & Architecture Expenses | 2010 | GR01 | 2010 |  |  |  | 0 | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
RE/0066-NPE-FI-01 | Bank Commission & Bg | 2010 | GR01 | 2010 |  |  |  | 0 | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
RE/0066-NPE-FI-02 | Certification Expenses | 2010 |  | 2010 |  |  |  | 0 | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
RE/0066-NPE-FI-03 | Event Conference & Seminar Expenses | 2010 | GR01 | 2010 |  |  |  | 0 | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
RE/0066-NPE-FI-05 | Other Membership/ Misc Expense | 2010 | GR01 | 2010 |  |  |  | 0 | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
RE/0066-NPE-FI-06 | Other Professional Charges | 2010 |  | 2010 | SMARTWORLD THE EDITION | Pnam & Co. LLP | 9160000383 | 10 |  |  | 2023-09-22 | Proff. fee for Advisory and Review | AU | 1 | 337500 | 337500 | 398250 | 225000 | 265500 | 112500 | 225000 | 265500 | ZGEN | 2023-09-07 | 2023-10-31
RE/0066-NPE-FI-07 | Printing & Stationery Expenses | 2010 | GR01 | 2010 |  |  |  | 0 | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
RE/0066-NPE-FI-09 | ROC Filling | 2010 |  | 2010 |  |  |  | 0 | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
RE/0066-NPE-FI-12 | Statutory Auditors - Fee,Tax,OoP,Cert. | 2010 |  | 2010 |  |  |  | 0 | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
RE/0066-NPE-HR-01 | Payroll | 2010 | GR01 | 2010 |  |  |  | 0 | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
RE/0066-NPE-HR-02 | Complaince and Registeration Charges | 2010 |  | 2010 | SMARTWORLD THE EDITION | Ma Foi Strategic Consultants (P) LtSunir Bhalla | 9160000182 | 10 |  |  | 2023-06-23 | Professional Fee for Payroll Compliance | AU | 1 | 18240 | 18240 | 21523.2 | 18239.49 | 21522.6 | 0.51 | 18240 | 21523.2 | ZGEN | 2023-05-01 | 2024-09-30
RE/0066-NPE-HR-03 | Perks & Perquisits | 2010 | GR01 | 2010 |  |  |  | 0 | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
RE/0066-NPE-HR-04 | Staff Welfare | 2010 | GR01 | 2010 |  |  |  | 0 | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
RE/0066-NPE-HR-05 | Recruitment Expenses | 2010 | GR01 | 2010 |  |  |  | 0 | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
RE/0066-NPE-HR-06 | Insurance & Mediclaim | 2010 | GR01 | 2010 |  |  |  | 0 | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
RE/0066-NPE-HR-07 | Employee Engagement Cost | 2010 | GR01 | 2010 |  |  |  | 0 | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
RE/0066-NPE-HR-08 | Consultancy Charges | 2010 | GR01 | 2010 |  |  |  | 0 | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
RE/0066-NPE-HR-09 | Other Professional Charges | 2010 | GR01 | 2010 |  |  |  | 0 | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
RE/0066-NPE-IA-01 | Internal Audit Expenses | 2010 | GR01 | 2010 |  |  |  | 0 | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
RE/0066-NPE-IT-01 | Lease Line Expenses - NPE | 2010 |  | 2010 | SMARTWORLD THE EDITION | Tripleplay Interactive Network PvtMr. Dhananjay | 9160000279 | 10 |  |  | 2023-07-31 | ILL 10 Mbps | AU | 1 | 65000 | 65000 | 76700 | 63507.93 | 74939.36 | 1492.07 | 58786.1 | 69367.6 | ZGEN | 2023-07-20 | 2024-07-19
RE/0066-NPE-IT-01 | Lease Line Expenses - NPE | 2010 |  | 2010 | SMARTWORLD THE EDITION | Fusionnet Web Services LimitedMs. Palak | 9160000444 | 10 |  |  | 2023-11-17 | ILL 100 Mbps for sales Gallery 66, ETSY | AU | 1 | 320000 | 320000 | 377600 | 275363.08 | 324928.43 | 44636.92 | 297255.45 | 350761.43 | ZGEN | 2023-11-09 | 2024-11-08
RE/0066-NPE-IT-04 | Rental Charges IT - Street | 2010 |  | 2010 | SMARTWORLD THE EDITION | Nuways Creation Pvt. Ltd.Ravinder | 9160000469 | 10 |  |  | 2023-11-29 | Color Photocopier Model – Sharp BP50C26 | AU | 1 | 60000 | 60000 | 70800 | 60000 | 70800 | 0 | 60000 | 70800 | ZGEN | 2023-11-25 | 2024-11-24
RE/0066-NPE-IT-10 | R & M - Computers & It Services | 2010 | GR01 | 2010 | SMARTWORLD THE EDITION | Delta IT Network Pvt. Ltd.Mr. Sunil Yadav | 9110000357 | 10 |  |  | 2024-01-16 | HONEYWELL CONVERTER | NO | 2 | 1200 | 2400 | 2832 | 2400 | 2832 | 0 | 2400 | 2832 | ZMAT | 2025-01-20 | 2025-03-20
RE/0066-NPE-IT-10 | R & M - Computers & It Services | 2010 | GR01 | 2010 | SMARTWORLD THE EDITION | Delta IT Network Pvt. Ltd.Mr. Sunil Yadav | 9110000357 | 20 |  |  | 2024-01-16 | Cadyce Display port to HDMI Cable | NO | 2 | 1400 | 2800 | 3304 | 2800 | 3304 | 0 | 2800 | 3304 | ZMAT | 2025-01-20 | 2025-03-20
RE/0066-NPE-IT-10 | R & M - Computers & It Services | 2010 | GR01 | 2010 | SMARTWORLD THE EDITION | Delta IT Network Pvt. Ltd.Mr. Sunil Yadav | 9110000357 | 30 |  |  | 2024-01-16 | Cadyce Display port to HDMI Converter | NO | 3 | 1200 | 3600 | 4248 | 3600 | 4248 | 0 | 3600 | 4248 | ZMAT | 2025-01-20 | 2025-03-20
RE/0066-NPE-LG-01 | Legal Expenses | 2010 | GR01 | 2010 |  |  |  | 0 | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
RE/0066-NPE-MK-01 | Advertisement Expenses | 2010 |  | 2010 | SMARTWORLD THE EDITION | Span Communications | 9160000459 | 10 |  |  | 2023-11-22 | Print ads for Launch SW The Edition | AU | 1 | 6612000 | 6612000 | 6942600 | 6612000 | 6942600 | 0 | 6612000 | 6942600 | ZGEN | 2023-11-24 | 2023-11-29
RE/0066-NPE-MK-01 | Advertisement Expenses | 2010 |  | 2010 | SMARTWORLD THE EDITION | HT Media Limited | 9160000460 | 10 |  |  | 2023-11-23 | Print ads for Launch SW The Edition | AU | 1 | 4250000 | 4250000 | 4462500 | 4250000 | 4462500 | 0 | 4250000 | 4462500 | ZGEN | 2023-11-24 | 2024-01-20
RE/0066-NPE-MK-01 | Advertisement Expenses | 2010 |  | 2010 | SMARTWORLD THE EDITION | Spike Advertising Private Limited | 9160000634 | 10 |  |  | 2024-02-14 | Print Adv. the Launch of T-20 Campaign | AU | 1 | 4785000 | 4785000 | 5024250 | 4785000 | 5024250 | 0 | 4785000 | 5024250 | ZGEN | 2024-02-17 | 2024-02-17
RE/0066-NPE-MK-02 | Digital marketing | 2010 |  | 2010 | SMARTWORLD THE EDITION | Dotwise Digital Pvt LtdDhiraj Shirode | 9160000406 | 10 |  |  | 2023-10-17 | Design & dev and SFDC integration | AU | 1 | 140000 | 140000 | 165200 | 140000 | 165200 | 0 | 140000 | 165200 | ZGEN | 2023-10-10 | 2023-10-17
RE/0066-NPE-MK-02 | Digital marketing | 2010 |  | 2010 | SMARTWORLD THE EDITION | Orange Sky | 9160000417 | 10 |  |  | 2023-10-19 | Animation of 270 Degree Viewing room | AU | 1 | 1380000 | 1380000 | 1628400 | 0 | 0 | 1380000 | 0 | 0 | ZGEN | 2025-01-20 | 2025-03-20
RE/0066-NPE-MK-02 | Digital marketing | 2010 |  | 2010 | SMARTWORLD THE EDITION | Alchemist Marketing Talent Solution | 9160000438 | 10 |  |  | 2023-11-09 | Making of interactive digital brochure | AU | 1 | 410000 | 410000 | 483800 | 0 | 0 | 410000 | 0 | 0 | ZGEN | 2023-10-31 | 2023-11-10
RE/0066-NPE-MK-02 | Digital marketing | 2010 |  | 2010 | SMARTWORLD THE EDITION | Dotwise Digital Pvt LtdDhiraj Shirode | 9160000455 | 10 |  |  | 2023-11-22 | Digital Campaign SW The Edition-Dotwise | AU | 1 | 10994707 | 10994707 | 12973754.26 | 10994706.78 | 12973754 | 0.22 | 10994707.63 | 12973755 | ZGEN | 2023-10-17 | 2023-12-01
RE/0066-NPE-MK-02 | Digital marketing | 2010 |  | 2010 | SMARTWORLD THE EDITION | Realatte Ventures LLP | 9160000457 | 10 |  |  | 2023-11-22 | Digital Lead Generation. | AU | 1 | 8024250 | 8024250 | 9468615 | 8024250 | 9468615 | 0 | 8024250 | 9468615 | ZGEN | 2023-10-17 | 2023-12-03
RE/0066-NPE-MK-02 | Digital marketing | 2010 |  | 2010 | SMARTWORLD THE EDITION | E Corp Info Systems | 9160000458 | 10 |  |  | 2023-11-22 | Running Digital Campaign for Lead gen. | AU | 1 | 1575000 | 1575000 | 1858500 | 1575000 | 1858500 | 0 | 1575000 | 1858500 | ZGEN | 2023-10-19 | 2023-12-03
RE/0066-NPE-MK-02 | Digital marketing | 2010 |  | 2010 | SMARTWORLD THE EDITION | Info Edge India Ltd. | 9160000470 | 10 |  |  | 2023-11-30 | Lead Generation 99 Acres-The Edition | AU | 1 | 850000 | 850000 | 1003000 | 850000 | 1003000 | 0 | 850000 | 1003000 | ZGEN | 2023-11-30 | 2023-12-30
RE/0066-NPE-MK-02 | Digital marketing | 2010 |  | 2010 | SMARTWORLD THE EDITION | Huella Services Private Limited | 9160000478 | 10 |  |  | 2023-12-04 | Digital Campaign - Huella Servics | AU | 1 | 800000 | 800000 | 944000 | 800000 | 944000 | 0 | 800000 | 944000 | ZGEN | 2023-12-04 | 2024-01-03
RE/0066-NPE-MK-02 | Digital marketing | 2010 |  | 2010 | SMARTWORLD THE EDITION | Icubeswire Technologies private Lim | 9160000479 | 10 |  |  | 2023-12-04 | Digital Campaign for "The Edition" | AU | 1 | 848000 | 848000 | 1000640 | 848000 | 1000640 | 0 | 848000 | 1000640 | ZGEN | 2025-01-20 | 2025-03-20
RE/0066-NPE-MK-02 | Digital marketing | 2010 |  | 2010 | SMARTWORLD THE EDITION | Magicbricks Realty Services Limited | 9160000480 | 10 |  |  | 2023-12-05 | Digital Campaign for "The Edition" | AU | 1 | 500000 | 500000 | 590000 | 500000 | 590000 | 0 | 500000 | 590000 | ZGEN | 2023-12-05 | 2024-01-04
RE/0066-NPE-MK-02 | Digital marketing | 2010 |  | 2010 | SMARTWORLD THE EDITION | Locon Solutions Private Limited | 9160000481 | 10 |  |  | 2023-12-05 | Digital Campaign for "The Edition" | AU | 1 | 500000 | 500000 | 590000 | 500000 | 590000 | 0 | 500000 | 590000 | ZGEN | 2023-12-05 | 2024-01-04
RE/0066-NPE-MK-02 | Digital marketing | 2010 |  | 2010 | SMARTWORLD THE EDITION | Realatte Ventures LLP | 9160000620 | 10 |  |  | 2024-02-09 | Edition-Lead Generate Campaign-Realatte | AU | 1 | 7215000 | 7215000 | 8513700 | 7215000 | 8513700 | 0 | 7215000 | 8513700 | ZGEN | 2024-02-07 | 2024-03-23
RE/0066-NPE-MK-02 | Digital marketing | 2010 |  | 2010 | SMARTWORLD THE EDITION | Dotwise Digital Pvt LtdDhiraj Shirode | 9160000626 | 10 |  |  | 2024-02-12 | Edition-Lead Gen Campaign-Dotwise | AU | 1 | 3913801 | 3913801 | 4618285.18 | 3913800.85 | 4618285 | 0.15 | 3913801.02 | 4618285.2 | ZGEN | 2024-02-11 | 2024-03-27
RE/0066-NPE-MK-02 | Digital marketing | 2010 |  | 2010 | SMARTWORLD THE EDITION | Dotwise Digital Pvt LtdDhiraj Shirode | 9160000626 | 20 |  |  | 2024-02-12 | Equilisation Levy at 6% on Linkedin | AU | 1 | 9918 | 9918 | 9918 | 9918 | 9918 | 0 | 9918 | 9918 | ZGEN | 2024-02-11 | 2024-03-27
RE/0066-NPE-MK-03 | OOH Expense | 2010 |  | 2010 | SMARTWORLD THE EDITION | Interactive Communication Services | 9160000544 | 10 |  |  | 2024-01-05 | OOH sites-Launch SW The Edition | AU | 1 | 3728736 | 3728736 | 4399908.48 | 3728735.59 | 4399908 | 0.41 | 3728736.02 | 4399908.5 | ZGEN | 2023-12-01 | 2024-02-29
RE/0066-NPE-MK-03 | OOH Expense | 2010 |  | 2010 | SMARTWORLD THE EDITION | Sakshi Advertising Co. | 9160000545 | 10 |  |  | 2024-01-05 | Innovation 4 Sites | AU | 1 | 665000 | 665000 | 784700 | 665000 | 784700 | 0 | 665000 | 784700 | ZGEN | 2023-12-02 | 2024-03-01
RE/0066-NPE-MK-03 | OOH Expense | 2010 |  | 2010 | SMARTWORLD THE EDITION | OAP Mediatech Private Limited | 9160000546 | 10 |  |  | 2024-01-05 | OOH sites-Launch SW The Edition | AU | 1 | 6854839.8 | 6854839.8 | 8088710.96 | 6854839.83 | 8088711 | 0.03 | 6854839.83 | 8088711 | ZGEN | 2023-12-02 | 2024-03-01
RE/0066-NPE-MK-03 | OOH Expense | 2010 |  | 2010 | SMARTWORLD THE EDITION | GO LIVE | 9160000547 | 10 |  |  | 2024-01-05 | OOH sites-Launch SW The Edition | AU | 1 | 355000 | 355000 | 418900 | 355000 | 418900 | 0 | 355000 | 418900 | ZGEN | 2023-11-28 | 2023-12-27
RE/0066-NPE-MK-03 | OOH Expense | 2010 |  | 2010 | SMARTWORLD THE EDITION | Addgrowth Media Private Limited | 9160000549 | 10 |  |  | 2024-01-06 | Metro Pillar for Gurgaon Site (10 sites) | AU | 1 | 3312000 | 3312000 | 3908160 | 3312000 | 3908160 | 0 | 3312000 | 3908160 | ZGEN | 2023-12-26 | 2024-02-29
RE/0066-NPE-MK-03 | OOH Expense | 2010 |  | 2010 | SMARTWORLD THE EDITION | Global Media Services | 9160000606 | 10 |  |  | 2024-02-05 | Outdoor display at Faridabad | AU | 1 | 255200 | 255200 | 301136 | 255200 | 301136 | 0 | 255200 | 301136 | ZGEN | 2024-01-27 | 2024-02-26
RE/0066-NPE-MK-03 | OOH Expense | 2010 |  | 2010 | SMARTWORLD THE EDITION | OAP Mediatech Private Limited | 9160000695 | 10 |  |  | 2024-03-14 | OOH-Gurugram Sites-T20-Campaign-Edition | AU | 1 | 821250 | 821250 | 969075 | 821250 | 969075 | 0 | 821250 | 969075 | ZGEN | 2024-02-23 | 2024-03-24
RE/0066-NPE-MK-03 | OOH Expense | 2010 |  | 2010 | SMARTWORLD THE EDITION | OAP Mediatech Private Limited | 9160000697 | 10 |  |  | 2024-03-14 | Extension of Outdoor Hoardings | AU | 1 | 1350000 | 1350000 | 1593000 | 1350000 | 1593000 | 0 | 1350000 | 1593000 | ZGEN | 2024-03-01 | 2024-03-31
RE/0066-NPE-MK-03 | OOH Expense | 2010 |  | 2010 | SMARTWORLD THE EDITION | Addgrowth Media Private Limited | 9160000698 | 10 |  |  | 2024-03-14 | Extension of Outdoor Hoardings | AU | 1 | 1112000 | 1112000 | 1312160 | 1112000 | 1312160 | 0 | 1112000 | 1312160 | ZGEN | 2024-03-01 | 2024-03-31
RE/0066-NPE-MK-03 | OOH Expense | 2010 |  | 2010 | SMARTWORLD THE EDITION | Interactive Communication Services | 9160000699 | 10 |  |  | 2024-03-14 | Extension of Outdoor Hoardings | AU | 1 | 600000 | 600000 | 708000 | 600000 | 708000 | 0 | 600000 | 708000 | ZGEN | 2024-03-01 | 2024-03-31
RE/0066-NPE-MK-04 | Other Marketing Expenses | 2010 |  | 2010 | SMARTWORLD THE EDITION | Print Edge INC | 9110000306 | 10 |  |  | 2023-11-27 | Info Pack - A3 Closed size (Landscape) | NO | 100 | 600 | 60000 | 70800 | 60000 | 70800 | 0 | 60000 | 70800 | ZMAT | 2025-01-20 | 2025-03-20
RE/0066-NPE-MK-04 | Other Marketing Expenses | 2010 |  | 2010 | SMARTWORLD THE EDITION | Print Edge INC | 9110000308 | 10 |  |  | 2023-11-28 | Code66 A3 Hardbound Brochure Printing | NO | 350 | 1280 | 448000 | 528640 | 448000 | 528640 | 0 | 448000 | 528640 | ZMAT | 2025-01-20 | 2025-03-20
RE/0066-NPE-MK-04 | Other Marketing Expenses | 2010 |  | 2010 | SMARTWORLD THE EDITION | Innovative Designs | 9110000310 | 10 |  |  | 2023-11-28 | Hydraulic Clubhouse Scale Model | NO | 1 | 1650000 | 1650000 | 1947000 | 1650000 | 1947000 | 0 | 1650000 | 1947000 | ZMAT | 2025-01-20 | 2025-03-20
RE/0066-NPE-MK-04 | Other Marketing Expenses | 2010 |  | 2010 | SMARTWORLD THE EDITION | The Grey Cell | 9110000316 | 10 |  |  | 2023-12-12 | Box masking of code 66 Model | FT2 | 960 | 50 | 48000 | 56640 | 48000 | 56640 | 0 | 48000 | 56640 | ZMAT | 2025-01-20 | 2025-03-20
RE/0066-NPE-MK-04 | Other Marketing Expenses | 2010 |  | 2010 | SMARTWORLD THE EDITION | The Grey Cell | 9110000316 | 20 |  |  | 2023-12-12 | Box masking | FT2 | 1 | 2500 | 2500 | 2950 | 2500 | 2950 | 0 | 2500 | 2950 | ZMAT | 2025-01-20 | 2025-03-20
RE/0066-NPE-MK-04 | Other Marketing Expenses | 2010 |  | 2010 | SMARTWORLD THE EDITION | Ipack Ind | 9110000317 | 10 |  |  | 2023-12-12 | Letterhead for SW The Edition | NO | 10000 | 3.25 | 32500 | 38350 | 32500 | 38350 | 0 | 32500 | 38350 | ZMAT | 2025-01-20 | 2025-03-20
RE/0066-NPE-MK-04 | Other Marketing Expenses | 2010 |  | 2010 | SMARTWORLD THE EDITION | Print Edge INC | 9110000318 | 10 |  |  | 2023-12-12 | Printing of 4 Pager Handout | NO | 3000 | 19 | 57000 | 67260 | 57000 | 67260 | 0 | 57000 | 67260 | ZMAT | 2025-01-20 | 2025-03-20
RE/0066-NPE-MK-04 | Other Marketing Expenses | 2010 |  | 2010 | SMARTWORLD THE EDITION | Ipack Ind | 9110000323 | 10 |  |  | 2023-12-14 | Letter heads | NO | 10000 | 3.25 | 32500 | 38350 | 32500 | 38350 | 0 | 32500 | 38350 | ZMAT | 2025-01-20 | 2025-03-20
RE/0066-NPE-MK-04 | Other Marketing Expenses | 2010 |  | 2010 | SMARTWORLD THE EDITION | Ipack Ind | 9110000323 | 20 |  |  | 2023-12-14 | Cheque Envelope | NO | 5000 | 7 | 35000 | 41300 | 35000 | 41300 | 0 | 35000 | 41300 | ZMAT | 2025-01-20 | 2025-03-20
RE/0066-NPE-MK-04 | Other Marketing Expenses | 2010 |  | 2010 | SMARTWORLD THE EDITION | Ipack Ind | 9110000323 | 30 |  |  | 2023-12-14 | A4 Window Envelope | NO | 5000 | 19.5 | 97500 | 115050 | 97500 | 115050 | 0 | 97500 | 115050 | ZMAT | 2025-01-20 | 2025-03-20
RE/0066-NPE-MK-04 | Other Marketing Expenses | 2010 |  | 2010 | SMARTWORLD THE EDITION | Ipack Ind | 9110000323 | 40 |  |  | 2023-12-14 | Folder Cover | NO | 2000 | 35 | 70000 | 82600 | 70000 | 82600 | 0 | 70000 | 82600 | ZMAT | 2025-01-20 | 2025-03-20
RE/0066-NPE-MK-04 | Other Marketing Expenses | 2010 |  | 2010 | SMARTWORLD THE EDITION | Ipack Ind | 9110000323 | 50 |  |  | 2023-12-14 | Folder Envelope | NO | 2000 | 18.5 | 37000 | 43660 | 37000 | 43660 | 0 | 37000 | 43660 | ZMAT | 2025-01-20 | 2025-03-20
RE/0066-NPE-MK-04 | Other Marketing Expenses | 2010 |  | 2010 | SMARTWORLD THE EDITION | Aditya Printers | 9110000324 | 10 |  |  | 2023-12-14 | Application Form | NO | 1000 | 36 | 36000 | 42480 | 36000 | 42480 | 0 | 36000 | 42480 | ZMAT | 2025-01-20 | 2025-03-20
RE/0066-NPE-MK-04 | Other Marketing Expenses | 2010 |  | 2010 | SMARTWORLD THE EDITION | The Grey Cell | 9110000327 | 10 |  |  | 2023-12-19 | Rollup Standee with Banner Media Printin | NO | 20 | 1500 | 30000 | 35400 | 30000 | 35400 | 0 | 30000 | 35400 | ZMAT | 2025-01-20 | 2025-03-20
RE/0066-NPE-MK-04 | Other Marketing Expenses | 2010 |  | 2010 | SMARTWORLD THE EDITION | The Grey Cell | 9110000327 | 20 |  |  | 2023-12-19 | Freight | NO | 1 | 1000 | 1000 | 1180 | 1000 | 1180 | 0 | 1000 | 1180 | ZMAT | 2025-01-20 | 2025-03-20
RE/0066-NPE-MK-04 | Other Marketing Expenses | 2010 |  | 2010 | SMARTWORLD THE EDITION | M2n Services | 9110000339 | 10 |  |  | 2023-12-30 | Backlit Signboard-Sample Apartment-Sec66 | NO | 5 | 4.88 | 24.4 | 24.4 | 0 | 0 | 24.4 | 0 | 0 | ZMAT | 2025-01-20 | 2025-03-20
RE/0066-NPE-MK-04 | Other Marketing Expenses | 2010 |  | 2010 | SMARTWORLD THE EDITION | M2n Services | 9110000339 | 20 |  |  | 2023-12-30 | Golden Frame-Sample Apartment-Sec 66 | NO | 5 | 4.88 | 24.4 | 24.4 | 0 | 0 | 24.4 | 0 | 0 | ZMAT | 2025-01-20 | 2025-03-20
RE/0066-NPE-MK-04 | Other Marketing Expenses | 2010 |  | 2010 | SMARTWORLD THE EDITION | M2n Services | 9110000339 | 30 |  |  | 2023-12-30 | Pneumonic of T-Sample Apartment-Sec 66 | NO | 3 | 4.88 | 14.64 | 14.64 | 0 | 0 | 14.64 | 0 | 0 | ZMAT | 2025-01-20 | 2025-03-20
RE/0066-NPE-MK-04 | Other Marketing Expenses | 2010 |  | 2010 | SMARTWORLD THE EDITION | M2n Services | 9110000339 | 40 |  |  | 2023-12-30 | Golden Leaf -Sample Apartment-Sec 66 | NO | 4 | 4.88 | 19.52 | 19.52 | 0 | 0 | 19.52 | 0 | 0 | ZMAT | 2025-01-20 | 2025-03-20
RE/0066-NPE-MK-04 | Other Marketing Expenses | 2010 |  | 2010 | SMARTWORLD THE EDITION | M2n Services | 9110000339 | 50 |  |  | 2023-12-30 | Black Mate Vinyl-Sample Apartment-Sec66 | M | 2 | 4.88 | 9.76 | 9.76 | 0 | 0 | 9.76 | 0 | 0 | ZMAT | 2025-01-20 | 2025-03-20
RE/0066-NPE-MK-04 | Other Marketing Expenses | 2010 |  | 2010 | SMARTWORLD THE EDITION | New Sign Grafix | 9110000352 | 10 |  |  | 2024-01-11 | SAMPLE FLAT BARRICADES BRANDING-Edition | FT2 | 1625 | 35 | 56875 | 67112.5 | 56875 | 67112.5 | 0 | 56875 | 67112 | ZMAT | 2025-01-20 | 2025-03-20
RE/0066-NPE-MK-04 | Other Marketing Expenses | 2010 |  | 2010 | SMARTWORLD THE EDITION | Print Edge INC | 9110000354 | 10 |  |  | 2024-01-11 | A3 Info Doc-Sales Kit-100 Nos-Sec 66 | NO | 100 | 600 | 60000 | 70800 | 60000 | 70800 | 0 | 60000 | 70800 | ZMAT | 2025-01-20 | 2025-03-20
RE/0066-NPE-MK-04 | Other Marketing Expenses | 2010 |  | 2010 | SMARTWORLD THE EDITION | Max Media Industries | 9110000386 | 10 |  |  | 2024-02-15 | Sup. & Ins. of Backdrop and Standees | FT2 | 116 | 65 | 7540 | 8897.2 | 7540 | 8897.2 | 0 | 7539.8 | 8897 | ZMAT | 2025-01-20 | 2025-03-20
RE/0066-NPE-MK-04 | Other Marketing Expenses | 2010 |  | 2010 | SMARTWORLD THE EDITION | Max Media Industries | 9110000386 | 20 |  |  | 2024-02-15 | Installation Charges | NO | 1 | 1500 | 1500 | 1770 | 1500 | 1770 | 0 | 1500 | 1770 | ZMAT | 2025-01-20 | 2025-03-20
RE/0066-NPE-MK-04 | Other Marketing Expenses | 2010 |  | 2010 | SMARTWORLD THE EDITION | Max Media Industries | 9110000386 | 30 |  |  | 2024-02-15 | Cartage | NO | 1 | 1500 | 1500 | 1770 | 1500 | 1770 | 0 | 1500 | 1770 | ZMAT | 2025-01-20 | 2025-03-20
RE/0066-NPE-MK-04 | Other Marketing Expenses | 2010 |  | 2010 | SMARTWORLD THE EDITION | HVT Media | 9110000398 | 10 |  |  | 2024-02-27 | The Edition Canopy Kiosk-QTY 10 Nos | NO | 10 | 2500 | 25000 | 29500 | 25000 | 29500 | 0 | 25000 | 29500 | ZMAT | 2025-01-20 | 2025-03-20
RE/0066-NPE-MK-04 | Other Marketing Expenses | 2010 |  | 2010 | SMARTWORLD THE EDITION | HVT Media | 9110000398 | 20 |  |  | 2024-02-27 | Freight | NO | 1 | 1500 | 1500 | 1770 | 1500 | 1770 | 0 | 1500 | 1770 | ZMAT | 2025-01-20 | 2025-03-20
RE/0066-NPE-MK-04 | Other Marketing Expenses | 2010 |  | 2010 | SMARTWORLD THE EDITION | Grapevine Entertainment | 9110000410 | 10 |  |  | 2024-03-07 | Retaining Element-Lobby Area-Sample Flat | NO | 1 | 45000 | 45000 | 53100 | 45000 | 53100 | 0 | 45000 | 53100 | ZMAT | 2025-01-20 | 2025-03-20
RE/0066-NPE-MK-04 | Other Marketing Expenses | 2010 |  | 2010 | SMARTWORLD THE EDITION | Adbrands. OOH | 9140000135 | 10 |  |  | 2023-05-22 | Branding at Sector-66 project | AU | 1 | 113000 | 113000 | 133340 | 113000 | 133340 | 0 | 113000 | 133340 | ZSER | 2023-04-28 | 2023-05-08
RE/0066-NPE-MK-04 | Other Marketing Expenses | 2010 |  | 2010 | SMARTWORLD THE EDITION | DAWN DIGITAL PRIVATE LIMITED Mr. Prabash | 9160000077 | 20 |  |  | 2023-05-16 | Providing 5 No of Render & Location map | AU | 1 | 1000000 | 1000000 | 1180000 | 1000000 | 1180000 | 0 | 1000000 | 1180000 | ZGEN | 2023-05-04 | 2023-05-11
RE/0066-NPE-MK-04 | Other Marketing Expenses | 2010 |  | 2010 | SMARTWORLD THE EDITION | DAWN MODELS PRIVATE LIMITEDMayur Mohan | 9160000079 | 20 |  |  | 2023-05-16 | Scale Model (1:100) with Model 4 Towers | AU | 1 | 1650000 | 1650000 | 1947000 | 1650000 | 1947000 | 0 | 1650000 | 1947000 | ZGEN | 2023-05-04 | 2023-05-11
RE/0066-NPE-MK-04 | Other Marketing Expenses | 2010 |  | 2010 | SMARTWORLD THE EDITION | Orange Sky | 9160000417 | 20 |  |  | 2023-10-19 | Animation of 270 Degree Viewing room | AU | 1 | 1380000 | 1380000 | 1628400 | 1380000 | 1628400 | 0 | 1380000 | 1628400 | ZGEN | 2025-01-20 | 2025-03-20
RE/0066-NPE-MK-04 | Other Marketing Expenses | 2010 |  | 2010 | SMARTWORLD THE EDITION | Orange Sky | 9160000495 | 10 |  |  | 2023-12-11 | Animation & Static Render | AU | 1 | 830000 | 830000 | 979400 | 830000 | 979400 | 0 | 830000 | 979400 | ZGEN | 2023-12-11 | 2024-12-10
RE/0066-NPE-MK-04 | Other Marketing Expenses | 2010 |  | 2010 | SMARTWORLD THE EDITION | Bluetick Technologies Pvt. Ltd. | 9160000498 | 10 |  |  | 2023-12-12 | Design & creation of Inventory Selector | AU | 1 | 475000 | 475000 | 560500 | 475000 | 560500 | 0 | 475000 | 560500 | ZGEN | 2023-12-12 | 2024-12-11
RE/0066-NPE-MK-04 | Other Marketing Expenses | 2010 |  | 2010 | SMARTWORLD THE EDITION | Daiko From Here On CommunicationsPrivate limited | 9160000520 | 10 |  |  | 2023-12-22 | 05 Nos of Code66 Videos Teaser | AU | 1 | 118000 | 118000 | 139240 | 118000 | 139240 | 0 | 118000 | 139240 | ZGEN | 2023-11-18 | 2023-11-28
RE/0066-NPE-MK-04 | Other Marketing Expenses | 2010 |  | 2010 | SMARTWORLD THE EDITION | M2n Services | 9160000542 | 10 |  |  | 2024-01-04 | Supply & installation of Branding on Lob | AU | 1 | 750000 | 750000 | 885000 | 750000 | 885000 | 0 | 750000 | 885000 | ZGEN | 2023-12-28 | 2024-01-12
RE/0066-NPE-MK-04 | Other Marketing Expenses | 2010 |  | 2010 | SMARTWORLD THE EDITION | M2n Services | 9160000552 | 10 |  |  | 2024-01-09 | Letter Signage of "SW" The EDITION | AU | 1 | 55000 | 55000 | 64900 | 55000 | 64900 | 0 | 55000 | 64900 | ZGEN | 2023-12-31 | 2024-01-11
RE/0066-NPE-MK-04 | Other Marketing Expenses | 2010 |  | 2010 | SMARTWORLD THE EDITION | Adbrands. OOH | 9160000553 | 10 |  |  | 2024-01-09 | Code66 Gallery Flagpoles Printing-SEC62 | AU | 1 | 30320 | 30320 | 35777.6 | 30319.49 | 35777 | 0.51 | 30320 | 35777.6 | ZGEN | 2023-11-09 | 2023-11-12
RE/0066-NPE-MK-04 | Other Marketing Expenses | 2010 |  | 2010 | SMARTWORLD THE EDITION | Mahatta Multimedia pvt Ltd. | 9160000556 | 10 |  |  | 2024-01-11 | Purchase High Resolution Image | AU | 1 | 132000 | 132000 | 155760 | 132000 | 155760 | 0 | 132000 | 155760 | ZGEN | 2024-01-08 | 2024-01-10
RE/0066-NPE-MK-04 | Other Marketing Expenses | 2010 |  | 2010 | SMARTWORLD THE EDITION | FLICKSBYJS | 9160000632 | 10 |  |  | 2024-02-14 | Videography of Sample Apartment-Edition | AU | 1 | 19000 | 19000 | 22420 | 19000 | 22420 | 0 | 19000 | 22420 | ZGEN | 2024-02-15 | 2024-02-15
RE/0066-NPE-MK-04 | Other Marketing Expenses | 2010 |  | 2010 | SMARTWORLD THE EDITION | Orange Sky | 9160000635 | 10 |  |  | 2024-02-14 | 3 Minutes 3D Animation Landscape-Edition | AU | 1 | 1200000 | 1200000 | 1416000 | 600000 | 708000 | 600000 | 600000 | 708000 | ZGEN | 2024-01-25 | 2024-03-05
RE/0066-NPE-MK-04 | Other Marketing Expenses | 2010 |  | 2010 | SMARTWORLD THE EDITION | The Photo Session | 9160000655 | 10 |  |  | 2024-02-22 | DRONE SHOOT-EDITION-One Month | AU | 1 | 12000 | 12000 | 14160 | 12000 | 14160 | 0 | 12000 | 14160 | ZGEN | 2024-02-15 | 2024-03-15
RE/0066-NPE-MK-04 | Other Marketing Expenses | 2010 |  | 2010 | SMARTWORLD THE EDITION | Adbrands. OOH | 9160000660 | 10 |  |  | 2024-02-27 | Edition-SAMPLE FLAT BARRICADES BRANDING | AU | 1 | 61412 | 61412 | 72466.16 | 61411.86 | 72466 | 0.14 | 61412.03 | 72466.2 | ZGEN | 2024-02-07 | 2024-02-22
RE/0066-NPE-MK-04 | Other Marketing Expenses | 2010 |  | 2010 | SMARTWORLD THE EDITION | AAS Graphics | 9160000702 | 10 |  |  | 2024-03-14 | Installation of Outdoor Flags | AU | 1 | 327600 | 327600 | 386568 | 327600 | 386568 | 0 | 327600 | 386568 | ZGEN | 2024-02-12 | 2024-03-11
RE/0066-NPE-MK-04 | Other Marketing Expenses | 2010 |  | 2010 | SMARTWORLD THE EDITION | Martech Mavericks | 9160000704 | 10 |  |  | 2024-03-16 | DRONE SHOOT-EDITION | AU | 1 | 13000 | 13000 | 15340 | 13000 | 15340 | 0 | 13000 | 15340 | ZGEN | 2024-03-01 | 2024-03-31
RE/0066-NPE-MK-04 | Other Marketing Expenses | 2010 |  | 2010 | SMARTWORLD THE EDITION | Adbrands. OOH | 9160000730 | 10 |  |  | 2024-03-29 | Sup. & Ins. of of Cut out standee & Cube | AU | 1 | 52400 | 52400 | 61832 | 52400 | 61832 | 0 | 52400 | 61832 | ZGEN | 2023-11-09 | 2023-11-12
RE/0066-NPE-MK-04 | Other Marketing Expenses | 2010 |  | 2010 | SMARTWORLD THE EDITION | Adbrands. OOH | 9160000755 | 10 |  |  | 2024-03-06 | Flagpole Repaired and Painting | AU | 1 | 15000 | 15000 | 17700 | 15000 | 17700 | 0 | 15000 | 17700 | ZGEN | 2024-02-17 | 2024-03-30
RE/0066-NPE-MK-04 | Other Marketing Expenses | 2010 |  | 2010 | SMARTWORLD THE EDITION | The Grey Cell | 9160000768 | 10 |  |  | 2024-03-16 | Masking Frame-LED screen At Gallery 62 | AU | 1 | 25000 | 25000 | 29500 | 25000 | 29500 | 0 | 25000 | 29500 | ZGEN | 2024-02-03 | 2024-02-04
RE/0066-NPE-MK-04 | Other Marketing Expenses | 2010 |  | 2010 | Sales Gallery-62 | Purple Wave Infocom Private Limited | 9160000901 | 10 |  |  | 2024-06-01 | LED Screen Un-install | AU | 1 | 90000 | 90000 | 106200 | 90000 | 106200 | 0 | 90000 | 106200 | ZGEN | 2023-11-08 | 2024-10-10
RE/0066-NPE-MK-08 | Sales Promotion & Entertainment | 2010 |  | 2010 | SMARTWORLD THE EDITION | Media 4 Masscomm Private Limited | 9110000378 | 10 |  |  | 2024-02-10 | Canopy for The Edition Project | NO | 2 | 24000 | 48000 | 56640 | 48000 | 56640 | 0 | 48000 | 56640 | ZMAT | 2025-01-20 | 2025-03-20
RE/0066-NPE-MK-08 | Sales Promotion & Entertainment | 2010 |  | 2010 | SMARTWORLD THE EDITION | Primar Partners | 9110000452 | 10 |  |  | 2024-04-02 | Backdrop | NO | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | ZMAT | 2025-01-20 | 2025-03-20
RE/0066-NPE-MK-08 | Sales Promotion & Entertainment | 2010 |  | 2010 | SMARTWORLD THE EDITION | Primar Partners | 9110000452 | 20 |  |  | 2024-04-02 | Standee | NO | 2 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | ZMAT | 2025-01-20 | 2025-03-20
RE/0066-NPE-MK-08 | Sales Promotion & Entertainment | 2010 |  | 2010 | SMARTWORLD THE EDITION | Events Dreamz | 9160000468 | 10 |  |  | 2023-11-29 | Eventing-Event Setup | AU | 1 | 264110 | 264110 | 311649.8 | 264110.17 | 311650 | 0.17 | 264110.17 | 311650 | ZGEN | 2023-10-18 | 2023-10-19
RE/0066-NPE-MK-08 | Sales Promotion & Entertainment | 2010 |  | 2010 | SMARTWORLD THE EDITION | Heights Promotion Company | 9160000490 | 10 |  |  | 2023-12-07 | The Edition Project Mall Activation | AU | 1 | 575000 | 575000 | 678500 | 575000 | 678500 | 0 | 575000 | 678500 | ZGEN | 2023-12-08 | 2024-02-06
RE/0066-NPE-MK-08 | Sales Promotion & Entertainment | 2010 |  | 2010 | SMARTWORLD THE EDITION | Heights Promotion Company | 9160000490 | 20 |  |  | 2023-12-07 | The Edition Project Mall Activation | AU | 1 | 800000 | 800000 | 944000 | 800000 | 944000 | 0 | 800000 | 944000 | ZGEN | 2023-12-08 | 2024-02-06
RE/0066-NPE-MK-08 | Sales Promotion & Entertainment | 2010 |  | 2010 | SMARTWORLD THE EDITION | Heights Promotion Company | 9160000490 | 30 |  |  | 2023-12-07 | MCG Tax charging on actual | AU | 1 | 189025 | 189025 | 223049.5 | 189025.07 | 223049.58 | 0.07 | 189025.08 | 223049.6 | ZGEN | 2023-12-08 | 2024-02-06
RE/0066-NPE-MK-08 | Sales Promotion & Entertainment | 2010 |  | 2010 | SMARTWORLD THE EDITION | Grapevine Entertainment | 9160000491 | 10 |  |  | 2023-12-07 | The Edition Project Mall Activation | AU | 1 | 1210000 | 1210000 | 1427800 | 1210000 | 1427800 | 0 | 1210000 | 1427800 | ZGEN | 2023-04-01 | 2024-03-31
RE/0066-NPE-MK-08 | Sales Promotion & Entertainment | 2010 |  | 2010 | SMARTWORLD THE EDITION | Kridha & Company | 9160000517 | 10 |  |  | 2023-12-20 | Meet & Greet Event-Gallery62,on14Dec2023 | AU | 1 | 38250 | 38250 | 40162.5 | 38250.48 | 40163 | 0.48 | 38250.1 | 40162.6 | ZGEN | 2023-12-14 | 2023-12-14
RE/0066-NPE-MK-08 | Sales Promotion & Entertainment | 2010 |  | 2010 | SMARTWORLD THE EDITION | Grapevine Entertainment | 9160000555 | 10 |  |  | 2024-01-11 | Sample Opening Event Setup-12,13&14JAN24 | AU | 1 | 385000 | 385000 | 454300 | 385000 | 454300 | 0 | 385000.17 | 454300.2 | ZGEN | 2024-01-11 | 2024-01-14
RE/0066-NPE-MK-08 | Sales Promotion & Entertainment | 2010 |  | 2010 | SMARTWORLD THE EDITION | Grapevine Entertainment | 9160000560 | 10 |  |  | 2024-01-16 | Sec 66 Model Unveiling on 16 Nov 2023 | AU | 1 | 500610 | 500610 | 590719.8 | 500610 | 590719.8 | 0 | 500610 | 590719.8 | ZGEN | 2023-11-15 | 2023-11-16
RE/0066-NPE-MK-08 | Sales Promotion & Entertainment | 2010 |  | 2010 | SMARTWORLD THE EDITION | Heights Promotion Company | 9160000574 | 10 |  |  | 2024-01-23 | Ext. Worldmark Mall retail Promotion-66 | AU | 1 | 700000 | 700000 | 826000 | 700000 | 826000 | 0 | 700000 | 826000 | ZGEN | 2024-01-17 | 2024-02-17
RE/0066-NPE-MK-08 | Sales Promotion & Entertainment | 2010 |  | 2010 | SMARTWORLD THE EDITION | Heights Promotion Company | 9160000574 | 20 |  |  | 2024-01-23 | MCG Tax charging on actual | AU | 1 | 81831 | 81831 | 96560.58 | 81831 | 96560.58 | 0 | 81831.02 | 96560.6 | ZGEN | 2024-01-17 | 2024-02-17
RE/0066-NPE-MK-08 | Sales Promotion & Entertainment | 2010 |  | 2010 | SMARTWORLD THE EDITION | Grapevine Entertainment | 9160000594 | 10 |  |  | 2024-02-02 | Elite-Setup-CP Event-62 Gallery-02Feb24 | AU | 1 | 79970 | 79970 | 94364.6 | 79970 | 94364.6 | 0 | 79970 | 94364.6 | ZGEN | 2024-02-02 | 2024-02-02
RE/0066-NPE-MK-08 | Sales Promotion & Entertainment | 2010 |  | 2010 | SMARTWORLD THE EDITION | J.K. Entertainment Event | 9160000596 | 10 |  |  | 2024-02-02 | Employee Event at Orana on 19 JAN 2024 | AU | 1 | 2503536 | 2503536 | 2954172.48 | 2503535.59 | 2954172 | 0.41 | 2503536.02 | 2954172.5 | ZGEN | 2024-01-19 | 2024-01-19
RE/0066-NPE-MK-08 | Sales Promotion & Entertainment | 2010 |  | 2010 | SMARTWORLD THE EDITION | Central Delhi Retail Company | 9160000602 | 10 |  |  | 2024-02-03 | F&B-Sample Opening Event-12,13&14 JAN24 | AU | 1 | 520000 | 520000 | 546000 | 520000 | 546000 | 0 | 520000 | 546000 | ZGEN | 2024-01-11 | 2024-01-14
RE/0066-NPE-MK-08 | Sales Promotion & Entertainment | 2010 |  | 2010 | SMARTWORLD THE EDITION | Central Delhi Retail Company | 9160000603 | 10 |  |  | 2024-02-05 | Evening-Event Setup | AU | 1 | 143000 | 143000 | 150150 | 143000 | 150150 | 0 | 143000 | 150150 | ZGEN | 2023-10-18 | 2023-10-19
RE/0066-NPE-MK-08 | Sales Promotion & Entertainment | 2010 |  | 2010 | SMARTWORLD THE EDITION | Central Delhi Retail Company | 9160000604 | 10 |  |  | 2024-02-05 | F&B arrangement | AU | 1 | 97500 | 97500 | 102375 | 97500 | 102375 | 0 | 97500 | 102375 | ZGEN | 2023-11-16 | 2023-11-16
RE/0066-NPE-MK-08 | Sales Promotion & Entertainment | 2010 |  | 2010 | SMARTWORLD THE EDITION | Kridha & Company | 9160000615 | 10 |  |  | 2024-02-09 | Meet & Greet Event-Gallery62,on18Dec2023 | AU | 1 | 110500 | 110500 | 116025 | 110500 | 116025 | 0 | 110500 | 116025 | ZGEN | 2023-12-18 | 2023-12-18
RE/0066-NPE-MK-08 | Sales Promotion & Entertainment | 2010 |  | 2010 | SMARTWORLD THE EDITION | DELLI DELICACIES | 9160000625 | 10 |  |  | 2024-02-12 | Elite-F&B-CP Event-62 Gallery-02 Feb2024 | AU | 1 | 122500 | 122500 | 144550 | 122500 | 144550 | 0 | 122500 | 144550 | ZGEN | 2024-02-02 | 2024-02-02
RE/0066-NPE-MK-08 | Sales Promotion & Entertainment | 2010 |  | 2010 | SMARTWORLD THE EDITION | Heights Promotion Company | 9160000638 | 10 |  |  | 2024-02-15 | 3Ext.Worldmark Mall retail Promotion-66 | AU | 1 | 700000 | 700000 | 826000 | 700000 | 826000 | 0 | 700000 | 826000 | ZGEN | 2024-02-17 | 2024-03-16
RE/0066-NPE-MK-08 | Sales Promotion & Entertainment | 2010 |  | 2010 | SMARTWORLD THE EDITION | Heights Promotion Company | 9160000638 | 20 |  |  | 2024-02-15 | MCG Tax charging on actual | AU | 1 | 81831 | 81831 | 96560.58 | 81831 | 96560.58 | 0 | 81831.02 | 96560.6 | ZGEN | 2024-02-17 | 2024-03-16
RE/0066-NPE-MK-08 | Sales Promotion & Entertainment | 2010 |  | 2010 | SMARTWORLD THE EDITION | Grapevine Entertainment | 9160000656 | 10 |  |  | 2024-02-23 | Mini Cricket Game Setup | AU | 1 | 100000 | 100000 | 118000 | 100000 | 118000 | 0 | 100000 | 118000 | ZGEN | 2024-02-18 | 2024-03-04
RE/0066-NPE-MK-08 | Sales Promotion & Entertainment | 2010 |  | 2010 | SMARTWORLD THE EDITION | Grapevine Entertainment | 9160000658 | 10 |  |  | 2024-02-27 | The Edition-Sales Kiosk Refurbishing | AU | 1 | 128150 | 128150 | 151217 | 128150 | 151217 | 0 | 128150 | 151217 | ZGEN | 2024-02-19 | 2024-02-29
RE/0066-NPE-MK-08 | Sales Promotion & Entertainment | 2010 |  | 2010 | SMARTWORLD THE EDITION | Square Yards ConsultingPrivate Limited | 9160000734 | 10 |  |  | 2024-03-30 | Participation Fee for Apne Ghar Diwali | AU | 1 | 300000 | 300000 | 354000 | 300000 | 354000 | 0 | 300000 | 354000 | ZGEN | 2023-11-04 | 2023-11-05
RE/0066-NPE-MK-08 | Sales Promotion & Entertainment | 2010 |  | 2010 | SMARTWORLD THE EDITION | Square Yards ConsultingPrivate Limited | 9160000735 | 10 |  |  | 2024-03-30 | Squareyards Event 10&11 Feb 2024-Edition | AU | 1 | 300000 | 300000 | 354000 | 300000 | 354000 | 0 | 300000 | 354000 | ZGEN | 2023-11-10 | 2023-11-11
RE/0066-NPE-MK-08 | Sales Promotion & Entertainment | 2010 |  | 2010 | SMARTWORLD THE EDITION | Studio Focus Vision | 9160000761 | 10 |  |  | 2024-03-28 | Video Model Unveiling-16 Nov 23-Edition | AU | 1 | 22500 | 22500 | 22500 | 22500 | 22500 | 0 | 22500 | 22500 | ZGEN | 2023-11-16 | 2023-11-17
RE/0066-NPE-MK-08 | Sales Promotion & Entertainment | 2010 |  | 2010 | SMARTWORLD THE EDITION | Studio Focus Vision | 9160000763 | 10 |  |  | 2024-03-28 | Video Sample Opening-12to14Jan24-Edition | AU | 1 | 41500 | 41500 | 41500 | 41500 | 41500 | 0 | 41500 | 41500 | ZGEN | 2024-01-12 | 2024-01-14
RE/0066-NPE-MK-08 | Sales Promotion & Entertainment | 2010 |  | 2010 | SMARTWORLD THE EDITION | Grapevine Entertainment | 9160000764 | 10 |  |  | 2024-02-11 | Entry Branding & Other Elements | AU | 1 | 640000 | 640000 | 755200 | 640000 | 755200 | 0 | 640000 | 755200 | ZGEN | 2024-02-11 | 2024-02-11
RE/0066-NPE-MK-08 | Sales Promotion & Entertainment | 2010 |  | 2010 | SMARTWORLD THE EDITION | Kridha & Company | 9160000774 | 10 |  |  | 2024-03-12 | Full Day F&B-CP&Cust-Edition-3 Months | AU | 1 | 3137750 | 3137750 | 3294637.5 | 3137750.48 | 3294638 | 0.48 | 3137750.1 | 3294637.6 | ZGEN | 2024-01-01 | 2024-03-31
RE/0066-NPE-MK-08 | Sales Promotion & Entertainment | 2010 |  | 2010 | Sales Gallery-62 | DELLI DELICACIES | 9160000838 | 10 |  |  | 2024-05-16 | F&B-CP Event-The Edition-11-Feb-2024 | AU | 1 | 318750 | 318750 | 376125 | 318750 | 376125 | 0 | 318750 | 376125 | ZGEN | 2024-02-11 | 2024-02-11
RE/0066-NPE-SD-01 | Sales Expenses | 2010 |  | 2010 | SMARTWORLD THE EDITION | Comnet Vision India Pvt.LtdMs. Renu | 9110000336 | 10 |  |  | 2023-12-26 | I Phone 15 Pro 128 GB | NO | 100 | 104661.02 | 10466102 | 12350000.36 | 10466101.69 | 12350000 | 0.31 | 10466100 | 12349998 | ZMAT | 2025-01-20 | 2025-03-20
RE/0066-NPE-SD-01 | Sales Expenses | 2010 |  | 2010 | SMARTWORLD THE EDITION | Tresor Ventures Private LimitedMr. Raman | 9110000371 | 10 |  |  | 2024-02-02 | I Phone 15 Pro 128 GB-100 Nos | NO | 100 | 104549 | 10454900 | 12336782 | 10454900 | 12336782 | 0 | 10454816.3 | 12336683 | ZMAT | 2025-01-20 | 2025-03-20
RE/0066-NPE-SD-01 | Sales Expenses | 2010 |  | 2010 | SMARTWORLD THE EDITION | Dev It Serv Private LimitedMs. Divya | 9110000395 | 10 |  |  | 2024-02-27 | MacBook Air: Apple M2 | NO | 15 | 82000 | 1230000 | 1451400 | 1230000 | 1451400 | 0 | 1230000 | 1451400 | ZMAT | 2025-01-20 | 2025-03-20
RE/0066-NPE-SD-01 | Sales Expenses | 2010 |  | 2010 | SMARTWORLD THE EDITION | Comnet Vision India Pvt.LtdMs. Renu | 9110000420 | 10 |  |  | 2024-03-14 | iPad Pro 11-inch Wi-Fi 128GB | NO | 15 | 62400 | 936000 | 1104480 | 936000 | 1104480 | 0 | 936000 | 1104480 | ZMAT | 2025-01-20 | 2025-03-20
RE/0066-NPE-SD-01 | Sales Expenses | 2010 |  | 2010 | Sales Gallery-62 | Tresor Ventures Private LimitedMr. Raman | 9110000454 | 10 |  |  | 2024-04-06 | I Phone 15 Pro 128 GB | NO | 150 | 102900 | 15435000 | 18213300 | 15435000 | 18213300 | 0 | 15435000 | 18213300 | ZMAT | 2025-01-20 | 2025-03-20
RE/0066-NPE-SD-01 | Sales Expenses | 2010 |  | 2010 | SMARTWORLD THE EDITION | Kridha & Company | 9160000617 | 10 |  |  | 2024-02-09 | Full Day F&B-CP & Cust -Sec 62-on24Nov23 | AU | 1 | 148500 | 148500 | 155925 | 148500 | 155925 | 0 | 148500 | 155925 | ZGEN | 2023-11-24 | 2023-11-24
RE/0066-NPE-SD-01 | Sales Expenses | 2010 |  | 2010 | SMARTWORLD THE EDITION | Kridha & Company | 9160000618 | 10 |  |  | 2024-02-09 | Full Day F&B-CP & Cust -Sec 62-on25Nov23 | AU | 1 | 192500 | 192500 | 202125 | 192500 | 202125 | 0 | 192500 | 202125 | ZGEN | 2025-01-20 | 2025-03-20
RE/0066-NPE-SD-01 | Sales Expenses | 2010 |  | 2010 | SMARTWORLD THE EDITION | Kridha & Company | 9160000624 | 10 |  |  | 2024-02-12 | F&B-CP Training-62Gallery-on18&19JAN2024 | AU | 1 | 273000 | 273000 | 286650 | 0 | 0 | 273000 | 0 | 0 | ZGEN | 2024-01-18 | 2024-01-19
RE/0066-NPE-SD-01 | Sales Expenses | 2010 |  | 2010 | SMARTWORLD THE EDITION | Kridha & Company | 9160000661 | 10 |  |  | 2024-02-27 | F&B service arrangement for CP meet | AU | 1 | 85000 | 85000 | 89250 | 85000 | 89250 | 0 | 85000 | 89250 | ZGEN | 2024-01-20 | 2024-01-21
RE/0066-NPE-SD-01 | Sales Expenses | 2010 |  | 2010 | SMARTWORLD THE EDITION | MAKE MY TRIP (INDIA) PVT. LTD | 9160000670 | 10 |  |  | 2024-03-02 | Generic Single Discounting Cards | AU | 1 | 9150000 | 9150000 | 9150000 | 9150000 | 9150000 | 0 | 9150000 | 9150000 | ZGEN | 2024-02-27 | 2024-03-05
RE/0066-NPE-SD-01 | Sales Expenses | 2010 |  | 2010 | SMARTWORLD THE EDITION | Moksh Events | 9160000683 | 10 |  |  | 2024-03-07 | Rental of Tent and Tables | AU | 1 | 59000 | 59000 | 69620 | 59000 | 69620 | 0 | 59000 | 69620 | ZGEN | 2024-01-06 | 2024-01-28
RE/0066-NPE-SD-01 | Sales Expenses | 2010 |  | 2010 | SMARTWORLD THE EDITION | Moksh Events | 9160000696 | 10 |  |  | 2024-03-14 | Rental of Tent & Tables | AU | 1 | 60000 | 60000 | 70800 | 2500 | 2950 | 57500 | 2500 | 2950 | ZGEN | 2024-03-01 | 2024-03-31
RE/0066-NPE-SD-01 | Sales Expenses | 2010 |  | 2010 | SMARTWORLD THE EDITION | Moksh Events | 9160000741 | 10 |  |  | 2024-04-02 | Tent/Tables-62 Gallery for Month Feb2024 | AU | 1 | 48000 | 48000 | 56640 | 43700 | 51566 | 4300 | 43700 | 51566 | ZGEN | 2024-02-01 | 2024-02-29
RE/0066-NPE-SD-01 | Sales Expenses | 2010 |  | 2010 | SMARTWORLD THE EDITION | Kridha & Company | 9160000771 | 10 |  |  | 2024-03-29 | Full Day F&B-CP & Cust -Edition-Mar 2024 | AU | 1 | 225000 | 225000 | 265500 | 0 | 0 | 225000 | 0 | 0 | ZGEN | 2025-01-20 | 2025-03-20
RE/0066-PBA-01 | Provisional Booking | 2010 | GR01 | 2010 |  |  |  | 0 | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
RE/0066-PH1-LI-01 | License/Stat. Fees | 2010 | GR01 | 2010 |  |  |  | 0 | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
RE/0066-PRJ-CL-CIV | Civil Works | 2010 | GR01 | 2010 | SMARTWORLD THE EDITION | Ahluwalia Contracts India Limited | 9140000321 | 10 |  |  | 2024-07-20 | SITE DEVLOPMENT AND EARTH WORK | AU | 1 | 46446011.45 | 566984 | 669041.12 | 0 | 0 | 566984 | 0 | 0 | ZSER | 2024-07-15 | 2027-01-14
RE/0066-PRJ-CL-CIV | Civil Works | 2010 | GR01 | 2010 | SMARTWORLD THE EDITION | Ahluwalia Contracts India Limited | 9140000321 | 20 |  |  | 2024-07-20 | REINFORCED CEMENT CONCRETE-I part A | AU | 1 | 817967533.89 | 840242 | 991485.56 | 0 | 0 | 840242 | 0 | 0 | ZSER | 2024-07-15 | 2027-01-14
RE/0066-PRJ-CL-CIV | Civil Works | 2010 | GR01 | 2010 | SMARTWORLD THE EDITION | Ahluwalia Contracts India Limited | 9140000321 | 30 |  |  | 2024-07-20 | REINFORCED CEMENT CONCRETE-I Part B | AU | 1 | 578839908.56 | 6606521.38 | 7795695.23 | 0 | 0 | 6606521.38 | 0 | 0 | ZSER | 2024-07-15 | 2027-01-14
RE/0066-PRJ-CL-CIV | Civil Works | 2010 | GR01 | 2010 | SMARTWORLD THE EDITION | Ahluwalia Contracts India Limited | 9140000321 | 40 |  |  | 2024-07-20 | REINFORCED CEMENT CONCRETE-I Part C | AU | 1 | 928679602.19 | 23687921 | 27951746.78 | 0 | 0 | 23687921 | 0 | 0 | ZSER | 2024-07-15 | 2027-01-14
RE/0066-PRJ-CL-CIV | Civil Works | 2010 | GR01 | 2010 | SMARTWORLD THE EDITION | Ahluwalia Contracts India Limited | 9140000321 | 50 |  |  | 2024-07-20 | CENTERING & SHUTTERING Part A | AU | 1 | 758682686.52 | 13036257.12 | 15382783.4 | 0 | 0 | 13036257.12 | 0 | 0 | ZSER | 2024-07-15 | 2027-01-14
RE/0066-PRJ-CL-CIV | Civil Works | 2010 | GR01 | 2010 | SMARTWORLD THE EDITION | Ahluwalia Contracts India Limited | 9140000321 | 60 |  |  | 2024-07-20 | CENTERING & SHUTTERING Part B | AU | 1 | 522232239.1 | 0.01 | 0.01 | 0 | 0 | 0.01 | 0 | 0 | ZSER | 2024-07-15 | 2027-01-14
RE/0066-PRJ-CL-CIV | Civil Works | 2010 | GR01 | 2010 | SMARTWORLD THE EDITION | Ahluwalia Contracts India Limited | 9140000321 | 70 |  |  | 2024-07-20 | REINFORCEMENT STEEL Installation Part A | AU | 1 | 807449034.84 | 280510 | 331001.8 | 0 | 0 | 280510 | 0 | 0 | ZSER | 2024-07-15 | 2027-01-14
RE/0066-PRJ-CL-CIV | Civil Works | 2010 | GR01 | 2010 | SMARTWORLD THE EDITION | Ahluwalia Contracts India Limited | 9140000321 | 80 |  |  | 2024-07-20 | REINFORCEMENT STEEL Installation Part B | AU | 1 | 378864484.45 | 24597258.99 | 29024765.61 | 0 | 0 | 24597258.99 | 0 | 0 | ZSER | 2024-07-15 | 2027-01-14
RE/0066-PRJ-CL-CIV | Civil Works | 2010 | GR01 | 2010 | SMARTWORLD THE EDITION | Ahluwalia Contracts India Limited | 9140000321 | 90 |  |  | 2024-07-20 | MASONARY WORKS | AU | 1 | 78919745.48 | 6216747 | 7335761.46 | 0 | 0 | 6216747 | 0 | 0 | ZSER | 2024-07-15 | 2027-01-14
RE/0066-PRJ-CL-CIV | Civil Works | 2010 | GR01 | 2010 | SMARTWORLD THE EDITION | Ahluwalia Contracts India Limited | 9140000321 | 100 |  |  | 2024-07-20 | STRUCTURAL STEEL WORKS | AU | 1 | 246548477.4 | 1749969.94 | 2064964.53 | 0 | 0 | 1749969.94 | 0 | 0 | ZSER | 2024-07-15 | 2027-01-14
RE/0066-PRJ-CL-CIV | Civil Works | 2010 | GR01 | 2010 | SMARTWORLD THE EDITION | Ahluwalia Contracts India Limited | 9140000321 | 110 |  |  | 2024-07-20 | FLOORING | AU | 1 | 73928703.29 | 74870.17 | 88346.8 | 0 | 0 | 74870.17 | 0 | 0 | ZSER | 2024-07-15 | 2027-01-14
RE/0066-PRJ-CL-CIV | Civil Works | 2010 | GR01 | 2010 | SMARTWORLD THE EDITION | Ahluwalia Contracts India Limited | 9140000321 | 120 |  |  | 2024-07-20 | WATER-PROOFING WORKS | AU | 1 | 177445488.88 | 5234931 | 6177218.58 | 0 | 0 | 5234931 | 0 | 0 | ZSER | 2024-07-15 | 2027-01-14
RE/0066-PRJ-CL-CIV | Civil Works | 2010 | GR01 | 2010 | SMARTWORLD THE EDITION | Ahluwalia Contracts India Limited | 9140000321 | 130 |  |  | 2024-07-20 | INTERNAL & EXTERNAL PLASTERING | AU | 1 | 84771287.89 | 6418910.51 | 7574314.4 | 0 | 0 | 6418910.51 | 0 | 0 | ZSER | 2024-07-15 | 2027-01-14
RE/0066-PRJ-CL-CIV | Civil Works | 2010 | GR01 | 2010 | SMARTWORLD THE EDITION | Unicorn Weighing Services | 9160000832 | 20 |  |  | 2024-05-13 | Amend-1 Weighing Services for Weighbrig | AU | 1 | 1857804 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | ZGEN | 2024-04-01 | 2025-03-31
RE/0066-PRJ-CL-CIV-CC-SL | Concrete Supply & La | 2010 | GR01 | 2010 |  |  |  | 0 | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
RE/0066-PRJ-CL-CIV-EW | Earthwork | 2010 | GR01 | 2010 |  |  |  | 0 | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
RE/0066-PRJ-CL-CIV-MS | Misc Structure Works | 2010 | GR01 | 2010 |  |  |  | 0 | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
RE/0066-PRJ-CL-CIV-MW | Masonry Works | 2010 | GR01 | 2010 |  |  |  | 0 | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
RE/0066-PRJ-CL-CIV-PW-IP | Internal Plaster | 2010 | GR01 | 2010 |  |  |  | 0 | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
RE/0066-PRJ-CL-CIV-PW-XP | External Plaster | 2010 | GR01 | 2010 |  |  |  | 0 | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
RE/0066-PRJ-CL-CIV-RS-LA | Reinforcement Labour | 2010 | GR01 | 2010 |  |  |  | 0 | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
RE/0066-PRJ-CL-CIV-RS-SU | Reinforcement Supply | 2010 | GR01 | 2010 | SMARTWORLD THE EDITION | JINDAL STEEL LIMITEDMr Robin Taneja | 9110000991 | 160 |  |  | 2025-04-17 | Steel Re-bar TMT 25 mm Dia. FE-550D | TO | 10 | 57750 | 577500 | 681450 | 577500 | 681450 | 0 | 577500 | 681450 | ZMAT
RE/0066-PRJ-CL-CIV-RS-SU | Reinforcement Supply | 2010 | GR01 | 2010 | SMARTWORLD THE EDITION | Ram Niwas & SonsDeepak gupta | 9110000992 | 10 |  |  | 2025-04-17 | Steel Re-bar TMT 08 mm Dia. FE-550D | TO | 10 | 57000 | 570000 | 672600 | 563160 | 664528.8 | 6840 | 563160 | 664528.8 | ZMAT
RE/0066-PRJ-CL-CIV-RS-SU | Reinforcement Supply | 2010 | GR01 | 2010 | SMARTWORLD THE EDITION | Ram Niwas & SonsDeepak gupta | 9110000992 | 20 |  |  | 2025-04-17 | Steel Re-bar TMT 10 mm Dia. FE-550D | TO | 60 | 56000 | 3360000 | 3964800 | 3360000 | 3964800 | 0 | 3360000 | 3964800 | ZMAT
RE/0066-PRJ-CL-CIV-RS-SU | Reinforcement Supply | 2010 | GR01 | 2010 | SMARTWORLD THE EDITION | Sapcon Steels Private Limited | 9110000999 | 10 |  |  | 2025-04-18 | Fe 550D TMT Steel Coil 08MM | TO | 40 | 60000 | 2400000 | 2832000 | 2100000 | 2478000 | 300000 | 2100000 | 2478000 | ZMAT | 2025-04-11 | 2025-04-30
RE/0066-PRJ-CL-CIV-RS-SU | Reinforcement Supply | 2010 | GR01 | 2010 | SMARTWORLD THE EDITION | Sapcon Steels Private Limited | 9110000999 | 20 |  |  | 2025-04-18 | Fe 550D TMT Steel Coil 10MM | TO | 60 | 58250 | 3495000 | 4124100 | 3507232.5 | 4138534.35 | 12232.5 | 3507232.5 | 4138534.35 | ZMAT | 2025-04-11 | 2025-04-30
RE/0066-PRJ-CL-CIV-RS-SU | Reinforcement Supply | 2010 | GR01 | 2010 | SMARTWORLD THE EDITION | Jindal Steel Limited | 9110001055 | 70 |  |  | 2025-05-17 | Steel Re-bar TMT 20 mm Dia. FE-550D | TO | 40 | 54850 | 2194000 | 2588920 | 1960229.3 | 2313070.57 | 233770.7 | 1960229.3 | 2313070.57 | ZMAT | 2025-05-29 | 2025-06-29
RE/0066-PRJ-CL-CIV-RS-SU | Reinforcement Supply | 2010 | GR01 | 2010 | SMARTWORLD THE EDITION | Jindal Steel Limited | 9110001055 | 140 |  |  | 2025-05-17 | Steel Re-bar TMT 25 mm Dia. FE-550D | TO | 22 | 54850 | 1206700 | 1423906 | 1206700 | 1423906 | 0 | 1206700 | 1423906 | ZMAT | 2025-05-29 | 2025-06-29
RE/0066-PRJ-CL-CIV-RS-SU | Reinforcement Supply | 2010 | GR01 | 2010 | SMARTWORLD THE EDITION | Jindal Steel Limited | 9110001073 | 10 |  |  | 2025-05-27 | Steel Re-bar TMT 12 mm Dia. FE-550D | TO | 40 | 57750 | 2310000 | 2725800 | 2310000 | 2725800 | 0 | 2310000 | 2725800 | ZMAT
RE/0066-PRJ-CL-CIV-RS-SU | Reinforcement Supply | 2010 | GR01 | 2010 | SMARTWORLD THE EDITION | Jindal Steel Limited | 9110001073 | 80 |  |  | 2025-05-27 | Steel Re-bar TMT 16 mm Dia. FE-550D | TO | 40 | 57750 | 2310000 | 2725800 | 2310000 | 2725800 | 0 | 2310000 | 2725800 | ZMAT
RE/0066-PRJ-CL-CIV-RS-SU | Reinforcement Supply | 2010 | GR01 | 2010 | SMARTWORLD THE EDITION | Jindal Steel Limited | 9110001073 | 150 |  |  | 2025-05-27 | Steel Re-bar TMT 20 mm Dia. FE-550D | TO | 10 | 57750 | 577500 | 681450 | 565603.5 | 667412.13 | 11896.5 | 565603.5 | 667412.13 | ZMAT
RE/0066-PRJ-CL-CIV-RS-SU | Reinforcement Supply | 2010 | GR01 | 2010 | SMARTWORLD THE EDITION | Jindal Steel Limited | 9110001073 | 160 |  |  | 2025-05-27 | Steel Re-bar TMT 25 mm Dia. FE-550D | TO | 10 | 57750 | 577500 | 681450 | 577500 | 681450 | 0 | 577500 | 681450 | ZMAT
RE/0066-PRJ-CL-CIV-RS-SU | Reinforcement Supply | 2010 | GR01 | 2010 | SMARTWORLD THE EDITION | JINDAL STEEL LIMITEDMr Robin Taneja | 9110001079 | 70 |  |  | 2025-05-29 | Steel Re-bar TMT 25 mm Dia. FE-550D | TO | 8 | 54850 | 438800 | 517784 | 441542.5 | 521020.15 | 2742.5 | 441542.5 | 521020.16 | ZMAT | 2025-05-29 | 2025-06-29
RE/0066-PRJ-CL-CIV-RS-SU | Reinforcement Supply | 2010 | GR01 | 2010 | SMARTWORLD THE EDITION | Ram Niwas & SonsDeepak gupta | 9110001126 | 70 |  |  | 2025-06-20 | Steel Re-bar TMT 10 mm Dia. FE-550D | TO | 25 | 50000 | 1250000 | 1475000 | 1224000 | 1444320 | 26000 | 1224000 | 1444320 | ZMAT | 2025-06-20 | 2025-07-20
RE/0066-PRJ-CL-CIV-RS-SU | Reinforcement Supply | 2010 | GR01 | 2010 | SMARTWORLD THE EDITION | Jindal Steel Limited | 9110001127 | 70 |  |  | 2025-06-20 | Steel Re-bar TMT 12 mm Dia. FE-550D | TO | 35 | 50600 | 1771000 | 2089780 | 1265000 | 1492700 | 506000 | 1265000 | 1492700 | ZMAT | 2025-06-20 | 2025-07-20
RE/0066-PRJ-CL-CIV-RS-SU | Reinforcement Supply | 2010 | GR01 | 2010 | SMARTWORLD THE EDITION | Jindal Steel Limited | 9110001127 | 150 |  |  | 2025-06-20 | Steel Re-bar TMT 16 mm Dia. FE-550D | TO | 25 | 50600 | 1265000 | 1492700 | 1265000 | 1492700 | 0 | 1265000 | 1492700 | ZMAT | 2025-06-20 | 2025-07-20
RE/0066-PRJ-CL-CIV-RS-SU | Reinforcement Supply | 2010 | GR01 | 2010 | SMARTWORLD THE EDITION | Jindal Steel Limited | 9110001127 | 230 |  |  | 2025-06-20 | Steel Re-bar TMT 20 mm Dia. FE-550D | TO | 10 | 50600 | 506000 | 597080 | 458942 | 541551.56 | 47058 | 458942 | 541551.56 | ZMAT | 2025-06-20 | 2025-07-20
RE/0066-PRJ-CL-CIV-RS-SU | Reinforcement Supply | 2010 | GR01 | 2010 | SMARTWORLD THE EDITION | Jindal Steel Limited | 9110001127 | 300 |  |  | 2025-06-20 | Steel Re-bar TMT 25 mm Dia. FE-550D | TO | 30 | 50600 | 1518000 | 1791240 | 1518000 | 1791240 | 0 | 1518000 | 1791240 | ZMAT | 2025-06-20 | 2025-07-20
RE/0066-PRJ-CL-CIV-RS-SU | Reinforcement Supply | 2010 | GR01 | 2010 | SMARTWORLD THE EDITION | Jindal Steel Limited | 9110001162 | 70 |  |  | 2025-07-17 | Steel Re-bar TMT 10 mm Dia. FE-550D | TO | 65 | 47500 | 3087500 | 3643250 | 0 | 0 | 3087500 | 0 | 0 | ZMAT | 2025-07-17 | 2025-08-17
RE/0066-PRJ-CL-CIV-RS-SU | Reinforcement Supply | 2010 | GR01 | 2010 | SMARTWORLD THE EDITION | Jindal Steel Limited | 9110001162 | 150 |  |  | 2025-07-17 | Steel Re-bar TMT 12 mm Dia. FE-550D | TO | 5 | 46500 | 232500 | 274350 | 0 | 0 | 232500 | 0 | 0 | ZMAT | 2025-07-17 | 2025-08-17
RE/0066-PRJ-CL-CIV-RS-SU | Reinforcement Supply | 2010 | GR01 | 2010 | SMARTWORLD THE EDITION | Jindal Steel Limited | 9110001162 | 160 |  |  | 2025-07-17 | Steel Re-bar TMT 12 mm Dia. FE-550D | TO | 15 | 46500 | 697500 | 823050 | 0 | 0 | 697500 | 0 | 0 | ZMAT | 2025-07-17 | 2025-08-17
RE/0066-PRJ-CL-CIV-RS-SU | Reinforcement Supply | 2010 | GR01 | 2010 | SMARTWORLD THE EDITION | Jindal Steel Limited | 9110001162 | 290 |  |  | 2025-07-17 | Steel Re-bar TMT 20 mm Dia. FE-550D | TO | 5 | 46500 | 232500 | 274350 | 0 | 0 | 232500 | 0 | 0 | ZMAT | 2025-07-17 | 2025-08-17
RE/0066-PRJ-CL-CIV-RS-SU | Reinforcement Supply | 2010 | GR01 | 2010 | SMARTWORLD THE EDITION | Jindal Steel Limited | 9110001162 | 360 |  |  | 2025-07-17 | Steel Re-bar TMT 25 mm Dia. FE-550D | TO | 5 | 46500 | 232500 | 274350 | 0 | 0 | 232500 | 0 | 0 | ZMAT | 2025-07-17 | 2025-08-17
RE/0066-PRJ-CL-CIV-RS-SU | Reinforcement Supply | 2010 | GR01 | 2010 | SMARTWORLD THE EDITION | Steel Authority Of India LTD | 9110001194 | 10 |  |  | 2025-08-06 | Steel Re-bar TMT 10 mm Dia. FE-550D | TO | 0.1 | 0.1 | 0.01 | 0.01 | 0 | 0 | 0.01 | 0 | 0 | ZMAT | 2025-08-05 | 2025-09-05
RE/0066-PRJ-CL-CIV-RS-SU | Reinforcement Supply | 2010 | GR01 | 2010 | SMARTWORLD THE EDITION | STEEL AUTHORITY OF INDIA LIMITED | 9110001272 | 10 |  |  | 2025-09-13 | Steel Re-bar TMT 10 mm Dia. FE-550D | TO | 30 | 49760 | 1492800 | 1761504 | 1464436.8 | 1728035.42 | 28363.2 | 1464436.8 | 1728035.42 | ZMAT
RE/0066-PRJ-CL-CIV-RS-SU | Reinforcement Supply | 2010 | GR01 | 2010 | SMARTWORLD THE EDITION | Sapcon Steels Private Limited | 9110001317 | 20 |  |  | 2025-10-10 | Fe 550D TMT Steel Coil 10MM | TO | 70 | 47500 | 3325000 | 3923500 | 2481400 | 2928052 | 843600 | 2481400 | 2928052 | ZMAT | 2025-10-10 | 2025-11-10
RE/0066-PRJ-CL-CIV-RS-SU | Reinforcement Supply | 2010 | GR01 | 2010 | SMARTWORLD THE EDITION | Sapcon Steels Private Limited | 9110001365 | 10 |  |  | 2025-11-07 | Fe 550D TMT Steel Coil 10MM | TO | 90 | 47750 | 4297500 | 5071050 | 0 | 0 | 4297500 | 0 | 0 | ZMAT | 2025-11-07 | 2025-12-07
RE/0066-PRJ-CL-CIV-RS-SU | Reinforcement Supply | 2010 | GR01 | 2010 | SMARTWORLD THE EDITION | Rashtriya Ispat Nigam Ltd | 9110001445 | 10 |  |  | 2025-12-23 | Fe 550D TMT Steel Coil 08MM | TO | 10 | 49900 | 499000 | 588820 | 420657 | 496375.26 | 78343 | 420657 | 496375.26 | ZMAT | 2025-12-23 | 2026-01-23
RE/0066-PRJ-CL-CIV-RS-SU | Reinforcement Supply | 2010 | GR01 | 2010 | SMARTWORLD THE EDITION | Rashtriya Ispat Nigam Ltd | 9110001445 | 20 |  |  | 2025-12-23 | Fe 550D TMT Steel Coil 10MM | TO | 44 | 48400 | 2129600 | 2512928 | 2129600 | 2512928 | 0 | 2129600 | 2512928 | ZMAT | 2025-12-23 | 2026-01-23
RE/0066-PRJ-CL-CIV-RS-SU | Reinforcement Supply | 2010 | GR01 | 2010 | SMARTWORLD THE EDITION | Rashtriya Ispat Nigam Ltd | 9110001445 | 30 |  |  | 2025-12-23 | Fe 550D TMT Steel Coil 10MM | TO | 66 | 48400 | 3194400 | 3769392 | 3111636 | 3671730.48 | 82764 | 3111636 | 3671730.48 | ZMAT | 2025-12-23 | 2026-01-23
RE/0066-PRJ-CL-CIV-RS-SU | Reinforcement Supply | 2010 | GR01 | 2010 | SMARTWORLD THE EDITION | Sapcon Steels Private Limited | 9110001494 | 10 |  |  | 2026-01-15 | Fe 550D TMT Steel Coil 10MM | TO | 60 | 56750 | 3405000 | 4017900 | 3402730 | 4015221.4 | 2270 | 3402730 | 4015221.4 | ZMAT | 2026-01-15 | 2026-02-15
RE/0066-PRJ-CL-CIV-RS-SU | Reinforcement Supply | 2010 | GR01 | 2010 | SMARTWORLD THE EDITION | Sapcon Steels Private Limited | 9110001494 | 20 |  |  | 2026-01-15 | Fe 550D TMT Steel Coil 08MM | TO | 150 | 58750 | 8812500 | 10398750 | 7203337.5 | 8499938.25 | 1609162.5 | 7203337.5 | 8499938.25 | ZMAT | 2026-01-15 | 2026-02-15
RE/0066-PRJ-CL-CIV-RS-SU | Reinforcement Supply | 2010 | GR01 | 2010 | SMARTWORLD THE EDITION | Sapcon Steels Private Limited | 9110001494 | 30 |  |  | 2026-01-15 | Fe 550D TMT Steel Coil 10MM | TO | 150 | 56750 | 8512500 | 10044750 | 8838245 | 10429129.1 | 325745 | 8838245 | 10429129.1 | ZMAT | 2026-01-15 | 2026-02-15
RE/0066-PRJ-CL-CIV-RS-SU | Reinforcement Supply | 2010 | GR01 | 2010 | SMARTWORLD THE EDITION | Rashtriya Ispat Nigam Ltd | 9110001604 | 10 |  |  | 2026-03-11 | Fe 550D TMT Steel Coil 08MM | TO | 130 | 63400 | 8242000 | 9725560 | 3987226 | 4704926.68 | 4254774 | 3987226 | 4704926.68 | ZMAT | 2026-03-11 | 2026-04-11
RE/0066-PRJ-CL-CIV-RS-SU | Reinforcement Supply | 2010 | GR01 | 2010 | SMARTWORLD THE EDITION | Rashtriya Ispat Nigam Ltd | 9110001604 | 20 |  |  | 2026-03-11 | Fe 550D TMT Steel Coil 10MM | TO | 80 | 61900 | 4952000 | 5843360 | 1930661 | 2278179.98 | 3021339 | 1930661 | 2278179.98 | ZMAT | 2026-03-11 | 2026-04-11
RE/0066-PRJ-CL-CIV-RS-SU | Reinforcement Supply | 2010 | GR01 | 2010 | SMARTWORLD THE EDITION | SAPCON STEELS PRIVATE LIMITEDParas Verma | 9110001731 | 10 |  |  | 2026-04-21 | Fe 550D TMT Steel Coil 08MM | TO | 60 | 64800 | 3888000 | 4587840 | 0 | 0 | 3888000 | 0 | 0 | ZMAT | 2026-04-21 | 2026-05-21
RE/0066-PRJ-CL-CIV-RS-SU | Reinforcement Supply | 2010 | GR01 | 2010 | SMARTWORLD THE EDITION | SAPCON STEELS PRIVATE LIMITEDParas Verma | 9110001731 | 20 |  |  | 2026-04-21 | Fe 550D TMT Steel Coil 10MM | TO | 40 | 62800 | 2512000 | 2964160 | 0 | 0 | 2512000 | 0 | 0 | ZMAT | 2026-04-21 | 2026-05-21
RE/0066-PRJ-CL-CIV-SW-CS | Conventional Shutter | 2010 | GR01 | 2010 |  |  |  | 0 | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
RE/0066-PRJ-CL-CIV-SW-SU | Aluminum Shuttering | 2010 | GR01 | 2010 |  |  |  | 0 | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
RE/0066-PRJ-CL-CIV-WP | Waterproofing Works | 2010 | GR01 | 2010 |  |  |  | 0 | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
RE/0066-PRJ-CL-EXP-TE | Club Total Expenses | 2010 | GR01 | 2010 | SMARTWORLD THE EDITION | Ahluwalia Contracts India Limited | 9140000321 | 10 |  |  | 2024-07-20 | SITE DEVLOPMENT AND EARTH WORK | AU | 1 | 0 | 0.01 | 0.01 | 220076462.71 | 259690226 | 220076462.7 | 0 | 0 | ZSER | 2024-07-15 | 2027-01-14
RE/0066-PRJ-CL-EXP-TE | Club Total Expenses | 2010 | GR01 | 2010 | SMARTWORLD THE EDITION | Ahluwalia Contracts India Limited | 9140000321 | 20 |  |  | 2024-07-20 | REINFORCED CEMENT CONCRETE-I part A | AU | 1 | 0 | 7772.01 | 9170.97 | 0 | 0 | 7772.01 | 0 | 0 | ZSER | 2024-07-15 | 2027-01-14
RE/0066-PRJ-CL-EXP-TE | Club Total Expenses | 2010 | GR01 | 2010 | SMARTWORLD THE EDITION | Ahluwalia Contracts India Limited | 9140000321 | 50 |  |  | 2024-07-20 | CENTERING & SHUTTERING Part A | AU | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | ZSER | 2024-07-15 | 2027-01-14
RE/0066-PRJ-CL-EXP-TE | Club Total Expenses | 2010 | GR01 | 2010 | SMARTWORLD THE EDITION | Ahluwalia Contracts India Limited | 9140000321 | 70 |  |  | 2024-07-20 | REINFORCEMENT STEEL Installation Part A | AU | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | ZSER | 2024-07-15 | 2027-01-14
RE/0066-PRJ-CL-EXP-TE | Club Total Expenses | 2010 | GR01 | 2010 | SMARTWORLD THE EDITION | Ahluwalia Contracts India Limited | 9140000321 | 90 |  |  | 2024-07-20 | MASONARY WORKS | AU | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | ZSER | 2024-07-15 | 2027-01-14
RE/0066-PRJ-CL-F&F | Finishing & facade works | 2010 | GR01 | 2010 |  |  |  | 0 | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
RE/0066-PRJ-CL-FIS-DW | Door Works | 2010 | GR01 | 2010 |  |  |  | 0 | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
RE/0066-PRJ-CL-MEP | MEP Works | 2010 | GR01 | 2010 | SMARTWORLD THE EDITION | Ahluwalia Contracts India Limited | 9140000321 | 140 |  |  | 2024-07-20 | CONDUITING | AU | 1 | 166109662.32 | 4863386.2 | 5738795.72 | 0 | 0 | 4863386.2 | 0 | 0 | ZSER | 2024-07-15 | 2027-01-14
RE/0066-PRJ-CL-MEP | MEP Works | 2010 | GR01 | 2010 | SMARTWORLD THE EDITION | Dehn India Pvt Ltd | 9140000379 | 10 |  |  | 2024-10-24 | Lightning Protection System for Basement | AU | 1 | 6470187 | 479803 | 566167.54 | 44010.14 | 51931.96 | 435792.86 | 44010.14 | 51931.97 | ZSER | 2024-10-24 | 2027-08-23
RE/0066-PRJ-CL-MEP | MEP Works | 2010 | GR01 | 2010 | SMARTWORLD THE EDITION | Atom MEP Engineers Pvt. Ltd. | 9140000668 | 40 |  |  | 2026-05-19 | SANITARY FIXTURES & FITTINGS Club | AU | 1 | 225240 | 225240 | 265783.2 | 0 | 0 | 225240 | 0 | 0 | ZSER | 2026-04-04 | 2028-02-04
RE/0066-PRJ-CL-MEP | MEP Works | 2010 | GR01 | 2010 | SMARTWORLD THE EDITION | Atom MEP Engineers Pvt. Ltd. | 9140000668 | 90 |  |  | 2026-05-19 | INTERNAL DRAINAGE -SOIL, CLUB | AU | 1 | 1686039.2 | 1686039.2 | 1989526.26 | 0 | 0 | 1686039.2 | 0 | 0 | ZSER | 2026-04-04 | 2028-02-04
RE/0066-PRJ-CL-MEP | MEP Works | 2010 | GR01 | 2010 | SMARTWORLD THE EDITION | Atom MEP Engineers Pvt. Ltd. | 9140000668 | 140 |  |  | 2026-05-19 | DOMESTIC AND FLUSHING WATER CLUB | AU | 1 | 682969.44 | 682969.44 | 805903.94 | 0 | 0 | 682969.44 | 0 | 0 | ZSER | 2026-04-04 | 2028-02-04
RE/0066-PRJ-CL-MEP | MEP Works | 2010 | GR01 | 2010 | SMARTWORLD THE EDITION | Atom MEP Engineers Pvt. Ltd. | 9140000668 | 200 |  |  | 2026-05-19 | MISCELLANEOUS ITEMS FOR TERRACE-Club | AU | 1 | 7300750 | 7300750 | 8614885 | 0 | 0 | 7300750 | 0 | 0 | ZSER | 2026-04-04 | 2028-02-04
RE/0066-PRJ-CL-MEP | MEP Works | 2010 | GR01 | 2010 | SMARTWORLD THE EDITION | Atom MEP Engineers Pvt. Ltd. | 9140000668 | 300 |  |  | 2026-05-19 | FF-FIRE HYDRANT & EQUIPMENT .- Club | AU | 1 | 956018 | 956018 | 1128101.24 | 0 | 0 | 956018 | 0 | 0 | ZSER | 2026-04-04 | 2028-02-04
RE/0066-PRJ-CL-MEP | MEP Works | 2010 | GR01 | 2010 | SMARTWORLD THE EDITION | Atom MEP Engineers Pvt. Ltd. | 9140000668 | 350 |  |  | 2026-05-19 | FF-AUTOMATIC SPRINKLER & WATER -Club | AU | 1 | 5155812 | 5155812 | 6083858.16 | 0 | 0 | 5155812 | 0 | 0 | ZSER | 2026-04-04 | 2028-02-04
RE/0066-PRJ-CL-MEP | MEP Works | 2010 | GR01 | 2010 | SMARTWORLD THE EDITION | Atom MEP Engineers Pvt. Ltd. | 9140000668 | 360 |  |  | 2026-05-19 | FF-AUTOMATIC SPRINKLER & WATER .-EWS | AU | 1 | 639438 | 639438 | 754536.84 | 0 | 0 | 639438 | 0 | 0 | ZSER | 2026-04-04 | 2028-02-04
RE/0066-PRJ-CL-MEP | MEP Works | 2010 | GR01 | 2010 | SMARTWORLD THE EDITION | Atom MEP Engineers Pvt. Ltd. | 9140000668 | 400 |  |  | 2026-05-19 | FF-PORTABLE FIRE EXTINGUISHERS -Club | AU | 1 | 59150 | 59150 | 69797 | 0 | 0 | 59150 | 0 | 0 | ZSER | 2026-04-04 | 2028-02-04
RE/0066-PRJ-CL-MEP-EW-LE | Low Side Electrical Works | 2010 | GR01 | 2010 |  |  |  | 0 | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
RE/0066-PRJ-CL-MEP-EW-LS | Light Fixtures Suppl | 2010 | GR01 | 2010 |  |  |  | 0 | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
RE/0066-PRJ-CL-MEP-FF | Fire Fighting Work | 2010 | GR01 | 2010 |  |  |  | 0 | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
RE/0066-PRJ-CL-MEP-HV-LS | Low Side | 2010 | GR01 | 2010 |  |  |  | 0 | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
RE/0066-PRJ-CL-MEP-LT | Lifts | 2010 | GR01 | 2010 |  |  |  | 0 | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
RE/0066-PRJ-CL-MEP-PB-FS | Fixtures Supply | 2010 | GR01 | 2010 |  |  |  | 0 | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
RE/0066-PRJ-CL-MEP-PB-IP | Internal Plumbing | 2010 | GR01 | 2010 |  |  |  | 0 | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
RE/0066-PRJ-CL-MEP-PB-JC | JACUZZI | 2010 | GR01 | 2010 |  |  |  | 0 | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
RE/0066-PRJ-CN-1 | Consultancy Charges | 2010 |  | 2010 | SMARTWORLD THE EDITION | R204 Design Global INC | 9140000042 | 10 |  |  | 2023-02-10 | CONCEPT DESIGN AND PRESENTATION CONSULTA | AU | 1 | 12000 | 0 | 0 | 6000 | 0 | 6000 | 489600 | 0 | ZSER | 2022-11-28 | 2023-02-28
RE/0066-PRJ-CN-1 | Consultancy Charges | 2010 |  | 2010 | SMARTWORLD THE EDITION | MAP LLC | 9140000044 | 10 |  |  | 2023-02-14 | CONCEPT DESIGN AND PRESENTATION CONSULTA | AU | 1 | 12000 | 12000 | 12000 | 0 | 0 | 12000 | 0 | 0 | ZSER | 2022-11-28 | 2023-02-28
RE/0066-PRJ-CN-1 | Consultancy Charges | 2010 |  | 2010 | SMARTWORLD THE EDITION | Green Tree Building Energy Pvt LtdAnurag Bajpai | 9140000047 | 10 |  |  | 2023-02-24 | Green Building Consultancy Services | AU | 1 | 1600000 | 0 | 0 | 1132800 | 1336704 | 1132800 | 960000 | 1132800 | ZSER | 2022-12-27 | 2026-12-27
RE/0066-PRJ-CN-1 | Consultancy Charges | 2010 |  | 2010 | SMARTWORLD THE EDITION | Trans. & Traffic Engineering Consul | 9140000068 | 10 |  |  | 2023-03-27 | Transportation & Traffic Engineering Con | AU | 1 | 700000 | 0 | 0 | 193900 | 228802 | 193900 | 175000 | 206500 | ZSER | 2023-03-16 | 2024-03-15
RE/0066-PRJ-CN-1 | Consultancy Charges | 2010 |  | 2010 | SMARTWORLD THE EDITION | Design Centre Consulting EngineersPrivate ltd | 9140000073 | 10 |  |  | 2023-04-03 | MEP DESIGN AND BIM COORDINATION CONSULTA | AU | 1 | 8500000 | 8500000 | 10030000 | 5992500 | 7071150 | 2507500 | 5992500 | 7071150 | ZSER | 2023-02-02 | 2023-10-18
RE/0066-PRJ-CN-1 | Consultancy Charges | 2010 |  | 2010 | SMARTWORLD THE EDITION | Citi Modeller | 9140000074 | 10 |  |  | 2023-04-03 | Physical Scaled Architectural BlockModel | AU | 1 | 100000 | 0 | 0 | 100000 | 118000 | 100000 | 100000 | 118000 | ZSER | 2023-02-02 | 2023-04-01
RE/0066-PRJ-CN-1 | Consultancy Charges | 2010 |  | 2010 | SMARTWORLD THE EDITION | Explore Engineering Consultants Pvt | 9140000075 | 10 |  |  | 2023-04-03 | Geo Technical Investigation Survey | AU | 1 | 894000 | 0 | 0 | 894000 | 1054920 | 894000 | 894000 | 1054920 | ZSER | 2023-01-16 | 2023-03-13
RE/0066-PRJ-CN-1 | Consultancy Charges | 2010 |  | 2010 | SMARTWORLD THE EDITION | Explore Engineering Consultants Pvt | 9140000087 | 10 |  |  | 2023-04-17 | Conducting Topographical Survey of Land | AU | 1 | 25000 | 0 | 0 | 25000 | 29500 | 25000 | 25000 | 29500 | ZSER | 2023-04-15 | 2023-05-14
RE/0066-PRJ-CN-1 | Consultancy Charges | 2010 |  | 2010 | SMARTWORLD THE EDITION | Facade Design Factory | 9140000164 | 10 |  |  | 2023-06-21 | SWD 66 - Facade Consultant | AU | 1 | 1650600 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | ZSER | 2023-06-15 | 2027-06-15
RE/0066-PRJ-CN-1 | Consultancy Charges | 2010 |  | 2010 | SMARTWORLD THE EDITION | Design Ahead Mr. Abhinav | 9140000181 | 10 |  |  | 2023-07-11 | SWD 66 - SIGNAGE CONSULTANT | AU | 1 | 750000 | 750000 | 885000 | 0 | 0 | 750000 | 0 | 0 | ZSER | 2023-06-19 | 2027-06-19
RE/0066-PRJ-CN-1 | Consultancy Charges | 2010 |  | 2010 | SMARTWORLD THE EDITION | Rwdi Consulting Engineers India PriLimited | 9140000199 | 10 |  |  | 2023-08-21 | WIND TUNNEL TESTING | AU | 1 | 1250000 | 1250000 | 1475000 | 1050000 | 1239000 | 200000 | 1050000 | 1239000 | ZSER | 2023-08-03 | 2023-10-03
RE/0066-PRJ-CN-1 | Consultancy Charges | 2010 |  | 2010 | SMARTWORLD THE EDITION | DS Consulting | 9140000302 | 10 |  |  | 2024-06-21 | Appointment Enviro conslt. for complianc | AU | 1 | 120000 | 120000 | 141600 | 120000 | 141600 | 0 | 120000 | 141600 | ZSER | 2024-06-04 | 2026-06-04
RE/0066-PRJ-CN-1 | Consultancy Charges | 2010 |  | 2010 | SMARTWORLD THE EDITION | DS Consulting | 9140000302 | 20 |  |  | 2024-06-21 | Amend-1 Appointment Enviro conslt. | AU | 1 | 120000 | 120000 | 141600 | 110000 | 129800 | 10000 | 110000 | 129800 | ZSER | 2024-06-04 | 2026-06-04
RE/0066-PRJ-CN-1 | Consultancy Charges | 2010 |  | 2010 | SMARTWORLD THE EDITION | Ambin Designs | 9140000304 | 10 |  |  | 2024-06-28 | Engineer's & Architect's Certificate | AU | 1 | 144000 | 144000 | 169920 | 40500 | 47790 | 103500 | 40500 | 47790 | ZSER | 2024-05-22 | 2025-05-31
RE/0066-PRJ-CN-1 | Consultancy Charges | 2010 |  | 2010 | SMARTWORLD THE EDITION | Perceptions | 9160000027 | 10 |  |  | 2023-03-17 | Certification of the Project by IITDelhi | AU | 1 | 1411345.5 | 0 | 0 | 1664980 | 1964676.4 | 1664980 | 1411000 | 1664980 | ZGEN | 2023-03-13 | 2023-03-27
RE/0066-PRJ-CN-1 | Consultancy Charges | 2010 |  | 2010 | SMARTWORLD THE EDITION | Manish Consultantsmanish kumar | 9160000053 | 20 |  |  | 2023-04-28 | Peer Review Consultant for Sec-66 | AU | 1 | 374000 | 374000 | 441320 | 374000 | 441320 | 0 | 374000 | 441320 | ZGEN | 2023-03-04 | 2027-03-31
RE/0066-PRJ-CN-1 | Consultancy Charges | 2010 |  | 2010 | SMARTWORLD THE EDITION | Manish Consultantsmanish kumar | 9160000053 | 30 |  |  | 2023-04-28 | Peer Review Consultant for Sec-66 | AU | 1 | 748000 | 748000 | 882640 | 748002 | 882642.36 | 2 | 748001.87 | 882642.21 | ZGEN | 2023-03-04 | 2027-03-31
RE/0066-PRJ-CN-1 | Consultancy Charges | 2010 |  | 2010 | SMARTWORLD THE EDITION | Manish Consultantsmanish kumar | 9160000053 | 40 |  |  | 2023-04-28 | Peer Review Consultant for Sec-66 | AU | 1 | 374000 | 374000 | 441320 | 374000.2 | 441320.24 | 0.2 | 374000.01 | 441320.01 | ZGEN | 2023-03-04 | 2027-03-31
RE/0066-PRJ-CN-1 | Consultancy Charges | 2010 |  | 2010 | SMARTWORLD THE EDITION | Manish Consultantsmanish kumar | 9160000053 | 50 |  |  | 2023-04-28 | Peer Review Consultant for Sec-66 | AU | 1 | 374000 | 374000 | 441320 | 374000 | 441320 | 0 | 374000 | 441320 | ZGEN | 2023-03-04 | 2027-03-31
RE/0066-PRJ-CN-1 | Consultancy Charges | 2010 |  | 2010 | SMARTWORLD THE EDITION | Manish Consultantsmanish kumar | 9160000053 | 60 |  |  | 2023-04-28 | Peer Review Consultant for Sec-66 | AU | 1 | 374000 | 374000 | 441320 | 374000 | 441320 | 0 | 374000 | 441320 | ZGEN | 2023-03-04 | 2027-03-31
RE/0066-PRJ-CN-1 | Consultancy Charges | 2010 |  | 2010 | SMARTWORLD THE EDITION | Manish Consultantsmanish kumar | 9160000053 | 70 |  |  | 2023-04-28 | Peer Review Consultant for Sec-66 | AU | 1 | 374000 | 374000 | 441320 | 374000 | 441320 | 0 | 374000 | 441320 | ZGEN | 2023-03-04 | 2027-03-31
RE/0066-PRJ-CN-1 | Consultancy Charges | 2010 |  | 2010 | SMARTWORLD THE EDITION | Manish Consultantsmanish kumar | 9160000053 | 80 |  |  | 2023-04-28 | Peer Review Consultant for Sec-66 | AU | 1 | 374000 | 374000 | 441320 | 374000 | 441320 | 0 | 374000 | 441320 | ZGEN | 2023-03-04 | 2027-03-31
RE/0066-PRJ-CN-1 | Consultancy Charges | 2010 |  | 2010 | SMARTWORLD THE EDITION | Manish Consultantsmanish kumar | 9160000053 | 90 |  |  | 2023-04-28 | Peer Review Consultant for Sec-66 | AU | 1 | 374000 | 374000 | 441320 | 0 | 0 | 374000 | 0 | 0 | ZGEN | 2023-03-04 | 2027-03-31
RE/0066-PRJ-CN-1 | Consultancy Charges | 2010 |  | 2010 | SMARTWORLD THE EDITION | Manish Consultantsmanish kumar | 9160000053 | 100 |  |  | 2023-04-28 | Peer Review Consultant for Sec-66 | AU | 1 | 374000 | 374000 | 441320 | 0 | 0 | 374000 | 0 | 0 | ZGEN | 2023-03-04 | 2027-03-31
RE/0066-PRJ-CN-1 | Consultancy Charges | 2010 |  | 2010 | SMARTWORLD THE EDITION | Sunil Nayyar Consulting Engineers L | 9160000302 | 10 |  |  | 2023-08-05 | Peer Review Consultant for Sec-66 | AU | 1 | 1250000 | 1250000 | 1475000 | 437500 | 516250 | 812500 | 437500 | 516250 | ZGEN | 2023-06-30 | 2024-06-30
RE/0066-PRJ-CN-1 | Consultancy Charges | 2010 |  | 2010 | SMARTWORLD THE EDITION | BDP Design Engineering Pvt. Ltd. | 9160000636 | 10 |  |  | 2024-02-14 | Landscape Design Consultancy (SD/DD/WD) | AU | 1 | 3450000 | 3450000 | 4071000 | 2328750 | 2747925 | 1121250 | 2328750 | 2747925 | ZGEN | 2024-01-11 | 2028-01-11
RE/0066-PRJ-CO-01 | Landscape Consultant | 2010 |  | 2010 | SMARTWORLD THE EDITION | Redland-Scape Company Limited | 9140000095 | 10 |  |  | 2023-04-27 | Landscape Design (Concept) | AU | 1 | 80000 | 0 | 0 | 86480 | 86480 | 86480 | 6555360 | 6555360 | ZSER | 2023-03-12 | 2023-05-10
RE/0066-PRJ-CO-02 | Architecture Design | 2010 |  | 2010 | SMARTWORLD THE EDITION | Studio SymbiosisMr. Amit Gupta | 9140000119 | 10 |  |  | 2023-05-10 | Architect Concept Design & Presentation | AU | 1 | 500000 | 500000 | 590000 | 500000 | 590000 | 0 | 500000 | 590000 | ZSER | 2022-11-28 | 2022-12-19
RE/0066-PRJ-CO-02 | Architecture Design | 2010 |  | 2010 | SMARTWORLD THE EDITION | Studio SymbiosisMr. Amit Gupta | 9140000120 | 10 |  |  | 2023-05-10 | Architectural Design Consultancy | AU | 1 | 35178576 | 35178576 | 41510719.68 | 29550003.05 | 34869003.6 | 5628572.95 | 29208950.69 | 34466561.82 | ZSER | 2023-03-27 | 2027-03-26
RE/0066-PRJ-CO-02 | Architecture Design | 2010 |  | 2010 | SMARTWORLD THE EDITION | Studio SymbiosisMr. Amit Gupta | 9140000120 | 30 |  |  | 2023-05-10 | Interior Design Consultancy | AU | 1 | 8000000 | 8000000 | 9440000 | 3304000 | 3898720 | 4696000 | 3304000 | 3898720 | ZSER | 2023-03-27 | 2027-03-26
RE/0066-PRJ-CO-02 | Architecture Design | 2010 |  | 2010 | SMARTWORLD THE EDITION | Design Centre Consulting EngineersPrivate ltd | 9140000207 | 10 |  |  | 2023-09-02 | Escalation for CLUB | AU | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | ZSER | 2023-07-18 | 2023-10-18
RE/0066-PRJ-CO-02 | Architecture Design | 2010 |  | 2010 | SMARTWORLD THE EDITION | DAWN MODELS PRIVATE LIMITEDMayur Mohan | 9160000079 | 10 |  |  | 2023-05-16 | Scale Model (1:100) with Model 4 Towers | AU | 1 | 1650000 | 1650000 | 1947000 | 0 | 0 | 1650000 | 0 | 0 | ZGEN | 2023-05-04 | 2023-05-11
RE/0066-PRJ-CO-02 | Architecture Design | 2010 |  | 2010 | SMARTWORLD THE EDITION | KAIZEN AI LLP | 9160001165 | 10 |  |  | 2024-06-03 | Design value optimization | AU | 1 | 50000000 | 50000000 | 59000000 | 0 | 0 | 50000000 | 0 | 0 | ZGEN | 2024-06-03 | 2024-08-02
RE/0066-PRJ-CO-03 | Structural Design | 2010 |  | 2010 | SMARTWORLD THE EDITION | Lkt Enginering Consultants Limited Lokesh Kumar Tyagi | 9140000156 | 10 |  |  | 2023-06-09 | Structural Consultancy Services | AU | 1 | 13600000 | 13600000 | 16048000 | 2720000 | 3209600 | 10880000 | 2720000 | 3209600 | ZSER | 2023-01-18 | 2027-01-17
RE/0066-PRJ-CO-03 | Structural Design | 2010 |  | 2010 | SMARTWORLD THE EDITION | Manish Consultantsmanish kumar | 9160000053 | 110 |  |  | 2023-04-28 | Proof consltancy ammendment | AU | 1 | 1600000 | 1600000 | 1888000 | 1600000 | 1888000 | 0 | 1600000 | 1888000 | ZGEN | 2023-03-04 | 2027-03-31
RE/0066-PRJ-CO-03 | Structural Design | 2010 |  | 2010 | SMARTWORLD THE EDITION | National Institute of Technology So Amrit Kumar Roy | 9160000395 | 10 |  |  | 2023-09-30 | STRUCTURE CONSULTANT | AU | 1 | 423728.82 | 423728.82 | 500000.01 | 423728.81 | 500000 | 0.01 | 423728.83 | 500000.02 | ZGEN | 2023-09-05 | 2023-11-05
RE/0066-PRJ-CO-03 | Structural Design | 2010 |  | 2010 | SMARTWORLD THE EDITION | Civtech | 9160000543 | 10 |  |  | 2024-01-04 | STRUCTURE CONSULTANT | AU | 1 | 26325000 | 26325000 | 31063500 | 20533500 | 24229530 | 5791500 | 20533500 | 24229530 | ZGEN | 2024-01-05 | 2028-01-05
RE/0066-PRJ-CO-03 | Structural Design | 2010 |  | 2010 | SMARTWORLD THE EDITION | Civtech | 9160000543 | 20 |  |  | 2024-01-04 | Amendmen Design consultancy | AU | 1 | 8424000 | 8424000 | 9940320 | 6040008 | 7127209.44 | 2383992 | 6040008 | 7127209.44 | ZGEN | 2024-01-05 | 2028-01-05
RE/0066-PRJ-CO-03 | Structural Design | 2010 |  | 2010 | SMARTWORLD THE EDITION | GEOCON INTERNATIONAL PRIVATE LIMITE | 9160001191 | 10 |  |  | 2024-08-31 | plaxis consultant | AU | 1 | 75000 | 75000 | 88500 | 75000 | 88500 | 0 | 75000 | 88500 | ZGEN | 2024-08-31 | 2024-09-30
RE/0066-PRJ-CO-04 | MEP Design | 2010 | GR01 | 2010 | SMARTWORLD THE EDITION | Eco Paryavaran Engineers & ConsultaPrivate Limited | 9140000339 | 10 |  |  | 2024-08-09 | Design & Preparation of 1020KLD STP | AU | 1 | 150000 | 150000 | 177000 | 150000 | 177000 | 0 | 150000 | 177000 | ZSER | 2024-08-09 | 2024-09-08
RE/0066-PRJ-CO-05 | Façade Consultant | 2010 |  | 2010 | SMARTWORLD THE EDITION | Facade Design Factory | 9140000164 | 10 |  |  | 2023-06-21 | SWD 66 - Facade Consultant | AU | 1 | 0 | 1650600 | 1947708 | 742770.17 | 876468.8 | 907829.83 | 742770.17 | 876468.8 | ZSER | 2023-06-15 | 2027-06-15
RE/0066-PRJ-CO-05 | Façade Consultant | 2010 |  | 2010 | SMARTWORLD THE EDITION | Facade Design Factory | 9140000164 | 20 |  |  | 2023-06-21 | Amend -1 SWD 66 - Facade Consultant | AU | 1 | 700000 | 700000 | 826000 | 0 | 0 | 700000 | 0 | 0 | ZSER | 2023-06-15 | 2027-06-15
RE/0066-PRJ-CO-05 | Façade Consultant | 2010 |  | 2010 | SMARTWORLD THE EDITION | LITE & METAL ( L M Design) | 9160002004 | 10 |  |  | 2025-07-07 | Peer review Façade consultant | AU | 1 | 575000 | 575000 | 678500 | 316307.51 | 373242.86 | 258692.49 | 316307.51 | 373242.86 | ZGEN | 2025-06-11 | 2028-06-11
RE/0066-PRJ-CO-06 | BOH | 2010 | GR01 | 2010 |  |  |  | 0 | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
RE/0066-PRJ-CO-07 | Lighting Design consultant | 2010 | GR01 | 2010 | SMARTWORLD THE EDITION | Sahvia Facade Private Limited | 9140000300 | 10 |  |  | 2024-05-09 | SWD 66 Lighting Consultant | AU | 1 | 1620000 | 1620000 | 1911600 | 324000 | 382320 | 1296000 | 324000 | 382320 | ZSER | 2024-05-09 | 2028-05-08
RE/0066-PRJ-CO-08 | Signages Design Consultant | 2010 | GR01 | 2010 |  |  |  | 0 | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
RE/0066-PRJ-CO-09 | 3D Animation/Rendering | 2010 |  | 2010 | SMARTWORLD THE EDITION | ATCHAIN | 9160000069 | 20 |  |  | 2023-05-05 | Rendering and 3D Animation Services | AU | 1 | 38820 | 0 | 0 | 21566.67 | 21566.67 | 21566.67 | 1571821.8 | 1571821.8 | ZGEN | 2023-03-21 | 2023-05-02
RE/0066-PRJ-CO-09 | 3D Animation/Rendering | 2010 |  | 2010 | SMARTWORLD THE EDITION | ATCHAIN | 9160000069 | 30 |  |  | 2023-05-05 | Rendering & 3D Animation (Amendment-01) | AU | 1 | 4500 | 4500 | 4500 | 5000 | 5000 | 500 | 366145.2 | 366145.2 | ZGEN | 2023-03-21 | 2023-05-02
RE/0066-PRJ-CO-09 | 3D Animation/Rendering | 2010 |  | 2010 | SMARTWORLD THE EDITION | Palmtech International LimitedMr Tommy Hou | 9160000112 | 10 |  |  | 2023-05-30 | SWD66 RENDERS | AU | 1 | 7200 | 7200 | 7200 | 4000 | 4000 | 3200 | 294300 | 294300 | ZGEN | 2023-05-26 | 2023-06-25
RE/0066-PRJ-CO-09 | 3D Animation/Rendering | 2010 |  | 2010 | SMARTWORLD THE EDITION | Orange Sky | 9160000550 | 10 |  |  | 2024-01-06 | SWD66_ORANGE SKY LANDSCAPE ANIMATION - F | AU | 1 | 1200000 | 1200000 | 1416000 | 0 | 0 | 1200000 | 0 | 0 | ZGEN | 2023-12-26 | 2024-01-26
RE/0066-PRJ-CO-09 | 3D Animation/Rendering | 2010 |  | 2010 | SMARTWORLD THE EDITION | M/S ANTARES | 9160001269 | 10 |  |  | 2024-08-17 | SWD66_CLUB INTERIOR VIEWS & ANIMATION | AU | 1 | 1980000 | 1980000 | 2336400 | 1839420 | 2170515.6 | 140580 | 1839420 | 2170515.6 | ZGEN | 2024-08-17 | 2024-10-16
RE/0066-PRJ-CO-09 | 3D Animation/Rendering | 2010 |  | 2010 | SMARTWORLD THE EDITION | M/S ANTARES | 9160001269 | 20 |  |  | 2024-08-17 | Amed-1 CLUB INTERIOR VIEWS & ANIMATION | AU | 1 | 119000 | 119000 | 140420 | 119000 | 140420 | 0 | 119000 | 140420 | ZGEN | 2024-08-17 | 2024-10-16
RE/0066-PRJ-CO-09 | 3D Animation/Rendering | 2010 |  | 2010 | SMARTWORLD THE EDITION | M/S ANTARES | 9160001269 | 30 |  |  | 2024-08-17 | Amed-2 CLUB INTERIOR VIEWS & ANIMATION | AU | 1 | 142000 | 142000 | 167560 | 142000 | 167560 | 0 | 142000 | 167560 | ZGEN | 2024-08-17 | 2024-10-16
RE/0066-PRJ-CO-09 | 3D Animation/Rendering | 2010 |  | 2010 | SMARTWORLD THE EDITION | Orange Sky | 9160001560 | 10 |  |  | 2025-03-01 | ANIMATION AND 3d RENDERS | AU | 1 | 2000000 | 2000000 | 2360000 | 2000000 | 2360000 | 0 | 2000000 | 2360000 | ZGEN | 2025-02-27 | 2026-02-27
RE/0066-PRJ-CO-09 | 3D Animation/Rendering | 2010 |  | 2010 | SMARTWORLD THE EDITION | Orange Sky | 9160001560 | 20 |  |  | 2025-03-01 | 3D Visualization Service for SW66 | AU | 1 | 400000 | 400000 | 472000 | 280000 | 330400 | 120000 | 280000 | 330400 | ZGEN | 2025-02-27 | 2026-02-27
RE/0066-PRJ-CO-10 | Block Model Consultant | 2010 | GR01 | 2010 |  |  |  | 0 | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
RE/0066-PRJ-CO-11 | Security Consultant | 2010 | GR01 | 2010 |  |  |  | 0 | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
RE/0066-PRJ-CO-12 | Fire Consultant | 2010 | GR01 | 2010 |  |  |  | 0 | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
RE/0066-PRJ-CO-13 | Interior Design Consultant - Commercial | 2010 |  | 2010 | SMARTWORLD THE EDITION | Suite Grey Matters Pte. Ltd. | 9160000070 | 10 |  |  | 2023-05-05 | SWD66 Interior Design Consultancy | AU | 1 | 175000 | 175000 | 175000 | 91875 | 91875 | 83125 | 7515112.5 | 7515112.5 | ZGEN | 2023-04-20 | 2023-10-19
RE/0066-PRJ-CO-13 | Interior Design Consultant - Commercial | 2010 |  | 2010 | SMARTWORLD THE EDITION | Suite Grey Matters Pte. Ltd. | 9160000070 | 20 |  |  | 2023-05-05 | Amendment in WO no ETSY/SECTOR 66/ INTE | AU | 1 | 25000 | 25000 | 25000 | 29500 | 29500 | 4500 | 2077000 | 2077000 | ZGEN | 2023-04-20 | 2023-10-19
RE/0066-PRJ-CO-14 | Interior Design Consultant - SA | 2010 | GR01 | 2010 | SMARTWORLD THE EDITION | LINE LUXE PRIVATE LIMITED | 9160002079 | 10 |  |  | 2025-07-24 | The Edition 66-Lead apartment design | AU | 1 | 935000 | 935000 | 1103300 | 374000 | 441320 | 561000 | 374000 | 441320 | ZGEN | 2025-07-14 | 2026-07-14
RE/0066-PRJ-CO-15 | Wind Tunnel Consultant | 2010 | GR01 | 2010 | SMARTWORLD THE EDITION | Rwdi Consulting Engineers India PriLimited | 9160003174 | 10 |  |  | 2026-06-03 | For facade Desktop analysis The edition | AU | 1 | 200000 | 200000 | 236000 | 0 | 0 | 200000 | 0 | 0 | ZGEN | 2026-05-22 | 2026-07-22
RE/0066-PRJ-CO-16 | Green Building Consultant | 2010 | GR01 | 2010 |  |  |  | 0 | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
RE/0066-PRJ-CO-17 | Traffic Design Consultancy | 2010 | GR01 | 2010 | SMARTWORLD THE EDITION | Matrix Management ConsultantsPrivate Limited | 9160001005 | 10 |  |  | 2024-07-03 | SWD66 VERTICAL TRANSPORTATION CONSULTANC | AU | 1 | 590000 | 590000 | 696200 | 501500 | 591770 | 88500 | 501500 | 591770 | ZGEN | 2024-05-09 | 2028-05-09
RE/0066-PRJ-CO-18 | BIM Design - Architectural & MEP | 2010 |  | 2010 | SMARTWORLD THE EDITION | Studio SymbiosisMr. Amit Gupta | 9140000120 | 20 |  |  | 2023-05-10 | BIM for Architecture | AU | 1 | 4138656 | 4138656 | 4883614.08 | 2710819.69 | 3198767.23 | 1427836.31 | 2710819.69 | 3198767.23 | ZSER | 2023-03-27 | 2027-03-26
RE/0066-PRJ-CO-19 | Soil Investigation/Topographical SurveyC | 2010 | GR01 | 2010 |  |  |  | 0 | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
RE/0066-PRJ-CO-20 | Project Management Consultant | 2010 |  | 2010 | SMARTWORLD THE EDITION | Cushman & Wakefied India Private Li | 9140000142 | 10 |  |  | 2023-05-26 | PMC for Project Monitoring Services | AU | 1 | 1950000 | 1950000 | 2301000 | 1893250 | 2234035 | 56750 | 1892800.51 | 2233504.6 | ZSER | 2023-03-24 | 2023-07-23
RE/0066-PRJ-CO-20 | Project Management Consultant | 2010 |  | 2010 | SMARTWORLD THE EDITION | HPG Consulting India Pvt. Ltd.Mr. Bhojra | 9160000430 | 10 |  |  | 2023-11-04 | Facility Planning and Food Service Desig | AU | 1 | 450000 | 450000 | 531000 | 247500 | 292050 | 202500 | 247500 | 292050 | ZGEN | 2023-10-21 | 2027-10-21
RE/0066-PRJ-CO-20 | Project Management Consultant | 2010 |  | 2010 | SMARTWORLD THE EDITION | Jones Lang Lasalle Property Consultants Pvt. Ltd. | 9160001930 | 10 |  |  | 2025-06-13 | Project Timelines Evaluation | AU | 1 | 250000 | 250000 | 295000 | 0 | 0 | 250000 | 0 | 0 | ZGEN | 2025-05-22 | 2025-07-22
RE/0066-PRJ-CO-20 | Project Management Consultant | 2010 |  | 2010 | SMARTWORLD THE EDITION | KPMG Assurance and Consulting ServiLLP | 9160002265 | 10 |  |  | 2025-09-09 | Periodic Project Monitoring Services | AU | 1 | 1410000 | 1410000 | 1663800 | 470000 | 554600 | 940000 | 470000 | 554600 | ZGEN | 2025-09-06 | 2026-09-06
RE/0066-PRJ-CO-20 | Project Management Consultant | 2010 |  | 2010 | SMARTWORLD THE EDITION | KPMG Assurance and Consulting ServiLLP | 9160002265 | 20 |  |  | 2025-09-09 | Additional Expenses as per WO | AU | 1 | 19375 | 19375 | 22862.5 | 19375 | 22862.5 | 0 | 19375 | 22862.5 | ZGEN | 2025-09-06 | 2026-09-06
RE/0066-PRJ-CO-20 | Project Management Consultant | 2010 |  | 2010 | SMARTWORLD THE EDITION | KPMG Assurance and Consulting ServiLLP | 9160002265 | 30 |  |  | 2025-09-09 | Additional Expensse provisional | AU | 1 | 112897.5 | 112897.5 | 133219.05 | 26030.51 | 30716 | 86866.99 | 26030.51 | 30716 | ZGEN | 2025-09-06 | 2026-09-06
RE/0066-PRJ-CO-21 | Cost Consultants | 2010 |  | 2010 | SMARTWORLD THE EDITION | IMCM Private Limited | 9140000126 | 10 |  |  | 2023-05-15 | Schematic Stage Budget Cost Consultancy | AU | 1 | 250000 | 250000 | 295000 | 250000 | 295000 | 0 | 250000 | 295000 | ZSER | 2023-02-28 | 2023-03-27
RE/0066-PRJ-CO-21 | Cost Consultants | 2010 |  | 2010 | SMARTWORLD THE EDITION | AECOM INDIA PRIVATE LIMITEDMr Suveer Popli | 9140000364 | 10 |  |  | 2023-05-15 | Schematic stage | AU | 1 | 600000 | 600000 | 708000 | 600000 | 708000 | 0 | 600000 | 708000 | ZSER | 2023-05-15 | 2024-12-31
RE/0066-PRJ-CO-21 | Cost Consultants | 2010 |  | 2010 | SMARTWORLD THE EDITION | AECOM INDIA PRIVATE LIMITEDMr Suveer Popli | 9140000364 | 20 |  |  | 2023-05-15 | Design Development & Tendering | AU | 1 | 1800000 | 1800000 | 2124000 | 1176000 | 1387680 | 624000 | 1176000 | 1387680 | ZSER | 2023-05-15 | 2024-12-31
RE/0066-PRJ-CO-21 | Cost Consultants | 2010 |  | 2010 | SMARTWORLD THE EDITION | AECOM INDIA PRIVATE LIMITEDMr Suveer Popli | 9140000364 | 30 |  |  | 2023-05-15 | RERA Documentations | AU | 1 | 600000 | 600000 | 708000 | 0 | 0 | 600000 | 0 | 0 | ZSER | 2023-05-15 | 2024-12-31
RE/0066-PRJ-CO-21 | Cost Consultants | 2010 |  | 2010 | SMARTWORLD THE EDITION | Savills Property Services (India)Private Limited | 9140000403 | 10 |  |  | 2024-08-04 | Cost Consultant Work (Post Contract) | AU | 1 | 31962280 | 31962280 | 37715490.4 | 9321313.92 | 10999150.43 | 22640966.08 | 9321313.97 | 10999150.49 | ZSER | 2024-08-04 | 2027-12-04
RE/0066-PRJ-CO-22 | Other Consultants | 2010 | GR01 | 2010 | SMARTWORLD THE EDITION | Visilean India Private Limited | 9140000361 | 10 |  |  | 2024-09-17 | Digital Construction Management Software | AU | 1 | 892500 | 892500 | 1053150 | 892500 | 1053150 | 0 | 892500 | 1053150 | ZSER | 2024-09-17 | 2025-09-16
RE/0066-PRJ-CO-22 | Other Consultants | 2010 | GR01 | 2010 | SMARTWORLD THE EDITION | Visilean India Private Limited | 9140000361 | 20 |  |  | 2024-09-17 | Digital Construction Management Amend-1 | AU | 1 | 780000 | 780000 | 920400 | 390000 | 460200 | 390000 | 390000 | 460200 | ZSER | 2024-09-17 | 2025-09-16
RE/0066-PRJ-CO-22 | Other Consultants | 2010 | GR01 | 2010 | SMARTWORLD THE EDITION | Ind Research & Devlopment House Pvt. Ltd | 9140000370 | 10 |  |  | 2024-03-01 | Environmental compliance | AU | 1 | 60000 | 60000 | 70800 | 60000 | 70800 | 0 | 60000 | 70800 | ZSER | 2024-03-01 | 2025-10-08
RE/0066-PRJ-CO-22 | Other Consultants | 2010 | GR01 | 2010 | SMARTWORLD THE EDITION | Tuv India Private Limited | 9140000458 | 10 |  |  | 2025-06-05 | Safety Audit Etsy | AU | 1 | 130000 | 130000 | 153400 | 130000 | 153400 | 0 | 130000 | 153400 | ZSER | 2025-06-06 | 2026-06-06
RE/0066-PRJ-CO-22 | Other Consultants | 2010 | GR01 | 2010 | SMARTWORLD THE EDITION | Tuv India Private Limited | 9140000458 | 20 |  |  | 2025-06-05 | Safety Audit ( Amend-1)FY2026-2027 | AU | 1 | 320000 | 320000 | 377600 | 0 | 0 | 320000 | 0 | 0 | ZSER | 2025-06-06 | 2026-06-06
RE/0066-PRJ-CO-22 | Other Consultants | 2010 | GR01 | 2010 | SMARTWORLD THE EDITION | Bureau Veritas (India ) Private limMr. Pranay Kumar Singh | 9140000461 | 10 |  |  | 2025-06-07 | Structure Audit Agency | AU | 1 | 2814000 | 2814000 | 3320520 | 594000 | 700920 | 2220000 | 594000 | 700920 | ZSER | 2025-06-06 | 2026-06-06
RE/0066-PRJ-CO-22 | Other Consultants | 2010 | GR01 | 2010 | SMARTWORLD THE EDITION | Ind Research & Devlopment House Pvt. Ltd | 9140000474 | 10 |  |  | 2025-07-08 | Environmental compliance | AU | 1 | 60000 | 60000 | 70800 | 60000 | 70800 | 0 | 60000 | 70800 | ZSER | 2025-03-01 | 2026-03-01
RE/0066-PRJ-CO-22 | Other Consultants | 2010 | GR01 | 2010 | SMARTWORLD THE EDITION | IMCM Private Limited | 9160001841 | 10 |  |  | 2025-05-22 | Consultancy services for Preparation of | AU | 1 | 425000 | 425000 | 501500 | 212500 | 250750 | 212500 | 212500 | 250750 | ZGEN | 2025-04-28 | 2025-06-28
RE/0066-PRJ-CO-22 | Other Consultants | 2010 | GR01 | 2010 | SMARTWORLD THE EDITION | Ashok Kumar Tiwari | 9160002257 | 10 |  |  | 2025-09-08 | Consuultancy for Concrete Technologist | AU | 1 | 900000 | 900000 | 900000 | 750000 | 750000 | 150000 | 750000 | 750000 | ZGEN | 2025-08-22 | 2026-01-22
RE/0066-PRJ-CO-22 | Other Consultants | 2010 | GR01 | 2010 | SMARTWORLD THE EDITION | Ashok Kumar Tiwari | 9160002257 | 20 |  |  | 2025-09-08 | Incorporate reimbursement 1 | AU | 1 | 20947.1 | 20947.1 | 20947.1 | 20947.1 | 20947.1 | 0 | 20947.1 | 20947.1 | ZGEN | 2025-08-22 | 2026-01-22
RE/0066-PRJ-CO-22 | Other Consultants | 2010 | GR01 | 2010 | SMARTWORLD THE EDITION | Ashok Kumar Tiwari | 9160002257 | 30 |  |  | 2025-09-08 | Incorporate reimbursement 2 | AU | 1 | 40314.79 | 40314.79 | 40314.79 | 40314.79 | 40314.79 | 0 | 40314.79 | 40314.79 | ZGEN | 2025-08-22 | 2026-01-22
RE/0066-PRJ-CO-22 | Other Consultants | 2010 | GR01 | 2010 | SMARTWORLD THE EDITION | Ashok Kumar Tiwari | 9160002257 | 40 |  |  | 2025-09-08 | Incorporate reimbursement 3 | AU | 1 | 25191.92 | 25191.92 | 25191.92 | 25166.73 | 25166.73 | 25.19 | 25166.73 | 25166.73 | ZGEN | 2025-08-22 | 2026-01-22
RE/0066-PRJ-CO-22 | Other Consultants | 2010 | GR01 | 2010 | SMARTWORLD THE EDITION | Ashok Kumar Tiwari | 9160002257 | 50 |  |  | 2025-09-08 | Incorporate reimbursement 4 | AU | 1 | 32831.12 | 32831.12 | 32831.12 | 32831.12 | 32831.12 | 0 | 32831.12 | 32831.12 | ZGEN | 2025-08-22 | 2026-01-22
RE/0066-PRJ-CO-22 | Other Consultants | 2010 | GR01 | 2010 | SMARTWORLD THE EDITION | Ashok Kumar Tiwari | 9160002257 | 60 |  |  | 2025-09-08 | Incorporate reimbursement 5 | AU | 1 | 46043 | 46043 | 46043 | 46043 | 46043 | 0 | 46043 | 46043 | ZGEN | 2025-08-22 | 2026-01-22
RE/0066-PRJ-CO-22 | Other Consultants | 2010 | GR01 | 2010 | SMARTWORLD THE EDITION | SPRINKLER ENGINEERINGMr. Rohit Kumar | 9160002744 | 10 |  |  | 2026-02-16 | Swimming Pool & Water Body Design Consul | AU | 1 | 200000 | 200000 | 236000 | 0 | 0 | 200000 | 0 | 0 | ZGEN | 2026-02-25 | 2027-02-25
RE/0066-PRJ-CO-AST-OA | Other Assets | 2010 | GR01 | 2010 |  |  |  | 0 | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
RE/0066-PRJ-CO-AST-PM | Plant & Machinery | 2010 | GR01 | 2010 |  |  |  | 0 | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
RE/0066-PRJ-CO-AST-VE | Vehicle | 2010 | GR01 | 2010 |  |  |  | 0 | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
RE/0066-PRJ-CO-CIV-CC-LA | Concrete Labour | 2010 | GR01 | 2010 |  |  |  | 0 | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
RE/0066-PRJ-CO-CIV-CC-SL | Concrete Supply & Labour | 2010 | GR01 | 2010 |  |  |  | 0 | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
RE/0066-PRJ-CO-CIV-CC-SU | Concrete Supply | 2010 | GR01 | 2010 |  |  |  | 0 | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
RE/0066-PRJ-CO-CIV-MS | Misc Structure Works | 2010 | GR01 | 2010 |  |  |  | 0 | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
RE/0066-PRJ-CO-CIV-MW | Masonry Works | 2010 | GR01 | 2010 |  |  |  | 0 | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
RE/0066-PRJ-CO-CIV-PW-IP | Internal Plaster | 2010 | GR01 | 2010 |  |  |  | 0 | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
RE/0066-PRJ-CO-CIV-PW-XP | External Plaster | 2010 | GR01 | 2010 |  |  |  | 0 | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
RE/0066-PRJ-CO-CIV-RS-LA | Reinforcement Labour | 2010 | GR01 | 2010 |  |  |  | 0 | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
RE/0066-PRJ-CO-CIV-RS-SU | Reinforcement Supply | 2010 | GR01 | 2010 |  |  |  | 0 | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
RE/0066-PRJ-CO-CIV-SW-CS | Conventional Shuttering | 2010 | GR01 | 2010 |  |  |  | 0 | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
RE/0066-PRJ-CO-CIV-SW-SU | Aluminum Shuttering | 2010 | GR01 | 2010 |  |  |  | 0 | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
RE/0066-PRJ-CO-CIV-WP | Waterproofing Works | 2010 | GR01 | 2010 |  |  |  | 0 | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
RE/0066-PRJ-CO-EXD-CO | Connection Through DHBVNL | 2010 | GR01 | 2010 |  |  |  | 0 | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
RE/0066-PRJ-CO-EXD-EW | Electrical Works | 2010 | GR01 | 2010 | SMARTWORLD THE EDITION | SATKARTAR ELECTRICALS AND ELECTRONIPRIVATE LIMITED | 9140000677 | 80 |  |  | 2026-06-02 | Electrical Works - External | AU | 1 | 13549325 | 13549325 | 15988203.5 | 0 | 0 | 13549325 | 0 | 0 | ZSER | 2026-06-01 | 2028-02-01
RE/0066-PRJ-CO-EXD-EW | Electrical Works | 2010 | GR01 | 2010 | SMARTWORLD THE EDITION | SATKARTAR ELECTRICALS AND ELECTRONIPRIVATE LIMITED | 9140000677 | 100 |  |  | 2026-06-02 | External Lighting Works | AU | 1 | 4302240 | 4302240 | 5076643.2 | 0 | 0 | 4302240 | 0 | 0 | ZSER | 2026-06-01 | 2028-02-01
RE/0066-PRJ-CO-EXD-HD | Hardscape Works | 2010 | GR01 | 2010 |  |  |  | 0 | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
RE/0066-PRJ-CO-EXD-HO | Horticulture Works | 2010 | GR01 | 2010 |  |  |  | 0 | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
RE/0066-PRJ-CO-EXD-MC | Misc Civil Works | 2010 | GR01 | 2010 |  |  |  | 0 | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
RE/0066-PRJ-CO-MEP-EW-LE | Low Side Electrical Works | 2010 | GR01 | 2010 |  |  |  | 0 | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
RE/0066-PRJ-CO-MEP-EW-LS | Light Fixtures Suppl | 2010 | GR01 | 2010 |  |  |  | 0 | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
RE/0066-PRJ-CO-MEP-FF-FX | Fire Fighting External | 2010 | GR01 | 2010 | SMARTWORLD THE EDITION | Atom MEP Engineers Pvt. Ltd. | 9140000668 | 420 |  |  | 2026-05-19 | FF-PORTABLE FIRE EXTINGUISHERS Ext. | AU | 1 | 103416 | 103416 | 122030.88 | 0 | 0 | 103416 | 0 | 0 | ZSER | 2026-04-04 | 2028-02-04
RE/0066-PRJ-CO-MEP-FF-FX | Fire Fighting External | 2010 | GR01 | 2010 | SMARTWORLD THE EDITION | Atom MEP Engineers Pvt. Ltd. | 9140000668 | 430 |  |  | 2026-05-19 | FF-EXTERNAL FIRE PROTECTION-Ext. | AU | 1 | 4417921 | 4417921 | 5213146.78 | 0 | 0 | 4417921 | 0 | 0 | ZSER | 2026-04-04 | 2028-02-04
RE/0066-PRJ-CO-MEP-PB-EP | External Plumbing | 2010 | GR01 | 2010 | SMARTWORLD THE EDITION | Atom MEP Engineers Pvt. Ltd. | 9140000668 | 160 |  |  | 2026-05-19 | DOMESTIC AND FLUSHING WATER Exter. | AU | 1 | 47593 | 47593 | 56159.74 | 0 | 0 | 47593 | 0 | 0 | ZSER | 2026-04-04 | 2028-02-04
RE/0066-PRJ-CO-MEP-PB-EP | External Plumbing | 2010 | GR01 | 2010 | SMARTWORLD THE EDITION | Atom MEP Engineers Pvt. Ltd. | 9140000668 | 170 |  |  | 2026-05-19 | EXTERNAL WATER SUPPLY & MUNCIPAL WATER I | AU | 1 | 2994031 | 2994031 | 3532956.58 | 0 | 0 | 2994031 | 0 | 0 | ZSER | 2026-04-04 | 2028-02-04
RE/0066-PRJ-CO-MEP-PB-EP | External Plumbing | 2010 | GR01 | 2010 | SMARTWORLD THE EDITION | Atom MEP Engineers Pvt. Ltd. | 9140000668 | 220 |  |  | 2026-05-19 | MISCELLANEOUS ITEMS FOR TERRACE-Ext. | AU | 1 | 383570 | 383570 | 452612.6 | 0 | 0 | 383570 | 0 | 0 | ZSER | 2026-04-04 | 2028-02-04
RE/0066-PRJ-CO-MEP-PB-EP | External Plumbing | 2010 | GR01 | 2010 | SMARTWORLD THE EDITION | Atom MEP Engineers Pvt. Ltd. | 9140000668 | 230 |  |  | 2026-05-19 | EXTERNAL SEWERAGE SYSTEM-.-Ext. | AU | 1 | 5440270 | 5440270 | 6419518.6 | 0 | 0 | 5440270 | 0 | 0 | ZSER | 2026-04-04 | 2028-02-04
RE/0066-PRJ-CO-MEP-PB-EP | External Plumbing | 2010 | GR01 | 2010 | SMARTWORLD THE EDITION | Atom MEP Engineers Pvt. Ltd. | 9140000668 | 240 |  |  | 2026-05-19 | EXTERNAL STORM WATER DRAINAGE-.-Ext. | AU | 1 | 19510361.84 | 19510361.84 | 23022226.97 | 0 | 0 | 19510361.84 | 0 | 0 | ZSER | 2026-04-04 | 2028-02-04
RE/0066-PRJ-CO-MEP-PB-EP | External Plumbing | 2010 | GR01 | 2010 | SMARTWORLD THE EDITION | Atom MEP Engineers Pvt. Ltd. | 9140000668 | 250 |  |  | 2026-05-19 | EXTERNAL IRRIGATION SYSTEM-.-Ext. | AU | 1 | 1652217.24 | 1652217.24 | 1949616.34 | 0 | 0 | 1652217.24 | 0 | 0 | ZSER | 2026-04-04 | 2028-02-04
RE/0066-PRJ-CO-MEP-PB-EP | External Plumbing | 2010 | GR01 | 2010 | SMARTWORLD THE EDITION | Atom MEP Engineers Pvt. Ltd. | 9140000668 | 260 |  |  | 2026-05-19 | WATER SUPPLY, DRAINAGE PUMPS--Ext. | AU | 1 | 854458 | 854458 | 1008260.44 | 0 | 0 | 854458 | 0 | 0 | ZSER | 2026-04-04 | 2028-02-04
RE/0066-PRJ-CO-MEP-PB-IP | Internal Plumbing | 2010 | GR01 | 2010 |  |  |  | 0 | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
RE/0066-PRJ-CO-MEP-PB-JC | JACUZZI | 2010 | GR01 | 2010 |  |  |  | 0 | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
RE/0066-PRJ-CO-MEP-PB-ST | STP/WTP/OWC | 2010 | GR01 | 2010 |  |  |  | 0 | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
RE/0066-PRJ-CO-OTH-AB | Additional Budget | 2010 | GR01 | 2010 | SMARTWORLD THE EDITION | SBJ Concrete Buildcon Private Limit | 9110000654 | 10 |  |  | 2024-08-05 | Ready Mix Concrete M - 7.5 | M3 | 200 | 3572.5 | 714500 | 843110 | 131182.2 | 154795 | 583317.8 | 131182.2 | 154795.24 | ZMAT | 2024-08-05 | 2024-09-05
RE/0066-PRJ-CO-OTH-AB | Additional Budget | 2010 | GR01 | 2010 | SMARTWORLD THE EDITION | SBJ Concrete Buildcon Private Limit | 9110000654 | 20 |  |  | 2024-08-05 | Ready Mix Concrete M - 25 | M3 | 50 | 4205 | 210250 | 248095 | 172236.8 | 203239.42 | 38013.2 | 172236.8 | 203239.76 | ZMAT | 2024-08-05 | 2024-09-05
RE/0066-PRJ-CO-OTH-AB | Additional Budget | 2010 | GR01 | 2010 | SMARTWORLD THE EDITION | Unified Formwork System Privatelimited | 9110001112 | 10 |  |  | 2025-06-13 | Safety Screen System | M2 | 10504 | 5800 | 60923200 | 71889376 | 60391746 | 71262260.28 | 531454 | 60391746 | 71262260.28 | ZMAT | 2025-05-14 | 2025-06-14
RE/0066-PRJ-CO-OTH-AB | Additional Budget | 2010 | GR01 | 2010 | SMARTWORLD THE EDITION | Unified Formwork System Privatelimited | 9110001112 | 20 |  |  | 2025-06-13 | Freight @ INR 50 Per Sqm | NO | 10504 | 50 | 525200 | 619736 | 520618.5 | 614329.83 | 4581.5 | 520618.5 | 614329.83 | ZMAT | 2025-05-14 | 2025-06-14
RE/0066-PRJ-CO-OTH-AB | Additional Budget | 2010 | GR01 | 2010 | SMARTWORLD THE EDITION | AMIT ENTERPRISESAMIT KHANDELWAL | 9110001801 | 20 |  |  | 2026-05-14 | Modular Mat | FT2 | 538.2 | 1695 | 912249 | 1076453.82 | 870501.15 | 1027191.36 | 41747.85 | 870501.15 | 1027191.36 | ZMAT | 2026-05-09 | 2026-05-16
RE/0066-PRJ-CO-OTH-AB | Additional Budget | 2010 | GR01 | 2010 | SMARTWORLD THE EDITION | karemete Global Solutions | 9110001851 | 10 |  |  | 2026-06-11 | Digital Right Angle | NO | 6 | 1450 | 8700 | 10266 | 0 | 0 | 8700 | 0 | 0 | ZMAT
RE/0066-PRJ-CO-OTH-AB | Additional Budget | 2010 | GR01 | 2010 | SMARTWORLD THE EDITION | karemete Global Solutions | 9110001851 | 20 |  |  | 2026-06-11 | Right Angle | NO | 6 | 1350 | 8100 | 9558 | 0 | 0 | 8100 | 0 | 0 | ZMAT
RE/0066-PRJ-CO-OTH-AB | Additional Budget | 2010 | GR01 | 2010 | SMARTWORLD THE EDITION | karemete Global Solutions | 9110001851 | 30 |  |  | 2026-06-11 | Digital Screw Gauge (Macro Meter) | NO | 1 | 2500 | 2500 | 2950 | 0 | 0 | 2500 | 0 | 0 | ZMAT
RE/0066-PRJ-CO-OTH-AB | Additional Budget | 2010 | GR01 | 2010 | SMARTWORLD THE EDITION | karemete Global Solutions | 9110001851 | 40 |  |  | 2026-06-11 | sprit level 2mtr Lenth | NO | 6 | 1190 | 7140 | 8425.2 | 0 | 0 | 7140 | 0 | 0 | ZMAT
RE/0066-PRJ-CO-OTH-AB | Additional Budget | 2010 | GR01 | 2010 | SMARTWORLD THE EDITION | karemete Global Solutions | 9110001851 | 50 |  |  | 2026-06-11 | Paint Thickness Gauge | NO | 1 | 6875 | 6875 | 8112.5 | 0 | 0 | 6875 | 0 | 0 | ZMAT
RE/0066-PRJ-CO-OTH-AB | Additional Budget | 2010 | GR01 | 2010 | SMARTWORLD THE EDITION | karemete Global Solutions | 9110001851 | 60 |  |  | 2026-06-11 | Straight Edge | NO | 1 | 750 | 750 | 885 | 0 | 0 | 750 | 0 | 0 | ZMAT
RE/0066-PRJ-CO-OTH-AB | Additional Budget | 2010 | GR01 | 2010 | SMARTWORLD THE EDITION | karemete Global Solutions | 9110001851 | 70 |  |  | 2026-06-11 | Feeler Gauge | NO | 1 | 110 | 110 | 129.8 | 0 | 0 | 110 | 0 | 0 | ZMAT
RE/0066-PRJ-CO-OTH-AB | Additional Budget | 2010 | GR01 | 2010 | SMARTWORLD THE EDITION | karemete Global Solutions | 9110001851 | 80 |  |  | 2026-06-11 | Tile Hollowness checker tool | NO | 6 | 450 | 2700 | 3186 | 0 | 0 | 2700 | 0 | 0 | ZMAT
RE/0066-PRJ-CO-OTH-AB | Additional Budget | 2010 | GR01 | 2010 | SMARTWORLD THE EDITION | karemete Global Solutions | 9110001851 | 90 |  |  | 2026-06-11 | Measuring Tape | NO | 40 | 125 | 5000 | 5900 | 0 | 0 | 5000 | 0 | 0 | ZMAT
RE/0066-PRJ-CO-OTH-AB | Additional Budget | 2010 | GR01 | 2010 | SMARTWORLD THE EDITION | karemete Global Solutions | 9110001851 | 100 |  |  | 2026-06-11 | Digital Measuring Tape | NO | 2 | 2500 | 5000 | 5900 | 0 | 0 | 5000 | 0 | 0 | ZMAT
RE/0066-PRJ-CO-OTH-AB | Additional Budget | 2010 | GR01 | 2010 | SMARTWORLD THE EDITION | karemete Global Solutions | 9110001851 | 110 |  |  | 2026-06-11 | Levelling Tool (Bosch) | NO | 4 | 8500 | 34000 | 40120 | 0 | 0 | 34000 | 0 | 0 | ZMAT
RE/0066-PRJ-CO-OTH-AB | Additional Budget | 2010 | GR01 | 2010 | SMARTWORLD THE EDITION | Aditya Electro Projects | 9140000268 | 10 |  |  | 2024-03-18 | EXTERNAL LIGHTING FIXTURES | AU | 1 | 1720540 | 1720540 | 2030237.2 | 1715840 | 2024691.2 | 4700 | 1715840 | 2024691.2 | ZSER | 2024-03-02 | 2024-04-17
RE/0066-PRJ-CO-OTH-AB | Additional Budget | 2010 | GR01 | 2010 | SMARTWORLD THE EDITION | Aditya Electro Projects | 9140000268 | 20 |  |  | 2024-03-18 | CABLES AND PIPES FOR STREET LIGHTING | AU | 1 | 633790 | 633790 | 747872.2 | 539500.17 | 636610.2 | 94289.83 | 539500 | 636610 | ZSER | 2024-03-02 | 2024-04-17
RE/0066-PRJ-CO-OTH-AB | Additional Budget | 2010 | GR01 | 2010 | SMARTWORLD THE EDITION | Aditya Electro Projects | 9140000268 | 30 |  |  | 2024-03-18 | SUPPLY OF FEEDER PILLARS | AU | 1 | 62100 | 62100 | 73278 | 62100 | 73278 | 0 | 62100 | 73278 | ZSER | 2024-03-02 | 2024-04-17
RE/0066-PRJ-CO-OTH-AB | Additional Budget | 2010 | GR01 | 2010 | SMARTWORLD THE EDITION | Aditya Electro Projects | 9140000268 | 40 |  |  | 2024-03-18 | EARTHING | AU | 1 | 73200 | 73200 | 86376 | 70440 | 83119.2 | 2760 | 70440 | 83119.2 | ZSER | 2024-03-02 | 2024-04-17
RE/0066-PRJ-CO-OTH-AB | Additional Budget | 2010 | GR01 | 2010 | SMARTWORLD THE EDITION | Aditya Electro Projects | 9140000268 | 50 |  |  | 2024-03-18 | Amendment to External elec work upgrad. | AU | 1 | 314700 | 314700 | 371346 | 148500 | 175230 | 166200 | 148500 | 175230 | ZSER | 2024-03-02 | 2024-04-17
RE/0066-PRJ-CO-OTH-AB | Additional Budget | 2010 | GR01 | 2010 | SMARTWORLD THE EDITION | Evolve Buildcon | 9140000276 | 10 |  |  | 2024-03-14 | LANDSCAPE CIVIL WORKS | AU | 1 | 236875 | 236875 | 279512.5 | 175141.36 | 206666.81 | 61733.64 | 175141.53 | 206667 | ZSER | 2024-03-14 | 2024-04-14
RE/0066-PRJ-CO-OTH-AB | Additional Budget | 2010 | GR01 | 2010 | SMARTWORLD THE EDITION | Evolve Buildcon | 9140000276 | 20 |  |  | 2024-03-14 | LANDSCAPE FINISHING WORKS | AU | 1 | 181500 | 181500 | 214170 | 181499.98 | 214169.98 | 0.02 | 181500 | 214170 | ZSER | 2024-03-14 | 2024-04-14
RE/0066-PRJ-CO-OTH-AB | Additional Budget | 2010 | GR01 | 2010 | SMARTWORLD THE EDITION | Evolve Buildcon | 9140000276 | 30 |  |  | 2024-03-14 | Amendment 1 External Hardscape Works | AU | 1 | 213211 | 213211 | 251588.98 | 208366.68 | 245872.68 | 4844.32 | 208366.59 | 245872.58 | ZSER | 2024-03-14 | 2024-04-14
RE/0066-PRJ-CO-OTH-AB | Additional Budget | 2010 | GR01 | 2010 | SMARTWORLD THE EDITION | Leafy Labs Private Limited | 9140000279 | 10 |  |  | 2024-04-25 | Trees | AU | 1 | 165000 | 165000 | 194700 | 98400 | 116112 | 66600 | 98400 | 116112 | ZSER | 2024-04-12 | 2024-11-12
RE/0066-PRJ-CO-OTH-AB | Additional Budget | 2010 | GR01 | 2010 | SMARTWORLD THE EDITION | Leafy Labs Private Limited | 9140000279 | 20 |  |  | 2024-04-25 | SHRUBS, CLIMBERS and PLANTS | AU | 1 | 504400 | 504400 | 595192 | 259000 | 305620 | 245400 | 259000 | 305620 | ZSER | 2024-04-12 | 2024-11-12
RE/0066-PRJ-CO-OTH-AB | Additional Budget | 2010 | GR01 | 2010 | SMARTWORLD THE EDITION | Leafy Labs Private Limited | 9140000279 | 30 |  |  | 2024-04-25 | GRASS COVERS | AU | 1 | 205750 | 205750 | 242785 | 164600 | 194228 | 41150 | 164600 | 194228 | ZSER | 2024-04-12 | 2024-11-12
RE/0066-PRJ-CO-OTH-AB | Additional Budget | 2010 | GR01 | 2010 | SMARTWORLD THE EDITION | Leafy Labs Private Limited | 9140000279 | 40 |  |  | 2024-04-25 | Amendment to Softscape works | AU | 1 | 1941200 | 1941200 | 2290616 | 1566800 | 1848824 | 374400 | 1566800 | 1848824 | ZSER | 2024-04-12 | 2024-11-12
RE/0066-PRJ-CO-OTH-AB | Additional Budget | 2010 | GR01 | 2010 | SMARTWORLD THE EDITION | Haarish Electric vehicles | 9140000297 | 10 |  |  | 2024-06-10 | Chain Link Fencing works | AU | 1 | 450767.74 | 450767.74 | 531905.93 | 72352.92 | 85376.45 | 378414.82 | 72352.92 | 85376.45 | ZSER | 2024-06-03 | 2024-06-20
RE/0066-PRJ-CO-OTH-AB | Additional Budget | 2010 | GR01 | 2010 | SMARTWORLD THE EDITION | Frontline Construction | 9140000306 | 10 |  |  | 2024-07-03 | Approach road & hardscape works of 1Acre | AU | 1 | 2467860 | 2467860 | 2912074.8 | 1843846.72 | 2175739.13 | 624013.28 | 1843845.87 | 2175738.13 | ZSER | 2024-06-13 | 2024-07-30
RE/0066-PRJ-CO-OTH-AB | Additional Budget | 2010 | GR01 | 2010 | SMARTWORLD THE EDITION | Ahluwalia Contracts India Limited | 9140000321 | 150 |  |  | 2024-07-20 | REINFORCEMENT STEEL SHIFTING | AU | 1 | 447488 | 447488 | 528035.84 | 447488 | 528035.84 | 0 | 447488 | 528035.84 | ZSER | 2024-07-15 | 2027-01-14
RE/0066-PRJ-CO-OTH-AB | Additional Budget | 2010 | GR01 | 2010 | SMARTWORLD THE EDITION | Ahluwalia Contracts India Limited | 9140000321 | 160 |  |  | 2024-07-20 | Amed-Monthly rental payment to M/S ACIL | AU | 1 | 105918991.81 | 69562008.01 | 82083169.45 | 40515649.52 | 47808466.43 | 29046358.49 | 9460000 | 11162800 | ZSER | 2024-07-15 | 2027-01-14
RE/0066-PRJ-CO-OTH-AB | Additional Budget | 2010 | GR01 | 2010 | SMARTWORLD THE EDITION | Sirajuddin Ali Contractor | 9140000333 | 10 |  |  | 2024-08-03 | Shoring for Soil Stabilization | AU | 1 | 406700 | 406700 | 479906 | 406700 | 479906 | 0 | 406700 | 479906 | ZSER | 2024-08-03 | 2024-09-02
RE/0066-PRJ-CO-OTH-AB | Additional Budget | 2010 | GR01 | 2010 | SMARTWORLD THE EDITION | Sirajuddin Ali Contractor | 9140000333 | 20 |  |  | 2024-08-03 | Amendment-1 for Shoring works | AU | 1 | 818300 | 818300 | 965594 | 757349.15 | 893672 | 60950.85 | 757348.91 | 893671.71 | ZSER | 2024-08-03 | 2024-09-02
RE/0066-PRJ-CO-OTH-AB | Additional Budget | 2010 | GR01 | 2010 | SMARTWORLD THE EDITION | CROSS ROAD BUILDCON PRIVATE LIMITED | 9140000562 | 10 |  |  | 2026-01-31 | 24m Wide Road Sec-66, Gurugram | AU | 1 | 26582860 | 26582860 | 31367774.8 | 0 | 0 | 26582860 | 0 | 0 | ZSER | 2026-01-06 | 2026-04-06
RE/0066-PRJ-CO-OTH-AB | Additional Budget | 2010 | GR01 | 2010 | SMARTWORLD THE EDITION | CROSS ROAD BUILDCON PRIVATE LIMITED | 9140000562 | 20 |  |  | 2026-01-31 | Kushal Sadh Marg With Project Entry Road | AU | 1 | 35253710 | 35253710 | 41599377.8 | 0 | 0 | 35253710 | 0 | 0 | ZSER | 2026-01-06 | 2026-04-06
RE/0066-PRJ-CO-OTH-AB | Additional Budget | 2010 | GR01 | 2010 | SMARTWORLD THE EDITION | CROSS ROAD BUILDCON PRIVATE LIMITED | 9140000562 | 30 |  |  | 2026-01-31 | Forest Area & Bundh Road | AU | 1 | 5072145 | 5072145 | 5985131.1 | 0 | 0 | 5072145 | 0 | 0 | ZSER | 2026-01-06 | 2026-04-06
RE/0066-PRJ-CO-OTH-AB | Additional Budget | 2010 | GR01 | 2010 | SMARTWORLD THE EDITION | CROSS ROAD BUILDCON PRIVATE LIMITED | 9140000562 | 40 |  |  | 2026-01-31 | MEP Services ( Plumbing )-External Road | AU | 1 | 19900575 | 19900575 | 23482678.5 | 0 | 0 | 19900575 | 0 | 0 | ZSER | 2026-01-06 | 2026-04-06
RE/0066-PRJ-CO-OTH-AB | Additional Budget | 2010 | GR01 | 2010 | SMARTWORLD THE EDITION | Admark | 9140000649 | 10 |  |  | 2026-05-02 | Branding on Tower Crane | AU | 1 | 208000 | 208000 | 245440 | 208000 | 245440 | 0 | 208000 | 245440 | ZSER | 2026-05-02 | 2026-05-23
RE/0066-PRJ-CO-OTH-AB | Additional Budget | 2010 | GR01 | 2010 | SMARTWORLD THE EDITION | Admark | 9140000649 | 20 |  |  | 2026-05-02 | Branding on Tower Crane | AU | 1 | 104000 | 104000 | 122720 | 0 | 0 | 104000 | 0 | 0 | ZSER | 2026-05-02 | 2026-05-23
RE/0066-PRJ-CO-OTH-AB | Additional Budget | 2010 | GR01 | 2010 | SMARTWORLD THE EDITION | HG Graphics Private Limited | 9160000796 | 10 |  |  | 2024-04-24 | Sup. & Installation of Signage Work | AU | 1 | 288000 | 288000 | 339840 | 288000 | 339840 | 0 | 288000 | 339840 | ZGEN | 2024-04-06 | 2024-04-22
RE/0066-PRJ-CO-OTH-AB | Additional Budget | 2010 | GR01 | 2010 | SMARTWORLD THE EDITION | HG Graphics Private Limited | 9160000796 | 20 |  |  | 2024-04-24 | Modification Charges | AU | 1 | 35000 | 35000 | 41300 | 35000 | 41300 | 0 | 35000 | 41300 | ZGEN | 2024-04-06 | 2024-04-22
RE/0066-PRJ-CO-OTH-AB | Additional Budget | 2010 | GR01 | 2010 | SMARTWORLD THE EDITION | Unified Formwork System Privatelimited | 9160001937 | 10 |  |  | 2025-06-13 | Erection of Hydraulic Safety Screen | AU | 1 | 3676400 | 3676400 | 4338152 | 0 | 0 | 3676400 | 0 | 0 | ZGEN | 2025-05-14 | 2025-06-14
RE/0066-PRJ-CO-OTH-AB | Additional Budget | 2010 | GR01 | 2010 | SMARTWORLD THE EDITION | LA Vista | 9160001954 | 10 |  |  | 2025-06-18 | Landscape Consultant for Ext Rd Sec-66 | AU | 1 | 600000 | 600000 | 708000 | 366240 | 432163.2 | 233760 | 366240 | 432163.2 | ZGEN | 2025-06-03 | 2027-06-03
RE/0066-PRJ-CO-OTH-AB | Additional Budget | 2010 | GR01 | 2010 | SMARTWORLD THE EDITION | LA Vista | 9160001954 | 20 |  |  | 2025-06-18 | Amend- 1 Landscape Consultant | AU | 1 | 650000 | 650000 | 767000 | 227500 | 268450 | 422500 | 227500 | 268450 | ZGEN | 2025-06-03 | 2027-06-03
RE/0066-PRJ-CO-OTH-CN | Consultancy Charges | 2010 |  | 2010 | SMARTWORLD THE EDITION | Visilean India Private Limited | 9140000587 | 10 |  |  | 2026-02-26 | Digital Construction Management Softwar | AU | 1 | 1300000 | 1300000 | 1534000 | 300000 | 354000 | 1000000 | 200000 | 236000 | ZSER | 2026-03-01 | 2027-03-01
RE/0066-PRJ-CO-OTH-PM | Plant & Machinery Cost | 2010 | GR01 | 2010 | SMARTWORLD THE EDITION | TIRTH HYGIENE TECHNOLOGY PRIVATE LI | 9140000366 | 10 |  |  | 2024-10-03 | Rental of Sweeping & Cleaning Machine fo | AU | 1 | 583940 | 583940 | 689049.2 | 583831.69 | 688921.4 | 108.31 | 583940 | 689049.2 | ZSER | 2024-10-04 | 2025-04-03
RE/0066-PRJ-CO-OTH-SI | Site Infrastructure Development | 2010 |  | 2010 | SMARTWORLD THE EDITION | Suposhaa Realcon Private Limited. | 9110000304 | 20 |  |  | 2023-11-23 | weigh Bridge | SET | 1 | 500000 | 500000 | 590000 | 500000 | 590000 | 0 | 500000 | 590000 | ZMAT | 2025-01-20 | 2025-03-20
RE/0066-PRJ-CO-OTH-SI | Site Infrastructure Development | 2010 |  | 2010 | SMARTWORLD THE EDITION | N S Concrete Pvt Ltd | 9110000320 | 10 |  |  | 2023-12-13 | Ready Mix Concrete M - 7.5 | M3 | 3 | 3572.5 | 10717.5 | 12646.65 | 10717.5 | 12646.65 | 0 | 10717.5 | 12646.7 | ZMAT | 2025-01-20 | 2025-03-20
RE/0066-PRJ-CO-OTH-SI | Site Infrastructure Development | 2010 |  | 2010 | SMARTWORLD THE EDITION | N S Concrete Pvt Ltd | 9110000320 | 20 |  |  | 2023-12-13 | Ready Mix Concrete M - 15 | M3 | 282.56 | 3743 | 1057622.08 | 1247994.05 | 1057622.15 | 1247994.14 | 0.07 | 1057621.59 | 1247993.84 | ZMAT | 2025-01-20 | 2025-03-20
RE/0066-PRJ-CO-OTH-SI | Site Infrastructure Development | 2010 |  | 2010 | SMARTWORLD THE EDITION | N S Concrete Pvt Ltd | 9110000320 | 30 |  |  | 2023-12-13 | Ready Mix Concrete M - 25 | M3 | 43.9 | 4205 | 184599.5 | 217827.41 | 184599.53 | 217827.45 | 0.03 | 184599.5 | 217827.49 | ZMAT | 2025-01-20 | 2025-03-20
RE/0066-PRJ-CO-OTH-SI | Site Infrastructure Development | 2010 |  | 2010 | SMARTWORLD THE EDITION | N S Concrete Pvt Ltd | 9110000320 | 40 |  |  | 2023-12-13 | Ready Mix Concrete M - 35 | M3 | 3399.71 | 4617.5 | 15698160.93 | 18523829.9 | 15698160.97 | 18523829.94 | 0.04 | 15698160.7 | 18523831.24 | ZMAT | 2025-01-20 | 2025-03-20
RE/0066-PRJ-CO-OTH-SI | Site Infrastructure Development | 2010 |  | 2010 | SMARTWORLD THE EDITION | N S Concrete Pvt Ltd | 9110000320 | 50 |  |  | 2023-12-13 | Ready Mix Concrete M - 7.5 | M3 | 40 | 3572.5 | 142900 | 168622 | 0 | 0 | 142900 | 0 | 0 | ZMAT | 2025-01-20 | 2025-03-20
RE/0066-PRJ-CO-OTH-SI | Site Infrastructure Development | 2010 |  | 2010 | SMARTWORLD THE EDITION | N S Concrete Pvt Ltd | 9110000320 | 70 |  |  | 2023-12-13 | Ready Mix Concrete M - 25 | M3 | 51.1 | 4205 | 214875.5 | 253553.09 | 21025 | 24809.5 | 193850.5 | 21025 | 24809.6 | ZMAT | 2025-01-20 | 2025-03-20
RE/0066-PRJ-CO-OTH-SI | Site Infrastructure Development | 2010 |  | 2010 | SMARTWORLD THE EDITION | Ceasefire Industries Private LimiteRahul Kumar | 9110000334 | 10 |  |  | 2023-12-26 | FIRE EXTINGUISHER ABC TYPE 4 KG | NO | 5 | 6187.5 | 30937.5 | 36506.25 | 30937.71 | 36506.5 | 0.21 | 30937.75 | 36506.51 | ZMAT | 2025-01-20 | 2025-03-20
RE/0066-PRJ-CO-OTH-SI | Site Infrastructure Development | 2010 |  | 2010 | SMARTWORLD THE EDITION | Ceasefire Industries Private LimiteRahul Kumar | 9110000334 | 20 |  |  | 2023-12-26 | FIRE EXTINGUISHER ABC TYPE 2 KG | NO | 2 | 4500 | 9000 | 10620 | 9000 | 10620 | 0 | 9000 | 10619.99 | ZMAT | 2025-01-20 | 2025-03-20
RE/0066-PRJ-CO-OTH-SI | Site Infrastructure Development | 2010 |  | 2010 | SMARTWORLD THE EDITION | Ceasefire Industries Private LimiteRahul Kumar | 9110000334 | 30 |  |  | 2023-12-26 | Freight | NO | 1 | 525 | 525 | 619.5 | 525.42 | 620 | 0.42 | 525 | 619.5 | ZMAT | 2025-01-20 | 2025-03-20
RE/0066-PRJ-CO-OTH-SI | Site Infrastructure Development | 2010 |  | 2010 | SMARTWORLD THE EDITION | RKSK SteelRamji gupta | 9110000344 | 10 |  |  | 2024-01-04 | Fe 550D TMT Steel 8 MM | TO | 6.75 | 52400 | 353700 | 417366 | 353700 | 417366 | 0 | 361560 | 426640.83 | ZMAT | 2024-01-08 | 2024-02-08
RE/0066-PRJ-CO-OTH-SI | Site Infrastructure Development | 2010 |  | 2010 | SMARTWORLD THE EDITION | RKSK SteelRamji gupta | 9110000344 | 20 |  |  | 2024-01-04 | Fe 550D TMT Steel 12 MM | TO | 8 | 49400 | 395200 | 466336 | 395200 | 466336 | 0 | 395200 | 466336.04 | ZMAT | 2024-01-08 | 2024-02-08
RE/0066-PRJ-CO-OTH-SI | Site Infrastructure Development | 2010 |  | 2010 | SMARTWORLD THE EDITION | RKSK SteelRamji gupta | 9110000344 | 30 |  |  | 2024-01-04 | Fe 550D TMT Steel 16 MM | TO | 26.68 | 50400 | 1344672 | 1586712.96 | 1344672 | 1586712.96 | 0 | 1344672 | 1586713.13 | ZMAT | 2024-01-08 | 2024-02-08
RE/0066-PRJ-CO-OTH-SI | Site Infrastructure Development | 2010 |  | 2010 | SMARTWORLD THE EDITION | Suposhaa Realcon Private Limited. | 9110000345 | 20 |  |  | 2024-01-06 | Porta Cabin | NO | 1 | 700000 | 700000 | 826000 | 700000 | 826000 | 0 | 700000 | 826000.14 | ZMAT | 2025-01-20 | 2025-03-20
RE/0066-PRJ-CO-OTH-SI | Site Infrastructure Development | 2010 |  | 2010 | SMARTWORLD THE EDITION | Petropol India LimitedSANJAY GUPTA | 9110000356 | 10 |  |  | 2024-01-15 | Fe 550D TMT Steel 12 MM | TO | 10 | 49000 | 490000 | 578200 | 489020 | 577043.6 | 980 | 489020 | 577043.6 | ZMAT | 2025-01-20 | 2025-03-20
RE/0066-PRJ-CO-OTH-SI | Site Infrastructure Development | 2010 |  | 2010 | SMARTWORLD THE EDITION | Petropol India LimitedSANJAY GUPTA | 9110000356 | 20 |  |  | 2024-01-15 | Fe 550D TMT Steel 16 MM | TO | 15 | 50000 | 750000 | 885000 | 747500 | 882050 | 2500 | 747500 | 882050 | ZMAT | 2025-01-20 | 2025-03-20
RE/0066-PRJ-CO-OTH-SI | Site Infrastructure Development | 2010 |  | 2010 | SMARTWORLD THE EDITION | Petropol India LimitedSANJAY GUPTA | 9110000356 | 30 |  |  | 2024-01-15 | Fe 550D TMT Steel 20 MM | TO | 10 | 50000 | 500000 | 590000 | 500000 | 590000 | 0 | 500000 | 590000 | ZMAT | 2025-01-20 | 2025-03-20
RE/0066-PRJ-CO-OTH-SI | Site Infrastructure Development | 2010 |  | 2010 | SMARTWORLD THE EDITION | Petropol India LimitedSANJAY GUPTA | 9110000383 | 10 |  |  | 2024-02-14 | Steel Re-bar TMT 08 mm Dia. FE-550D | TO | 1.2 | 51400 | 61680 | 72782.4 | 60138 | 70962.84 | 1542 | 60138 | 70962.79 | ZMAT | 2025-01-20 | 2025-03-20
RE/0066-PRJ-CO-OTH-SI | Site Infrastructure Development | 2010 |  | 2010 | SMARTWORLD THE EDITION | Petropol India LimitedSANJAY GUPTA | 9110000383 | 20 |  |  | 2024-02-14 | Steel Re-bar TMT 10 mm Dia. FE-550D | TO | 10 | 50400 | 504000 | 594720 | 492408 | 581041.44 | 11592 | 492408 | 581041.32 | ZMAT | 2025-01-20 | 2025-03-20
RE/0066-PRJ-CO-OTH-SI | Site Infrastructure Development | 2010 |  | 2010 | SMARTWORLD THE EDITION | Petropol India LimitedSANJAY GUPTA | 9110000383 | 30 |  |  | 2024-02-14 | Steel Re-bar TMT 12 mm Dia. FE-550D | TO | 15 | 48400 | 726000 | 856680 | 725516 | 856108.88 | 484 | 725516 | 856108.77 | ZMAT | 2025-01-20 | 2025-03-20
RE/0066-PRJ-CO-OTH-SI | Site Infrastructure Development | 2010 |  | 2010 | SMARTWORLD THE EDITION | Petropol India LimitedSANJAY GUPTA | 9110000383 | 40 |  |  | 2024-02-14 | Steel Re-bar TMT 16 mm Dia. FE-550D | TO | 31 | 49400 | 1531400 | 1807052 | 1530906 | 1806469.08 | 494 | 1530906 | 1806468.94 | ZMAT | 2025-01-20 | 2025-03-20
RE/0066-PRJ-CO-OTH-SI | Site Infrastructure Development | 2010 |  | 2010 | SMARTWORLD THE EDITION | Petropol India LimitedSANJAY GUPTA | 9110000383 | 50 |  |  | 2024-02-14 | Steel Re-bar TMT 20 mm Dia. FE-550D | TO | 18 | 49400 | 889200 | 1049256 | 887224 | 1046924.32 | 1976 | 887224 | 1046924.18 | ZMAT | 2025-01-20 | 2025-03-20
RE/0066-PRJ-CO-OTH-SI | Site Infrastructure Development | 2010 |  | 2010 | SMARTWORLD THE EDITION | SBJ Concrete Buildcon Private Limit | 9110000397 | 10 |  |  | 2024-02-08 | Ready Mix Concrete M - 15 | M3 | 99.98 | 3743 | 374225.14 | 441585.67 | 374225.14 | 441585.67 | 0 | 374225.14 | 441585.73 | ZMAT | 2025-01-20 | 2025-03-20
RE/0066-PRJ-CO-OTH-SI | Site Infrastructure Development | 2010 |  | 2010 | SMARTWORLD THE EDITION | SBJ Concrete Buildcon Private Limit | 9110000397 | 20 |  |  | 2024-02-08 | Ready Mix Concrete M - 35 | M3 | 2996.42 | 4617.5 | 13835969.35 | 16326443.83 | 13835969.35 | 16326443.83 | 0 | 13835969.35 | 16326443.66 | ZMAT | 2025-01-20 | 2025-03-20
RE/0066-PRJ-CO-OTH-SI | Site Infrastructure Development | 2010 |  | 2010 | SMARTWORLD THE EDITION | Industrial Safety Hub | 9110000402 | 20 |  |  | 2024-02-28 | Caution Tape 4" | M | 5000 | 0.85 | 4250 | 5015 | 4250 | 5015 | 0 | 4250 | 5015 | ZMAT | 2025-01-20 | 2025-03-20
RE/0066-PRJ-CO-OTH-SI | Site Infrastructure Development | 2010 |  | 2010 | SMARTWORLD THE EDITION | Akshay Udyog | 9110000406 | 10 |  |  | 2024-02-29 | Cement PPC grade | BAG | 60 | 269.53 | 16171.8 | 20699.9 | 16171.88 | 20700 | 0.08 | 16171.8 | 20700 | ZMAT | 2025-01-20 | 2025-03-20
RE/0066-PRJ-CO-OTH-SI | Site Infrastructure Development | 2010 |  | 2010 | SMARTWORLD THE EDITION | SBJ Concrete Buildcon Private Limit | 9110000413 | 50 |  |  | 2024-03-13 | Ready Mix Concrete M - 7.5 | M3 | 23.5 | 3572.5 | 83953.75 | 99065.43 | 56945.6 | 67195.81 | 27008.15 | 56945.65 | 67195.53 | ZMAT | 2025-01-20 | 2025-03-20
RE/0066-PRJ-CO-OTH-SI | Site Infrastructure Development | 2010 |  | 2010 | SMARTWORLD THE EDITION | SBJ Concrete Buildcon Private Limit | 9110000413 | 60 |  |  | 2024-03-13 | Ready Mix Concrete M - 25 | M3 | 84.1 | 4205 | 353640.5 | 417295.79 | 175180.36 | 206712.82 | 178460.14 | 175180.3 | 206713.28 | ZMAT | 2025-01-20 | 2025-03-20
RE/0066-PRJ-CO-OTH-SI | Site Infrastructure Development | 2010 |  | 2010 | SMARTWORLD THE EDITION | Industrial Safety Hub | 9110000491 | 10 |  |  | 2024-04-12 | Green Net | ROL | 10 | 1450 | 14500 | 15225 | 14500 | 15225 | 0 | 14500 | 15225 | ZMAT | 2025-01-20 | 2025-03-20
RE/0066-PRJ-CO-OTH-SI | Site Infrastructure Development | 2010 |  | 2010 | SMARTWORLD THE EDITION | N S Concrete Pvt Ltd | 9110000520 | 10 |  |  | 2024-05-13 | Pumping charges | M3 | 30 | 200 | 6000 | 7080 | 0 | 0 | 6000 | 0 | 0 | ZMAT | 2025-01-20 | 2025-03-20
RE/0066-PRJ-CO-OTH-SI | Site Infrastructure Development | 2010 |  | 2010 | SMARTWORLD THE EDITION | SBJ Concrete Buildcon Private Limit | 9110000521 | 10 |  |  | 2024-05-13 | Pumping Charges | M3 | 30 | 200 | 6000 | 7080 | 4746 | 5600.28 | 1254 | 4746 | 5600 | ZMAT | 2025-01-20 | 2025-03-20
RE/0066-PRJ-CO-OTH-SI | Site Infrastructure Development | 2010 |  | 2010 | SMARTWORLD THE EDITION | Industrial Safety Hub | 9110000569 | 10 |  |  | 2024-05-16 | Caution Tape | M | 5000 | 0.85 | 4250 | 5015 | 4250 | 5015 | 0 | 4250 | 5015 | ZMAT | 2025-01-20 | 2025-03-20
RE/0066-PRJ-CO-OTH-SI | Site Infrastructure Development | 2010 |  | 2010 | SMARTWORLD THE EDITION | Industrial Safety Hub | 9110000671 | 10 |  |  | 2024-08-20 | Safety Helmet-Hard Hat (white color) | NO | 16 | 115 | 1840 | 2171.2 | 1840 | 2171.2 | 0 | 1840.3 | 2171.48 | ZMAT | 2024-09-02 | 2024-09-17
RE/0066-PRJ-CO-OTH-SI | Site Infrastructure Development | 2010 |  | 2010 | SMARTWORLD THE EDITION | Industrial Safety Hub | 9110000671 | 20 |  |  | 2024-08-20 | Reflective Safety Jacket (fluorescent gr | NO | 18 | 180 | 3240 | 3402 | 3240 | 3402 | 0 | 3240 | 3402 | ZMAT | 2024-09-02 | 2024-09-17
RE/0066-PRJ-CO-OTH-SI | Site Infrastructure Development | 2010 |  | 2010 | SMARTWORLD THE EDITION | Industrial Safety Hub | 9110000671 | 30 |  |  | 2024-08-20 | Safety Shoes for staff(Black/Brown) size | PAA | 22 | 795 | 17490 | 19588.8 | 17490 | 19588.8 | 0 | 17490 | 19588.8 | ZMAT | 2024-09-02 | 2024-09-17
RE/0066-PRJ-CO-OTH-SI | Site Infrastructure Development | 2010 |  | 2010 | SMARTWORLD THE EDITION | Industrial Safety Hub | 9110000671 | 40 |  |  | 2024-08-20 | Goggles | NO | 15 | 55 | 825 | 973.5 | 825.08 | 973.6 | 0.08 | 825 | 973.59 | ZMAT | 2024-09-02 | 2024-09-17
RE/0066-PRJ-CO-OTH-SI | Site Infrastructure Development | 2010 |  | 2010 | SMARTWORLD THE EDITION | Industrial Safety Hub | 9110000671 | 50 |  |  | 2024-08-20 | Gumboots- size 7-4 no's,size 8- 6 no's, | PAA | 16 | 340 | 5440 | 6419.2 | 5440 | 6419.2 | 0 | 5440 | 6419.13 | ZMAT | 2024-09-02 | 2024-09-17
RE/0066-PRJ-CO-OTH-SI | Site Infrastructure Development | 2010 |  | 2010 | SMARTWORLD THE EDITION | Industrial Safety Hub | 9110000824 | 10 |  |  | 2024-12-24 | Reflective Safety Jacket | NO | 65 | 80 | 5200 | 6136 | 5200 | 6136 | 0 | 5200 | 6136 | ZMAT | 2024-12-24 | 2025-01-13
RE/0066-PRJ-CO-OTH-SI | Site Infrastructure Development | 2010 |  | 2010 | SMARTWORLD THE EDITION | Industrial Safety Hub | 9110000824 | 20 |  |  | 2024-12-24 | Safety Helmet | NO | 75 | 115 | 8625 | 10177.5 | 8625 | 10177.5 | 0 | 8625 | 10177.5 | ZMAT | 2024-12-24 | 2025-01-13
RE/0066-PRJ-CO-OTH-SI | Site Infrastructure Development | 2010 |  | 2010 | SMARTWORLD THE EDITION | Industrial Safety Hub | 9110000824 | 30 |  |  | 2024-12-24 | Safety Shoes | PAA | 50 | 860 | 43000 | 48160 | 43000 | 48160 | 0 | 43000 | 48160 | ZMAT | 2024-12-24 | 2025-01-13
RE/0066-PRJ-CO-OTH-SI | Site Infrastructure Development | 2010 |  | 2010 | SMARTWORLD THE EDITION | Industrial Safety Hub | 9110000824 | 40 |  |  | 2024-12-24 | Mask | NO | 100 | 5 | 500 | 525 | 500 | 525 | 0 | 500 | 525 | ZMAT | 2024-12-24 | 2025-01-13
RE/0066-PRJ-CO-OTH-SI | Site Infrastructure Development | 2010 |  | 2010 | SMARTWORLD THE EDITION | Industrial Safety Hub | 9110000824 | 50 |  |  | 2024-12-24 | Safety Shoes | PAA | 16 | 900 | 14400 | 16128 | 14400 | 16128 | 0 | 14400 | 16128 | ZMAT | 2024-12-24 | 2025-01-13
RE/0066-PRJ-CO-OTH-SI | Site Infrastructure Development | 2010 |  | 2010 | SMARTWORLD THE EDITION | Industrial Safety Hub | 9110000881 | 10 |  |  | 2025-03-09 | Reflective Safety Jacket | NO | 35 | 80 | 2800 | 3304 | 2800 | 3304 | 0 | 2800 | 3304 | ZMAT
RE/0066-PRJ-CO-OTH-SI | Site Infrastructure Development | 2010 |  | 2010 | SMARTWORLD THE EDITION | Industrial Safety Hub | 9110000881 | 20 |  |  | 2025-03-09 | Safety Helmet | NO | 10 | 115 | 1150 | 1357 | 1150 | 1357 | 0 | 1150 | 1357 | ZMAT
RE/0066-PRJ-CO-OTH-SI | Site Infrastructure Development | 2010 |  | 2010 | SMARTWORLD THE EDITION | Industrial Safety Hub | 9110000881 | 30 |  |  | 2025-03-09 | Safety Shoes | PAA | 30 | 1475 | 44250 | 52215 | 44250 | 52215 | 0 | 44250 | 52215 | ZMAT
RE/0066-PRJ-CO-OTH-SI | Site Infrastructure Development | 2010 |  | 2010 | SMARTWORLD THE EDITION | Industrial Safety Hub | 9110000881 | 40 |  |  | 2025-03-09 | Mask | NO | 50 | 5 | 250 | 262.5 | 250 | 262.5 | 0 | 250 | 262.5 | ZMAT
RE/0066-PRJ-CO-OTH-SI | Site Infrastructure Development | 2010 |  | 2010 | SMARTWORLD THE EDITION | Industrial Safety Hub | 9110001024 | 10 |  |  | 2025-05-05 | Breath analyser | NO | 1 | 1400 | 1400 | 1652 | 0 | 0 | 1400 | 0 | 0 | ZMAT
RE/0066-PRJ-CO-OTH-SI | Site Infrastructure Development | 2010 |  | 2010 | SMARTWORLD THE EDITION | Industrial Safety Hub | 9110001024 | 20 |  |  | 2025-05-05 | Lux Meter | NO | 1 | 2100 | 2100 | 2478 | 0 | 0 | 2100 | 0 | 0 | ZMAT
RE/0066-PRJ-CO-OTH-SI | Site Infrastructure Development | 2010 |  | 2010 | SMARTWORLD THE EDITION | Industrial Safety Hub | 9110001024 | 30 |  |  | 2025-05-05 | Personal Gas Detector | NO | 1 | 49500 | 49500 | 58410 | 0 | 0 | 49500 | 0 | 0 | ZMAT
RE/0066-PRJ-CO-OTH-SI | Site Infrastructure Development | 2010 |  | 2010 | SMARTWORLD THE EDITION | Industrial Safety Hub | 9110001024 | 40 |  |  | 2025-05-05 | Digital Noise level meter/ Sound Level M | NO | 1 | 2100 | 2100 | 2478 | 0 | 0 | 2100 | 0 | 0 | ZMAT
RE/0066-PRJ-CO-OTH-SI | Site Infrastructure Development | 2010 |  | 2010 | SMARTWORLD THE EDITION | Industrial Safety Hub | 9110001024 | 60 |  |  | 2025-05-05 | 30 Meter | NO | 4 | 500 | 2000 | 2360 | 0 | 0 | 2000 | 0 | 0 | ZMAT
RE/0066-PRJ-CO-OTH-SI | Site Infrastructure Development | 2010 |  | 2010 | SMARTWORLD THE EDITION | Industrial Safety Hub | 9110001024 | 70 |  |  | 2025-05-05 | Standard Tool Kit | NO | 1 | 4500 | 4500 | 5310 | 0 | 0 | 4500 | 0 | 0 | ZMAT
RE/0066-PRJ-CO-OTH-SI | Site Infrastructure Development | 2010 |  | 2010 | SMARTWORLD THE EDITION | Industrial Safety Hub | 9110001024 | 80 |  |  | 2025-05-05 | "A" Type Ladder | NO | 2 | 6500 | 13000 | 15340 | 0 | 0 | 13000 | 0 | 0 | ZMAT
RE/0066-PRJ-CO-OTH-SI | Site Infrastructure Development | 2010 |  | 2010 | SMARTWORLD THE EDITION | Industrial Safety Hub | 9110001024 | 90 |  |  | 2025-05-05 | Plumb | NO | 5 | 140 | 700 | 826 | 0 | 0 | 700 | 0 | 0 | ZMAT
RE/0066-PRJ-CO-OTH-SI | Site Infrastructure Development | 2010 |  | 2010 | SMARTWORLD THE EDITION | Industrial Safety Hub | 9110001024 | 100 |  |  | 2025-05-05 | Right Angle | NO | 5 | 170 | 850 | 1003 | 0 | 0 | 850 | 0 | 0 | ZMAT
RE/0066-PRJ-CO-OTH-SI | Site Infrastructure Development | 2010 |  | 2010 | SMARTWORLD THE EDITION | Industrial Safety Hub | 9110001024 | 110 |  |  | 2025-05-05 | Digital Multimeter | NO | 2 | 1250 | 2500 | 2950 | 0 | 0 | 2500 | 0 | 0 | ZMAT
RE/0066-PRJ-CO-OTH-SI | Site Infrastructure Development | 2010 |  | 2010 | SMARTWORLD THE EDITION | Industrial Safety Hub | 9110001024 | 120 |  |  | 2025-05-05 | Anenometer | NO | 1 | 2100 | 2100 | 2478 | 0 | 0 | 2100 | 0 | 0 | ZMAT
RE/0066-PRJ-CO-OTH-SI | Site Infrastructure Development | 2010 |  | 2010 | SMARTWORLD THE EDITION | Industrial Safety Hub | 9110001024 | 130 |  |  | 2025-05-05 | Levelling Tool | NO | 2 | 10500 | 21000 | 24780 | 0 | 0 | 21000 | 0 | 0 | ZMAT
RE/0066-PRJ-CO-OTH-SI | Site Infrastructure Development | 2010 |  | 2010 | SMARTWORLD THE EDITION | Industrial Safety Hub | 9110001024 | 150 |  |  | 2025-05-05 | Digital Vernier Calliper | NO | 2 | 3500 | 7000 | 8260 | 0 | 0 | 7000 | 0 | 0 | ZMAT
RE/0066-PRJ-CO-OTH-SI | Site Infrastructure Development | 2010 |  | 2010 | SMARTWORLD THE EDITION | INDUSTRIAL SAFETY HUB | 9110001301 | 10 |  |  | 2025-10-08 | Safety Helmet White | NO | 25 | 92 | 2300 | 2714 | 2300 | 2714 | 0 | 2300 | 2714 | ZMAT
RE/0066-PRJ-CO-OTH-SI | Site Infrastructure Development | 2010 |  | 2010 | SMARTWORLD THE EDITION | INDUSTRIAL SAFETY HUB | 9110001301 | 20 |  |  | 2025-10-08 | Safety Helmet Green | NO | 5 | 92 | 460 | 542.8 | 460 | 542.8 | 0 | 460 | 542.8 | ZMAT
RE/0066-PRJ-CO-OTH-SI | Site Infrastructure Development | 2010 |  | 2010 | SMARTWORLD THE EDITION | INDUSTRIAL SAFETY HUB | 9110001301 | 30 |  |  | 2025-10-08 | Reflective Safety Jacket | NO | 30 | 280 | 8400 | 8820 | 8400 | 8820 | 0 | 8400 | 8820 | ZMAT
RE/0066-PRJ-CO-OTH-SI | Site Infrastructure Development | 2010 |  | 2010 | SMARTWORLD THE EDITION | INDUSTRIAL SAFETY HUB | 9110001301 | 40 |  |  | 2025-10-08 | Safety Spectacles | NO | 30 | 60 | 1800 | 2124 | 1800 | 2124 | 0 | 1800 | 2124 | ZMAT
RE/0066-PRJ-CO-OTH-SI | Site Infrastructure Development | 2010 |  | 2010 | SMARTWORLD THE EDITION | INDUSTRIAL SAFETY HUB | 9110001465 | 10 |  |  | 2026-01-08 | Safety Shoes | PAA | 28 | 1250 | 35000 | 36750 | 35000 | 36750 | 0 | 35000 | 36750 | ZMAT | 2026-01-05 | 2026-02-05
RE/0066-PRJ-CO-OTH-SI | Site Infrastructure Development | 2010 |  | 2010 | SMARTWORLD THE EDITION | INDUSTRIAL SAFETY HUB | 9110001521 | 10 |  |  | 2026-02-02 | Breath analyser | NO | 1 | 1400 | 1400 | 1652 | 1400 | 1652 | 0 | 1400 | 1652 | ZMAT | 2026-02-03 | 2026-03-03
RE/0066-PRJ-CO-OTH-SI | Site Infrastructure Development | 2010 |  | 2010 | SMARTWORLD THE EDITION | INDUSTRIAL SAFETY HUB | 9110001521 | 20 |  |  | 2026-02-02 | Lux Meter | NO | 1 | 2100 | 2100 | 2478 | 2100 | 2478 | 0 | 2100 | 2478 | ZMAT | 2026-02-03 | 2026-03-03
RE/0066-PRJ-CO-OTH-SI | Site Infrastructure Development | 2010 |  | 2010 | SMARTWORLD THE EDITION | INDUSTRIAL SAFETY HUB | 9110001521 | 30 |  |  | 2026-02-02 | Personal Gas Detector | NO | 1 | 49500 | 49500 | 58410 | 49500 | 58410 | 0 | 49500 | 58410 | ZMAT | 2026-02-03 | 2026-03-03
RE/0066-PRJ-CO-OTH-SI | Site Infrastructure Development | 2010 |  | 2010 | SMARTWORLD THE EDITION | INDUSTRIAL SAFETY HUB | 9110001521 | 40 |  |  | 2026-02-02 | Digital Noise level meter/ Sound Level M | NO | 1 | 2100 | 2100 | 2478 | 2100 | 2478 | 0 | 2100 | 2478 | ZMAT | 2026-02-03 | 2026-03-03
RE/0066-PRJ-CO-OTH-SI | Site Infrastructure Development | 2010 |  | 2010 | SMARTWORLD THE EDITION | INDUSTRIAL SAFETY HUB | 9110001521 | 60 |  |  | 2026-02-02 | 30 Meter | NO | 4 | 500 | 2000 | 2360 | 2000 | 2360 | 0 | 2000 | 2360 | ZMAT | 2026-02-03 | 2026-03-03
RE/0066-PRJ-CO-OTH-SI | Site Infrastructure Development | 2010 |  | 2010 | SMARTWORLD THE EDITION | INDUSTRIAL SAFETY HUB | 9110001521 | 70 |  |  | 2026-02-02 | Standard Tool Kit | NO | 1 | 4500 | 4500 | 5310 | 4500 | 5310 | 0 | 4500 | 5310 | ZMAT | 2026-02-03 | 2026-03-03
RE/0066-PRJ-CO-OTH-SI | Site Infrastructure Development | 2010 |  | 2010 | SMARTWORLD THE EDITION | INDUSTRIAL SAFETY HUB | 9110001521 | 80 |  |  | 2026-02-02 | "A" Type Ladder | NO | 2 | 6500 | 13000 | 15340 | 13000 | 15340 | 0 | 13000 | 15340 | ZMAT | 2026-02-03 | 2026-03-03
RE/0066-PRJ-CO-OTH-SI | Site Infrastructure Development | 2010 |  | 2010 | SMARTWORLD THE EDITION | INDUSTRIAL SAFETY HUB | 9110001521 | 90 |  |  | 2026-02-02 | Plumb | NO | 5 | 140 | 700 | 826 | 700 | 826 | 0 | 700 | 826 | ZMAT | 2026-02-03 | 2026-03-03
RE/0066-PRJ-CO-OTH-SI | Site Infrastructure Development | 2010 |  | 2010 | SMARTWORLD THE EDITION | INDUSTRIAL SAFETY HUB | 9110001521 | 100 |  |  | 2026-02-02 | Right Angle | NO | 5 | 170 | 850 | 1003 | 850 | 1003 | 0 | 850 | 1003 | ZMAT | 2026-02-03 | 2026-03-03
RE/0066-PRJ-CO-OTH-SI | Site Infrastructure Development | 2010 |  | 2010 | SMARTWORLD THE EDITION | INDUSTRIAL SAFETY HUB | 9110001521 | 110 |  |  | 2026-02-02 | Digital Multimeter | NO | 2 | 1250 | 2500 | 2950 | 2500 | 2950 | 0 | 2500 | 2950 | ZMAT | 2026-02-03 | 2026-03-03
RE/0066-PRJ-CO-OTH-SI | Site Infrastructure Development | 2010 |  | 2010 | SMARTWORLD THE EDITION | INDUSTRIAL SAFETY HUB | 9110001521 | 120 |  |  | 2026-02-02 | Anenometer | NO | 1 | 2100 | 2100 | 2478 | 2100 | 2478 | 0 | 2100 | 2478 | ZMAT | 2026-02-03 | 2026-03-03
RE/0066-PRJ-CO-OTH-SI | Site Infrastructure Development | 2010 |  | 2010 | SMARTWORLD THE EDITION | INDUSTRIAL SAFETY HUB | 9110001521 | 130 |  |  | 2026-02-02 | Levelling Tool | NO | 2 | 10500 | 21000 | 24780 | 21000 | 24780 | 0 | 21000 | 24780 | ZMAT | 2026-02-03 | 2026-03-03
RE/0066-PRJ-CO-OTH-SI | Site Infrastructure Development | 2010 |  | 2010 | SMARTWORLD THE EDITION | INDUSTRIAL SAFETY HUB | 9110001521 | 140 |  |  | 2026-02-02 | Digital Vernier Calliper | NO | 2 | 3500 | 7000 | 8260 | 7000 | 8260 | 0 | 7000 | 8260 | ZMAT | 2026-02-03 | 2026-03-03
RE/0066-PRJ-CO-OTH-SI | Site Infrastructure Development | 2010 |  | 2010 | SMARTWORLD THE EDITION | INDUSTRIAL SAFETY HUB | 9110001573 | 10 |  |  | 2026-02-17 | Reflective Safety Jacket | NO | 30 | 280 | 8400 | 8820 | 8400 | 8820 | 0 | 8400 | 8820 | ZMAT | 2026-02-19 | 2026-03-19
RE/0066-PRJ-CO-OTH-SI | Site Infrastructure Development | 2010 |  | 2010 | SMARTWORLD THE EDITION | INDUSTRIAL SAFETY HUB | 9110001573 | 20 |  |  | 2026-02-17 | Safety Helmet | NO | 15 | 92 | 1380 | 1628.4 | 1380 | 1628.4 | 0 | 1380 | 1628.4 | ZMAT | 2026-02-19 | 2026-03-19
RE/0066-PRJ-CO-OTH-SI | Site Infrastructure Development | 2010 |  | 2010 | SMARTWORLD THE EDITION | INDUSTRIAL SAFETY HUB | 9110001573 | 30 |  |  | 2026-02-17 | Safety Shoes | PAA | 18 | 1250 | 22500 | 23625 | 22500 | 23625 | 0 | 22500 | 23625 | ZMAT | 2026-02-19 | 2026-03-19
RE/0066-PRJ-CO-OTH-SI | Site Infrastructure Development | 2010 |  | 2010 | SMARTWORLD THE EDITION | INDUSTRIAL SAFETY HUB | 9110001674 | 10 |  |  | 2026-04-08 | Safety Helmet White | NO | 50 | 92 | 4600 | 5428 | 4600 | 5428 | 0 | 4600 | 5428 | ZMAT
RE/0066-PRJ-CO-OTH-SI | Site Infrastructure Development | 2010 |  | 2010 | SMARTWORLD THE EDITION | INDUSTRIAL SAFETY HUB | 9110001674 | 20 |  |  | 2026-04-08 | Reflective Safety Jacket | NO | 50 | 280 | 14000 | 14700 | 14000 | 14700 | 0 | 14000 | 14700 | ZMAT
RE/0066-PRJ-CO-OTH-SI | Site Infrastructure Development | 2010 |  | 2010 | SMARTWORLD THE EDITION | INDUSTRIAL SAFETY HUB | 9110001826 | 10 |  |  | 2026-05-29 | Safety Helmet White | NO | 100 | 145 | 14500 | 17110 | 14500 | 17110 | 0 | 14500 | 17110 | ZMAT
RE/0066-PRJ-CO-OTH-SI | Site Infrastructure Development | 2010 |  | 2010 | SMARTWORLD THE EDITION | INDUSTRIAL SAFETY HUB | 9110001826 | 20 |  |  | 2026-05-29 | Reflective Safety Jacket | NO | 100 | 150 | 15000 | 15750 | 15000 | 15750 | 0 | 15000 | 15750 | ZMAT
RE/0066-PRJ-CO-OTH-SI | Site Infrastructure Development | 2010 |  | 2010 | SMARTWORLD THE EDITION | Mahmud Ansari | 9140000168 | 20 |  |  | 2023-06-26 | Tree Cutting and Amendment 1 | AU | 1 | 19000 | 19000 | 22420 | 0 | 0 | 19000 | 0 | 0 | ZSER | 2023-06-26 | 2023-07-10
RE/0066-PRJ-CO-OTH-SI | Site Infrastructure Development | 2010 |  | 2010 | SMARTWORLD THE EDITION | Puja Construction | 9140000232 | 10 |  |  | 2023-11-22 | Site Establishment | AU | 1 | 223182 | 223182 | 263354.76 | 164769.99 | 194428.59 | 58412.01 | 164770.33 | 194428.99 | ZSER | 2023-11-21 | 2023-12-11
RE/0066-PRJ-CO-OTH-SI | Site Infrastructure Development | 2010 |  | 2010 | SMARTWORLD THE EDITION | Puja Construction | 9140000232 | 20 |  |  | 2023-11-22 | Amend-1 Approach Road Repair works | AU | 1 | 1263400 | 1263400 | 1490812 | 960055.07 | 1132864.98 | 303344.93 | 960055.15 | 1132865.08 | ZSER | 2023-11-21 | 2023-12-11
RE/0066-PRJ-CO-OTH-SI | Site Infrastructure Development | 2010 |  | 2010 | SMARTWORLD THE EDITION | Haarish Electric vehicles | 9140000237 | 10 |  |  | 2023-12-22 | MS SHEET BARRICADING WORKS | AU | 1 | 1336871.2 | 1336871.2 | 1577508.02 | 1157914.68 | 1366339.32 | 178956.52 | 1157907.57 | 1366330.93 | ZSER | 2023-12-21 | 2024-01-21
RE/0066-PRJ-CO-OTH-SI | Site Infrastructure Development | 2010 |  | 2010 | SMARTWORLD THE EDITION | Haarish Electric vehicles | 9140000237 | 20 |  |  | 2023-12-22 | MS Sheet Barricading Works | AU | 1 | 624318.6 | 624318.6 | 736695.95 | 603753.77 | 712429.45 | 20564.83 | 603753.77 | 712429.45 | ZSER | 2023-12-21 | 2024-01-21
RE/0066-PRJ-CO-OTH-SI | Site Infrastructure Development | 2010 |  | 2010 | SMARTWORLD THE EDITION | Cartel Infratech Pvt. Ltd. | 9140000242 | 10 |  |  | 2023-12-30 | Lighting works | AU | 1 | 216101.52 | 216101.52 | 254999.79 | 136990.68 | 161649 | 79110.84 | 136990.69 | 161649.02 | ZSER | 2023-12-27 | 2024-01-12
RE/0066-PRJ-CO-OTH-SI | Site Infrastructure Development | 2010 |  | 2010 | SMARTWORLD THE EDITION | Classic Landscapers | 9140000243 | 10 |  |  | 2024-01-06 | Softscape works at showflat | AU | 1 | 708871 | 708871 | 836467.78 | 479450 | 565751 | 229421 | 479450 | 565751 | ZSER | 2024-01-06 | 2025-01-06
RE/0066-PRJ-CO-OTH-SI | Site Infrastructure Development | 2010 |  | 2010 | SMARTWORLD THE EDITION | Chandila Crane Services | 9140000244 | 10 |  |  | 2024-01-08 | Rental of JCB & Hydra for Sector 66 Site | AU | 1 | 540000 | 540000 | 637200 | 144800 | 170864 | 395200 | 144800 | 170864 | ZSER | 2023-09-19 | 2023-12-31
RE/0066-PRJ-CO-OTH-SI | Site Infrastructure Development | 2010 |  | 2010 | SMARTWORLD THE EDITION | Wagad Buildcon | 9140000250 | 10 |  |  | 2023-08-16 | Diaphragm Wall Work at Sector-66 Project | AU | 1 | 46895492 | 46895492 | 55336680.56 | 46895489.36 | 55336677.45 | 2.64 | 46895489.03 | 55336677.05 | ZSER | 2023-07-04 | 2023-10-04
RE/0066-PRJ-CO-OTH-SI | Site Infrastructure Development | 2010 |  | 2010 | SMARTWORLD THE EDITION | Bharat Electricals | 9140000251 | 10 |  |  | 2024-02-02 | DG Set 62.5 KVA CPCB-IV standards | AU | 1 | 300000 | 300000 | 354000 | 293550 | 346389 | 6450 | 293550 | 346389 | ZSER | 2024-02-02 | 2025-02-02
RE/0066-PRJ-CO-OTH-SI | Site Infrastructure Development | 2010 |  | 2010 | SMARTWORLD THE EDITION | Bharat Electricals | 9140000251 | 20 |  |  | 2024-02-02 | DG Set 62.5 KVA CPCB-IV standards | AU | 1 | 300000 | 300000 | 354000 | 200000 | 236000 | 100000 | 200000 | 236000 | ZSER | 2024-02-02 | 2025-02-02
RE/0066-PRJ-CO-OTH-SI | Site Infrastructure Development | 2010 |  | 2010 | SMARTWORLD THE EDITION | Indivalue Advisors pvt ltd | 9140000260 | 10 |  |  | 2024-02-23 | Engineer's & Architect's Certificate | AU | 1 | 12000 | 12000 | 14160 | 6000 | 7080 | 6000 | 6000 | 7080 | ZSER | 2024-02-03 | 2024-03-03
RE/0066-PRJ-CO-OTH-SI | Site Infrastructure Development | 2010 |  | 2010 | SMARTWORLD THE EDITION | Tripleplay Interactive Network PvtMr. Dhananjay | 9140000261 | 10 |  |  | 2024-02-27 | SITC of CCTV System | AU | 1 | 1089274.1 | 1089274.1 | 1285343.44 | 970609.32 | 1145319 | 118664.78 | 970609.92 | 1145319.7 | ZSER | 2024-02-16 | 2024-03-11
RE/0066-PRJ-CO-OTH-SI | Site Infrastructure Development | 2010 |  | 2010 | SMARTWORLD THE EDITION | HKE Electric Contracts | 9140000262 | 10 |  |  | 2024-03-06 | SUB-HEAD - I SITC OF HT Panel & TRANSFO | AU | 1 | 1325000 | 1325000 | 1563500 | 1325000 | 1563500 | 0 | 1325000 | 1563500 | ZSER | 2024-02-27 | 2024-05-27
RE/0066-PRJ-CO-OTH-SI | Site Infrastructure Development | 2010 |  | 2010 | SMARTWORLD THE EDITION | HKE Electric Contracts | 9140000262 | 20 |  |  | 2024-03-06 | SUB-HEAD - II SITC OF HT CABLES, LT cab | AU | 1 | 858000 | 858000 | 1012440 | 565000 | 666700 | 293000 | 565000 | 666700 | ZSER | 2024-02-27 | 2024-05-27
RE/0066-PRJ-CO-OTH-SI | Site Infrastructure Development | 2010 |  | 2010 | SMARTWORLD THE EDITION | HKE Electric Contracts | 9140000262 | 30 |  |  | 2024-03-06 | SUB-HEAD - III SITC of LT PANELS & Dis | AU | 1 | 965000 | 965000 | 1138700 | 965000 | 1138700 | 0 | 965000 | 1138700 | ZSER | 2024-02-27 | 2024-05-27
RE/0066-PRJ-CO-OTH-SI | Site Infrastructure Development | 2010 |  | 2010 | SMARTWORLD THE EDITION | HKE Electric Contracts | 9140000262 | 40 |  |  | 2024-03-06 | SUB-HEAD - IV EARTHING INSTALLATION FOR | AU | 1 | 158700 | 158700 | 187266 | 154000 | 181720 | 4700 | 154000 | 181720 | ZSER | 2024-02-27 | 2024-05-27
RE/0066-PRJ-CO-OTH-SI | Site Infrastructure Development | 2010 |  | 2010 | SMARTWORLD THE EDITION | HKE Electric Contracts | 9140000262 | 50 |  |  | 2024-03-06 | SUB HEAD V: MISCELLANEOUS WORKS | AU | 1 | 274296 | 274296 | 323669.28 | 256171.19 | 302282 | 18124.81 | 256171.19 | 302282 | ZSER | 2024-02-27 | 2024-05-27
RE/0066-PRJ-CO-OTH-SI | Site Infrastructure Development | 2010 |  | 2010 | SMARTWORLD THE EDITION | HKE Electric Contracts | 9140000262 | 60 |  |  | 2024-03-06 | Amendment to SITC of Construction power | AU | 1 | 211500 | 211500 | 249570 | 169000 | 199420 | 42500 | 169000 | 199420 | ZSER | 2024-02-27 | 2024-05-27
RE/0066-PRJ-CO-OTH-SI | Site Infrastructure Development | 2010 |  | 2010 | SMARTWORLD THE EDITION | HKE Electric Contracts | 9140000262 | 70 |  |  | 2024-03-06 | Amendment-2 to SITC of Constn. Power | AU | 1 | 92150 | 92150 | 108737 | 92150 | 108737 | 0 | 92150 | 108737 | ZSER | 2024-02-27 | 2024-05-27
RE/0066-PRJ-CO-OTH-SI | Site Infrastructure Development | 2010 |  | 2010 | SMARTWORLD THE EDITION | Navidiz Software Solutions Private | 9140000267 | 10 |  |  | 2024-03-18 | Digital Mobile Application | AU | 1 | 1640000 | 1640000 | 1935200 | 930685 | 1098208.3 | 709315 | 1040000 | 1227200 | ZSER | 2024-03-12 | 2028-08-12
RE/0066-PRJ-CO-OTH-SI | Site Infrastructure Development | 2010 |  | 2010 | SMARTWORLD THE EDITION | Vats Buildcon Private Limited | 9140000270 | 10 |  |  | 2024-03-20 | Site Office Civil Foundation | AU | 1 | 907290 | 907290 | 1070602.2 | 553370.75 | 652977.48 | 353919.25 | 553370.75 | 652977.48 | ZSER | 2024-01-09 | 2024-02-09
RE/0066-PRJ-CO-OTH-SI | Site Infrastructure Development | 2010 |  | 2010 | SMARTWORLD THE EDITION | Evolve Buildcon | 9140000276 | 40 |  |  | 2024-03-14 | Amendment 2 External Hardscape Works | AU | 1 | 274500 | 274500 | 323910 | 270134.97 | 318759.26 | 4365.03 | 270134.75 | 318759 | ZSER | 2024-03-14 | 2024-04-14
RE/0066-PRJ-CO-OTH-SI | Site Infrastructure Development | 2010 |  | 2010 | SMARTWORLD THE EDITION | Evolve Buildcon | 9140000276 | 50 |  |  | 2024-03-14 | BASE RATE VARIATION | AU | 1 | 152913.9 | 152913.9 | 180438.4 | 152913.89 | 180438.39 | 0.01 | 152913.91 | 180438.41 | ZSER | 2024-03-14 | 2024-04-14
RE/0066-PRJ-CO-OTH-SI | Site Infrastructure Development | 2010 |  | 2010 | SMARTWORLD THE EDITION | Kamal Electricales | 9140000288 | 10 |  |  | 2024-05-14 | DHBVN External Electrification works | AU | 1 | 1760000 | 1760000 | 2076800 | 695588.14 | 820794 | 1064411.86 | 695586.44 | 820792 | ZSER | 2024-04-30 | 2024-05-30
RE/0066-PRJ-CO-OTH-SI | Site Infrastructure Development | 2010 |  | 2010 | SMARTWORLD THE EDITION | Kamal Electricales | 9140000288 | 10 |  |  | 2024-05-14 | DHBVN External Electrification works | AU | 1 | 0 | 1760000 | 2076800 | 695588.14 | 820794 | 1064411.86 | 695586.44 | 820792 | ZSER | 2024-04-30 | 2024-05-30
RE/0066-PRJ-CO-OTH-SI | Site Infrastructure Development | 2010 |  | 2010 | SMARTWORLD THE EDITION | AIR SYSTEMS | 9140000330 | 10 |  |  | 2024-08-02 | HIGH AND LOW SIDE WORKS | AU | 1 | 759772 | 702122 | 898716.16 | 755268.09 | 966743.16 | 53146.09 | 755268.05 | 966743.1 | ZSER | 2024-07-30 | 2024-08-30
RE/0066-PRJ-CO-OTH-SI | Site Infrastructure Development | 2010 |  | 2010 | SMARTWORLD THE EDITION | AIR SYSTEMS | 9140000330 | 10 |  |  | 2024-08-02 | HIGH AND LOW SIDE WORKS | AU | 1 | 0 | 57650 | 68027 | 819273.86 | 966743.16 | 761623.86 | 819273.81 | 966743.1 | ZSER | 2024-07-30 | 2024-08-30
RE/0066-PRJ-CO-OTH-SI | Site Infrastructure Development | 2010 |  | 2010 | SMARTWORLD THE EDITION | AIR SYSTEMS | 9140000330 | 20 |  |  | 2024-08-02 | PIPING WORKS | AU | 1 | 108989.5 | 108989.5 | 128607.61 | 98090.55 | 115746.85 | 10898.95 | 98090.55 | 115746.85 | ZSER | 2024-07-30 | 2024-08-30
RE/0066-PRJ-CO-OTH-SI | Site Infrastructure Development | 2010 |  | 2010 | SMARTWORLD THE EDITION | AIR SYSTEMS | 9140000330 | 30 |  |  | 2024-08-02 | Amendment 1 Air conditioning work | AU | 1 | 37480 | 37480 | 44226.4 | 0 | 0 | 37480 | 0 | 0 | ZSER | 2024-07-30 | 2024-08-30
RE/0066-PRJ-CO-OTH-SI | Site Infrastructure Development | 2010 |  | 2010 | SMARTWORLD THE EDITION | AIR SYSTEMS | 9140000330 | 40 |  |  | 2024-08-02 | Amendment 2 Air conditioning work | AU | 1 | 59558.01 | 59558.01 | 70278.45 | 0 | 0 | 59558.01 | 0 | 0 | ZSER | 2024-07-30 | 2024-08-30
RE/0066-PRJ-CO-OTH-SI | Site Infrastructure Development | 2010 |  | 2010 | SMARTWORLD THE EDITION | AIR SYSTEMS | 9140000330 | 50 |  |  | 2024-08-02 | Extra Item Amendment 2 | AU | 1 | 2295 | 2295 | 2708.1 | 0 | 0 | 2295 | 0 | 0 | ZSER | 2024-07-30 | 2024-08-30
RE/0066-PRJ-CO-OTH-SI | Site Infrastructure Development | 2010 |  | 2010 | SMARTWORLD THE EDITION | Haarish Electric vehicles | 9140000402 | 10 |  |  | 2025-01-01 | MS barrication | AU | 1 | 1052000 | 1052000 | 1241360 | 743786.25 | 877667.78 | 308213.75 | 743786.25 | 877667.78 | ZSER | 2025-01-01 | 2025-03-01
RE/0066-PRJ-CO-OTH-SI | Site Infrastructure Development | 2010 |  | 2010 | SMARTWORLD THE EDITION | Rakesh | 9140000450 | 10 |  |  | 2025-05-09 | Approach Road Repair works | AU | 1 | 880848 | 880848 | 1039400.64 | 880848 | 1039400.64 | 0 | 880848 | 1039400.64 | ZSER | 2025-04-03 | 2025-05-03
RE/0066-PRJ-CO-OTH-SI | Site Infrastructure Development | 2010 |  | 2010 | SMARTWORLD THE EDITION | Rakesh | 9140000450 | 20 |  |  | 2025-05-09 | Amedn - 1 Seal coat above road repair | AU | 1 | 134574 | 134574 | 158797.32 | 134574 | 158797.32 | 0 | 134574 | 158797.32 | ZSER | 2025-04-03 | 2025-05-03
RE/0066-PRJ-CO-OTH-SI | Site Infrastructure Development | 2010 |  | 2010 | SMARTWORLD THE EDITION | KRITARTH ADVERTISING PRIVATE LIMITE | 9140000512 | 10 |  |  | 2025-10-14 | Branding work at Project 66 | AU | 1 | 139695.1 | 139695.1 | 164840.22 | 99901.39 | 117883.64 | 39793.71 | 99901.39 | 117883.64 | ZSER | 2025-09-30 | 2025-10-20
RE/0066-PRJ-CO-OTH-SI | Site Infrastructure Development | 2010 |  | 2010 | SMARTWORLD THE EDITION | Sokuryo Technologies India PrivateLimited | 9140000647 | 10 |  |  | 2026-05-02 | Service & Calibaration of TS &AL | AU | 1 | 14200 | 14200 | 16756 | 14200 | 16756 | 0 | 14200 | 16756 | ZSER | 2026-05-02 | 2026-05-31
RE/0066-PRJ-CO-OTH-SI | Site Infrastructure Development | 2010 |  | 2010 | SMARTWORLD THE EDITION | RUDRA ENTERPRISESMANJEET | 9140000651 | 10 |  |  | 2026-05-11 | SITC Noise Monitoring System | AU | 1 | 107520 | 107520 | 126873.6 | 0 | 0 | 107520 | 0 | 0 | ZSER | 2026-05-11 | 2026-05-26
RE/0066-PRJ-CO-OTH-SI | Site Infrastructure Development | 2010 |  | 2010 | SMARTWORLD THE EDITION | Anil SoormaMr. Anil Soorma | 9160000526 | 10 |  |  | 2023-12-28 | Providing Engineers Certificate | AU | 1 | 200000 | 200000 | 200000 | 120000 | 120000 | 80000 | 120000 | 120000 | ZGEN | 2023-12-22 | 2024-12-22
RE/0066-PRJ-CO-OTH-SI | Site Infrastructure Development | 2010 |  | 2010 | SMARTWORLD THE EDITION | Haarish Electric vehicles | 9160000527 | 10 |  |  | 2023-12-28 | Welded Wire Mesh Fencing | AU | 1 | 684012 | 684012 | 807134.16 | 682386.44 | 805216 | 1625.56 | 682385.36 | 805214.72 | ZGEN | 2024-01-03 | 2024-02-03
RE/0066-PRJ-CO-OTH-SI | Site Infrastructure Development | 2010 |  | 2010 | SMARTWORLD THE EDITION | D.D Pradhan & CO. Pvt. Ltd. | 9160000692 | 10 |  |  | 2024-03-13 | Providing & Installation of Water Tank | AU | 1 | 118900 | 118900 | 140302 | 114315.25 | 134892 | 4584.75 | 114315.51 | 134892.3 | ZGEN | 2024-02-13 | 2024-03-29
RE/0066-PRJ-CO-OTH-SI | Site Infrastructure Development | 2010 |  | 2010 | SMARTWORLD THE EDITION | CL Construction | 9160000807 | 10 |  |  | 2024-05-01 | Civil & Finishing works | AU | 1 | 3378430.55 | 3378430.55 | 3986548.05 | 3327152.26 | 3926039.67 | 51278.29 | 3327142.46 | 3926028.1 | ZGEN | 2024-04-30 | 2024-06-30
RE/0066-PRJ-CO-OTH-SI | Site Infrastructure Development | 2010 |  | 2010 | SMARTWORLD THE EDITION | CL Construction | 9160000807 | 20 |  |  | 2024-05-01 | Interior Works | AU | 1 | 1948255.12 | 1948255.12 | 2298941.04 | 1656905.15 | 1955148.08 | 291349.97 | 1656903.17 | 1955145.74 | ZGEN | 2024-04-30 | 2024-06-30
RE/0066-PRJ-CO-OTH-SI | Site Infrastructure Development | 2010 |  | 2010 | SMARTWORLD THE EDITION | CL Construction | 9160000807 | 30 |  |  | 2024-05-01 | Extra Item | AU | 1 | 1585988.3 | 1585988.3 | 1871466.19 | 1444926.08 | 1705012.77 | 141062.22 | 1444926.08 | 1705012.77 | ZGEN | 2024-04-30 | 2024-06-30
RE/0066-PRJ-CO-OTH-SI | Site Infrastructure Development | 2010 |  | 2010 | SMARTWORLD THE EDITION | Unicorn Weighing Services | 9160000832 | 10 |  |  | 2024-05-13 | Weighing Services for Weighbridge | AU | 1 | 1954512 | 1954512 | 2306324.16 | 1202347.19 | 1418769.69 | 752164.81 | 1202313.99 | 1418730.51 | ZGEN | 2024-04-01 | 2025-03-31
RE/0066-PRJ-CO-OTH-SI | Site Infrastructure Development | 2010 |  | 2010 | SMARTWORLD THE EDITION | Unicorn Weighing Services | 9160000832 | 20 |  |  | 2024-05-13 | Amend-1 Weighing Services for Weighbrig | AU | 1 | 0 | 1857804 | 2192208.72 | 1475976.69 | 1741652.49 | 381827.31 | 1475976.69 | 1741652.49 | ZGEN | 2024-04-01 | 2025-03-31
RE/0066-PRJ-CO-OTH-SI | Site Infrastructure Development | 2010 |  | 2010 | SMARTWORLD THE EDITION | Unicorn Weighing Services | 9160000832 | 30 |  |  | 2024-05-13 | Amend-2Weighing Services for Weighbridge | AU | 1 | 2028013.2 | 2028013.2 | 2393055.58 | 215215 | 253953.7 | 1812798.2 | 215215 | 253953.7 | ZGEN | 2024-04-01 | 2025-03-31
RE/0066-PRJ-CO-OTH-SI | Site Infrastructure Development | 2010 |  | 2010 | SMARTWORLD THE EDITION | Bureau Veritas (India ) Private limMr. Pranay Kumar Singh | 9160001424 | 10 |  |  | 2024-12-24 | Reinforcement steel testing | AU | 1 | 140000 | 140000 | 165200 | 0 | 0 | 140000 | 0 | 0 | ZGEN | 2024-12-24 | 2025-06-24
RE/0066-PRJ-CO-OTH-SI | Site Infrastructure Development | 2010 |  | 2010 | SMARTWORLD THE EDITION | National Safety Council | 9160001838 | 10 |  |  | 2025-05-21 | Registartion to NSC | AU | 1 | 30000 | 30000 | 35400 | 30000 | 35400 | 0 | 30000 | 35400 | ZGEN | 2025-05-21 | 2025-11-21
RE/0066-PRJ-CO-OTH-SI | Site Infrastructure Development | 2010 |  | 2010 | SMARTWORLD THE EDITION | Admark | 9160002365 | 10 |  |  | 2025-10-06 | SITC of SMARTWORLD logo on safety screen | AU | 1 | 208000 | 208000 | 245440 | 208000 | 245440 | 0 | 208000 | 245440 | ZGEN | 2025-10-05 | 2025-10-25
RE/0066-PRJ-CO-OTH-SI | Site Infrastructure Development | 2010 |  | 2010 | SMARTWORLD THE EDITION | Admark | 9160002567 | 10 |  |  | 2025-12-30 | Branding on safety screen | AU | 1 | 220000 | 220000 | 259600 | 220000 | 259600 | 0 | 220000 | 259600 | ZGEN | 2025-12-30 | 2026-01-20
RE/0066-PRJ-CO-OTH-SI | Site Infrastructure Development | 2010 |  | 2010 | SMARTWORLD THE EDITION | SAFETY CIRCLE PRIVATE LIMITEDSonia Dawra | 9160002804 | 10 |  |  | 2026-03-09 | Safety Traing & certification | AU | 1 | 37000 | 37000 | 43660 | 37000 | 43660 | 0 | 37000 | 43660 | ZGEN | 2026-03-07 | 2026-04-07
RE/0066-PRJ-CO-OTH-SI | Site Infrastructure Development | 2010 |  | 2010 | SMARTWORLD THE EDITION | Griha Council | 9160002813 | 10 |  |  | 2026-03-11 | GRIHA registration fee | AU | 1 | 2000000 | 2000000 | 2360000 | 2000000 | 2360000 | 0 | 2000000 | 2360000 | ZGEN | 2026-03-11 | 2026-04-11
RE/0066-PRJ-CO-OTH-SS | Staff Salaries & Administrative Expenses | 2010 |  | 2010 |  |  |  | 0 | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
RE/0066-PRJ-CS-SH | CONV SHOPPING EXPENSES | 2010 | GR01 | 2010 |  |  |  | 0 | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
RE/0066-PRJ-ES-AAC | Escalation- AAC Blocks | 2010 | GR01 | 2010 |  |  |  | 0 | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
RE/0066-PRJ-ES-AF | Escalation- Aluminium Formwork | 2010 | GR01 | 2010 |  |  |  | 0 | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
RE/0066-PRJ-ES-CEM | Escalation- Cement | 2010 | GR01 | 2010 |  |  |  | 0 | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
RE/0066-PRJ-ES-RMC | Escalation- RMC | 2010 | GR01 | 2010 | SMARTWORLD THE EDITION | Ahluwalia Contracts India Limited | 9140000321 | 170 |  |  | 2024-07-20 | Price Variation - RMC | AU | 1 | 139000000 | 139000000 | 164020000 | 91656982.85 | 108155239.76 | 47343017.15 | 69999999.88 | 82599999.86 | ZSER | 2024-07-15 | 2027-01-14
RE/0066-PRJ-ES-SS | Escalation- Structural steel | 2010 | GR01 | 2010 |  |  |  | 0 | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
RE/0066-PRJ-EW-CIV-CC-LA | Concrete Labour | 2010 | GR01 | 2010 |  |  |  | 0 | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
RE/0066-PRJ-EW-CIV-CC-SL | Concrete Supply&Labour | 2010 | GR01 | 2010 | SMARTWORLD THE EDITION | Ahluwalia Contracts India Limited | 9140000321 | 20 |  |  | 2024-07-20 | REINFORCED CEMENT CONCRETE-I part A | AU | 1 | 0 | 18780547.2 | 22161045.7 | 0 | 0 | 18780547.2 | 0 | 0 | ZSER | 2024-07-15 | 2027-01-14
RE/0066-PRJ-EW-CIV-CC-SL | Concrete Supply&Labour | 2010 | GR01 | 2010 | SMARTWORLD THE EDITION | Ahluwalia Contracts India Limited | 9140000321 | 30 |  |  | 2024-07-20 | REINFORCED CEMENT CONCRETE-I Part B | AU | 1 | 0 | 16972816.12 | 20027923.02 | 0 | 0 | 16972816.12 | 0 | 0 | ZSER | 2024-07-15 | 2027-01-14
RE/0066-PRJ-EW-CIV-CC-SL | Concrete Supply&Labour | 2010 | GR01 | 2010 | SMARTWORLD THE EDITION | Ahluwalia Contracts India Limited | 9140000321 | 40 |  |  | 2024-07-20 | REINFORCED CEMENT CONCRETE-I Part C | AU | 1 | 0 | 18270116.46 | 21558737.42 | 0 | 0 | 18270116.46 | 0 | 0 | ZSER | 2024-07-15 | 2027-01-14
RE/0066-PRJ-EW-CIV-CC-SU | Concrete Supply | 2010 | GR01 | 2010 |  |  |  | 0 | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
RE/0066-PRJ-EW-CIV-EW | Earthwork | 2010 | GR01 | 2010 | SMARTWORLD THE EDITION | Ahluwalia Contracts India Limited | 9140000321 | 10 |  |  | 2024-07-20 | SITE DEVLOPMENT AND EARTH WORK | AU | 1 | 0 | 4263388.44 | 5030798.36 | 0 | 0 | 4263388.44 | 0 | 0 | ZSER | 2024-07-15 | 2027-01-14
RE/0066-PRJ-EW-CIV-MS | Misc Structure Works | 2010 | GR01 | 2010 | SMARTWORLD THE EDITION | Ahluwalia Contracts India Limited | 9140000321 | 100 |  |  | 2024-07-20 | STRUCTURAL STEEL WORKS | AU | 1 | 0 | 2035822 | 2402269.96 | 0 | 0 | 2035822 | 0 | 0 | ZSER | 2024-07-15 | 2027-01-14
RE/0066-PRJ-EW-CIV-MS | Misc Structure Works | 2010 | GR01 | 2010 | SMARTWORLD THE EDITION | Ahluwalia Contracts India Limited | 9140000321 | 130 |  |  | 2024-07-20 | INTERNAL & EXTERNAL PLASTERING | AU | 1 | 0 | 255360 | 301324.8 | 0 | 0 | 255360 | 0 | 0 | ZSER | 2024-07-15 | 2027-01-14
RE/0066-PRJ-EW-CIV-MW | Masonry Works | 2010 | GR01 | 2010 | SMARTWORLD THE EDITION | Ahluwalia Contracts India Limited | 9140000321 | 90 |  |  | 2024-07-20 | MASONARY WORKS | AU | 1 | 0 | 8317484 | 9814631.12 | 0 | 0 | 8317484 | 0 | 0 | ZSER | 2024-07-15 | 2027-01-14
RE/0066-PRJ-EW-CIV-PW-IP | Internal Cement Plaster | 2010 | GR01 | 2010 | SMARTWORLD THE EDITION | Ahluwalia Contracts India Limited | 9140000321 | 130 |  |  | 2024-07-20 | INTERNAL & EXTERNAL PLASTERING | AU | 1 | 0 | 9191070 | 10845462.6 | 0 | 0 | 9191070 | 0 | 0 | ZSER | 2024-07-15 | 2027-01-14
RE/0066-PRJ-EW-CIV-PW-XP | External Cement Plaster | 2010 | GR01 | 2010 | SMARTWORLD THE EDITION | Ahluwalia Contracts India Limited | 9140000321 | 130 |  |  | 2024-07-20 | INTERNAL & EXTERNAL PLASTERING | AU | 1 | 0 | 1004000 | 1184720 | 0 | 0 | 1004000 | 0 | 0 | ZSER | 2024-07-15 | 2027-01-14
RE/0066-PRJ-EW-CIV-RS-LA | Reinforcement Labour | 2010 | GR01 | 2010 | SMARTWORLD THE EDITION | Ahluwalia Contracts India Limited | 9140000321 | 70 |  |  | 2024-07-20 | REINFORCEMENT STEEL Installation Part A | AU | 1 | 0 | 6255373 | 7381340.14 | 0 | 0 | 6255373 | 0 | 0 | ZSER | 2024-07-15 | 2027-01-14
RE/0066-PRJ-EW-CIV-RS-LA | Reinforcement Labour | 2010 | GR01 | 2010 | SMARTWORLD THE EDITION | Ahluwalia Contracts India Limited | 9140000321 | 80 |  |  | 2024-07-20 | REINFORCEMENT STEEL Installation Part B | AU | 1 | 0 | 23046298.67 | 27194632.43 | 0 | 0 | 23046298.67 | 0 | 0 | ZSER | 2024-07-15 | 2027-01-14
RE/0066-PRJ-EW-CIV-RS-SU | Reinforcement Supply | 2010 | GR01 | 2010 |  |  |  | 0 | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
RE/0066-PRJ-EW-CIV-SW-CS | Conventional Shuttering | 2010 | GR01 | 2010 | SMARTWORLD THE EDITION | Ahluwalia Contracts India Limited | 9140000321 | 50 |  |  | 2024-07-20 | CENTERING & SHUTTERING Part A | AU | 1 | 0 | 13123590 | 15485836.2 | 0 | 0 | 13123590 | 0 | 0 | ZSER | 2024-07-15 | 2027-01-14
RE/0066-PRJ-EW-CIV-SW-SO | Shuttering Other | 2010 | GR01 | 2010 |  |  |  | 0 | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
RE/0066-PRJ-EW-CIV-SW-SU | Aluminum Shuttering Supply | 2010 | GR01 | 2010 | SMARTWORLD THE EDITION | Ahluwalia Contracts India Limited | 9140000321 | 60 |  |  | 2024-07-20 | CENTERING & SHUTTERING Part B | AU | 1 | 0 | 18208111.98 | 21485572.14 | 0 | 0 | 18208111.98 | 0 | 0 | ZSER | 2024-07-15 | 2027-01-14
RE/0066-PRJ-EW-CIV-WP | Waterproofing Works | 2010 | GR01 | 2010 | SMARTWORLD THE EDITION | Ahluwalia Contracts India Limited | 9140000321 | 110 |  |  | 2024-07-20 | FLOORING | AU | 1 | 0 | 1431.57 | 1689.25 | 0 | 0 | 1431.57 | 0 | 0 | ZSER | 2024-07-15 | 2027-01-14
RE/0066-PRJ-EW-CIV-WP | Waterproofing Works | 2010 | GR01 | 2010 | SMARTWORLD THE EDITION | Ahluwalia Contracts India Limited | 9140000321 | 120 |  |  | 2024-07-20 | WATER-PROOFING WORKS | AU | 1 | 0 | 14175988 | 16727665.84 | 0 | 0 | 14175988 | 0 | 0 | ZSER | 2024-07-15 | 2027-01-14
RE/0066-PRJ-EW-FAC-EF | Elevation Feature | 2010 | GR01 | 2010 |  |  |  | 0 | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
RE/0066-PRJ-EW-FAC-EP | External Paint | 2010 | GR01 | 2010 |  |  |  | 0 | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
RE/0066-PRJ-EW-FAC-GL | Glazing Works | 2010 | GR01 | 2010 |  |  |  | 0 | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
RE/0066-PRJ-EW-FAC-RA | Railing Works | 2010 | GR01 | 2010 |  |  |  | 0 | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
RE/0066-PRJ-EW-FIS-CF | Ceiling Finish Works | 2010 | GR01 | 2010 |  |  |  | 0 | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
RE/0066-PRJ-EW-FIS-DW | Door Works | 2010 | GR01 | 2010 |  |  |  | 0 | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
RE/0066-PRJ-EW-FIS-FF | Floor Finish Works | 2010 | GR01 | 2010 | SMARTWORLD THE EDITION | Ahluwalia Contracts India Limited | 9140000321 | 110 |  |  | 2024-07-20 | FLOORING | AU | 1 | 0 | 2091190.01 | 2467604.21 | 0 | 0 | 2091190.01 | 0 | 0 | ZSER | 2024-07-15 | 2027-01-14
RE/0066-PRJ-EW-FIS-LF | Lobby Furniture | 2010 | GR01 | 2010 |  |  |  | 0 | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
RE/0066-PRJ-EW-FIS-MD | Modular Kitchen Works | 2010 | GR01 | 2010 |  |  |  | 0 | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
RE/0066-PRJ-EW-FIS-MF | Misc Finish Works | 2010 | GR01 | 2010 |  |  |  | 0 | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
RE/0066-PRJ-EW-FIS-MW | MS works | 2010 | GR01 | 2010 |  |  |  | 0 | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
RE/0066-PRJ-EW-FIS-WF | Wall Finish Works | 2010 | GR01 | 2010 |  |  |  | 0 | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
RE/0066-PRJ-EW-FIS-WO | Wood Work | 2010 | GR01 | 2010 |  |  |  | 0 | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
RE/0066-PRJ-EW-MEP-EW-HE | High Side Electrical Works | 2010 | GR01 | 2010 | SMARTWORLD THE EDITION | Dehn India Pvt Ltd | 9140000379 | 10 |  |  | 2024-10-24 | Lightning Protection System for Basement | AU | 1 | 0 | 223011 | 263152.98 | 28497 | 33626.46 | 194514 | 28497 | 33626.46 | ZSER | 2024-10-24 | 2027-08-23
RE/0066-PRJ-EW-MEP-EW-LE | Low Side Electrical Works | 2010 | GR01 | 2010 | SMARTWORLD THE EDITION | Ahluwalia Contracts India Limited | 9140000321 | 140 |  |  | 2024-07-20 | CONDUITING | AU | 1 | 0 | 4001534 | 4721810.12 | 0 | 0 | 4001534 | 0 | 0 | ZSER | 2024-07-15 | 2027-01-14
RE/0066-PRJ-EW-MEP-EW-LE | Low Side Electrical Works | 2010 | GR01 | 2010 | SMARTWORLD THE EDITION | TRIPLE A ENGINEERING PRIVATE LIMIT | 9140000688 | 50 |  |  | 2026-06-06 | EWS -CCTV | AU | 1 | 374858 | 374858 | 374858 | 0 | 0 | 374858 | 0 | 0 | ZSER | 2026-06-01 | 2028-02-01
RE/0066-PRJ-EW-MEP-EW-LE | Low Side Electrical Works | 2010 | GR01 | 2010 | SMARTWORLD THE EDITION | TRIPLE A ENGINEERING PRIVATE LIMIT | 9140000688 | 60 |  |  | 2026-06-06 | Electrical Works EWS | AU | 1 | 10327459 | 10327459 | 10327459 | 0 | 0 | 10327459 | 0 | 0 | ZSER | 2026-06-01 | 2028-02-01
RE/0066-PRJ-EW-MEP-EW-LS | Light Fixtures Supply | 2010 | GR01 | 2010 |  |  |  | 0 | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
RE/0066-PRJ-EW-MEP-FF | Fire Fighting Work | 2010 | GR01 | 2010 | SMARTWORLD THE EDITION | Atom MEP Engineers Pvt. Ltd. | 9140000668 | 310 |  |  | 2026-05-19 | FF-FIRE HYDRANT & EQUIPMENT - EWS | AU | 1 | 810690.44 | 810690.44 | 956614.72 | 0 | 0 | 810690.44 | 0 | 0 | ZSER | 2026-04-04 | 2028-02-04
RE/0066-PRJ-EW-MEP-FF | Fire Fighting Work | 2010 | GR01 | 2010 | SMARTWORLD THE EDITION | Atom MEP Engineers Pvt. Ltd. | 9140000668 | 410 |  |  | 2026-05-19 | FF-PORTABLE FIRE EXTINGUISHERS-EW | AU | 1 | 129318 | 129318 | 152595.24 | 0 | 0 | 129318 | 0 | 0 | ZSER | 2026-04-04 | 2028-02-04
RE/0066-PRJ-EW-MEP-HV | HVAC WORKS SYSTEM | 2010 | GR01 | 2010 |  |  |  | 0 | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
RE/0066-PRJ-EW-MEP-LF | Lifts | 2010 | GR01 | 2010 |  |  |  | 0 | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
RE/0066-PRJ-EW-MEP-LT | Lifts | 2010 | GR01 | 2010 |  |  |  | 0 | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
RE/0066-PRJ-EW-MEP-PB-FS | Plumbing Fixtures Supply | 2010 | GR01 | 2010 |  |  |  | 0 | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
RE/0066-PRJ-EW-MEP-PB-IP | Internal Plumbing | 2010 | GR01 | 2010 | SMARTWORLD THE EDITION | Atom MEP Engineers Pvt. Ltd. | 9140000668 | 50 |  |  | 2026-05-19 | SANITARY FIXTURES & FITTINGS EWS/School | AU | 1 | 670975 | 670975 | 791750.5 | 0 | 0 | 670975 | 0 | 0 | ZSER | 2026-04-04 | 2028-02-04
RE/0066-PRJ-EW-MEP-PB-IP | Internal Plumbing | 2010 | GR01 | 2010 | SMARTWORLD THE EDITION | Atom MEP Engineers Pvt. Ltd. | 9140000668 | 100 |  |  | 2026-05-19 | INTERNAL DRAINAGE -EWS/SCHOOL | AU | 1 | 4295441.6 | 4295441.6 | 5068621.09 | 0 | 0 | 4295441.6 | 0 | 0 | ZSER | 2026-04-04 | 2028-02-04
RE/0066-PRJ-EW-MEP-PB-IP | Internal Plumbing | 2010 | GR01 | 2010 | SMARTWORLD THE EDITION | Atom MEP Engineers Pvt. Ltd. | 9140000668 | 150 |  |  | 2026-05-19 | DOMESTIC AND FLUSHING WATER EWS/SC | AU | 1 | 3829018.48 | 3829018.48 | 4518241.81 | 0 | 0 | 3829018.48 | 0 | 0 | ZSER | 2026-04-04 | 2028-02-04
RE/0066-PRJ-EW-MEP-PB-IP | Internal Plumbing | 2010 | GR01 | 2010 | SMARTWORLD THE EDITION | Atom MEP Engineers Pvt. Ltd. | 9140000668 | 210 |  |  | 2026-05-19 | MISCELLANEOUS ITEMS FOR TERRACE-EWS | AU | 1 | 425270 | 425270 | 501818.6 | 0 | 0 | 425270 | 0 | 0 | ZSER | 2026-04-04 | 2028-02-04
RE/0066-PRJ-EW-MEP-PN | PNG Gas Pipe Line | 2010 | GR01 | 2010 |  |  |  | 0 | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
RE/0066-PRJ-EW-MEP-PP | PNG Gas Pipe Line | 2010 | GR01 | 2010 |  |  |  | 0 | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
RE/0066-PRJ-NT-CIV-CC-LA | Concrete Labour | 2010 | GR01 | 2010 |  |  |  | 0 | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
RE/0066-PRJ-NT-CIV-CC-SL | Concrete Supply & Labour | 2010 | GR01 | 2010 | SMARTWORLD THE EDITION | Ahluwalia Contracts India Limited | 9140000321 | 20 |  |  | 2024-07-20 | REINFORCED CEMENT CONCRETE-I part A | AU | 1 | 0 | 132797073.16 | 156700546.33 | 68130761.41 | 80394298.46 | 64666311.75 | 66146541.72 | 78052919.23 | ZSER | 2024-07-15 | 2027-01-14
RE/0066-PRJ-NT-CIV-CC-SL | Concrete Supply & Labour | 2010 | GR01 | 2010 | SMARTWORLD THE EDITION | Ahluwalia Contracts India Limited | 9140000321 | 30 |  |  | 2024-07-20 | REINFORCED CEMENT CONCRETE-I Part B | AU | 1 | 0 | 37518642.99 | 44271998.73 | 15318418.86 | 18075734.26 | 22200224.13 | 10269444.02 | 12117943.94 | ZSER | 2024-07-15 | 2027-01-14
RE/0066-PRJ-NT-CIV-CC-SL | Concrete Supply & Labour | 2010 | GR01 | 2010 | SMARTWORLD THE EDITION | Ahluwalia Contracts India Limited | 9140000321 | 40 |  |  | 2024-07-20 | REINFORCED CEMENT CONCRETE-I Part C | AU | 1 | 0 | 199971698.7 | 235966604.47 | 105641440.97 | 124656900.35 | 94330257.73 | 103087866.76 | 121643682.78 | ZSER | 2024-07-15 | 2027-01-14
RE/0066-PRJ-NT-CIV-CC-SL | Concrete Supply & Labour | 2010 | GR01 | 2010 | SMARTWORLD THE EDITION | Ahluwalia Contracts India Limited | 9140000321 | 180 |  |  | 2024-07-20 | SUBSTITUTE ITEM | AU | 1 | 87270067.32 | 353535 | 417171.3 | 296000 | 349280 | 57535 | 296000 | 349280 | ZSER | 2024-07-15 | 2027-01-14
RE/0066-PRJ-NT-CIV-CC-SU | Concrete Supply | 2010 | GR01 | 2010 |  |  |  | 0 | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
RE/0066-PRJ-NT-CIV-DW | D-Wall | 2010 | GR01 | 2010 | SMARTWORLD THE EDITION | Shree Balaji RMC | 9110000071 | 10 |  |  | 2023-04-14 | Ready Mix Concrete M - 7.5 | M3 | 60 | 3427.5 | 205650 | 242667 | 0 | 0 | 205650 | 0 | 0 | ZMAT | 2025-01-20 | 2025-03-20
RE/0066-PRJ-NT-CIV-DW | D-Wall | 2010 | GR01 | 2010 | SMARTWORLD THE EDITION | Shree Balaji RMC | 9110000071 | 40 |  |  | 2023-04-14 | Ready Mix Concrete M - 30 | M3 | 15 | 4125 | 61875 | 73012.5 | 0 | 0 | 61875 | 0 | 0 | ZMAT | 2025-01-20 | 2025-03-20
RE/0066-PRJ-NT-CIV-DW | D-Wall | 2010 | GR01 | 2010 | SMARTWORLD THE EDITION | RKSK SteelRamji gupta | 9110000289 | 50 |  |  | 2023-11-02 | Steel Re-bar TMT 10 mm Dia. FE-550D | TO | 4.48 | 53400 | 239232 | 282293.76 | 0 | 0 | 239232 | 0 | 0 | ZMAT | 2025-01-20 | 2025-03-20
RE/0066-PRJ-NT-CIV-DW | D-Wall | 2010 | GR01 | 2010 | SMARTWORLD THE EDITION | RKSK SteelRamji gupta | 9110000289 | 60 |  |  | 2023-11-02 | Steel Re-bar TMT 16 mm Dia. FE-550D | TO | 2.63 | 52400 | 137812 | 162618.16 | 0 | 0 | 137812 | 0 | 0 | ZMAT | 2025-01-20 | 2025-03-20
RE/0066-PRJ-NT-CIV-DW | D-Wall | 2010 | GR01 | 2010 | SMARTWORLD THE EDITION | RKSK SteelRamji gupta | 9110000289 | 70 |  |  | 2023-11-02 | Steel Re-bar TMT 20 mm Dia. FE-550D | TO | 1.55 | 52400 | 81220 | 95839.6 | 0 | 0 | 81220 | 0 | 0 | ZMAT | 2025-01-20 | 2025-03-20
RE/0066-PRJ-NT-CIV-DW | D-Wall | 2010 | GR01 | 2010 | SMARTWORLD THE EDITION | N S Concrete Pvt Ltd | 9110000320 | 60 |  |  | 2023-12-13 | Ready Mix Concrete M - 15 | M3 | 403.44 | 3743 | 1510075.92 | 1781889.59 | 0 | 0 | 1510075.92 | 0 | 0 | ZMAT | 2025-01-20 | 2025-03-20
RE/0066-PRJ-NT-CIV-DW | D-Wall | 2010 | GR01 | 2010 | SMARTWORLD THE EDITION | N S Concrete Pvt Ltd | 9110000320 | 80 |  |  | 2023-12-13 | Ready Mix Concrete M - 35 | M3 | 2817.29 | 4617.5 | 13008836.58 | 15350427.16 | 69262.5 | 81729.75 | 12939574.08 | 69262.2 | 81729.4 | ZMAT | 2025-01-20 | 2025-03-20
RE/0066-PRJ-NT-CIV-DW | D-Wall | 2010 | GR01 | 2010 | SMARTWORLD THE EDITION | RKSK SteelRamji gupta | 9110000344 | 40 |  |  | 2024-01-04 | Fe 550D TMT Steel 8 MM | TO | 1.25 | 52400 | 65500 | 77290 | 0 | 0 | 65500 | 0 | 0 | ZMAT | 2024-01-08 | 2024-02-08
RE/0066-PRJ-NT-CIV-DW | D-Wall | 2010 | GR01 | 2010 | SMARTWORLD THE EDITION | RKSK SteelRamji gupta | 9110000344 | 50 |  |  | 2024-01-04 | Fe 550D TMT Steel 12 MM | TO | 1 | 49400 | 49400 | 58292 | 0 | 0 | 49400 | 0 | 0 | ZMAT | 2024-01-08 | 2024-02-08
RE/0066-PRJ-NT-CIV-DW | D-Wall | 2010 | GR01 | 2010 | SMARTWORLD THE EDITION | RKSK SteelRamji gupta | 9110000344 | 60 |  |  | 2024-01-04 | Fe 550D TMT Steel 16 MM | TO | 3.32 | 50400 | 167328 | 197447.04 | 0 | 0 | 167328 | 0 | 0 | ZMAT | 2024-01-08 | 2024-02-08
RE/0066-PRJ-NT-CIV-DW | D-Wall | 2010 | GR01 | 2010 | SMARTWORLD THE EDITION | SBJ Concrete Buildcon Private Limit | 9110000397 | 30 |  |  | 2024-02-08 | Ready Mix Concrete M - 15 | M3 | 0.02 | 3743 | 74.86 | 88.33 | 0 | 0 | 74.86 | 0 | 0 | ZMAT | 2025-01-20 | 2025-03-20
RE/0066-PRJ-NT-CIV-DW | D-Wall | 2010 | GR01 | 2010 | SMARTWORLD THE EDITION | SBJ Concrete Buildcon Private Limit | 9110000397 | 40 |  |  | 2024-02-08 | Ready Mix Concrete M - 35 | M3 | 3.58 | 4617.5 | 16530.65 | 19506.17 | 0 | 0 | 16530.65 | 0 | 0 | ZMAT | 2025-01-20 | 2025-03-20
RE/0066-PRJ-NT-CIV-DW | D-Wall | 2010 | GR01 | 2010 | SMARTWORLD THE EDITION | SBJ Concrete Buildcon Private Limit | 9110000413 | 10 |  |  | 2024-03-13 | Ready Mix Concrete M - 7.5 | M3 | 26.5 | 3572.5 | 94671.25 | 111712.08 | 94671.3 | 111712.13 | 0.05 | 94671.25 | 111712.05 | ZMAT | 2025-01-20 | 2025-03-20
RE/0066-PRJ-NT-CIV-DW | D-Wall | 2010 | GR01 | 2010 | SMARTWORLD THE EDITION | SBJ Concrete Buildcon Private Limit | 9110000413 | 20 |  |  | 2024-03-13 | Ready Mix Concrete M - 15 | M3 | 101 | 3743 | 378043 | 446090.74 | 203207.5 | 239784.85 | 174835.5 | 203207.47 | 239784.77 | ZMAT | 2025-01-20 | 2025-03-20
RE/0066-PRJ-NT-CIV-DW | D-Wall | 2010 | GR01 | 2010 | SMARTWORLD THE EDITION | SBJ Concrete Buildcon Private Limit | 9110000413 | 30 |  |  | 2024-03-13 | Ready Mix Concrete M - 25 | M3 | 30.9 | 4205 | 129934.5 | 153322.71 | 129934.53 | 153322.74 | 0.03 | 129934.5 | 153322.7 | ZMAT | 2025-01-20 | 2025-03-20
RE/0066-PRJ-NT-CIV-DW | D-Wall | 2010 | GR01 | 2010 | SMARTWORLD THE EDITION | SBJ Concrete Buildcon Private Limit | 9110000413 | 40 |  |  | 2024-03-13 | Ready Mix Concrete M - 35 | M3 | 2290 | 4617.5 | 10574075 | 12477408.5 | 10416433.63 | 12291391.68 | 157641.37 | 10416433.56 | 12291391.67 | ZMAT | 2025-01-20 | 2025-03-20
RE/0066-PRJ-NT-CIV-DW | D-Wall | 2010 | GR01 | 2010 | SMARTWORLD THE EDITION | Petropol India LimitedSANJAY GUPTA | 9110000423 | 10 |  |  | 2024-03-15 | Steel Re-bar TMT 08 mm Dia. FE-550D | TO | 2 | 51200 | 102400 | 120832 | 97792 | 115394.56 | 4608 | 97792 | 115394.57 | ZMAT | 2025-01-20 | 2025-03-20
RE/0066-PRJ-NT-CIV-DW | D-Wall | 2010 | GR01 | 2010 | SMARTWORLD THE EDITION | Petropol India LimitedSANJAY GUPTA | 9110000423 | 20 |  |  | 2024-03-15 | Steel Re-bar TMT 10 mm Dia. FE-550D | TO | 16 | 50200 | 803200 | 947776 | 780610 | 921119.8 | 22590 | 780610 | 921119.7 | ZMAT | 2025-01-20 | 2025-03-20
RE/0066-PRJ-NT-CIV-DW | D-Wall | 2010 | GR01 | 2010 | SMARTWORLD THE EDITION | Petropol India LimitedSANJAY GUPTA | 9110000423 | 30 |  |  | 2024-03-15 | Steel Re-bar TMT 12 mm Dia. FE-550D | TO | 70.29 | 48200 | 3387978 | 3997814.04 | 3360503.97 | 3965394.68 | 27474.03 | 3360504 | 3965394.3 | ZMAT | 2025-01-20 | 2025-03-20
RE/0066-PRJ-NT-CIV-DW | D-Wall | 2010 | GR01 | 2010 | SMARTWORLD THE EDITION | Petropol India LimitedSANJAY GUPTA | 9110000423 | 40 |  |  | 2024-03-15 | Steel Re-bar TMT 16 mm Dia. FE-550D | TO | 61 | 49200 | 3001200 | 3541416 | 3003168 | 3543738.24 | 1968 | 3003168 | 3543737.89 | ZMAT | 2025-01-20 | 2025-03-20
RE/0066-PRJ-NT-CIV-DW | D-Wall | 2010 | GR01 | 2010 | SMARTWORLD THE EDITION | Petropol India LimitedSANJAY GUPTA | 9110000423 | 50 |  |  | 2024-03-15 | Steel Re-bar TMT 20 mm Dia. FE-550D | TO | 65 | 49200 | 3198000 | 3773640 | 3135516 | 3699908.88 | 62484 | 3135516 | 3699908.54 | ZMAT | 2025-01-20 | 2025-03-20
RE/0066-PRJ-NT-CIV-DW | D-Wall | 2010 | GR01 | 2010 | SMARTWORLD THE EDITION | SBJ Concrete Buildcon Private Limit | 9110000447 | 10 |  |  | 2024-03-21 | Ready Mix Concrete Grade M-35 | M3 | 1500 | 4617.5 | 6926250 | 8172975 | 0 | 0 | 6926250 | 0 | 0 | ZMAT | 2024-04-01
RE/0066-PRJ-NT-CIV-DW | D-Wall | 2010 | GR01 | 2010 | SMARTWORLD THE EDITION | Ultratech Cement LimitedMR SHOBHAN CHAND | 9110000449 | 10 |  |  | 2024-03-16 | Cement OPC 53 grade | BAG | 9967 | 253.91 | 2530720.97 | 3239322.84 | 2530720.97 | 3239322.84 | 0 | 2530691.62 | 3239283.6 | ZMAT | 2025-01-20 | 2025-03-20
RE/0066-PRJ-NT-CIV-DW | D-Wall | 2010 | GR01 | 2010 | SMARTWORLD THE EDITION | N S Concrete Pvt Ltd | 9110000520 | 20 |  |  | 2024-05-13 | Pumping charges | M3 | 180 | 200 | 36000 | 42480 | 0 | 0 | 36000 | 0 | 0 | ZMAT | 2025-01-20 | 2025-03-20
RE/0066-PRJ-NT-CIV-DW | D-Wall | 2010 | GR01 | 2010 | SMARTWORLD THE EDITION | SBJ Concrete Buildcon Private Limit | 9110000521 | 20 |  |  | 2024-05-13 | Pumping Charges | M3 | 180 | 200 | 36000 | 42480 | 23500 | 27730 | 12500 | 23500 | 27730 | ZMAT | 2025-01-20 | 2025-03-20
RE/0066-PRJ-NT-CIV-DW | D-Wall | 2010 | GR01 | 2010 | SMARTWORLD THE EDITION | Wonder Cement LimitedMr. Avinash Kumar | 9110000537 | 10 |  |  | 2024-05-14 | Cement OPC 53 grade | BAG | 4270 | 244.53 | 1044143.1 | 1336503.17 | 1044143.09 | 1336503.16 | 0.01 | 1044148.9 | 1336510 | ZMAT | 2025-01-20 | 2025-03-20
RE/0066-PRJ-NT-CIV-DW | D-Wall | 2010 | GR01 | 2010 | SMARTWORLD THE EDITION | Wonder Cement LimitedMr. Avinash Kumar | 9110000585 | 10 |  |  | 2024-06-13 | Cement OPC 53 grade | BAG | 2520 | 2578.13 | 649688.76 | 831601.61 | 649688.74 | 831601.59 | 0.02 | 649687.5 | 831600 | ZMAT | 2025-01-20 | 2025-03-20
RE/0066-PRJ-NT-CIV-DW | D-Wall | 2010 | GR01 | 2010 | SMARTWORLD THE EDITION | Wonder Cement LimitedMr. Avinash Kumar | 9110000605 | 10 |  |  | 2024-07-04 | Cement OPC 53 grade | BAG | 980 | 250 | 245000 | 313600 | 0 | 0 | 245000 | 0 | 0 | ZMAT | 2025-01-20 | 2025-03-20
RE/0066-PRJ-NT-CIV-DW | D-Wall | 2010 | GR01 | 2010 | SMARTWORLD THE EDITION | Ultratech Cement LimitedMR SHOBHAN CHAND | 9110000639 | 10 |  |  | 2024-07-29 | Cement OPC 53 grade for Anchor Grouting | BAG | 1800 | 2382.82 | 428907.6 | 549001.73 | 190625.63 | 244000.8 | 238281.98 | 190625.6 | 244000.8 | ZMAT | 2025-01-20 | 2025-03-20
RE/0066-PRJ-NT-CIV-DW | D-Wall | 2010 | GR01 | 2010 | SMARTWORLD THE EDITION | Ultratech Cement LimitedMR SHOBHAN CHAND | 9110000667 | 10 |  |  | 2024-08-16 | Cement OPC 53 grade | BAG | 800 | 2265.62 | 181249.6 | 231999.49 | 181249.61 | 231999.5 | 0.01 | 181249.6 | 231999.5 | ZMAT | 2024-08-20 | 2024-09-19
RE/0066-PRJ-NT-CIV-DW | D-Wall | 2010 | GR01 | 2010 | SMARTWORLD THE EDITION | Wagad Buildcon | 9140000250 | 20 |  |  | 2023-08-16 | Diaphragm Wall Work D Wall as per Amend | AU | 1 | 79908294.5 | 79908294.5 | 94291787.51 | 61967429.83 | 73121567.2 | 17940864.67 | 61967418.01 | 73121553.25 | ZSER | 2023-07-04 | 2023-10-04
RE/0066-PRJ-NT-CIV-DW | D-Wall | 2010 | GR01 | 2010 | SMARTWORLD THE EDITION | Wagad Buildcon | 9140000250 | 30 |  |  | 2023-08-16 | Amendment 2 to Construction of D-Wall | AU | 1 | 6733125 | 6733125 | 7945087.5 | 6075000 | 7168500 | 658125 | 6075000 | 7168500 | ZSER | 2023-07-04 | 2023-10-04
RE/0066-PRJ-NT-CIV-DW | D-Wall | 2010 | GR01 | 2010 | SMARTWORLD THE EDITION | KUBER ENTERPRISES | 9140000363 | 10 |  |  | 2024-09-15 | Remedial Treatment of D-Wall | AU | 1 | 554000 | 554000 | 653720 | 0 | 0 | 554000 | 0 | 0 | ZSER | 2024-09-26 | 2024-11-25
RE/0066-PRJ-NT-CIV-EW | Earthwork | 2010 | GR01 | 2010 | SMARTWORLD THE EDITION | MSC ConstructionManish | 9140000259 | 10 |  |  | 2024-02-22 | Mass Excavation works | AU | 1 | 543851.12 | 543851.12 | 641744.32 | 0 | 0 | 543851.12 | 0 | 0 | ZSER | 2024-01-17 | 2024-04-17
RE/0066-PRJ-NT-CIV-EW | Earthwork | 2010 | GR01 | 2010 | SMARTWORLD THE EDITION | Infinity Constructions | 9140000303 | 10 |  |  | 2024-06-27 | Mass Excavation works | AU | 1 | 1786000 | 1786000 | 1875300 | 84788.1 | 89027.5 | 1701211.9 | 84788.1 | 89027.5 | ZSER | 2024-06-24 | 2024-08-24
RE/0066-PRJ-NT-CIV-EW | Earthwork | 2010 | GR01 | 2010 | SMARTWORLD THE EDITION | Ahluwalia Contracts India Limited | 9140000321 | 10 |  |  | 2024-07-20 | SITE DEVLOPMENT AND EARTH WORK | AU | 1 | 0 | 33610174 | 39660005.32 | 2242108.27 | 2645687.76 | 31368065.73 | 1948808.7 | 2299594.27 | ZSER | 2024-07-15 | 2027-01-14
RE/0066-PRJ-NT-CIV-EW | Earthwork | 2010 | GR01 | 2010 | SMARTWORLD THE EDITION | K.K. Infrastructure Company | 9140000378 | 10 |  |  | 2024-07-23 | Mass Excavation works | AU | 1 | 2393837.33 | 2393837.33 | 2824728.05 | 2393837.33 | 2824728.05 | 0 | 2393837.33 | 2824728.05 | ZSER | 2024-07-23 | 2024-09-14
RE/0066-PRJ-NT-CIV-EW | Earthwork | 2010 | GR01 | 2010 | SMARTWORLD THE EDITION | SUKHRAM EARTH MOVERSSukhram | 9140000573 | 10 |  |  | 2026-02-16 | Supply of Earth brought from outside | AU | 1 | 3375000 | 3375000 | 3982500 | 0 | 0 | 3375000 | 0 | 0 | ZSER | 2026-02-11 | 2026-08-11
RE/0066-PRJ-NT-CIV-MS | Misc Structure Works | 2010 | GR01 | 2010 | SMARTWORLD THE EDITION | Ahluwalia Contracts India Limited | 9140000321 | 100 |  |  | 2024-07-20 | STRUCTURAL STEEL WORKS | AU | 1 | 0 | 17974885.38 | 21210364.75 | 3777070 | 4456942.6 | 14197815.38 | 3749295 | 4424168.1 | ZSER | 2024-07-15 | 2027-01-14
RE/0066-PRJ-NT-CIV-MS | Misc Structure Works | 2010 | GR01 | 2010 | SMARTWORLD THE EDITION | Ahluwalia Contracts India Limited | 9140000321 | 130 |  |  | 2024-07-20 | INTERNAL & EXTERNAL PLASTERING | AU | 1 | 0 | 751800 | 887124 | 0 | 0 | 751800 | 0 | 0 | ZSER | 2024-07-15 | 2027-01-14
RE/0066-PRJ-NT-CIV-MW | Masonry Works | 2010 | GR01 | 2010 | SMARTWORLD THE EDITION | Ahluwalia Contracts India Limited | 9140000321 | 90 |  |  | 2024-07-20 | MASONARY WORKS | AU | 1 | 0 | 11209100 | 13226738 | 0 | 0 | 11209100 | 0 | 0 | ZSER | 2024-07-15 | 2027-01-14
RE/0066-PRJ-NT-CIV-PW-IP | Internal Plaster | 2010 | GR01 | 2010 | SMARTWORLD THE EDITION | Ahluwalia Contracts India Limited | 9140000321 | 130 |  |  | 2024-07-20 | INTERNAL & EXTERNAL PLASTERING | AU | 1 | 0 | 20020353 | 23624016.54 | 0 | 0 | 20020353 | 0 | 0 | ZSER | 2024-07-15 | 2027-01-14
RE/0066-PRJ-NT-CIV-PW-XP | External Plaster | 2010 | GR01 | 2010 | SMARTWORLD THE EDITION | Ahluwalia Contracts India Limited | 9140000321 | 130 |  |  | 2024-07-20 | INTERNAL & EXTERNAL PLASTERING | AU | 1 | 0 | 100400 | 118472 | 0 | 0 | 100400 | 0 | 0 | ZSER | 2024-07-15 | 2027-01-14
RE/0066-PRJ-NT-CIV-RS-LA | Reinforcement Labour | 2010 | GR01 | 2010 | SMARTWORLD THE EDITION | Ahluwalia Contracts India Limited | 9140000321 | 70 |  |  | 2024-07-20 | REINFORCEMENT STEEL Installation Part A | AU | 1 | 0 | 157769735.84 | 186168288.29 | 74535322.03 | 87951679.99 | 83234413.81 | 70415583.85 | 83090388.94 | ZSER | 2024-07-15 | 2027-01-14
RE/0066-PRJ-NT-CIV-RS-LA | Reinforcement Labour | 2010 | GR01 | 2010 | SMARTWORLD THE EDITION | Ahluwalia Contracts India Limited | 9140000321 | 80 |  |  | 2024-07-20 | REINFORCEMENT STEEL Installation Part B | AU | 1 | 0 | 21316332.89 | 25153272.81 | 2306690 | 2721894.2 | 19009642.89 | 1956055 | 2308144.9 | ZSER | 2024-07-15 | 2027-01-14
RE/0066-PRJ-NT-CIV-RS-SU | Reinforcement Supply | 2010 | GR01 | 2010 | SMARTWORLD THE EDITION | JINDAL STEEL LIMITEDMr Robin Taneja | 9110000725 | 60 |  |  | 2024-10-10 | Fe 550D TMT Steel 16MM | TO | 20 | 53500 | 1070000 | 1262600 | 1070000 | 1262600 | 0 | 1070000 | 1262600 | ZMAT | 2025-01-20 | 2025-03-20
RE/0066-PRJ-NT-CIV-RS-SU | Reinforcement Supply | 2010 | GR01 | 2010 | SMARTWORLD THE EDITION | Carna Corporation Pvt LtdVISHWANATH | 9110000726 | 30 |  |  | 2024-10-11 | Fe 550D TMT Steel 10 MM | TO | 57 | 54250 | 3092250 | 3648855 | 2515464 | 2968247.52 | 576786 | 2515464 | 2968247.51 | ZMAT | 2024-10-11 | 2024-11-11
RE/0066-PRJ-NT-CIV-RS-SU | Reinforcement Supply | 2010 | GR01 | 2010 | SMARTWORLD THE EDITION | Northern Steel and General MillsPrivate Limited | 9110000774 | 50 |  |  | 2024-11-15 | Steel Re-bar TMT 16 mm Dia. FE-550D | TO | 50 | 54500 | 2725000 | 3215500 | 2653060 | 3130610.8 | 71940 | 2653060 | 3130610.8 | ZMAT | 2025-01-20 | 2025-03-20
RE/0066-PRJ-NT-CIV-RS-SU | Reinforcement Supply | 2010 | GR01 | 2010 | SMARTWORLD THE EDITION | Northern Steel and General MillsPrivate Limited | 9110000774 | 120 |  |  | 2024-11-15 | Steel Re-bar TMT 20 mm Dia. FE-550D | TO | 9 | 54500 | 490500 | 578790 | 497585 | 587150.3 | 7085 | 497585 | 587150.3 | ZMAT | 2025-01-20 | 2025-03-20
RE/0066-PRJ-NT-CIV-RS-SU | Reinforcement Supply | 2010 | GR01 | 2010 | SMARTWORLD THE EDITION | Northern Steel and General MillsPrivate Limited | 9110000774 | 190 |  |  | 2024-11-15 | Steel Re-bar TMT 25 mm Dia. FE-550D | TO | 33 | 54500 | 1798500 | 2122230 | 1750540 | 2065637.2 | 47960 | 1750540 | 2065637.2 | ZMAT | 2025-01-20 | 2025-03-20
RE/0066-PRJ-NT-CIV-RS-SU | Reinforcement Supply | 2010 | GR01 | 2010 | SMARTWORLD THE EDITION | Jindal Steel Limited | 9110000777 | 70 |  |  | 2024-11-15 | Steel Re-bar TMT 20 mm Dia. FE-550D | TO | 12 | 54500 | 654000 | 771720 | 654000 | 771720 | 0 | 654000 | 771720 | ZMAT | 2025-01-20 | 2025-03-20
RE/0066-PRJ-NT-CIV-RS-SU | Reinforcement Supply | 2010 | GR01 | 2010 | SMARTWORLD THE EDITION | Jindal Steel Limited | 9110000777 | 140 |  |  | 2024-11-15 | Steel Re-bar TMT 25 mm Dia. FE-550D | TO | 24 | 54500 | 1308000 | 1543440 | 1271158 | 1499966.44 | 36842 | 1271158 | 1499966.44 | ZMAT | 2025-01-20 | 2025-03-20
RE/0066-PRJ-NT-CIV-RS-SU | Reinforcement Supply | 2010 | GR01 | 2010 | SMARTWORLD THE EDITION | Jindal Steel Limited | 9110000777 | 210 |  |  | 2024-11-15 | Steel Re-bar TMT 32 mm Dia. FE-550D | TO | 2 | 54500 | 109000 | 128620 | 0 | 0 | 109000 | 0 | 0 | ZMAT | 2025-01-20 | 2025-03-20
RE/0066-PRJ-NT-CIV-RS-SU | Reinforcement Supply | 2010 | GR01 | 2010 | SMARTWORLD THE EDITION | Carna Corporation Pvt LtdVISHWANATH | 9110000779 | 70 |  |  | 2024-11-16 | Steel Re-bar TMT 20 mm Dia. FE-550D | TO | 10 | 54500 | 545000 | 643100 | 389675 | 459816.5 | 155325 | 389675 | 459816.5 | ZMAT | 2025-01-20 | 2025-03-20
RE/0066-PRJ-NT-CIV-RS-SU | Reinforcement Supply | 2010 | GR01 | 2010 | SMARTWORLD THE EDITION | Carna Corporation Pvt LtdVISHWANATH | 9110000779 | 140 |  |  | 2024-11-16 | Steel Re-bar TMT 25 mm Dia. FE-550D | TO | 26 | 54500 | 1417000 | 1672060 | 1417000 | 1672060 | 0 | 1417000 | 1672060 | ZMAT | 2025-01-20 | 2025-03-20
RE/0066-PRJ-NT-CIV-RS-SU | Reinforcement Supply | 2010 | GR01 | 2010 | SMARTWORLD THE EDITION | Carna Corporation Pvt LtdVISHWANATH | 9110000779 | 220 |  |  | 2024-11-16 | Steel Re-bar TMT 12 mm Dia. FE-550D | TO | 103.11 | 54500 | 5619495 | 6631004.1 | 4179278 | 4931548.04 | 1440217 | 4179278 | 4931548.04 | ZMAT | 2025-01-20 | 2025-03-20
RE/0066-PRJ-NT-CIV-RS-SU | Reinforcement Supply | 2010 | GR01 | 2010 | SMARTWORLD THE EDITION | Ram Niwas & SonsDeepak gupta | 9110000782 | 40 |  |  | 2024-11-16 | Steel Re-bar TMT 08 mm Dia. FE-550D | TO | 34 | 52500 | 1785000 | 2106300 | 1753500 | 2069130 | 31500 | 1753500 | 2069130.25 | ZMAT | 2024-11-16 | 2024-12-15
RE/0066-PRJ-NT-CIV-RS-SU | Reinforcement Supply | 2010 | GR01 | 2010 | SMARTWORLD THE EDITION | Rashtriya Ispat Nigam Ltd | 9110000790 | 80 |  |  | 2024-11-29 | Fe 550D TMT Steel Coil 10MM | TO | 58 | 54450 | 3158100 | 3726558 | 3158100 | 3726558 | 0 | 3158100 | 3726558.02 | ZMAT | 2024-11-29 | 2024-12-28
RE/0066-PRJ-NT-CIV-RS-SU | Reinforcement Supply | 2010 | GR01 | 2010 | SMARTWORLD THE EDITION | Rashtriya Ispat Nigam Ltd | 9110000790 | 150 |  |  | 2024-11-29 | Fe 550D TMT Steel Coil 12MM | TO | 17 | 53950 | 917150 | 1082237 | 809250 | 954915 | 107900 | 809250 | 954915 | ZMAT | 2024-11-29 | 2024-12-28
RE/0066-PRJ-NT-CIV-RS-SU | Reinforcement Supply | 2010 | GR01 | 2010 | SMARTWORLD THE EDITION | Jindal Steel Limited | 9110000820 | 30 |  |  | 2024-10-10 | Fe 550D TMT Steel 12MM | TO | 8 | 53500 | 428000 | 505040 | 428000 | 505040 | 0 | 428000 | 505040 | ZMAT | 2025-01-20 | 2025-03-20
RE/0066-PRJ-NT-CIV-RS-SU | Reinforcement Supply | 2010 | GR01 | 2010 | SMARTWORLD THE EDITION | Jindal Steel Limited | 9110000820 | 60 |  |  | 2024-10-10 | Fe 550D TMT Steel 16MM | TO | 7 | 53500 | 374500 | 441910 | 293822 | 346709.96 | 80678 | 293822 | 346709.96 | ZMAT | 2025-01-20 | 2025-03-20
RE/0066-PRJ-NT-CIV-RS-SU | Reinforcement Supply | 2010 | GR01 | 2010 | SMARTWORLD THE EDITION | Jindal Steel Limited | 9110000820 | 90 |  |  | 2024-10-10 | Fe 550D TMT Steel 20MM | TO | 47.5 | 53500 | 2541250 | 2998675 | 2498396.5 | 2948107.87 | 42853.5 | 2498396.5 | 2948107.87 | ZMAT | 2025-01-20 | 2025-03-20
RE/0066-PRJ-NT-CIV-RS-SU | Reinforcement Supply | 2010 | GR01 | 2010 | SMARTWORLD THE EDITION | Jindal Steel Limited | 9110000820 | 120 |  |  | 2024-10-10 | Fe 550D TMT Steel 25MM | TO | 12.5 | 53500 | 668750 | 789125 | 460421 | 543296.78 | 208329 | 460421 | 543296.78 | ZMAT | 2025-01-20 | 2025-03-20
RE/0066-PRJ-NT-CIV-RS-SU | Reinforcement Supply | 2010 | GR01 | 2010 | SMARTWORLD THE EDITION | Carna Corporation Pvt LtdVISHWANATH | 9110000837 | 50 |  |  | 2025-01-09 | Steel Re-bar TMT 08 mm Dia. FE-550D | TO | 25 | 51400 | 1285000 | 1516300 | 1025275.8 | 1209825.44 | 259724.2 | 1025275.8 | 1209825.44 | ZMAT | 2025-01-20 | 2025-03-20
RE/0066-PRJ-NT-CIV-RS-SU | Reinforcement Supply | 2010 | GR01 | 2010 | SMARTWORLD THE EDITION | Carna Corporation Pvt LtdVISHWANATH | 9110000837 | 100 |  |  | 2025-01-09 | Steel Re-bar TMT 10 mm Dia. FE-550D | TO | 41 | 50150 | 2056150 | 2426257 | 2056150 | 2426257 | 0 | 2056150 | 2426257 | ZMAT | 2025-01-20 | 2025-03-20
RE/0066-PRJ-NT-CIV-RS-SU | Reinforcement Supply | 2010 | GR01 | 2010 | SMARTWORLD THE EDITION | Jindal Steel Limited | 9110000859 | 50 |  |  | 2025-02-15 | Steel Re-bar TMT 16 mm Dia. FE-550D | TO | 16 | 50900 | 814400 | 960992 | 690169.49 | 814400 | 124230.51 | 814400 | 960992 | ZMAT
RE/0066-PRJ-NT-CIV-RS-SU | Reinforcement Supply | 2010 | GR01 | 2010 | SMARTWORLD THE EDITION | Jindal Steel Limited | 9110000859 | 80 |  |  | 2025-02-15 | Steel Re-bar TMT 20 mm Dia. FE-550D | TO | 42 | 50900 | 2137800 | 2522604 | 1749320.85 | 2064198.6 | 388479.15 | 2064198.6 | 2435754.35 | ZMAT
RE/0066-PRJ-NT-CIV-RS-SU | Reinforcement Supply | 2010 | GR01 | 2010 | SMARTWORLD THE EDITION | Ram Niwas & SonsDeepak gupta | 9110000862 | 90 |  |  | 2025-02-15 | Steel Re-bar TMT 10 mm Dia. FE-550D | TO | 34 | 50200 | 1706800 | 2014024 | 1650576 | 1947679.68 | 56224 | 1650576 | 1947679.68 | ZMAT
RE/0066-PRJ-NT-CIV-RS-SU | Reinforcement Supply | 2010 | GR01 | 2010 | SMARTWORLD THE EDITION | PRAGYAN METALS PRIVATE LIMITED | 9110000868 | 30 |  |  | 2025-02-18 | Steel Re-bar TMT 16 mm Dia. FE-550D | TO | 9 | 50900 | 458100 | 540558 | 379377.54 | 447665.5 | 78722.46 | 447665.5 | 528245.3 | ZMAT
RE/0066-PRJ-NT-CIV-RS-SU | Reinforcement Supply | 2010 | GR01 | 2010 | SMARTWORLD THE EDITION | Rashtriya Ispat Nigam Ltd | 9110000961 | 70 |  |  | 2025-04-08 | Fe 550D TMT Steel Coil 10MM | TO | 6 | 58750 | 352500 | 415950 | 344275 | 406244.5 | 8225 | 344275 | 406244.52 | ZMAT
RE/0066-PRJ-NT-CIV-RS-SU | Reinforcement Supply | 2010 | GR01 | 2010 | SMARTWORLD THE EDITION | Rashtriya Ispat Nigam Ltd | 9110000961 | 140 |  |  | 2025-04-08 | Fe 550D TMT Steel Coil 08MM | TO | 6 | 60000 | 360000 | 424800 | 381600 | 450288 | 21600 | 381600 | 450288 | ZMAT
RE/0066-PRJ-NT-CIV-RS-SU | Reinforcement Supply | 2010 | GR01 | 2010 | SMARTWORLD THE EDITION | Vikrant Ispat Udyog | 9110000966 | 70 |  |  | 2025-04-09 | Fe 550D TMT Steel Coil 10MM | TO | 2 | 64250 | 128500 | 151630 | 132676.25 | 156557.98 | 4176.25 | 132676.25 | 156557.98 | ZMAT
RE/0066-PRJ-NT-CIV-RS-SU | Reinforcement Supply | 2010 | GR01 | 2010 | SMARTWORLD THE EDITION | Vikrant Ispat Udyog | 9110000966 | 140 |  |  | 2025-04-09 | Fe 550D TMT Steel Coil 08MM | TO | 2 | 65750 | 131500 | 155170 | 128541.25 | 151678.68 | 2958.75 | 128541.25 | 151678.68 | ZMAT
RE/0066-PRJ-NT-CIV-RS-SU | Reinforcement Supply | 2010 | GR01 | 2010 | SMARTWORLD THE EDITION | Jindal Steel Limited | 9110001127 | 80 |  |  | 2025-06-20 | Steel Re-bar TMT 12 mm Dia. FE-550D | TO | 35 | 50600 | 1771000 | 2089780 | 1516886.8 | 1789926.42 | 254113.2 | 1516886.8 | 1789926.42 | ZMAT | 2025-06-20 | 2025-07-20
RE/0066-PRJ-NT-CIV-RS-SU | Reinforcement Supply | 2010 | GR01 | 2010 | SMARTWORLD THE EDITION | Jindal Steel Limited | 9110001127 | 160 |  |  | 2025-06-20 | Steel Re-bar TMT 16 mm Dia. FE-550D | TO | 25 | 50600 | 1265000 | 1492700 | 1265000 | 1492700 | 0 | 1265000 | 1492700 | ZMAT | 2025-06-20 | 2025-07-20
RE/0066-PRJ-NT-CIV-RS-SU | Reinforcement Supply | 2010 | GR01 | 2010 | SMARTWORLD THE EDITION | Jindal Steel Limited | 9110001127 | 310 |  |  | 2025-06-20 | Steel Re-bar TMT 32 mm Dia. FE-550D | TO | 10 | 50600 | 506000 | 597080 | 506000 | 597080 | 0 | 506000 | 597080 | ZMAT | 2025-06-20 | 2025-07-20
RE/0066-PRJ-NT-CIV-RS-SU | Reinforcement Supply | 2010 | GR01 | 2010 | SMARTWORLD THE EDITION | Rashtriya Ispat Nigam Ltd | 9110001138 | 10 |  |  | 2025-06-24 | Fe 550D TMT Steel Coil 08MM | TO | 35 | 55500 | 1942500 | 2292150 | 0 | 0 | 1942500 | 0 | 0 | ZMAT | 2025-06-24 | 2025-07-24
RE/0066-PRJ-NT-CIV-RS-SU | Reinforcement Supply | 2010 | GR01 | 2010 | SMARTWORLD THE EDITION | Jindal Steel Limited | 9110001162 | 80 |  |  | 2025-07-17 | Steel Re-bar TMT 10 mm Dia. FE-550D | TO | 55 | 47500 | 2612500 | 3082750 | 0 | 0 | 2612500 | 0 | 0 | ZMAT | 2025-07-17 | 2025-08-17
RE/0066-PRJ-NT-CIV-RS-SU | Reinforcement Supply | 2010 | GR01 | 2010 | SMARTWORLD THE EDITION | Jindal Steel Limited | 9110001162 | 370 |  |  | 2025-07-17 | Steel Re-bar TMT 25 mm Dia. FE-550D | TO | 5 | 46500 | 232500 | 274350 | 0 | 0 | 232500 | 0 | 0 | ZMAT | 2025-07-17 | 2025-08-17
RE/0066-PRJ-NT-CIV-RS-SU | Reinforcement Supply | 2010 | GR01 | 2010 | SMARTWORLD THE EDITION | Jindal Steel Limited | 9110001162 | 440 |  |  | 2025-07-17 | Steel Re-bar TMT 32 mm Dia. FE-550D | TO | 5 | 46500 | 232500 | 274350 | 0 | 0 | 232500 | 0 | 0 | ZMAT | 2025-07-17 | 2025-08-17
RE/0066-PRJ-NT-CIV-RS-SU | Reinforcement Supply | 2010 | GR01 | 2010 | SMARTWORLD THE EDITION | Steel Authority Of India LTD | 9110001203 | 10 |  |  | 2025-08-13 | Steel Re-bar TMT 32 mm Dia. FE-550D | TO | 30 | 47900 | 1437000 | 1695660 | 1402033 | 1654398.94 | 34967 | 1402033 | 1654398.94 | ZMAT
RE/0066-PRJ-NT-CIV-RS-SU | Reinforcement Supply | 2010 | GR01 | 2010 | SMARTWORLD THE EDITION | Petropol India LimitedSANJAY GUPTA | 9110001204 | 10 |  |  | 2025-08-13 | Steel Re-bar TMT 10 mm Dia. FE-550D | TO | 150 | 48000 | 7200000 | 8496000 | 7171680 | 8462582.4 | 28320 | 7171680 | 8462582.4 | ZMAT
RE/0066-PRJ-NT-CIV-RS-SU | Reinforcement Supply | 2010 | GR01 | 2010 | SMARTWORLD THE EDITION | Rashtriya Ispat Nigam Ltd | 9110001219 | 10 |  |  | 2025-08-19 | Fe 550D TMT Steel Coil 10MM | TO | 35 | 47200 | 1652000 | 1949360 | 0 | 0 | 1652000 | 0 | 0 | ZMAT | 2025-08-19 | 2025-09-19
RE/0066-PRJ-NT-CIV-RS-SU | Reinforcement Supply | 2010 | GR01 | 2010 | SMARTWORLD THE EDITION | Steel Authority Of India LTD | 9110001280 | 370 |  |  | 2025-09-18 | Steel Re-bar TMT 25 mm Dia. FE-550D | TO | 11.69 | 46260 | 540779.4 | 638119.69 | 540779.41 | 638119.7 | 0.01 | 540779.4 | 638119.7 | ZMAT | 2025-09-18 | 2025-10-18
RE/0066-PRJ-NT-CIV-RS-SU | Reinforcement Supply | 2010 | GR01 | 2010 | SMARTWORLD THE EDITION | Sapcon Steels Private Limited | 9110001317 | 40 |  |  | 2025-10-10 | Fe 550D TMT Steel Coil 10MM | TO | 51.5 | 47500 | 2446250 | 2886575 | 1541850 | 1819383 | 904400 | 1541850 | 1819383 | ZMAT | 2025-10-10 | 2025-11-10
RE/0066-PRJ-NT-CIV-RS-SU | Reinforcement Supply | 2010 | GR01 | 2010 | SMARTWORLD THE EDITION | Ram Niwas & SonsDeepak gupta | 9110001362 | 130 |  |  | 2025-11-07 | Steel Re-bar TMT 08 mm Dia. FE-550D | TO | 19.99 | 46900 | 937531 | 1106286.58 | 937531 | 1106286.58 | 0 | 937531 | 1106286.58 | ZMAT | 2025-11-07 | 2025-12-07
RE/0066-PRJ-NT-CIV-RS-SU | Reinforcement Supply | 2010 | GR01 | 2010 | SMARTWORLD THE EDITION | Ram Niwas & SonsDeepak gupta | 9110001362 | 140 |  |  | 2025-11-07 | Steel Re-bar TMT 08 mm Dia. FE-550D | TO | 70.87 | 46900 | 3323803 | 3922087.54 | 3323803 | 3922087.54 | 0 | 3323803 | 3922087.54 | ZMAT | 2025-11-07 | 2025-12-07
RE/0066-PRJ-NT-CIV-RS-SU | Reinforcement Supply | 2010 | GR01 | 2010 | SMARTWORLD THE EDITION | Ram Niwas & SonsDeepak gupta | 9110001421 | 130 |  |  | 2025-12-10 | 08 mm AMD QTY PO No. 9110001421 | TO | 170 | 47500 | 8075000 | 9528500 | 3590050 | 4236259 | 4484950 | 3590050 | 4236259 | ZMAT | 2025-12-10 | 2026-01-10
RE/0066-PRJ-NT-CIV-RS-SU | Reinforcement Supply | 2010 | GR01 | 2010 | SMARTWORLD THE EDITION | Ram Niwas & SonsDeepak gupta | 9110001471 | 130 |  |  | 2026-01-12 | 08 mm AMD QTY PO No. 9110001471 | TO | 42 | 52000 | 2184000 | 2577120 | 1718080 | 2027334.4 | 465920 | 1718080 | 2027334.4 | ZMAT | 2026-01-12 | 2026-02-12
RE/0066-PRJ-NT-CIV-RS-SU | Reinforcement Supply | 2010 | GR01 | 2010 | SMARTWORLD THE EDITION | Jindal Steel Limited | 9110001557 | 170 |  |  | 2026-02-10 | Steel Re-bar TMT 20 mm Dia. FE-550D | TO | 125 | 58500 | 7312500 | 8628750 | 7275060 | 8584570.8 | 37440 | 7275060 | 8584570.8 | ZMAT | 2026-02-10 | 2026-03-10
RE/0066-PRJ-NT-CIV-RS-SU | Reinforcement Supply | 2010 | GR01 | 2010 | SMARTWORLD THE EDITION | Petropol India LimitedSANJAY GUPTA | 9110001575 | 10 |  |  | 2026-02-17 | 08 mm | TO | 140 | 55300 | 7742000 | 9135560 | 7675087 | 9056602.66 | 66913 | 7675087 | 9056602.66 | ZMAT | 2026-02-17 | 2026-03-17
RE/0066-PRJ-NT-CIV-RS-SU | Reinforcement Supply | 2010 | GR01 | 2010 | SMARTWORLD THE EDITION | Petropol India LimitedSANJAY GUPTA | 9110001575 | 20 |  |  | 2026-02-17 | 10 mm | TO | 280 | 54300 | 15204000 | 17940720 | 15184452 | 17917653.36 | 19548 | 15184452 | 17917653.36 | ZMAT | 2026-02-17 | 2026-03-17
RE/0066-PRJ-NT-CIV-SW-CS | Conventional Shuttering | 2010 | GR01 | 2010 | SMARTWORLD THE EDITION | Ahluwalia Contracts India Limited | 9140000321 | 50 |  |  | 2024-07-20 | CENTERING & SHUTTERING Part A | AU | 1 | 0 | 136730910.6 | 161342474.51 | 65657547.27 | 77475905.78 | 71073363.33 | 62807028.01 | 74112293.05 | ZSER | 2024-07-15 | 2027-01-14
RE/0066-PRJ-NT-CIV-SW-SO | Shuttering Other | 2010 | GR01 | 2010 |  |  |  | 0 | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
RE/0066-PRJ-NT-CIV-WP | Waterproofing Works | 2010 | GR01 | 2010 | SMARTWORLD THE EDITION | Ahluwalia Contracts India Limited | 9140000321 | 110 |  |  | 2024-07-20 | FLOORING | AU | 1 | 0 | 2864.57 | 3380.19 | 0 | 0 | 2864.57 | 0 | 0 | ZSER | 2024-07-15 | 2027-01-14
RE/0066-PRJ-NT-CIV-WP | Waterproofing Works | 2010 | GR01 | 2010 | SMARTWORLD THE EDITION | Ahluwalia Contracts India Limited | 9140000321 | 120 |  |  | 2024-07-20 | WATER-PROOFING WORKS | AU | 1 | 0 | 44274291 | 52243663.38 | 2364480.14 | 2790086.56 | 41909810.86 | 1929123.25 | 2276365.44 | ZSER | 2024-07-15 | 2027-01-14
RE/0066-PRJ-NT-FAC-EF | Glazing Works | 2010 | GR01 | 2010 |  |  |  | 0 | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
RE/0066-PRJ-NT-FAC-EP | Railing Works | 2010 | GR01 | 2010 |  |  |  | 0 | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
RE/0066-PRJ-NT-FAC-GL | External Paint | 2010 | GR01 | 2010 |  |  |  | 0 | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
RE/0066-PRJ-NT-FAC-RA | Elevation Feature | 2010 | GR01 | 2010 |  |  |  | 0 | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
RE/0066-PRJ-NT-FIS-CF | Ceiling Finish Works | 2010 | GR01 | 2010 | SMARTWORLD THE EDITION | Sanrachna InteriorsMANOJ GOEL | 9140000595 | 10 |  |  | 2026-03-05 | Basement Painting Work | AU | 1 | 19409000 | 13189000 | 15563020 | 0 | 0 | 13189000 | 0 | 0 | ZSER | 2026-02-26 | 2027-02-26
RE/0066-PRJ-NT-FIS-DW | Door Works | 2010 | GR01 | 2010 |  |  |  | 0 | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
RE/0066-PRJ-NT-FIS-FF | Floor Finish Works | 2010 | GR01 | 2010 | SMARTWORLD THE EDITION | Ahluwalia Contracts India Limited | 9140000321 | 110 |  |  | 2024-07-20 | FLOORING | AU | 1 | 0 | 202628 | 239101.04 | 0 | 0 | 202628 | 0 | 0 | ZSER | 2024-07-15 | 2027-01-14
RE/0066-PRJ-NT-FIS-LF | Lobby Furniture | 2010 | GR01 | 2010 |  |  |  | 0 | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
RE/0066-PRJ-NT-FIS-MI | Misc Finish Works | 2010 | GR01 | 2010 |  |  |  | 0 | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
RE/0066-PRJ-NT-FIS-MK | Modular Kitchen Works | 2010 | GR01 | 2010 |  |  |  | 0 | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
RE/0066-PRJ-NT-FIS-MS | MS works | 2010 | GR01 | 2010 |  |  |  | 0 | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
RE/0066-PRJ-NT-FIS-TF | Trimix Flooring | 2010 | GR01 | 2010 | SMARTWORLD THE EDITION | Ahluwalia Contracts India Limited | 9140000321 | 110 |  |  | 2024-07-20 | FLOORING | AU | 1 | 0 | 10125328.9 | 11947888.1 | 938858.05 | 1107852.5 | 9186470.85 | 47888.29 | 56508.18 | ZSER | 2024-07-15 | 2027-01-14
RE/0066-PRJ-NT-FIS-TF | Trimix Flooring | 2010 | GR01 | 2010 | SMARTWORLD THE EDITION | Ahluwalia Contracts India Limited | 9140000321 | 180 |  |  | 2024-07-20 | SUBSTITUTE ITEM | AU | 1 | 0 | 79320300 | 93597954 | 6694581.98 | 7899606.74 | 72625718.02 | 0 | 0 | ZSER | 2024-07-15 | 2027-01-14
RE/0066-PRJ-NT-FIS-WF | Wall Finish Works | 2010 | GR01 | 2010 | SMARTWORLD THE EDITION | Sanrachna InteriorsMANOJ GOEL | 9140000595 | 10 |  |  | 2026-03-05 | Basement Painting Work | AU | 1 | 0 | 6220000 | 7339600 | 0 | 0 | 6220000 | 0 | 0 | ZSER | 2026-02-26 | 2027-02-26
RE/0066-PRJ-NT-FIS-WO | Wood Work | 2010 | GR01 | 2010 |  |  |  | 0 | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
RE/0066-PRJ-NT-MEP-EW-HE | High Side Electrical Works | 2010 | GR01 | 2010 | SMARTWORLD THE EDITION | SATKARTAR ELECTRICALS AND ELECTRONIPRIVATE LIMITED | 9140000677 | 70 |  |  | 2026-06-02 | Electrical Works -NTA ( Basement ) | AU | 1 | 149167622.48 | 73966812.92 | 87280839.25 | 0 | 0 | 73966812.92 | 0 | 0 | ZSER | 2026-06-01 | 2028-02-01
RE/0066-PRJ-NT-MEP-EW-LE | Low Side Electrical Works | 2010 | GR01 | 2010 | SMARTWORLD THE EDITION | Ahluwalia Contracts India Limited | 9140000321 | 140 |  |  | 2024-07-20 | CONDUITING | AU | 1 | 0 | 31851037.9 | 37584224.72 | 763344.41 | 900746.4 | 31087693.49 | 0 | 0 | ZSER | 2024-07-15 | 2027-01-14
RE/0066-PRJ-NT-MEP-EW-LE | Low Side Electrical Works | 2010 | GR01 | 2010 | SMARTWORLD THE EDITION | SATKARTAR ELECTRICALS AND ELECTRONIPRIVATE LIMITED | 9140000677 | 70 |  |  | 2026-06-02 | Electrical Works -NTA ( Basement ) | AU | 1 | 0 | 75200809.56 | 88736955.28 | 0 | 0 | 75200809.56 | 0 | 0 | ZSER | 2026-06-01 | 2028-02-01
RE/0066-PRJ-NT-MEP-EW-LS | Light Fixtures Supply | 2010 | GR01 | 2010 |  |  |  | 0 | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
RE/0066-PRJ-NT-MEP-FF | Fire Fighting Work | 2010 | GR01 | 2010 | SMARTWORLD THE EDITION | Jagrati Civil Constructions Pvt Ltd | 9140000633 | 260 |  |  | 2026-04-15 | FF-FIRE HYDRANT & EQUIPMENT SUPPLY- NTA | AU | 1 | 11650650 | 11650650 | 13747767 | 0 | 0 | 11650650 | 0 | 0 | ZSER | 2026-04-08 | 2028-01-31
RE/0066-PRJ-NT-MEP-FF | Fire Fighting Work | 2010 | GR01 | 2010 | SMARTWORLD THE EDITION | Jagrati Civil Constructions Pvt Ltd | 9140000633 | 310 |  |  | 2026-04-15 | FF-AUTOMATIC SPRINKLER & WATER Supply-NT | AU | 1 | 51354000 | 51354000 | 60597720 | 0 | 0 | 51354000 | 0 | 0 | ZSER | 2026-04-08 | 2028-01-31
RE/0066-PRJ-NT-MEP-FF | Fire Fighting Work | 2010 | GR01 | 2010 | SMARTWORLD THE EDITION | Jagrati Civil Constructions Pvt Ltd | 9140000633 | 360 |  |  | 2026-04-15 | FF-PORTABLE FIRE EXTINGUISHERS Supply-NT | AU | 1 | 980500 | 980500 | 1156990 | 0 | 0 | 980500 | 0 | 0 | ZSER | 2026-04-08 | 2028-01-31
RE/0066-PRJ-NT-MEP-FF | Fire Fighting Work | 2010 | GR01 | 2010 | SMARTWORLD THE EDITION | Jagrati Civil Constructions Pvt Ltd | 9140000633 | 370 |  |  | 2026-04-15 | FF-FIRE PUMPS, VALVES & ACCE Supply-NTA | AU | 1 | 13556450 | 13556450 | 15996611 | 0 | 0 | 13556450 | 0 | 0 | ZSER | 2026-04-08 | 2028-01-31
RE/0066-PRJ-NT-MEP-FF | Fire Fighting Work | 2010 | GR01 | 2010 | SMARTWORLD THE EDITION | Jagrati Civil Constructions Pvt Ltd | 9140000633 | 380 |  |  | 2026-04-15 | FF-ELECTRICAL WORK FOR FIRE Supply-NTA | AU | 1 | 8709250 | 8709250 | 10276915 | 0 | 0 | 8709250 | 0 | 0 | ZSER | 2026-04-08 | 2028-01-31
RE/0066-PRJ-NT-MEP-FF | Fire Fighting Work | 2010 | GR01 | 2010 | SMARTWORLD THE EDITION | Atom MEP Engineers Pvt. Ltd. | 9140000668 | 290 |  |  | 2026-05-19 | FF-FIRE HYDRANT & EQUIPMENT .- NTA | AU | 1 | 7725703 | 7725703 | 9116329.54 | 0 | 0 | 7725703 | 0 | 0 | ZSER | 2026-04-04 | 2028-02-04
RE/0066-PRJ-NT-MEP-FF | Fire Fighting Work | 2010 | GR01 | 2010 | SMARTWORLD THE EDITION | Atom MEP Engineers Pvt. Ltd. | 9140000668 | 340 |  |  | 2026-05-19 | FF-AUTOMATIC SPRINKLER & WATER .-NTA | AU | 1 | 29928614 | 29928614 | 35315764.52 | 0 | 0 | 29928614 | 0 | 0 | ZSER | 2026-04-04 | 2028-02-04
RE/0066-PRJ-NT-MEP-FF | Fire Fighting Work | 2010 | GR01 | 2010 | SMARTWORLD THE EDITION | Atom MEP Engineers Pvt. Ltd. | 9140000668 | 390 |  |  | 2026-05-19 | FF-PORTABLE FIRE EXTINGUISHERS -NTA | AU | 1 | 682800 | 682800 | 805704 | 0 | 0 | 682800 | 0 | 0 | ZSER | 2026-04-04 | 2028-02-04
RE/0066-PRJ-NT-MEP-HV-HS | Basement Ventilation-High Side | 2010 | GR01 | 2010 | SMARTWORLD THE EDITION | Accumen | 9140000634 | 10 |  |  | 2026-04-15 | SITC of Ventilation Work-Basement & Towe | AU | 1 | 136304092 | 136304092 | 160838828.56 | 0 | 0 | 136304092 | 0 | 0 | ZSER | 2026-04-15 | 2026-05-15
RE/0066-PRJ-NT-MEP-HV-HS | Basement Ventilation-High Side | 2010 | GR01 | 2010 | SMARTWORLD THE EDITION | Accumen | 9140000634 | 20 |  |  | 2026-04-15 | SITC of Ventilation Work-EWS | AU | 1 | 6695908 | 6695908 | 7901171.44 | 0 | 0 | 6695908 | 0 | 0 | ZSER | 2026-04-15 | 2026-05-15
RE/0066-PRJ-NT-MEP-HV-LS | Low Side | 2010 | GR01 | 2010 |  |  |  | 0 | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
RE/0066-PRJ-NT-MEP-PB-EP | External Plumbing | 2010 | GR01 | 2010 |  |  |  | 0 | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
RE/0066-PRJ-NT-MEP-PB-IP | Internal Plumbing | 2010 | GR01 | 2010 | SMARTWORLD THE EDITION | Jagrati Civil Constructions Pvt Ltd | 9140000633 | 50 |  |  | 2026-04-15 | SANITARY FIXTURES & FITTINGS NTA Area | AU | 1 | 38725 | 38725 | 45695.5 | 0 | 0 | 38725 | 0 | 0 | ZSER | 2026-04-08 | 2028-01-31
RE/0066-PRJ-NT-MEP-PB-IP | Internal Plumbing | 2010 | GR01 | 2010 | SMARTWORLD THE EDITION | Jagrati Civil Constructions Pvt Ltd | 9140000633 | 100 |  |  | 2026-04-15 | INTERNAL DRAINAGE SUPPLY(SOIL, WASTE NTA | AU | 1 | 15849420 | 15849420 | 18702315.6 | 0 | 0 | 15849420 | 0 | 0 | ZSER | 2026-04-08 | 2028-01-31
RE/0066-PRJ-NT-MEP-PB-IP | Internal Plumbing | 2010 | GR01 | 2010 | SMARTWORLD THE EDITION | Jagrati Civil Constructions Pvt Ltd | 9140000633 | 150 |  |  | 2026-04-15 | DOMESTIC AND FLUSHING WATER SUPPLY NTA | AU | 1 | 854511.96 | 854511.96 | 1008324.11 | 0 | 0 | 854511.96 | 0 | 0 | ZSER | 2026-04-08 | 2028-01-31
RE/0066-PRJ-NT-MEP-PB-IP | Internal Plumbing | 2010 | GR01 | 2010 | SMARTWORLD THE EDITION | Jagrati Civil Constructions Pvt Ltd | 9140000633 | 200 |  |  | 2026-04-15 | WATER SUPPLY, DRAINAGE PUMPS-SUPPLY-NTA | AU | 1 | 15576400 | 15576400 | 18380152 | 0 | 0 | 15576400 | 0 | 0 | ZSER | 2026-04-08 | 2028-01-31
RE/0066-PRJ-NT-MEP-PB-IP | Internal Plumbing | 2010 | GR01 | 2010 | SMARTWORLD THE EDITION | Jagrati Civil Constructions Pvt Ltd | 9140000633 | 210 |  |  | 2026-04-15 | ELECTRICAL WORK FOR PLUMBING-SUPPLY-NTA | AU | 1 | 9223250 | 9223250 | 10883435 | 0 | 0 | 9223250 | 0 | 0 | ZSER | 2026-04-08 | 2028-01-31
RE/0066-PRJ-NT-MEP-PB-IP | Internal Plumbing | 2010 | GR01 | 2010 | SMARTWORLD THE EDITION | Atom MEP Engineers Pvt. Ltd. | 9140000668 | 30 |  |  | 2026-05-19 | SANITARY FIXTURES & FITTINGS NTA Area | AU | 1 | 23285 | 23285 | 27476.3 | 0 | 0 | 23285 | 0 | 0 | ZSER | 2026-04-04 | 2028-02-04
RE/0066-PRJ-NT-MEP-PB-IP | Internal Plumbing | 2010 | GR01 | 2010 | SMARTWORLD THE EDITION | Atom MEP Engineers Pvt. Ltd. | 9140000668 | 80 |  |  | 2026-05-19 | INTERNAL DRAINAGE NTA | AU | 1 | 7401670.24 | 7401670.24 | 8733970.88 | 0 | 0 | 7401670.24 | 0 | 0 | ZSER | 2026-04-04 | 2028-02-04
RE/0066-PRJ-NT-MEP-PB-IP | Internal Plumbing | 2010 | GR01 | 2010 | SMARTWORLD THE EDITION | Atom MEP Engineers Pvt. Ltd. | 9140000668 | 130 |  |  | 2026-05-19 | DOMESTIC AND FLUSHING WATER NTA | AU | 1 | 502022.56 | 502022.56 | 592386.62 | 0 | 0 | 502022.56 | 0 | 0 | ZSER | 2026-04-04 | 2028-02-04
RE/0066-PRJ-NT-MEP-PB-PS | Plumbing Fixtures Supply | 2010 | GR01 | 2010 |  |  |  | 0 | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
RE/0066-PRJ-SE | Short & Excess | 2010 | GR01 | 2010 |  |  |  | 0 | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
RE/0066-PRJ-SI-1 | Site Infrastructure Development | 2010 |  | 2010 | SMARTWORLD THE EDITION | Shree Balaji RMC | 9110000071 | 20 |  |  | 2023-04-14 | Ready Mix Concrete M - 30 | M3 | 263 | 4125 | 1084875 | 1280152.5 | 1084875.81 | 1280153.45 | 0.81 | 1084875 | 1280153 | ZMAT | 2025-01-20 | 2025-03-20
RE/0066-PRJ-SI-1 | Site Infrastructure Development | 2010 |  | 2010 | SMARTWORLD THE EDITION | Shree Balaji RMC | 9110000071 | 30 |  |  | 2023-04-14 | Pumping Charge | M3 | 263 | 200 | 52600 | 62068 | 52600 | 62068 | 0 | 52600 | 62068 | ZMAT | 2025-01-20 | 2025-03-20
RE/0066-PRJ-SI-1 | Site Infrastructure Development | 2010 |  | 2010 | SMARTWORLD THE EDITION | Treis Solutions LLP | 9110000212 | 10 |  |  | 2023-07-24 | Diesel | L | 5000 | 100 | 500000 | 500000 | 0 | 0 | 500000 | 0 | 0 | ZMAT | 2025-01-20 | 2025-03-20
RE/0066-PRJ-SI-1 | Site Infrastructure Development | 2010 |  | 2010 | SMARTWORLD THE EDITION | Sania Enterprises | 9110000256 | 10 |  |  | 2023-08-24 | Safety Shoes | PAA | 15 | 1380 | 20700 | 21735 | 0 | 0 | 20700 | 0 | 0 | ZMAT | 2025-01-20 | 2025-03-20
RE/0066-PRJ-SI-1 | Site Infrastructure Development | 2010 |  | 2010 | SMARTWORLD THE EDITION | Sania Enterprises | 9110000256 | 20 |  |  | 2023-08-24 | Safety Helmet | NO | 15 | 120 | 1800 | 2124 | 0 | 0 | 1800 | 0 | 0 | ZMAT | 2025-01-20 | 2025-03-20
RE/0066-PRJ-SI-1 | Site Infrastructure Development | 2010 |  | 2010 | SMARTWORLD THE EDITION | Sania Enterprises | 9110000256 | 30 |  |  | 2023-08-24 | Reflective Safety Jacket | NO | 15 | 190 | 2850 | 3363 | 0 | 0 | 2850 | 0 | 0 | ZMAT | 2025-01-20 | 2025-03-20
RE/0066-PRJ-SI-1 | Site Infrastructure Development | 2010 |  | 2010 | SMARTWORLD THE EDITION | RKSK SteelRamji gupta | 9110000289 | 10 |  |  | 2023-11-02 | 10mm dia Fe550D | TO | 68.52 | 53400 | 3658968 | 4317582.24 | 3658968 | 4317582.24 | 0 | 3671250 | 4332075 | ZMAT | 2025-01-20 | 2025-03-20
RE/0066-PRJ-SI-1 | Site Infrastructure Development | 2010 |  | 2010 | SMARTWORLD THE EDITION | RKSK SteelRamji gupta | 9110000289 | 20 |  |  | 2023-11-02 | 12mm dia. Fe550D | TO | 100 | 51400 | 5140000 | 6065200 | 5199624 | 6135556.32 | 59624 | 5214530 | 6153145.23 | ZMAT | 2025-01-20 | 2025-03-20
RE/0066-PRJ-SI-1 | Site Infrastructure Development | 2010 |  | 2010 | SMARTWORLD THE EDITION | RKSK SteelRamji gupta | 9110000289 | 30 |  |  | 2023-11-02 | 16mm dia.Fe550D | TO | 205.37 | 52400 | 10761388 | 12698437.84 | 10761388 | 12698437.84 | 0 | 10793876 | 12736773.77 | ZMAT | 2025-01-20 | 2025-03-20
RE/0066-PRJ-SI-1 | Site Infrastructure Development | 2010 |  | 2010 | SMARTWORLD THE EDITION | RKSK SteelRamji gupta | 9110000289 | 40 |  |  | 2023-11-02 | 20mm dia.Fe550D | TO | 142.45 | 52400 | 7464380 | 8807968.4 | 7464380 | 8807968.4 | 0 | 7483768 | 8830846 | ZMAT | 2025-01-20 | 2025-03-20
RE/0066-PRJ-SI-1 | Site Infrastructure Development | 2010 |  | 2010 | SMARTWORLD THE EDITION | RKSK SteelRamji gupta | 9110000290 | 10 |  |  | 2023-11-02 | 8mm dia | TO | 5 | 54400 | 272000 | 320960 | 194208 | 229165.44 | 77792 | 201280 | 237510 | ZMAT | 2025-01-20 | 2025-03-20
RE/0066-PRJ-SI-1 | Site Infrastructure Development | 2010 |  | 2010 | SMARTWORLD THE EDITION | RKSK SteelRamji gupta | 9110000290 | 20 |  |  | 2023-11-02 | 10mm dia | TO | 9 | 53400 | 480600 | 567108 | 479532 | 565847.76 | 1068 | 479532 | 565848 | ZMAT | 2025-01-20 | 2025-03-20
RE/0066-PRJ-SI-1 | Site Infrastructure Development | 2010 |  | 2010 | SMARTWORLD THE EDITION | RKSK SteelRamji gupta | 9110000290 | 30 |  |  | 2023-11-02 | 12mm dia | TO | 9 | 51400 | 462600 | 545868 | 462600 | 545868 | 0 | 462600 | 545868 | ZMAT | 2025-01-20 | 2025-03-20
RE/0066-PRJ-SI-1 | Site Infrastructure Development | 2010 |  | 2010 | SMARTWORLD THE EDITION | RKSK SteelRamji gupta | 9110000290 | 40 |  |  | 2023-11-02 | 16mm dia | TO | 9 | 52400 | 471600 | 556488 | 471600 | 556488 | 0 | 471600 | 556488 | ZMAT | 2025-01-20 | 2025-03-20
RE/0066-PRJ-SI-1 | Site Infrastructure Development | 2010 |  | 2010 | SMARTWORLD THE EDITION | Industrial Safety Hub | 9110000330 | 10 |  |  | 2023-12-20 | Safety Helmet | NO | 30 | 120 | 3600 | 4248 | 3600 | 4248 | 0 | 3600 | 4248 | ZMAT | 2023-12-10 | 2023-12-20
RE/0066-PRJ-SI-1 | Site Infrastructure Development | 2010 |  | 2010 | SMARTWORLD THE EDITION | Industrial Safety Hub | 9110000330 | 20 |  |  | 2023-12-20 | Safety Reflective Jacket | NO | 25 | 270 | 6750 | 7965 | 6750.85 | 7966 | 0.85 | 6750 | 7965 | ZMAT | 2023-12-10 | 2023-12-20
RE/0066-PRJ-SI-1 | Site Infrastructure Development | 2010 |  | 2010 | SMARTWORLD THE EDITION | Industrial Safety Hub | 9110000330 | 30 |  |  | 2023-12-20 | Safety Shoes | PAA | 30 | 890 | 26700 | 31506 | 26700 | 31506 | 0 | 26700 | 31506 | ZMAT | 2023-12-10 | 2023-12-20
RE/0066-PRJ-SI-1 | Site Infrastructure Development | 2010 |  | 2010 | SMARTWORLD THE EDITION | Industrial Safety Hub | 9110000330 | 40 |  |  | 2023-12-20 | FIRE EXTINGUISHER ABC TYPE 4 KG | NO | 5 | 1450 | 7250 | 8555 | 7250.85 | 8556 | 0.85 | 7250 | 8555 | ZMAT | 2023-12-10 | 2023-12-20
RE/0066-PRJ-SI-1 | Site Infrastructure Development | 2010 |  | 2010 | SMARTWORLD THE EDITION | Industrial Safety Hub | 9110000330 | 50 |  |  | 2023-12-20 | FIRE EXTINGUISHER ABC TYPE 2 KG | NO | 2 | 1050 | 2100 | 2478 | 2100 | 2478 | 0 | 2100 | 2478 | ZMAT | 2023-12-10 | 2023-12-20
RE/0066-PRJ-SI-1 | Site Infrastructure Development | 2010 |  | 2010 | SMARTWORLD THE EDITION | Sarthak TradingMr. Monu Tyagi | 9110000588 | 10 |  |  | 2024-06-13 | Potable Water | L | 3653800 | 0.74 | 270381.2 | 270381.2 | 202390 | 202390 | 67991.2 | 202390 | 202390 | ZMAT | 2025-01-20 | 2025-03-20
RE/0066-PRJ-SI-1 | Site Infrastructure Development | 2010 |  | 2010 | SMARTWORLD THE EDITION | Sarthak TradingMr. Monu Tyagi | 9110000588 | 20 |  |  | 2024-06-13 | STP Water | L | 480000 | 0.12 | 57600 | 57600 | 0 | 0 | 57600 | 0 | 0 | ZMAT | 2025-01-20 | 2025-03-20
RE/0066-PRJ-SI-1 | Site Infrastructure Development | 2010 |  | 2010 | SMARTWORLD THE EDITION | NK Electrical | 9140000107 | 10 |  |  | 2023-05-04 | 25 KVA DG Set on Rental | AU | 1 | 163000 | 163000 | 192340 | 151300 | 178534 | 11700 | 151295.51 | 178528.7 | ZSER | 2023-05-03 | 2024-05-02
RE/0066-PRJ-SI-1 | Site Infrastructure Development | 2010 |  | 2010 | SMARTWORLD THE EDITION | NK Electrical | 9140000107 | 30 |  |  | 2023-05-04 | Amednment 1 | AU | 1 | 81000 | 81000 | 95580 | 45900 | 54162 | 35100 | 45900 | 54162 | ZSER | 2023-05-03 | 2024-05-02
RE/0066-PRJ-SI-1 | Site Infrastructure Development | 2010 |  | 2010 | SMARTWORLD THE EDITION | CRB Industry Private LimitedMr. Rajesh Bharadwaj | 9140000109 | 10 |  |  | 2023-05-05 | Supply 6pax Container with Toilet Pantry | AU | 1 | 305000 | 305000 | 359900 | 305000 | 359900 | 0 | 305000 | 359900 | ZSER | 2023-04-28 | 2023-05-31
RE/0066-PRJ-SI-1 | Site Infrastructure Development | 2010 |  | 2010 | SMARTWORLD THE EDITION | M/s Hi-Tech InfraMr. Ajay Bhati | 9140000122 | 10 |  |  | 2023-05-12 | Civil & Structure Show Flat for sec-66 | AU | 1 | 6128511.7 | 6128511.7 | 7231643.81 | 4533458.47 | 5349481 | 1595053.23 | 4533457.71 | 5349480.1 | ZSER | 2023-05-12 | 2023-06-12
RE/0066-PRJ-SI-1 | Site Infrastructure Development | 2010 |  | 2010 | SMARTWORLD THE EDITION | Mahmud Ansari | 9140000168 | 10 |  |  | 2023-06-26 | Tree cutting work | AU | 1 | 310000 | 310000 | 365800 | 300000 | 354000 | 10000 | 300000 | 354000 | ZSER | 2023-06-26 | 2023-07-10
RE/0066-PRJ-SI-1 | Site Infrastructure Development | 2010 |  | 2010 | SMARTWORLD THE EDITION | Reikan Engineering Consultant Pvt L | 9140000191 | 10 |  |  | 2023-07-26 | Site Survey Work for Sector 66 Project. | AU | 1 | 22000 | 22000 | 25960 | 22000 | 25960 | 0 | 22000 | 25960 | ZSER | 2023-07-24 | 2023-08-10
RE/0066-PRJ-SI-1 | Site Infrastructure Development | 2010 |  | 2010 | SMARTWORLD THE EDITION | Daksh Engineers & InteriorsGaurav Mittal | 9140000209 | 10 |  |  | 2023-09-14 | Site Office Civil Foundation Works-Sec66 | AU | 1 | 820190 | 820190 | 967824.2 | 0 | 0 | 820190 | 0 | 0 | ZSER | 2023-09-16 | 2023-10-16
RE/0066-PRJ-SI-1 | Site Infrastructure Development | 2010 |  | 2010 | SMARTWORLD THE EDITION | Haarish Electric vehicles | 9140000210 | 10 |  |  | 2023-09-14 | 1.75mtr Ht Welded WireMesh Fencing Works | AU | 1 | 504866 | 504866 | 595741.88 | 485566.21 | 572968.13 | 19299.79 | 485566.21 | 572968.13 | ZSER | 2023-09-12 | 2023-10-12
RE/0066-PRJ-SI-1 | Site Infrastructure Development | 2010 |  | 2010 | SMARTWORLD THE EDITION | Kanta King | 9140000225 | 10 |  |  | 2023-10-21 | Installation work of weighbridge | AU | 1 | 1360000 | 1360000 | 1604800 | 1360000 | 1604800 | 0 | 1360000 | 1604800 | ZSER | 2023-09-11 | 2023-11-08
RE/0066-PRJ-SI-1 | Site Infrastructure Development | 2010 |  | 2010 | SMARTWORLD THE EDITION | Asia Enviro Lab | 9140000283 | 10 |  |  | 2024-05-08 | Environment Monitoring System | AU | 1 | 16600 | 16600 | 19588 | 6800 | 8024 | 9800 | 6800 | 8024 | ZSER | 2024-04-12 | 2025-04-12
RE/0066-PRJ-SI-1 | Site Infrastructure Development | 2010 |  | 2010 | SMARTWORLD THE EDITION | Cartel Infratech Pvt. Ltd. | 9160000281 | 10 |  |  | 2023-07-31 | SITC OF BOUNDARY & EXTERNAL AREA LIGHTIN | AU | 1 | 1983000 | 1983000 | 2339940 | 863983.38 | 1019500.39 | 1119016.62 | 863984.06 | 1019501.19 | ZGEN | 2023-07-04 | 2023-09-04
RE/0066-PRJ-SI-1 | Site Infrastructure Development | 2010 |  | 2010 | SMARTWORLD THE EDITION | Cartel Infratech Pvt. Ltd. | 9160000281 | 20 |  |  | 2023-07-31 | Amendment to SITC Boundary lighting | AU | 1 | 110500 | 110500 | 130390 | 91000 | 107380 | 19500 | 91000 | 107380 | ZGEN | 2023-07-04 | 2023-09-04
RE/0066-PRJ-T1-CIV-CC-LA | Concrete Labour | 2010 | GR01 | 2010 |  |  |  | 0 | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
RE/0066-PRJ-T1-CIV-CC-SL | Concrete Supply & Labour | 2010 | GR01 | 2010 | SMARTWORLD THE EDITION | Ahluwalia Contracts India Limited | 9140000321 | 20 |  |  | 2024-07-20 | REINFORCED CEMENT CONCRETE-I part A | AU | 1 | 0 | 111354234.42 | 131397996.62 | 61382497.44 | 72431346.98 | 49971736.98 | 61382497.49 | 72431347.04 | ZSER | 2024-07-15 | 2027-01-14
RE/0066-PRJ-T1-CIV-CC-SL | Concrete Supply & Labour | 2010 | GR01 | 2010 | SMARTWORLD THE EDITION | Ahluwalia Contracts India Limited | 9140000321 | 30 |  |  | 2024-07-20 | REINFORCED CEMENT CONCRETE-I Part B | AU | 1 | 0 | 87478224.82 | 103224305.29 | 42556006.98 | 50216088.24 | 44922217.84 | 39411955.53 | 46506107.52 | ZSER | 2024-07-15 | 2027-01-14
RE/0066-PRJ-T1-CIV-CC-SL | Concrete Supply & Labour | 2010 | GR01 | 2010 | SMARTWORLD THE EDITION | Ahluwalia Contracts India Limited | 9140000321 | 40 |  |  | 2024-07-20 | REINFORCED CEMENT CONCRETE-I Part C | AU | 1 | 0 | 114682149.03 | 135324935.86 | 77424491.98 | 91360900.54 | 37257657.05 | 34646521.78 | 40882895.7 | ZSER | 2024-07-15 | 2027-01-14
RE/0066-PRJ-T1-CIV-CC-SL | Concrete Supply & Labour | 2010 | GR01 | 2010 | SMARTWORLD THE EDITION | Ahluwalia Contracts India Limited | 9140000321 | 180 |  |  | 2024-07-20 | SUBSTITUTE ITEM | AU | 1 | 0 | 1266038.72 | 1493925.69 | 1004708.94 | 1185556.55 | 261329.78 | 1004708.94 | 1185556.55 | ZSER | 2024-07-15 | 2027-01-14
RE/0066-PRJ-T1-CIV-CC-SU | Concrete Supply | 2010 | GR01 | 2010 |  |  |  | 0 | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
RE/0066-PRJ-T1-CIV-EW | Earthwork | 2010 | GR01 | 2010 | SMARTWORLD THE EDITION | Ahluwalia Contracts India Limited | 9140000321 | 10 |  |  | 2024-07-20 | SITE DEVLOPMENT AND EARTH WORK | AU | 1 | 0 | 1493433 | 1762250.94 | 470073.13 | 554686.29 | 1023359.87 | 470073.13 | 554686.29 | ZSER | 2024-07-15 | 2027-01-14
RE/0066-PRJ-T1-CIV-MS | Misc Structure Works | 2010 | GR01 | 2010 | SMARTWORLD THE EDITION | Ahluwalia Contracts India Limited | 9140000321 | 100 |  |  | 2024-07-20 | STRUCTURAL STEEL WORKS | AU | 1 | 0 | 37847029.48 | 44659494.79 | 3493908.92 | 4122812.52 | 34353120.56 | 3093149.27 | 3649916.14 | ZSER | 2024-07-15 | 2027-01-14
RE/0066-PRJ-T1-CIV-MS | Misc Structure Works | 2010 | GR01 | 2010 | SMARTWORLD THE EDITION | Ahluwalia Contracts India Limited | 9140000321 | 130 |  |  | 2024-07-20 | INTERNAL & EXTERNAL PLASTERING | AU | 1 | 0 | 607320 | 716637.6 | 0 | 0 | 607320 | 0 | 0 | ZSER | 2024-07-15 | 2027-01-14
RE/0066-PRJ-T1-CIV-MS | Misc Structure Works | 2010 | GR01 | 2010 | SMARTWORLD THE EDITION | Ahluwalia Contracts India Limited | 9140000321 | 160 |  |  | 2024-07-20 | Amed-Monthly rental payment to M/S ACIL | AU | 1 | 0 | 1230377.3 | 1451845.21 | 262615.32 | 309886.08 | 967761.98 | 0 | 0 | ZSER | 2024-07-15 | 2027-01-14
RE/0066-PRJ-T1-CIV-MW | Masonry Works | 2010 | GR01 | 2010 | SMARTWORLD THE EDITION | Ahluwalia Contracts India Limited | 9140000321 | 90 |  |  | 2024-07-20 | MASONARY WORKS | AU | 1 | 0 | 8720220.87 | 10289860.63 | 1133181.36 | 1337154.01 | 7587039.51 | 1133181.36 | 1337154.01 | ZSER | 2024-07-15 | 2027-01-14
RE/0066-PRJ-T1-CIV-MW | Masonry Works | 2010 | GR01 | 2010 | SMARTWORLD THE EDITION | JJDJ CONSTRUCTION PVT. LTD. | 9140000602 | 10 |  |  | 2026-03-10 | Finishing Work - T1 | AU | 1 | 299773018.22 | 1912000 | 2256160 | 0 | 0 | 1912000 | 0 | 0 | ZSER | 2026-04-03 | 2028-04-03
RE/0066-PRJ-T1-CIV-MW | Masonry Works | 2010 | GR01 | 2010 | SMARTWORLD THE EDITION | H. S. OBEROI BUILDTECH PVT. LTD.MANISH SINGH | 9140000689 | 10 |  |  | 2026-06-10 | Finishing Work - T1 | AU | 1 | 299773018.22 | 1912000 | 2256160 | 0 | 0 | 1912000 | 0 | 0 | ZSER | 2026-04-03 | 2028-04-03
RE/0066-PRJ-T1-CIV-PW-IP | Internal Plaster | 2010 | GR01 | 2010 | SMARTWORLD THE EDITION | Ahluwalia Contracts India Limited | 9140000321 | 130 |  |  | 2024-07-20 | INTERNAL & EXTERNAL PLASTERING | AU | 1 | 0 | 7140671.46 | 8425992.32 | 0 | 0 | 7140671.46 | 0 | 0 | ZSER | 2024-07-15 | 2027-01-14
RE/0066-PRJ-T1-CIV-PW-XP | External Plaster | 2010 | GR01 | 2010 | SMARTWORLD THE EDITION | Ahluwalia Contracts India Limited | 9140000321 | 130 |  |  | 2024-07-20 | INTERNAL & EXTERNAL PLASTERING | AU | 1 | 0 | 225900 | 266562 | 0 | 0 | 225900 | 0 | 0 | ZSER | 2024-07-15 | 2027-01-14
RE/0066-PRJ-T1-CIV-RS-LA | Reinforcement Labour | 2010 | GR01 | 2010 | SMARTWORLD THE EDITION | Ahluwalia Contracts India Limited | 9140000321 | 70 |  |  | 2024-07-20 | REINFORCEMENT STEEL Installation Part A | AU | 1 | 0 | 146689345 | 173093427.1 | 66619478.73 | 78610984.9 | 80069866.27 | 64661713.04 | 76300821.39 | ZSER | 2024-07-15 | 2027-01-14
RE/0066-PRJ-T1-CIV-RS-LA | Reinforcement Labour | 2010 | GR01 | 2010 | SMARTWORLD THE EDITION | Ahluwalia Contracts India Limited | 9140000321 | 80 |  |  | 2024-07-20 | REINFORCEMENT STEEL Installation Part B | AU | 1 | 0 | 12916678.89 | 15241681.09 | 4950270 | 5841318.6 | 7966408.89 | 4739796.07 | 5592959.36 | ZSER | 2024-07-15 | 2027-01-14
RE/0066-PRJ-T1-CIV-RS-SU | Reinforcement Supply | 2010 | GR01 | 2010 | SMARTWORLD THE EDITION | JINDAL STEEL LIMITEDMr Robin Taneja | 9110000725 | 130 |  |  | 2024-10-10 | Fe 550D TMT Steel 32MM | TO | 16.1 | 53500 | 861350 | 1016393 | 861350 | 1016393 | 0 | 861350 | 1016393 | ZMAT | 2025-01-20 | 2025-03-20
RE/0066-PRJ-T1-CIV-RS-SU | Reinforcement Supply | 2010 | GR01 | 2010 | SMARTWORLD THE EDITION | Carna Corporation Pvt LtdVISHWANATH | 9110000726 | 10 |  |  | 2024-10-11 | Fe 550D TMT Steel 10 MM | TO | 74 | 54250 | 4014500 | 4737110 | 4014500 | 4737110 | 0 | 4014499.65 | 4737109.65 | ZMAT | 2024-10-11 | 2024-11-11
RE/0066-PRJ-T1-CIV-RS-SU | Reinforcement Supply | 2010 | GR01 | 2010 | SMARTWORLD THE EDITION | Northern Steel and General MillsPrivate Limited | 9110000774 | 10 |  |  | 2024-11-15 | Steel Re-bar TMT 16 mm Dia. FE-550D | TO | 22.5 | 54500 | 1226250 | 1446975 | 1226250 | 1446975 | 0 | 1226250 | 1446975 | ZMAT | 2025-01-20 | 2025-03-20
RE/0066-PRJ-T1-CIV-RS-SU | Reinforcement Supply | 2010 | GR01 | 2010 | SMARTWORLD THE EDITION | Northern Steel and General MillsPrivate Limited | 9110000774 | 60 |  |  | 2024-11-15 | Steel Re-bar TMT 20 mm Dia. FE-550D | TO | 8 | 54500 | 436000 | 514480 | 436000 | 514480 | 0 | 436000 | 514480 | ZMAT | 2025-01-20 | 2025-03-20
RE/0066-PRJ-T1-CIV-RS-SU | Reinforcement Supply | 2010 | GR01 | 2010 | SMARTWORLD THE EDITION | Northern Steel and General MillsPrivate Limited | 9110000774 | 130 |  |  | 2024-11-15 | Steel Re-bar TMT 25 mm Dia. FE-550D | TO | 16 | 54500 | 872000 | 1028960 | 872000 | 1028960 | 0 | 872000 | 1028960 | ZMAT | 2025-01-20 | 2025-03-20
RE/0066-PRJ-T1-CIV-RS-SU | Reinforcement Supply | 2010 | GR01 | 2010 | SMARTWORLD THE EDITION | Jindal Steel Limited | 9110000777 | 10 |  |  | 2024-11-15 | Steel Re-bar TMT 20 mm Dia. FE-550D | TO | 8.5 | 54500 | 463250 | 546635 | 463250 | 546635 | 0 | 463250 | 546635 | ZMAT | 2025-01-20 | 2025-03-20
RE/0066-PRJ-T1-CIV-RS-SU | Reinforcement Supply | 2010 | GR01 | 2010 | SMARTWORLD THE EDITION | Jindal Steel Limited | 9110000777 | 80 |  |  | 2024-11-15 | Steel Re-bar TMT 25 mm Dia. FE-550D | TO | 12 | 54500 | 654000 | 771720 | 654000 | 771720 | 0 | 654000 | 771720 | ZMAT | 2025-01-20 | 2025-03-20
RE/0066-PRJ-T1-CIV-RS-SU | Reinforcement Supply | 2010 | GR01 | 2010 | SMARTWORLD THE EDITION | Jindal Steel Limited | 9110000777 | 150 |  |  | 2024-11-15 | Steel Re-bar TMT 32 mm Dia. FE-550D | TO | 27 | 54500 | 1471500 | 1736370 | 1471500 | 1736370 | 0 | 1471500 | 1736370 | ZMAT | 2025-01-20 | 2025-03-20
RE/0066-PRJ-T1-CIV-RS-SU | Reinforcement Supply | 2010 | GR01 | 2010 | SMARTWORLD THE EDITION | Carna Corporation Pvt LtdVISHWANATH | 9110000779 | 10 |  |  | 2024-11-16 | Steel Re-bar TMT 20 mm Dia. FE-550D | TO | 9 | 54500 | 490500 | 578790 | 490500 | 578790 | 0 | 490499.9 | 578789.88 | ZMAT | 2025-01-20 | 2025-03-20
RE/0066-PRJ-T1-CIV-RS-SU | Reinforcement Supply | 2010 | GR01 | 2010 | SMARTWORLD THE EDITION | Carna Corporation Pvt LtdVISHWANATH | 9110000779 | 80 |  |  | 2024-11-16 | Steel Re-bar TMT 25 mm Dia. FE-550D | TO | 13 | 54500 | 708500 | 836030 | 708500 | 836030 | 0 | 708499.8 | 836029.77 | ZMAT | 2025-01-20 | 2025-03-20
RE/0066-PRJ-T1-CIV-RS-SU | Reinforcement Supply | 2010 | GR01 | 2010 | SMARTWORLD THE EDITION | Carna Corporation Pvt LtdVISHWANATH | 9110000779 | 150 |  |  | 2024-11-16 | Steel Re-bar TMT 32 mm Dia. FE-550D | TO | 87 | 54500 | 4741500 | 5594970 | 4741500 | 5594970 | 0 | 4741500 | 5594970.03 | ZMAT | 2025-01-20 | 2025-03-20
RE/0066-PRJ-T1-CIV-RS-SU | Reinforcement Supply | 2010 | GR01 | 2010 | SMARTWORLD THE EDITION | Rashtriya Ispat Nigam Ltd | 9110000790 | 10 |  |  | 2024-11-29 | Fe 550D TMT Steel Coil 08MM | TO | 15 | 55950 | 839250 | 990315 | 793930.5 | 936837.99 | 45319.5 | 793930.5 | 936838 | ZMAT | 2024-11-29 | 2024-12-28
RE/0066-PRJ-T1-CIV-RS-SU | Reinforcement Supply | 2010 | GR01 | 2010 | SMARTWORLD THE EDITION | Rashtriya Ispat Nigam Ltd | 9110000790 | 20 |  |  | 2024-11-29 | Fe 550D TMT Steel Coil 10MM | TO | 52 | 54450 | 2831400 | 3341052 | 2831400 | 3341052 | 0 | 2831400 | 3341052.02 | ZMAT | 2024-11-29 | 2024-12-28
RE/0066-PRJ-T1-CIV-RS-SU | Reinforcement Supply | 2010 | GR01 | 2010 | SMARTWORLD THE EDITION | Rashtriya Ispat Nigam Ltd | 9110000790 | 90 |  |  | 2024-11-29 | Fe 550D TMT Steel Coil 12MM | TO | 20 | 53950 | 1079000 | 1273220 | 1079000 | 1273220 | 0 | 1079000 | 1273220 | ZMAT | 2024-11-29 | 2024-12-28
RE/0066-PRJ-T1-CIV-RS-SU | Reinforcement Supply | 2010 | GR01 | 2010 | SMARTWORLD THE EDITION | Jindal Steel Limited | 9110000820 | 10 |  |  | 2024-10-10 | Fe 550D TMT Steel 12MM | TO | 24 | 53500 | 1284000 | 1515120 | 1284000 | 1515120 | 0 | 1284000 | 1515120 | ZMAT | 2025-01-20 | 2025-03-20
RE/0066-PRJ-T1-CIV-RS-SU | Reinforcement Supply | 2010 | GR01 | 2010 | SMARTWORLD THE EDITION | Jindal Steel Limited | 9110000820 | 40 |  |  | 2024-10-10 | Fe 550D TMT Steel 16MM | TO | 5.4 | 53500 | 288900 | 340902 | 288900 | 340902 | 0 | 288900 | 340902 | ZMAT | 2025-01-20 | 2025-03-20
RE/0066-PRJ-T1-CIV-RS-SU | Reinforcement Supply | 2010 | GR01 | 2010 | SMARTWORLD THE EDITION | Jindal Steel Limited | 9110000820 | 70 |  |  | 2024-10-10 | Fe 550D TMT Steel 20MM | TO | 41.25 | 53500 | 2206875 | 2604112.5 | 2206875 | 2604112.5 | 0 | 2206875 | 2604112.5 | ZMAT | 2025-01-20 | 2025-03-20
RE/0066-PRJ-T1-CIV-RS-SU | Reinforcement Supply | 2010 | GR01 | 2010 | SMARTWORLD THE EDITION | Jindal Steel Limited | 9110000820 | 100 |  |  | 2024-10-10 | Fe 550D TMT Steel 25MM | TO | 99.25 | 53500 | 5309875 | 6265652.5 | 5309875 | 6265652.5 | 0 | 5309875 | 6265652.5 | ZMAT | 2025-01-20 | 2025-03-20
RE/0066-PRJ-T1-CIV-RS-SU | Reinforcement Supply | 2010 | GR01 | 2010 | SMARTWORLD THE EDITION | Jindal Steel Limited | 9110000820 | 130 |  |  | 2024-10-10 | Fe 550D TMT Steel 32MM | TO | 611.62 | 53500 | 32721670 | 38611570.6 | 32449087.5 | 38289923.25 | 272582.5 | 32449087.5 | 38289923.25 | ZMAT | 2025-01-20 | 2025-03-20
RE/0066-PRJ-T1-CIV-RS-SU | Reinforcement Supply | 2010 | GR01 | 2010 | SMARTWORLD THE EDITION | Carna Corporation Pvt LtdVISHWANATH | 9110000837 | 10 |  |  | 2025-01-09 | Steel Re-bar TMT 08 mm Dia. FE-550D | TO | 15 | 51400 | 771000 | 909780 | 514000 | 606520 | 257000 | 514000 | 606520 | ZMAT | 2025-01-20 | 2025-03-20
RE/0066-PRJ-T1-CIV-RS-SU | Reinforcement Supply | 2010 | GR01 | 2010 | SMARTWORLD THE EDITION | Ram Niwas & SonsDeepak gupta | 9110000862 | 30 |  |  | 2025-02-15 | Steel Re-bar TMT 10 mm Dia. FE-550D | TO | 39 | 50200 | 1957800 | 2310204 | 1692233.49 | 1996835.52 | 265566.51 | 1957800 | 2310204 | ZMAT
RE/0066-PRJ-T1-CIV-RS-SU | Reinforcement Supply | 2010 | GR01 | 2010 | SMARTWORLD THE EDITION | Jindal Steel Limited | 9110000886 | 10 |  |  | 2025-03-12 | Steel Re-bar TMT 12 mm Dia. FE-550D | TO | 50 | 54750 | 2737500 | 3230250 | 2737500 | 3230250 | 0 | 2737500 | 3230250 | ZMAT
RE/0066-PRJ-T1-CIV-RS-SU | Reinforcement Supply | 2010 | GR01 | 2010 | SMARTWORLD THE EDITION | Jindal Steel Limited | 9110000886 | 70 |  |  | 2025-03-12 | Steel Re-bar TMT 16 mm Dia. FE-550D | TO | 25 | 54750 | 1368750 | 1615125 | 1368750 | 1615125 | 0 | 1368750 | 1615125 | ZMAT
RE/0066-PRJ-T1-CIV-RS-SU | Reinforcement Supply | 2010 | GR01 | 2010 | SMARTWORLD THE EDITION | Jindal Steel Limited | 9110000886 | 130 |  |  | 2025-03-12 | Steel Re-bar TMT 20 mm Dia. FE-550D | TO | 30 | 54750 | 1642500 | 1938150 | 1642500 | 1938150 | 0 | 1642500 | 1938150 | ZMAT
RE/0066-PRJ-T1-CIV-RS-SU | Reinforcement Supply | 2010 | GR01 | 2010 | SMARTWORLD THE EDITION | Ram Niwas & SonsDeepak gupta | 9110000887 | 10 |  |  | 2025-03-12 | Steel Re-bar TMT 10 mm Dia. FE-550D | TO | 10.5 | 52900 | 555450 | 655431 | 529000 | 624220 | 26450 | 529000 | 624220 | ZMAT
RE/0066-PRJ-T1-CIV-RS-SU | Reinforcement Supply | 2010 | GR01 | 2010 | SMARTWORLD THE EDITION | Carna Corporation Pvt LtdVISHWANATH | 9110000889 | 10 |  |  | 2025-03-12 | Steel Re-bar TMT 10 mm Dia. FE-550D | TO | 4.5 | 55500 | 249750 | 294705 | 249750 | 294705 | 0 | 249750 | 294705 | ZMAT
RE/0066-PRJ-T1-CIV-RS-SU | Reinforcement Supply | 2010 | GR01 | 2010 | SMARTWORLD THE EDITION | Rashtriya Ispat Nigam Ltd | 9110000961 | 10 |  |  | 2025-04-08 | Fe 550D TMT Steel Coil 10MM | TO | 9 | 58750 | 528750 | 623925 | 528750 | 623925 | 0 | 528750 | 623925 | ZMAT
RE/0066-PRJ-T1-CIV-RS-SU | Reinforcement Supply | 2010 | GR01 | 2010 | SMARTWORLD THE EDITION | Rashtriya Ispat Nigam Ltd | 9110000961 | 80 |  |  | 2025-04-08 | Fe 550D TMT Steel Coil 08MM | TO | 9 | 60000 | 540000 | 637200 | 540000 | 637200 | 0 | 540000 | 637200 | ZMAT
RE/0066-PRJ-T1-CIV-RS-SU | Reinforcement Supply | 2010 | GR01 | 2010 | SMARTWORLD THE EDITION | Vikrant Ispat Udyog | 9110000966 | 10 |  |  | 2025-04-09 | Fe 550D TMT Steel Coil 10MM | TO | 3 | 64250 | 192750 | 227445 | 192750 | 227445 | 0 | 192750 | 227445 | ZMAT
RE/0066-PRJ-T1-CIV-RS-SU | Reinforcement Supply | 2010 | GR01 | 2010 | SMARTWORLD THE EDITION | Vikrant Ispat Udyog | 9110000966 | 80 |  |  | 2025-04-09 | Fe 550D TMT Steel Coil 08MM | TO | 3 | 65750 | 197250 | 232755 | 197250 | 232755 | 0 | 197250 | 232755 | ZMAT
RE/0066-PRJ-T1-CIV-RS-SU | Reinforcement Supply | 2010 | GR01 | 2010 | SMARTWORLD THE EDITION | JINDAL STEEL LIMITEDMr Robin Taneja | 9110000991 | 170 |  |  | 2025-04-17 | Steel Re-bar TMT 25 mm Dia. FE-550D | TO | 8 | 57750 | 462000 | 545160 | 462000 | 545160 | 0 | 462000 | 545160 | ZMAT
RE/0066-PRJ-T1-CIV-RS-SU | Reinforcement Supply | 2010 | GR01 | 2010 | SMARTWORLD THE EDITION | Ram Niwas & SonsDeepak gupta | 9110000992 | 30 |  |  | 2025-04-17 | Steel Re-bar TMT 10 mm Dia. FE-550D | TO | 40 | 56000 | 2240000 | 2643200 | 2240000 | 2643200 | 0 | 2240000 | 2643200 | ZMAT
RE/0066-PRJ-T1-CIV-RS-SU | Reinforcement Supply | 2010 | GR01 | 2010 | SMARTWORLD THE EDITION | Sapcon Steels Private Limited | 9110000999 | 30 |  |  | 2025-04-18 | Fe 550D TMT Steel Coil 10MM | TO | 40 | 58250 | 2330000 | 2749400 | 2388250 | 2818135 | 58250 | 2388250 | 2818135 | ZMAT | 2025-04-11 | 2025-04-30
RE/0066-PRJ-T1-CIV-RS-SU | Reinforcement Supply | 2010 | GR01 | 2010 | SMARTWORLD THE EDITION | Sapcon Steels Private Limited | 9110001009 | 10 |  |  | 2025-04-28 | Steel Re-bar TMT 32 mm Dia. FE-550D | TO | 11 | 57000 | 627000 | 739860 | 399000 | 470820 | 228000 | 399000 | 470820 | ZMAT
RE/0066-PRJ-T1-CIV-RS-SU | Reinforcement Supply | 2010 | GR01 | 2010 | SMARTWORLD THE EDITION | Jindal Steel Limited | 9110001055 | 10 |  |  | 2025-05-17 | Steel Re-bar TMT 20 mm Dia. FE-550D | TO | 10 | 54850 | 548500 | 647230 | 548500 | 647230 | 0 | 548500 | 647230 | ZMAT | 2025-05-29 | 2025-06-29
RE/0066-PRJ-T1-CIV-RS-SU | Reinforcement Supply | 2010 | GR01 | 2010 | SMARTWORLD THE EDITION | Jindal Steel Limited | 9110001055 | 80 |  |  | 2025-05-17 | Steel Re-bar TMT 25 mm Dia. FE-550D | TO | 33 | 54850 | 1810050 | 2135859 | 1834677.65 | 2164919.63 | 24627.65 | 1834677.65 | 2164919.63 | ZMAT | 2025-05-29 | 2025-06-29
RE/0066-PRJ-T1-CIV-RS-SU | Reinforcement Supply | 2010 | GR01 | 2010 | SMARTWORLD THE EDITION | Jindal Steel Limited | 9110001055 | 150 |  |  | 2025-05-17 | Steel Re-bar TMT 32 mm Dia. FE-550D | TO | 10 | 54850 | 548500 | 647230 | 548500 | 647230 | 0 | 548500 | 647230 | ZMAT | 2025-05-29 | 2025-06-29
RE/0066-PRJ-T1-CIV-RS-SU | Reinforcement Supply | 2010 | GR01 | 2010 | SMARTWORLD THE EDITION | Jindal Steel Limited | 9110001073 | 20 |  |  | 2025-05-27 | Steel Re-bar TMT 12 mm Dia. FE-550D | TO | 10 | 57750 | 577500 | 681450 | 577500 | 681450 | 0 | 577500 | 681450 | ZMAT
RE/0066-PRJ-T1-CIV-RS-SU | Reinforcement Supply | 2010 | GR01 | 2010 | SMARTWORLD THE EDITION | Jindal Steel Limited | 9110001073 | 90 |  |  | 2025-05-27 | Steel Re-bar TMT 16 mm Dia. FE-550D | TO | 15 | 57750 | 866250 | 1022175 | 866250 | 1022175 | 0 | 866250 | 1022175 | ZMAT
RE/0066-PRJ-T1-CIV-RS-SU | Reinforcement Supply | 2010 | GR01 | 2010 | SMARTWORLD THE EDITION | Jindal Steel Limited | 9110001073 | 170 |  |  | 2025-05-27 | Steel Re-bar TMT 25 mm Dia. FE-550D | TO | 2 | 57750 | 115500 | 136290 | 115500 | 136290 | 0 | 115500 | 136290 | ZMAT
RE/0066-PRJ-T1-CIV-RS-SU | Reinforcement Supply | 2010 | GR01 | 2010 | SMARTWORLD THE EDITION | JINDAL STEEL LIMITEDMr Robin Taneja | 9110001079 | 10 |  |  | 2025-05-29 | Steel Re-bar TMT 25 mm Dia. FE-550D | TO | 12 | 54850 | 658200 | 776676 | 658200 | 776676 | 0 | 658200 | 776676 | ZMAT | 2025-05-29 | 2025-06-29
RE/0066-PRJ-T1-CIV-RS-SU | Reinforcement Supply | 2010 | GR01 | 2010 | SMARTWORLD THE EDITION | Ram Niwas & SonsDeepak gupta | 9110001126 | 10 |  |  | 2025-06-20 | Steel Re-bar TMT 08 mm Dia. FE-550D | TO | 10 | 51000 | 510000 | 601800 | 535500 | 631890 | 25500 | 535500 | 631890 | ZMAT | 2025-06-20 | 2025-07-20
RE/0066-PRJ-T1-CIV-RS-SU | Reinforcement Supply | 2010 | GR01 | 2010 | SMARTWORLD THE EDITION | Jindal Steel Limited | 9110001127 | 10 |  |  | 2025-06-20 | Steel Re-bar TMT 12 mm Dia. FE-550D | TO | 30 | 50600 | 1518000 | 1791240 | 1518000 | 1791240 | 0 | 1518000 | 1791240 | ZMAT | 2025-06-20 | 2025-07-20
RE/0066-PRJ-T1-CIV-RS-SU | Reinforcement Supply | 2010 | GR01 | 2010 | SMARTWORLD THE EDITION | Jindal Steel Limited | 9110001127 | 90 |  |  | 2025-06-20 | Steel Re-bar TMT 16 mm Dia. FE-550D | TO | 25 | 50600 | 1265000 | 1492700 | 1265000 | 1492700 | 0 | 1265000 | 1492700 | ZMAT | 2025-06-20 | 2025-07-20
RE/0066-PRJ-T1-CIV-RS-SU | Reinforcement Supply | 2010 | GR01 | 2010 | SMARTWORLD THE EDITION | Jindal Steel Limited | 9110001127 | 170 |  |  | 2025-06-20 | Steel Re-bar TMT 20 mm Dia. FE-550D | TO | 15 | 50600 | 759000 | 895620 | 759000 | 895620 | 0 | 759000 | 895620 | ZMAT | 2025-06-20 | 2025-07-20
RE/0066-PRJ-T1-CIV-RS-SU | Reinforcement Supply | 2010 | GR01 | 2010 | SMARTWORLD THE EDITION | Jindal Steel Limited | 9110001127 | 240 |  |  | 2025-06-20 | Steel Re-bar TMT 25 mm Dia. FE-550D | TO | 20 | 50600 | 1012000 | 1194160 | 1012000 | 1194160 | 0 | 1012000 | 1194160 | ZMAT | 2025-06-20 | 2025-07-20
RE/0066-PRJ-T1-CIV-RS-SU | Reinforcement Supply | 2010 | GR01 | 2010 | SMARTWORLD THE EDITION | Jindal Steel Limited | 9110001127 | 320 |  |  | 2025-06-20 | Steel Re-bar TMT 32 mm Dia. FE-550D | TO | 10 | 50600 | 506000 | 597080 | 506000 | 597080 | 0 | 506000 | 597080 | ZMAT | 2025-06-20 | 2025-07-20
RE/0066-PRJ-T1-CIV-RS-SU | Reinforcement Supply | 2010 | GR01 | 2010 | SMARTWORLD THE EDITION | Jindal Steel Limited | 9110001162 | 10 |  |  | 2025-07-17 | Steel Re-bar TMT 10 mm Dia. FE-550D | TO | 40 | 47500 | 1900000 | 2242000 | 0 | 0 | 1900000 | 0 | 0 | ZMAT | 2025-07-17 | 2025-08-17
RE/0066-PRJ-T1-CIV-RS-SU | Reinforcement Supply | 2010 | GR01 | 2010 | SMARTWORLD THE EDITION | Jindal Steel Limited | 9110001162 | 90 |  |  | 2025-07-17 | Steel Re-bar TMT 12 mm Dia. FE-550D | TO | 15 | 46500 | 697500 | 823050 | 0 | 0 | 697500 | 0 | 0 | ZMAT | 2025-07-17 | 2025-08-17
RE/0066-PRJ-T1-CIV-RS-SU | Reinforcement Supply | 2010 | GR01 | 2010 | SMARTWORLD THE EDITION | Jindal Steel Limited | 9110001162 | 170 |  |  | 2025-07-17 | Steel Re-bar TMT 16 mm Dia. FE-550D | TO | 5 | 46500 | 232500 | 274350 | 0 | 0 | 232500 | 0 | 0 | ZMAT | 2025-07-17 | 2025-08-17
RE/0066-PRJ-T1-CIV-RS-SU | Reinforcement Supply | 2010 | GR01 | 2010 | SMARTWORLD THE EDITION | Jindal Steel Limited | 9110001162 | 230 |  |  | 2025-07-17 | Steel Re-bar TMT 20 mm Dia. FE-550D | TO | 5 | 46500 | 232500 | 274350 | 0 | 0 | 232500 | 0 | 0 | ZMAT | 2025-07-17 | 2025-08-17
RE/0066-PRJ-T1-CIV-RS-SU | Reinforcement Supply | 2010 | GR01 | 2010 | SMARTWORLD THE EDITION | Jindal Steel Limited | 9110001162 | 300 |  |  | 2025-07-17 | Steel Re-bar TMT 25 mm Dia. FE-550D | TO | 5 | 46500 | 232500 | 274350 | 0 | 0 | 232500 | 0 | 0 | ZMAT | 2025-07-17 | 2025-08-17
RE/0066-PRJ-T1-CIV-RS-SU | Reinforcement Supply | 2010 | GR01 | 2010 | SMARTWORLD THE EDITION | Jindal Steel Limited | 9110001162 | 380 |  |  | 2025-07-17 | Steel Re-bar TMT 32 mm Dia. FE-550D | TO | 5 | 46500 | 232500 | 274350 | 0 | 0 | 232500 | 0 | 0 | ZMAT | 2025-07-17 | 2025-08-17
RE/0066-PRJ-T1-CIV-RS-SU | Reinforcement Supply | 2010 | GR01 | 2010 | SMARTWORLD THE EDITION | Rashtriya Ispat Nigam Ltd | 9110001212 | 10 |  |  | 2025-08-14 | Steel Re-bar TMT 08 mm Dia. FE-550D | TO | 10 | 49300 | 493000 | 581740 | 493000 | 581740 | 0 | 493000 | 581740 | ZMAT | 2025-08-14 | 2025-09-14
RE/0066-PRJ-T1-CIV-RS-SU | Reinforcement Supply | 2010 | GR01 | 2010 | SMARTWORLD THE EDITION | Rashtriya Ispat Nigam Ltd | 9110001212 | 70 |  |  | 2025-08-14 | Steel Re-bar TMT 10 mm Dia. FE-550D | TO | 55 | 47800 | 2629000 | 3102220 | 2629000 | 3102220 | 0 | 2629000 | 3102220 | ZMAT | 2025-08-14 | 2025-09-14
RE/0066-PRJ-T1-CIV-RS-SU | Reinforcement Supply | 2010 | GR01 | 2010 | SMARTWORLD THE EDITION | Jindal Steel Limited | 9110001213 | 10 |  |  | 2025-08-14 | Steel Re-bar TMT 12 mm Dia. FE-550D | TO | 35 | 47000 | 1645000 | 1941100 | 1645000 | 1941100 | 0 | 1645000 | 1941100 | ZMAT | 2025-08-14 | 2025-09-14
RE/0066-PRJ-T1-CIV-RS-SU | Reinforcement Supply | 2010 | GR01 | 2010 | SMARTWORLD THE EDITION | Jindal Steel Limited | 9110001213 | 70 |  |  | 2025-08-14 | Steel Re-bar TMT 16 mm Dia. FE-550D | TO | 15 | 47000 | 705000 | 831900 | 705000 | 831900 | 0 | 705000 | 831900 | ZMAT | 2025-08-14 | 2025-09-14
RE/0066-PRJ-T1-CIV-RS-SU | Reinforcement Supply | 2010 | GR01 | 2010 | SMARTWORLD THE EDITION | Jindal Steel Limited | 9110001213 | 130 |  |  | 2025-08-14 | Steel Re-bar TMT 20 mm Dia. FE-550D | TO | 15 | 47000 | 705000 | 831900 | 705000 | 831900 | 0 | 705000 | 831900 | ZMAT | 2025-08-14 | 2025-09-14
RE/0066-PRJ-T1-CIV-RS-SU | Reinforcement Supply | 2010 | GR01 | 2010 | SMARTWORLD THE EDITION | Jindal Steel Limited | 9110001213 | 190 |  |  | 2025-08-14 | Steel Re-bar TMT 25 mm Dia. FE-550D | TO | 20 | 47000 | 940000 | 1109200 | 940000 | 1109200 | 0 | 940000 | 1109200 | ZMAT | 2025-08-14 | 2025-09-14
RE/0066-PRJ-T1-CIV-RS-SU | Reinforcement Supply | 2010 | GR01 | 2010 | SMARTWORLD THE EDITION | Jindal Steel Limited | 9110001213 | 250 |  |  | 2025-08-14 | Steel Re-bar TMT 32 mm Dia. FE-550D | TO | 20 | 47000 | 940000 | 1109200 | 940000 | 1109200 | 0 | 940000 | 1109200 | ZMAT | 2025-08-14 | 2025-09-14
RE/0066-PRJ-T1-CIV-RS-SU | Reinforcement Supply | 2010 | GR01 | 2010 | SMARTWORLD THE EDITION | Steel Authority Of India LTD | 9110001280 | 10 |  |  | 2025-09-18 | Steel Re-bar TMT 10 mm Dia. FE-550D | TO | 15.75 | 47260 | 744345 | 878327.1 | 744345 | 878327.1 | 0 | 744345 | 878327.1 | ZMAT | 2025-09-18 | 2025-10-18
RE/0066-PRJ-T1-CIV-RS-SU | Reinforcement Supply | 2010 | GR01 | 2010 | SMARTWORLD THE EDITION | Steel Authority Of India LTD | 9110001280 | 20 |  |  | 2025-09-18 | Steel Re-bar TMT 12 mm Dia. FE-550D | TO | 25.6 | 46260 | 1184256 | 1397422.08 | 1184256 | 1397422.08 | 0 | 1184256 | 1397422.08 | ZMAT | 2025-09-18 | 2025-10-18
RE/0066-PRJ-T1-CIV-RS-SU | Reinforcement Supply | 2010 | GR01 | 2010 | SMARTWORLD THE EDITION | Steel Authority Of India LTD | 9110001280 | 80 |  |  | 2025-09-18 | Steel Re-bar TMT 16 mm Dia. FE-550D | TO | 20 | 46260 | 925200 | 1091736 | 925200 | 1091736 | 0 | 925200 | 1091736 | ZMAT | 2025-09-18 | 2025-10-18
RE/0066-PRJ-T1-CIV-RS-SU | Reinforcement Supply | 2010 | GR01 | 2010 | SMARTWORLD THE EDITION | Steel Authority Of India LTD | 9110001280 | 140 |  |  | 2025-09-18 | Steel Re-bar TMT 20 mm Dia. FE-550D | TO | 24.8 | 46260 | 1147248 | 1353752.64 | 1147248 | 1353752.64 | 0 | 1147248 | 1353752.64 | ZMAT | 2025-09-18 | 2025-10-18
RE/0066-PRJ-T1-CIV-RS-SU | Reinforcement Supply | 2010 | GR01 | 2010 | SMARTWORLD THE EDITION | Steel Authority Of India LTD | 9110001280 | 200 |  |  | 2025-09-18 | Steel Re-bar TMT 25 mm Dia. FE-550D | TO | 13 | 46260 | 601380 | 709628.4 | 601380 | 709628.4 | 0 | 601380 | 709628.4 | ZMAT | 2025-09-18 | 2025-10-18
RE/0066-PRJ-T1-CIV-RS-SU | Reinforcement Supply | 2010 | GR01 | 2010 | SMARTWORLD THE EDITION | Steel Authority Of India LTD | 9110001280 | 260 |  |  | 2025-09-18 | Steel Re-bar TMT 32 mm Dia. FE-550D | TO | 12.75 | 46260 | 589815 | 695981.7 | 589815 | 695981.7 | 0 | 589815 | 695981.7 | ZMAT | 2025-09-18 | 2025-10-18
RE/0066-PRJ-T1-CIV-RS-SU | Reinforcement Supply | 2010 | GR01 | 2010 | SMARTWORLD THE EDITION | Ram Niwas & SonsDeepak gupta | 9110001305 | 10 |  |  | 2025-10-09 | Steel Re-bar TMT 08 mm Dia. FE-550D | TO | 6 | 47500 | 285000 | 336300 | 285000 | 336300 | 0 | 285000 | 336300 | ZMAT | 2025-10-09 | 2025-11-08
RE/0066-PRJ-T1-CIV-RS-SU | Reinforcement Supply | 2010 | GR01 | 2010 | SMARTWORLD THE EDITION | Ram Niwas & SonsDeepak gupta | 9110001305 | 20 |  |  | 2025-10-09 | Steel Re-bar TMT 08 mm Dia. FE-550D | TO | 6 | 47500 | 285000 | 336300 | 285000 | 336300 | 0 | 285000 | 336300 | ZMAT | 2025-10-09 | 2025-11-08
RE/0066-PRJ-T1-CIV-RS-SU | Reinforcement Supply | 2010 | GR01 | 2010 | SMARTWORLD THE EDITION | Ram Niwas & SonsDeepak gupta | 9110001305 | 70 |  |  | 2025-10-09 | Steel Re-bar TMT 10 mm Dia. FE-550D | TO | 29 | 46500 | 1348500 | 1591230 | 1348500 | 1591230 | 0 | 1348500 | 1591230 | ZMAT | 2025-10-09 | 2025-11-08
RE/0066-PRJ-T1-CIV-RS-SU | Reinforcement Supply | 2010 | GR01 | 2010 | SMARTWORLD THE EDITION | Jindal Steel Limited | 9110001307 | 10 |  |  | 2025-10-09 | Steel Re-bar TMT 12 mm Dia. FE-550D | TO | 5 | 46500 | 232500 | 274350 | 232500 | 274350 | 0 | 232500 | 274350 | ZMAT | 2025-10-09 | 2025-11-08
RE/0066-PRJ-T1-CIV-RS-SU | Reinforcement Supply | 2010 | GR01 | 2010 | SMARTWORLD THE EDITION | Jindal Steel Limited | 9110001307 | 70 |  |  | 2025-10-09 | Steel Re-bar TMT 16 mm Dia. FE-550D | TO | 20 | 46500 | 930000 | 1097400 | 930000 | 1097400 | 0 | 930000 | 1097400 | ZMAT | 2025-10-09 | 2025-11-08
RE/0066-PRJ-T1-CIV-RS-SU | Reinforcement Supply | 2010 | GR01 | 2010 | SMARTWORLD THE EDITION | Jindal Steel Limited | 9110001307 | 130 |  |  | 2025-10-09 | Steel Re-bar TMT 20 mm Dia. FE-550D | TO | 20 | 46500 | 930000 | 1097400 | 930000 | 1097400 | 0 | 930000 | 1097400 | ZMAT | 2025-10-09 | 2025-11-08
RE/0066-PRJ-T1-CIV-RS-SU | Reinforcement Supply | 2010 | GR01 | 2010 | SMARTWORLD THE EDITION | Jindal Steel Limited | 9110001307 | 190 |  |  | 2025-10-09 | Steel Re-bar TMT 25 mm Dia. FE-550D | TO | 16 | 46500 | 744000 | 877920 | 744000 | 877920 | 0 | 744000 | 877920 | ZMAT | 2025-10-09 | 2025-11-08
RE/0066-PRJ-T1-CIV-RS-SU | Reinforcement Supply | 2010 | GR01 | 2010 | SMARTWORLD THE EDITION | Jindal Steel Limited | 9110001307 | 250 |  |  | 2025-10-09 | Steel Re-bar TMT 32 mm Dia. FE-550D | TO | 16 | 46500 | 744000 | 877920 | 655557 | 773557.26 | 88443 | 655557 | 773557.26 | ZMAT | 2025-10-09 | 2025-11-08
RE/0066-PRJ-T1-CIV-RS-SU | Reinforcement Supply | 2010 | GR01 | 2010 | SMARTWORLD THE EDITION | Jindal Steel Limited | 9110001361 | 10 |  |  | 2025-11-07 | Steel Re-bar TMT 12 mm Dia. FE-550D | TO | 34 | 46100 | 1567400 | 1849532 | 1567400 | 1849532 | 0 | 1567400 | 1849532 | ZMAT | 2025-11-07 | 2025-12-07
RE/0066-PRJ-T1-CIV-RS-SU | Reinforcement Supply | 2010 | GR01 | 2010 | SMARTWORLD THE EDITION | Jindal Steel Limited | 9110001361 | 70 |  |  | 2025-11-07 | Steel Re-bar TMT 16 mm Dia. FE-550D | TO | 25 | 46100 | 1152500 | 1359950 | 1152500 | 1359950 | 0 | 1152500 | 1359950 | ZMAT | 2025-11-07 | 2025-12-07
RE/0066-PRJ-T1-CIV-RS-SU | Reinforcement Supply | 2010 | GR01 | 2010 | SMARTWORLD THE EDITION | Jindal Steel Limited | 9110001361 | 130 |  |  | 2025-11-07 | Steel Re-bar TMT 20 mm Dia. FE-550D | TO | 8 | 46100 | 368800 | 435184 | 368800 | 435184 | 0 | 368800 | 435184 | ZMAT | 2025-11-07 | 2025-12-07
RE/0066-PRJ-T1-CIV-RS-SU | Reinforcement Supply | 2010 | GR01 | 2010 | SMARTWORLD THE EDITION | Jindal Steel Limited | 9110001361 | 190 |  |  | 2025-11-07 | Steel Re-bar TMT 25 mm Dia. FE-550D | TO | 30 | 46100 | 1383000 | 1631940 | 1383000 | 1631940 | 0 | 1383000 | 1631940 | ZMAT | 2025-11-07 | 2025-12-07
RE/0066-PRJ-T1-CIV-RS-SU | Reinforcement Supply | 2010 | GR01 | 2010 | SMARTWORLD THE EDITION | Jindal Steel Limited | 9110001361 | 250 |  |  | 2025-11-07 | Steel Re-bar TMT 32 mm Dia. FE-550D | TO | 10 | 46100 | 461000 | 543980 | 461000 | 543980 | 0 | 461000 | 543980 | ZMAT | 2025-11-07 | 2025-12-07
RE/0066-PRJ-T1-CIV-RS-SU | Reinforcement Supply | 2010 | GR01 | 2010 | SMARTWORLD THE EDITION | Ram Niwas & SonsDeepak gupta | 9110001362 | 10 |  |  | 2025-11-07 | Steel Re-bar TMT 08 mm Dia. FE-550D | TO | 2.5 | 46900 | 117250 | 138355 | 117250 | 138355 | 0 | 117250 | 138355 | ZMAT | 2025-11-07 | 2025-12-07
RE/0066-PRJ-T1-CIV-RS-SU | Reinforcement Supply | 2010 | GR01 | 2010 | SMARTWORLD THE EDITION | Ram Niwas & SonsDeepak gupta | 9110001362 | 120 |  |  | 2025-11-07 | Steel Re-bar TMT 10 mm Dia. FE-550D | TO | 38 | 45900 | 1744200 | 2058156 | 1744200 | 2058156 | 0 | 1744200 | 2058156 | ZMAT | 2025-11-07 | 2025-12-07
RE/0066-PRJ-T1-CIV-RS-SU | Reinforcement Supply | 2010 | GR01 | 2010 | SMARTWORLD THE EDITION | Ram Niwas & SonsDeepak gupta | 9110001421 | 10 |  |  | 2025-12-10 | Steel Re-bar TMT 10 mm Dia. FE-550D | TO | 58 | 46500 | 2697000 | 3182460 | 2697000 | 3182460 | 0 | 2697000 | 3182460 | ZMAT | 2025-12-10 | 2026-01-10
RE/0066-PRJ-T1-CIV-RS-SU | Reinforcement Supply | 2010 | GR01 | 2010 | SMARTWORLD THE EDITION | Ram Niwas & SonsDeepak gupta | 9110001421 | 70 |  |  | 2025-12-10 | Steel Re-bar TMT 08 mm Dia. FE-550D | TO | 12 | 47500 | 570000 | 672600 | 570000 | 672600 | 0 | 570000 | 672600 | ZMAT | 2025-12-10 | 2026-01-10
RE/0066-PRJ-T1-CIV-RS-SU | Reinforcement Supply | 2010 | GR01 | 2010 | SMARTWORLD THE EDITION | Ram Niwas & SonsDeepak gupta | 9110001421 | 80 |  |  | 2025-12-10 | Steel Re-bar TMT 08 mm Dia. FE-550D | TO | 12 | 47500 | 570000 | 672600 | 570000 | 672600 | 0 | 570000 | 672600 | ZMAT | 2025-12-10 | 2026-01-10
RE/0066-PRJ-T1-CIV-RS-SU | Reinforcement Supply | 2010 | GR01 | 2010 | SMARTWORLD THE EDITION | Jindal Steel Limited | 9110001422 | 10 |  |  | 2025-12-10 | Steel Re-bar TMT 12 mm Dia. FE-550D | TO | 20 | 46400 | 928000 | 1095040 | 928000 | 1095040 | 0 | 928000 | 1095040 | ZMAT | 2025-12-10 | 2026-01-10
RE/0066-PRJ-T1-CIV-RS-SU | Reinforcement Supply | 2010 | GR01 | 2010 | SMARTWORLD THE EDITION | Jindal Steel Limited | 9110001422 | 70 |  |  | 2025-12-10 | Steel Re-bar TMT 16 mm Dia. FE-550D | TO | 18 | 46400 | 835200 | 985536 | 835200 | 985536 | 0 | 835200 | 985536 | ZMAT | 2025-12-10 | 2026-01-10
RE/0066-PRJ-T1-CIV-RS-SU | Reinforcement Supply | 2010 | GR01 | 2010 | SMARTWORLD THE EDITION | Jindal Steel Limited | 9110001422 | 130 |  |  | 2025-12-10 | Steel Re-bar TMT 20 mm Dia. FE-550D | TO | 13 | 46400 | 603200 | 711776 | 601761.6 | 710078.69 | 1438.4 | 601761.6 | 710078.69 | ZMAT | 2025-12-10 | 2026-01-10
RE/0066-PRJ-T1-CIV-RS-SU | Reinforcement Supply | 2010 | GR01 | 2010 | SMARTWORLD THE EDITION | Jindal Steel Limited | 9110001422 | 190 |  |  | 2025-12-10 | Steel Re-bar TMT 25 mm Dia. FE-550D | TO | 15 | 46400 | 696000 | 821280 | 696000 | 821280 | 0 | 696000 | 821280 | ZMAT | 2025-12-10 | 2026-01-10
RE/0066-PRJ-T1-CIV-RS-SU | Reinforcement Supply | 2010 | GR01 | 2010 | SMARTWORLD THE EDITION | Ram Niwas & SonsDeepak gupta | 9110001471 | 10 |  |  | 2026-01-12 | Steel Re-bar TMT 08 mm Dia. FE-550D | TO | 10 | 52000 | 520000 | 613600 | 520000 | 613600 | 0 | 520000 | 613600 | ZMAT | 2026-01-12 | 2026-02-12
RE/0066-PRJ-T1-CIV-RS-SU | Reinforcement Supply | 2010 | GR01 | 2010 | SMARTWORLD THE EDITION | Ram Niwas & SonsDeepak gupta | 9110001471 | 20 |  |  | 2026-01-12 | Steel Re-bar TMT 08 mm Dia. FE-550D | TO | 10 | 52000 | 520000 | 613600 | 487240 | 574943.2 | 32760 | 487240 | 574943.2 | ZMAT | 2026-01-12 | 2026-02-12
RE/0066-PRJ-T1-CIV-RS-SU | Reinforcement Supply | 2010 | GR01 | 2010 | SMARTWORLD THE EDITION | Ram Niwas & SonsDeepak gupta | 9110001471 | 70 |  |  | 2026-01-12 | Steel Re-bar TMT 10 mm Dia. FE-550D | TO | 10 | 51000 | 510000 | 601800 | 510000 | 601800 | 0 | 510000 | 601800 | ZMAT | 2026-01-12 | 2026-02-12
RE/0066-PRJ-T1-CIV-RS-SU | Reinforcement Supply | 2010 | GR01 | 2010 | SMARTWORLD THE EDITION | ESL STEEL LIMITED | 9110001481 | 10 |  |  | 2026-01-12 | Steel Re-bar TMT 12 mm Dia. FE-550D | TO | 42 | 51800 | 2175600 | 2567208 | 2123800 | 2506084 | 51800 | 2123800 | 2506084 | ZMAT | 2026-01-12 | 2026-02-12
RE/0066-PRJ-T1-CIV-RS-SU | Reinforcement Supply | 2010 | GR01 | 2010 | SMARTWORLD THE EDITION | ESL STEEL LIMITED | 9110001481 | 70 |  |  | 2026-01-12 | Steel Re-bar TMT 16 mm Dia. FE-550D | TO | 1 | 51800 | 51800 | 61124 | 51800 | 61124 | 0 | 51800 | 61124 | ZMAT | 2026-01-12 | 2026-02-12
RE/0066-PRJ-T1-CIV-RS-SU | Reinforcement Supply | 2010 | GR01 | 2010 | SMARTWORLD THE EDITION | ESL STEEL LIMITED | 9110001481 | 130 |  |  | 2026-01-12 | Steel Re-bar TMT 20 mm Dia. FE-550D | TO | 25 | 51800 | 1295000 | 1528100 | 1295000 | 1528100 | 0 | 1295000 | 1528100 | ZMAT | 2026-01-12 | 2026-02-12
RE/0066-PRJ-T1-CIV-RS-SU | Reinforcement Supply | 2010 | GR01 | 2010 | SMARTWORLD THE EDITION | ESL STEEL LIMITED | 9110001481 | 190 |  |  | 2026-01-12 | Steel Re-bar TMT 25 mm Dia. FE-550D | TO | 10 | 51800 | 518000 | 611240 | 509712 | 601460.16 | 8288 | 509712 | 601460.16 | ZMAT | 2026-01-12 | 2026-02-12
RE/0066-PRJ-T1-CIV-RS-SU | Reinforcement Supply | 2010 | GR01 | 2010 | SMARTWORLD THE EDITION | Ram Niwas & SonsDeepak gupta | 9110001541 | 10 |  |  | 2026-02-07 | Steel Re-bar TMT 08 mm Dia. FE-550D | TO | 7 | 55300 | 387100 | 456778 | 384335 | 453515.3 | 2765 | 384335 | 453515.3 | ZMAT | 2026-02-07 | 2026-03-31
RE/0066-PRJ-T1-CIV-RS-SU | Reinforcement Supply | 2010 | GR01 | 2010 | SMARTWORLD THE EDITION | Ram Niwas & SonsDeepak gupta | 9110001541 | 20 |  |  | 2026-02-07 | Steel Re-bar TMT 08 mm Dia. FE-550D | TO | 7 | 55300 | 387100 | 456778 | 386547 | 456125.46 | 553 | 386547 | 456125.46 | ZMAT | 2026-02-07 | 2026-03-31
RE/0066-PRJ-T1-CIV-RS-SU | Reinforcement Supply | 2010 | GR01 | 2010 | SMARTWORLD THE EDITION | Ram Niwas & SonsDeepak gupta | 9110001541 | 70 |  |  | 2026-02-07 | Steel Re-bar TMT 10 mm Dia. FE-550D | TO | 11 | 54300 | 597300 | 704814 | 597300 | 704814 | 0 | 597300 | 704814 | ZMAT | 2026-02-07 | 2026-03-31
RE/0066-PRJ-T1-CIV-RS-SU | Reinforcement Supply | 2010 | GR01 | 2010 | SMARTWORLD THE EDITION | Petropol India LimitedSANJAY GUPTA | 9110001546 | 10 |  |  | 2026-02-07 | Steel Re-bar TMT 08 mm Dia. FE-550D | TO | 6 | 55300 | 331800 | 391524 | 331800 | 391524 | 0 | 331800 | 391524 | ZMAT | 2026-02-07 | 2026-03-31
RE/0066-PRJ-T1-CIV-RS-SU | Reinforcement Supply | 2010 | GR01 | 2010 | SMARTWORLD THE EDITION | Petropol India LimitedSANJAY GUPTA | 9110001546 | 20 |  |  | 2026-02-07 | Steel Re-bar TMT 08 mm Dia. FE-550D | TO | 6 | 55300 | 331800 | 391524 | 331800 | 391524 | 0 | 331800 | 391524 | ZMAT | 2026-02-07 | 2026-03-31
RE/0066-PRJ-T1-CIV-RS-SU | Reinforcement Supply | 2010 | GR01 | 2010 | SMARTWORLD THE EDITION | Petropol India LimitedSANJAY GUPTA | 9110001546 | 70 |  |  | 2026-02-07 | Steel Re-bar TMT 10 mm Dia. FE-550D | TO | 15 | 54300 | 814500 | 961110 | 814500 | 961110 | 0 | 814500 | 961110 | ZMAT | 2026-02-07 | 2026-03-31
RE/0066-PRJ-T1-CIV-RS-SU | Reinforcement Supply | 2010 | GR01 | 2010 | SMARTWORLD THE EDITION | Jindal Steel Limited | 9110001551 | 10 |  |  | 2026-02-07 | Steel Re-bar TMT 12 mm Dia. FE-550D | TO | 27 | 58500 | 1579500 | 1863810 | 1567800 | 1850004 | 11700 | 1567800 | 1850004 | ZMAT | 2026-02-07 | 2026-03-07
RE/0066-PRJ-T1-CIV-RS-SU | Reinforcement Supply | 2010 | GR01 | 2010 | SMARTWORLD THE EDITION | Jindal Steel Limited | 9110001551 | 70 |  |  | 2026-02-07 | Steel Re-bar TMT 16 mm Dia. FE-550D | TO | 30 | 58500 | 1755000 | 2070900 | 1753186.5 | 2068760.07 | 1813.5 | 1753186.5 | 2068760.07 | ZMAT | 2026-02-07 | 2026-03-07
RE/0066-PRJ-T1-CIV-RS-SU | Reinforcement Supply | 2010 | GR01 | 2010 | SMARTWORLD THE EDITION | Jindal Steel Limited | 9110001551 | 130 |  |  | 2026-02-07 | Steel Re-bar TMT 20 mm Dia. FE-550D | TO | 30 | 58500 | 1755000 | 2070900 | 1743300 | 2057094 | 11700 | 1743300 | 2057094 | ZMAT | 2026-02-07 | 2026-03-07
RE/0066-PRJ-T1-CIV-RS-SU | Reinforcement Supply | 2010 | GR01 | 2010 | SMARTWORLD THE EDITION | Jindal Steel Limited | 9110001551 | 190 |  |  | 2026-02-07 | Steel Re-bar TMT 25 mm Dia. FE-550D | TO | 20 | 58500 | 1170000 | 1380600 | 1158300 | 1366794 | 11700 | 1158300 | 1366794 | ZMAT | 2026-02-07 | 2026-03-07
RE/0066-PRJ-T1-CIV-RS-SU | Reinforcement Supply | 2010 | GR01 | 2010 | SMARTWORLD THE EDITION | Jindal Steel Limited | 9110001557 | 10 |  |  | 2026-02-10 | Steel Re-bar TMT 12 mm Dia. FE-550D | TO | 26 | 58500 | 1521000 | 1794780 | 1517490 | 1790638.2 | 3510 | 1517490 | 1790638.2 | ZMAT | 2026-02-10 | 2026-03-10
RE/0066-PRJ-T1-CIV-RS-SU | Reinforcement Supply | 2010 | GR01 | 2010 | SMARTWORLD THE EDITION | Jindal Steel Limited | 9110001557 | 70 |  |  | 2026-02-10 | Steel Re-bar TMT 25 mm Dia. FE-550D | TO | 49 | 58500 | 2866500 | 3382470 | 2862990 | 3378328.2 | 3510 | 2862990 | 3378328.2 | ZMAT | 2026-02-10 | 2026-03-10
RE/0066-PRJ-T1-CIV-RS-SU | Reinforcement Supply | 2010 | GR01 | 2010 | SMARTWORLD THE EDITION | Jindal Steel Limited | 9110001557 | 130 |  |  | 2026-02-10 | Steel Re-bar TMT 32 mm Dia. FE-550D | TO | 15 | 58500 | 877500 | 1035450 | 877500 | 1035450 | 0 | 877500 | 1035450 | ZMAT | 2026-02-10 | 2026-03-10
RE/0066-PRJ-T1-CIV-RS-SU | Reinforcement Supply | 2010 | GR01 | 2010 | SMARTWORLD THE EDITION | Petropol India LimitedSANJAY GUPTA | 9110001558 | 10 |  |  | 2026-02-10 | Steel Re-bar TMT 08 mm Dia. FE-550D | TO | 19 | 55300 | 1050700 | 1239826 | 1050700 | 1239826 | 0 | 1050700 | 1239826 | ZMAT | 2026-02-10 | 2026-03-10
RE/0066-PRJ-T1-CIV-RS-SU | Reinforcement Supply | 2010 | GR01 | 2010 | SMARTWORLD THE EDITION | Petropol India LimitedSANJAY GUPTA | 9110001558 | 20 |  |  | 2026-02-10 | Steel Re-bar TMT 08 mm Dia. FE-550D | TO | 19 | 55300 | 1050700 | 1239826 | 1050700 | 1239826 | 0 | 1050700 | 1239826 | ZMAT | 2026-02-10 | 2026-03-10
RE/0066-PRJ-T1-CIV-RS-SU | Reinforcement Supply | 2010 | GR01 | 2010 | SMARTWORLD THE EDITION | Ram Niwas & SonsDeepak gupta | 9110001607 | 10 |  |  | 2026-03-11 | Steel Re-bar TMT 10 mm Dia. FE-550D | TO | 37 | 55800 | 2064600 | 2436228 | 2064600 | 2436228 | 0 | 2064600 | 2436228 | ZMAT | 2026-03-11 | 2026-04-11
RE/0066-PRJ-T1-CIV-RS-SU | Reinforcement Supply | 2010 | GR01 | 2010 | SMARTWORLD THE EDITION | Ram Niwas & SonsDeepak gupta | 9110001607 | 70 |  |  | 2026-03-11 | Steel Re-bar TMT 08 mm Dia. FE-550D | TO | 30 | 56800 | 1704000 | 2010720 | 1698320 | 2004017.6 | 5680 | 1698320 | 2004017.6 | ZMAT | 2026-03-11 | 2026-04-11
RE/0066-PRJ-T1-CIV-RS-SU | Reinforcement Supply | 2010 | GR01 | 2010 | SMARTWORLD THE EDITION | Ram Niwas & SonsDeepak gupta | 9110001607 | 80 |  |  | 2026-03-11 | Steel Re-bar TMT 08 mm Dia. FE-550D | TO | 30 | 56800 | 1704000 | 2010720 | 1704000 | 2010720 | 0 | 1704000 | 2010720 | ZMAT | 2026-03-11 | 2026-04-11
RE/0066-PRJ-T1-CIV-RS-SU | Reinforcement Supply | 2010 | GR01 | 2010 | SMARTWORLD THE EDITION | ESL STEEL LIMITED | 9110001613 | 10 |  |  | 2026-03-11 | Steel Re-bar TMT 12 mm Dia. FE-550D | TO | 37 | 58250 | 2155250 | 2543195 | 2155250 | 2543195 | 0 | 2155250 | 2543195 | ZMAT | 2026-03-11 | 2026-04-11
RE/0066-PRJ-T1-CIV-RS-SU | Reinforcement Supply | 2010 | GR01 | 2010 | SMARTWORLD THE EDITION | ESL STEEL LIMITED | 9110001613 | 70 |  |  | 2026-03-11 | Steel Re-bar TMT 16 mm Dia. FE-550D | TO | 30 | 58250 | 1747500 | 2062050 | 1747500 | 2062050 | 0 | 1747500 | 2062050 | ZMAT | 2026-03-11 | 2026-04-11
RE/0066-PRJ-T1-CIV-RS-SU | Reinforcement Supply | 2010 | GR01 | 2010 | SMARTWORLD THE EDITION | ESL STEEL LIMITED | 9110001613 | 130 |  |  | 2026-03-11 | Steel Re-bar TMT 20 mm Dia. FE-550D | TO | 27 | 58250 | 1572750 | 1855845 | 1572750 | 1855845 | 0 | 1572750 | 1855845 | ZMAT | 2026-03-11 | 2026-04-11
RE/0066-PRJ-T1-CIV-RS-SU | Reinforcement Supply | 2010 | GR01 | 2010 | SMARTWORLD THE EDITION | ESL STEEL LIMITED | 9110001613 | 190 |  |  | 2026-03-11 | Steel Re-bar TMT 25 mm Dia. FE-550D | TO | 25 | 58250 | 1456250 | 1718375 | 1456250 | 1718375 | 0 | 1456250 | 1718375 | ZMAT | 2026-03-11 | 2026-04-11
RE/0066-PRJ-T1-CIV-RS-SU | Reinforcement Supply | 2010 | GR01 | 2010 | SMARTWORLD THE EDITION | Ram Niwas & SonsDeepak gupta | 9110001691 | 10 |  |  | 2026-04-10 | Steel Re-bar TMT 08 mm Dia. FE-550D | TO | 33 | 60800 | 2006400 | 2367552 | 2006400 | 2367552 | 0 | 2006400 | 2367552 | ZMAT | 2026-04-10 | 2026-05-10
RE/0066-PRJ-T1-CIV-RS-SU | Reinforcement Supply | 2010 | GR01 | 2010 | SMARTWORLD THE EDITION | Ram Niwas & SonsDeepak gupta | 9110001691 | 20 |  |  | 2026-04-10 | Steel Re-bar TMT 08 mm Dia. FE-550D | TO | 33 | 60800 | 2006400 | 2367552 | 2006400 | 2367552 | 0 | 2006400 | 2367552 | ZMAT | 2026-04-10 | 2026-05-10
RE/0066-PRJ-T1-CIV-RS-SU | Reinforcement Supply | 2010 | GR01 | 2010 | SMARTWORLD THE EDITION | Ram Niwas & SonsDeepak gupta | 9110001691 | 70 |  |  | 2026-04-10 | Steel Re-bar TMT 10 mm Dia. FE-550D | TO | 8 | 59800 | 478400 | 564512 | 478400 | 564512 | 0 | 478400 | 564512 | ZMAT | 2026-04-10 | 2026-05-10
RE/0066-PRJ-T1-CIV-RS-SU | Reinforcement Supply | 2010 | GR01 | 2010 | SMARTWORLD THE EDITION | ESL STEEL LIMITED | 9110001698 | 10 |  |  | 2026-04-10 | Steel Re-bar TMT 12 mm Dia. FE-550D | TO | 43 | 60500 | 2601500 | 3069770 | 2601500 | 3069770 | 0 | 2601500 | 3069770 | ZMAT | 2026-04-10 | 2026-05-10
RE/0066-PRJ-T1-CIV-RS-SU | Reinforcement Supply | 2010 | GR01 | 2010 | SMARTWORLD THE EDITION | ESL STEEL LIMITED | 9110001698 | 70 |  |  | 2026-04-10 | Steel Re-bar TMT 16 mm Dia. FE-550D | TO | 8.5 | 60500 | 514250 | 606815 | 526350 | 621093 | 12100 | 526350 | 621093 | ZMAT | 2026-04-10 | 2026-05-10
RE/0066-PRJ-T1-CIV-RS-SU | Reinforcement Supply | 2010 | GR01 | 2010 | SMARTWORLD THE EDITION | ESL STEEL LIMITED | 9110001698 | 130 |  |  | 2026-04-10 | Steel Re-bar TMT 20 mm Dia. FE-550D | TO | 14 | 60500 | 847000 | 999460 | 847000 | 999460 | 0 | 847000 | 999460 | ZMAT | 2026-04-10 | 2026-05-10
RE/0066-PRJ-T1-CIV-RS-SU | Reinforcement Supply | 2010 | GR01 | 2010 | SMARTWORLD THE EDITION | ESL STEEL LIMITED | 9110001698 | 190 |  |  | 2026-04-10 | Steel Re-bar TMT 25 mm Dia. FE-550D | TO | 25 | 60500 | 1512500 | 1784750 | 1512500 | 1784750 | 0 | 1512500 | 1784750 | ZMAT | 2026-04-10 | 2026-05-10
RE/0066-PRJ-T1-CIV-RS-SU | Reinforcement Supply | 2010 | GR01 | 2010 | SMARTWORLD THE EDITION | ESL STEEL LIMITED | 9110001698 | 250 |  |  | 2026-04-10 | Steel Re-bar TMT 32 mm Dia. FE-550D | TO | 7 | 60500 | 423500 | 499730 | 423500 | 499730 | 0 | 423500 | 499730 | ZMAT | 2026-04-10 | 2026-05-10
RE/0066-PRJ-T1-CIV-RS-SU | Reinforcement Supply | 2010 | GR01 | 2010 | SMARTWORLD THE EDITION | Petropol India LimitedSANJAY GUPTA | 9110001791 | 10 |  |  | 2026-05-11 | Steel Re-bar TMT 08 mm Dia. FE-550D | TO | 54 | 55700 | 3007800 | 3549204 | 3007800 | 3549204 | 0 | 3007800 | 3549204 | ZMAT | 2026-05-11 | 2026-06-11
RE/0066-PRJ-T1-CIV-RS-SU | Reinforcement Supply | 2010 | GR01 | 2010 | SMARTWORLD THE EDITION | Petropol India LimitedSANJAY GUPTA | 9110001791 | 20 |  |  | 2026-05-11 | Steel Re-bar TMT 08 mm Dia. FE-550D | TO | 54 | 55700 | 3007800 | 3549204 | 3007800 | 3549204 | 0 | 3007800 | 3549204 | ZMAT | 2026-05-11 | 2026-06-11
RE/0066-PRJ-T1-CIV-RS-SU | Reinforcement Supply | 2010 | GR01 | 2010 | SMARTWORLD THE EDITION | Petropol India LimitedSANJAY GUPTA | 9110001791 | 70 |  |  | 2026-05-11 | Steel Re-bar TMT 10 mm Dia. FE-550D | TO | 4 | 54700 | 218800 | 258184 | 218800 | 258184 | 0 | 218800 | 258184 | ZMAT | 2026-05-11 | 2026-06-11
RE/0066-PRJ-T1-CIV-RS-SU | Reinforcement Supply | 2010 | GR01 | 2010 | SMARTWORLD THE EDITION | Jindal Steel Limited | 9110001796 | 10 |  |  | 2026-05-11 | Steel Re-bar TMT 12 mm Dia. FE-550D | TO | 33 | 57200 | 1887600 | 2227368 | 1887600 | 2227368 | 0 | 0 | 0 | ZMAT | 2026-05-11 | 2026-06-11
RE/0066-PRJ-T1-CIV-RS-SU | Reinforcement Supply | 2010 | GR01 | 2010 | SMARTWORLD THE EDITION | Jindal Steel Limited | 9110001796 | 70 |  |  | 2026-05-11 | Steel Re-bar TMT 16 mm Dia. FE-550D | TO | 3 | 57200 | 171600 | 202488 | 85800 | 101244 | 85800 | 0 | 0 | ZMAT | 2026-05-11 | 2026-06-11
RE/0066-PRJ-T1-CIV-RS-SU | Reinforcement Supply | 2010 | GR01 | 2010 | SMARTWORLD THE EDITION | Jindal Steel Limited | 9110001796 | 130 |  |  | 2026-05-11 | Steel Re-bar TMT 20 mm Dia. FE-550D | TO | 29 | 57200 | 1658800 | 1957384 | 1658800 | 1957384 | 0 | 0 | 0 | ZMAT | 2026-05-11 | 2026-06-11
RE/0066-PRJ-T1-CIV-RS-SU | Reinforcement Supply | 2010 | GR01 | 2010 | SMARTWORLD THE EDITION | Jindal Steel Limited | 9110001796 | 190 |  |  | 2026-05-11 | Steel Re-bar TMT 25 mm Dia. FE-550D | TO | 13 | 57200 | 743600 | 877448 | 713512.8 | 841945.1 | 30087.2 | 0 | 0 | ZMAT | 2026-05-11 | 2026-06-11
RE/0066-PRJ-T1-CIV-RS-SU | Reinforcement Supply | 2010 | GR01 | 2010 | SMARTWORLD THE EDITION | Jindal Steel Limited | 9110001796 | 250 |  |  | 2026-05-11 | Steel Re-bar TMT 32 mm Dia. FE-550D | TO | 4 | 57200 | 228800 | 269984 | 228800 | 269984 | 0 | 0 | 0 | ZMAT | 2026-05-11 | 2026-06-11
RE/0066-PRJ-T1-CIV-RS-SU | Reinforcement Supply | 2010 | GR01 | 2010 | SMARTWORLD THE EDITION | DAGA TRADING COMPANY PVT. LTD. | 9110001848 | 10 |  |  | 2026-06-09 | Steel mesh For NS wall | TO | 3 | 72000 | 216000 | 254880 | 0 | 0 | 216000 | 0 | 0 | ZMAT | 2026-06-06 | 2026-07-06
RE/0066-PRJ-T1-CIV-SW-AS | Aluminum Shuttering | 2010 | GR01 | 2010 | SMARTWORLD THE EDITION | Ahluwalia Contracts India Limited | 9140000321 | 50 |  |  | 2024-07-20 | CENTERING & SHUTTERING Part A | AU | 1 | 0 | 165879580.36 | 195737904.82 | 39289550.57 | 46361669.67 | 126590029.79 | 35360656.66 | 41725574.86 | ZSER | 2024-07-15 | 2027-01-14
RE/0066-PRJ-T1-CIV-SW-CS | Conventional Shuttering | 2010 | GR01 | 2010 | SMARTWORLD THE EDITION | Ahluwalia Contracts India Limited | 9140000321 | 50 |  |  | 2024-07-20 | CENTERING & SHUTTERING Part A | AU | 1 | 0 | 18183985.36 | 21457102.72 | 15783450.8 | 18624471.94 | 2400534.56 | 15783450.84 | 18624471.99 | ZSER | 2024-07-15 | 2027-01-14
RE/0066-PRJ-T1-CIV-SW-SO | Shuttering Other | 2010 | GR01 | 2010 |  |  |  | 0 | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
RE/0066-PRJ-T1-CIV-WP | Waterproofing Works | 2010 | GR01 | 2010 | SMARTWORLD THE EDITION | Ahluwalia Contracts India Limited | 9140000321 | 110 |  |  | 2024-07-20 | FLOORING | AU | 1 | 0 | 1433 | 1690.94 | 0 | 0 | 1433 | 0 | 0 | ZSER | 2024-07-15 | 2027-01-14
RE/0066-PRJ-T1-CIV-WP | Waterproofing Works | 2010 | GR01 | 2010 | SMARTWORLD THE EDITION | Ahluwalia Contracts India Limited | 9140000321 | 120 |  |  | 2024-07-20 | WATER-PROOFING WORKS | AU | 1 | 0 | 19000859.04 | 22421013.67 | 700376.11 | 826443.81 | 18300482.93 | 700376.11 | 826443.81 | ZSER | 2024-07-15 | 2027-01-14
RE/0066-PRJ-T1-FAC-EF | Elevation Feature | 2010 | GR01 | 2010 | SMARTWORLD THE EDITION | Ahluwalia Contracts India Limited | 9140000321 | 100 |  |  | 2024-07-20 | STRUCTURAL STEEL WORKS | AU | 1 | 0 | 0.01 | 0.01 | 0 | 0 | 0.01 | 0 | 0 | ZSER | 2024-07-15 | 2027-01-14
RE/0066-PRJ-T1-FAC-EF | Elevation Feature | 2010 | GR01 | 2010 | SMARTWORLD THE EDITION | MECH TECHNO FACADE SOLUTIONSSMukesh Kumar Panday | 9140000654 | 10 |  |  | 2026-05-14 | Facade ( Alu Sheet ) -3 Floor-Lead | AU | 1 | 1400000.6 | 1400000.6 | 1652000.71 | 0 | 0 | 1400000.6 | 0 | 0 | ZSER | 2026-05-07 | 2026-07-07
RE/0066-PRJ-T1-FAC-EP | External Paint | 2010 | GR01 | 2010 | SMARTWORLD THE EDITION | Ahluwalia Contracts India Limited | 9140000321 | 160 |  |  | 2024-07-20 | Amed-Monthly rental payment to M/S ACIL | AU | 1 | 0 | 4866880 | 5742918.4 | 0 | 0 | 4866880 | 0 | 0 | ZSER | 2024-07-15 | 2027-01-14
RE/0066-PRJ-T1-FAC-GL | Glazing Works | 2010 | GR01 | 2010 | SMARTWORLD THE EDITION | SHANKAR FENESTRATIONS & GLASSES IND PRIVATE LIMITED | 9140000606 | 10 |  |  | 2026-03-10 | Glazing & Railing Work - Lead Apartment | AU | 1 | 2517563.98 | 2517563.98 | 2970725.5 | 0 | 0 | 2517563.98 | 0 | 0 | ZSER | 2026-02-04 | 2026-03-19
RE/0066-PRJ-T1-FAC-RA | Railing Works | 2010 | GR01 | 2010 |  |  |  | 0 | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
RE/0066-PRJ-T1-FIS-CF | Ceiling Finish Works | 2010 | GR01 | 2010 | SMARTWORLD THE EDITION | H. S. OBEROI BUILDTECH PVT. LTD.MANISH SINGH | 9140000561 | 40 |  |  | 2026-01-31 | Lead Apt 3.5+4.5 BHK Finishing -LOA | AU | 1 | 3715454.04 | 655671.87 | 773692.81 | 0 | 0 | 655671.87 | 0 | 0 | ZSER | 2026-01-16 | 2026-04-16
RE/0066-PRJ-T1-FIS-CF | Ceiling Finish Works | 2010 | GR01 | 2010 | SMARTWORLD THE EDITION | JJDJ CONSTRUCTION PVT. LTD. | 9140000602 | 10 |  |  | 2026-03-10 | Finishing Work - T1 | AU | 1 | 0 | 76049264.22 | 89738131.78 | 0 | 0 | 76049264.22 | 0 | 0 | ZSER | 2026-04-03 | 2028-04-03
RE/0066-PRJ-T1-FIS-CF | Ceiling Finish Works | 2010 | GR01 | 2010 | SMARTWORLD THE EDITION | JJDJ CONSTRUCTION PVT. LTD. | 9140000602 | 20 |  |  | 2026-03-10 | Finishing Work - Lift Lobby-T1 | AU | 1 | 46230888.06 | 1167800 | 1378004 | 0 | 0 | 1167800 | 0 | 0 | ZSER | 2026-04-03 | 2028-04-03
RE/0066-PRJ-T1-FIS-CF | Ceiling Finish Works | 2010 | GR01 | 2010 | SMARTWORLD THE EDITION | H. S. OBEROI BUILDTECH PVT. LTD.MANISH SINGH | 9140000689 | 10 |  |  | 2026-06-10 | Finishing Work - T1 | AU | 1 | 0 | 76049264.22 | 89738131.78 | 0 | 0 | 76049264.22 | 0 | 0 | ZSER | 2026-04-03 | 2028-04-03
RE/0066-PRJ-T1-FIS-CF | Ceiling Finish Works | 2010 | GR01 | 2010 | SMARTWORLD THE EDITION | H. S. OBEROI BUILDTECH PVT. LTD.MANISH SINGH | 9140000689 | 20 |  |  | 2026-06-10 | Finishing Work - Lift Lobby-T1 | AU | 1 | 46230888.06 | 1167800 | 1378004 | 0 | 0 | 1167800 | 0 | 0 | ZSER | 2026-04-03 | 2028-04-03
RE/0066-PRJ-T1-FIS-DW | Door Works | 2010 | GR01 | 2010 | SMARTWORLD THE EDITION | DORSET INDUSTRIES PRIVATE LIMITED | 9110001657 | 10 |  |  | 2026-03-31 | Main Door Biometric Lock ( Including Al | NO | 1 | 18402 | 18402 | 21714.36 | 0 | 0 | 18402 | 0 | 0 | ZMAT | 2026-02-04 | 2026-03-04
RE/0066-PRJ-T1-FIS-DW | Door Works | 2010 | GR01 | 2010 | SMARTWORLD THE EDITION | DORSET INDUSTRIES PRIVATE LIMITED | 9110001657 | 20 |  |  | 2026-03-31 | Main Door Catcher Magnetic | NO | 2 | 390 | 780 | 920.4 | 0 | 0 | 780 | 0 | 0 | ZMAT | 2026-02-04 | 2026-03-04
RE/0066-PRJ-T1-FIS-DW | Door Works | 2010 | GR01 | 2010 | SMARTWORLD THE EDITION | DORSET INDUSTRIES PRIVATE LIMITED | 9110001657 | 30 |  |  | 2026-03-31 | Main Door Hinges 125mm | NO | 10 | 211 | 2110 | 2489.8 | 2110 | 2489.8 | 0 | 2110 | 2489.8 | ZMAT | 2026-02-04 | 2026-03-04
RE/0066-PRJ-T1-FIS-DW | Door Works | 2010 | GR01 | 2010 | SMARTWORLD THE EDITION | DORSET INDUSTRIES PRIVATE LIMITED | 9110001657 | 40 |  |  | 2026-03-31 | Door Handle with lock body | NO | 4 | 1548 | 6192 | 7306.56 | 1548 | 1826.64 | 4644 | 1548 | 1826.64 | ZMAT | 2026-02-04 | 2026-03-04
RE/0066-PRJ-T1-FIS-DW | Door Works | 2010 | GR01 | 2010 | SMARTWORLD THE EDITION | DORSET INDUSTRIES PRIVATE LIMITED | 9110001657 | 50 |  |  | 2026-03-31 | Main Door Catcher Magnetic | NO | 4 | 390 | 1560 | 1840.8 | 1560 | 1840.8 | 0 | 1560 | 1840.8 | ZMAT | 2026-02-04 | 2026-03-04
RE/0066-PRJ-T1-FIS-DW | Door Works | 2010 | GR01 | 2010 | SMARTWORLD THE EDITION | DORSET INDUSTRIES PRIVATE LIMITED | 9110001657 | 60 |  |  | 2026-03-31 | Hinges | NO | 36 | 179 | 6444 | 7603.92 | 6444 | 7603.92 | 0 | 6444 | 7603.92 | ZMAT | 2026-02-04 | 2026-03-04
RE/0066-PRJ-T1-FIS-DW | Door Works | 2010 | GR01 | 2010 | SMARTWORLD THE EDITION | DORSET INDUSTRIES PRIVATE LIMITED | 9110001657 | 70 |  |  | 2026-03-31 | Door Handle with lock body | NO | 4 | 1528 | 6112 | 7212.16 | 0 | 0 | 6112 | 0 | 0 | ZMAT | 2026-02-04 | 2026-03-04
RE/0066-PRJ-T1-FIS-DW | Door Works | 2010 | GR01 | 2010 | SMARTWORLD THE EDITION | DORSET INDUSTRIES PRIVATE LIMITED | 9110001657 | 80 |  |  | 2026-03-31 | Hinges 4 | NO | 36 | 179 | 6444 | 7603.92 | 6444 | 7603.92 | 0 | 6444 | 7603.92 | ZMAT | 2026-02-04 | 2026-03-04
RE/0066-PRJ-T1-FIS-DW | Door Works | 2010 | GR01 | 2010 | SMARTWORLD THE EDITION | DORSET INDUSTRIES PRIVATE LIMITED | 9110001657 | 90 |  |  | 2026-03-31 | Main Door Catcher Magnetic | NO | 15 | 390 | 5850 | 6903 | 0 | 0 | 5850 | 0 | 0 | ZMAT | 2026-02-04 | 2026-03-04
RE/0066-PRJ-T1-FIS-DW | Door Works | 2010 | GR01 | 2010 | SMARTWORLD THE EDITION | OZONE OVERSEAS LTD.Mr.Ankush | 9110001658 | 10 |  |  | 2026-03-31 | Biometric Lock | NO | 1 | 18900 | 18900 | 22302 | 0 | 0 | 18900 | 0 | 0 | ZMAT | 2026-02-04 | 2026-02-24
RE/0066-PRJ-T1-FIS-DW | Door Works | 2010 | GR01 | 2010 | SMARTWORLD THE EDITION | OZONE OVERSEAS LTD.Mr.Ankush | 9110001658 | 20 |  |  | 2026-03-31 | Door Handle with lock body | NO | 5 | 2200 | 11000 | 12980 | 11000 | 12980 | 0 | 11000 | 12980 | ZMAT | 2026-02-04 | 2026-02-24
RE/0066-PRJ-T1-FIS-DW | Door Works | 2010 | GR01 | 2010 | SMARTWORLD THE EDITION | OZONE OVERSEAS LTD.Mr.Ankush | 9110001658 | 30 |  |  | 2026-03-31 | Door Handle with lock body | NO | 5 | 2200 | 11000 | 12980 | 11000 | 12980 | 0 | 11000 | 12980 | ZMAT | 2026-02-04 | 2026-02-24
RE/0066-PRJ-T1-FIS-DW | Door Works | 2010 | GR01 | 2010 | SMARTWORLD THE EDITION | R.K. Sales CorporationMr. Sanjeev Gupta | 9140000599 | 10 |  |  | 2026-03-10 | S & F of Wooden Doors 3.5 BHK | AU | 1 | 194845 | 194845 | 229917.1 | 194845 | 229917.1 | 0 | 194845 | 229917.1 | ZSER | 2026-01-29 | 2026-03-16
RE/0066-PRJ-T1-FIS-DW | Door Works | 2010 | GR01 | 2010 | SMARTWORLD THE EDITION | R.K. Sales CorporationMr. Sanjeev Gupta | 9140000599 | 20 |  |  | 2026-03-10 | S & F of Wooden Doors 4.5 BHK | AU | 1 | 226475 | 226475 | 267240.5 | 226475 | 267240.5 | 0 | 226475 | 267240.5 | ZSER | 2026-01-29 | 2026-03-16
RE/0066-PRJ-T1-FIS-DW | Door Works | 2010 | GR01 | 2010 | SMARTWORLD THE EDITION | Bhawani Fire Protection PVT LTD | 9140000600 | 10 |  |  | 2026-03-10 | SITC Fire Door - Lead Apartment | AU | 1 | 94371 | 94371 | 111357.78 | 0 | 0 | 94371 | 0 | 0 | ZSER | 2026-01-29 | 2026-03-16
RE/0066-PRJ-T1-FIS-DW | Door Works | 2010 | GR01 | 2010 | SMARTWORLD THE EDITION | UNISYSTEMRohit Gautam | 9140000601 | 10 |  |  | 2026-03-10 | Glazing & Railing Work -Lead Apartment | AU | 1 | 944552.87 | 944552.87 | 1114572.39 | 923122.92 | 1089285.04 | 21429.95 | 923122.92 | 1089285.04 | ZSER | 2026-02-05 | 2026-03-20
RE/0066-PRJ-T1-FIS-DW | Door Works | 2010 | GR01 | 2010 | SMARTWORLD THE EDITION | R.K. Sales CorporationMr. Sanjeev Gupta | 9140000690 | 10 |  |  | 2026-06-12 | Supply Installation of Doors & Panelling | AU | 1 | 143538.24 | 143538.24 | 169375.12 | 0 | 0 | 143538.24 | 0 | 0 | ZSER | 2026-02-27 | 2026-03-27
RE/0066-PRJ-T1-FIS-DW | Door Works | 2010 | GR01 | 2010 | SMARTWORLD THE EDITION | R.K. Sales CorporationMr. Sanjeev Gupta | 9140000690 | 10 |  |  | 2026-06-12 | Supply Installation of Doors & Panelling | AU | 1 | 0 | 143538.24 | 169375.12 | 0 | 0 | 143538.24 | 0 | 0 | ZSER | 2026-02-27 | 2026-03-27
RE/0066-PRJ-T1-FIS-FF | Floor Finish Works | 2010 | GR01 | 2010 | SMARTWORLD THE EDITION | Ahluwalia Contracts India Limited | 9140000321 | 110 |  |  | 2024-07-20 | FLOORING | AU | 1 | 0 | 10332767.25 | 12192665.36 | 926063.05 | 1092754.4 | 9406704.2 | 416728.37 | 491739.48 | ZSER | 2024-07-15 | 2027-01-14
RE/0066-PRJ-T1-FIS-FF | Floor Finish Works | 2010 | GR01 | 2010 | SMARTWORLD THE EDITION | H. S. OBEROI BUILDTECH PVT. LTD.MANISH SINGH | 9140000561 | 40 |  |  | 2026-01-31 | Lead Apt 3.5+4.5 BHK Finishing -LOA | AU | 1 | 0 | 1605517.37 | 1894510.5 | 0 | 0 | 1605517.37 | 0 | 0 | ZSER | 2026-01-16 | 2026-04-16
RE/0066-PRJ-T1-FIS-FF | Floor Finish Works | 2010 | GR01 | 2010 | SMARTWORLD THE EDITION | JJDJ CONSTRUCTION PVT. LTD. | 9140000602 | 10 |  |  | 2026-03-10 | Finishing Work - T1 | AU | 1 | 0 | 115430682 | 136208204.76 | 0 | 0 | 115430682 | 0 | 0 | ZSER | 2026-04-03 | 2028-04-03
RE/0066-PRJ-T1-FIS-FF | Floor Finish Works | 2010 | GR01 | 2010 | SMARTWORLD THE EDITION | JJDJ CONSTRUCTION PVT. LTD. | 9140000602 | 20 |  |  | 2026-03-10 | Finishing Work - Lift Lobby-T1 | AU | 1 | 0 | 26590118.4 | 31376339.71 | 0 | 0 | 26590118.4 | 0 | 0 | ZSER | 2026-04-03 | 2028-04-03
RE/0066-PRJ-T1-FIS-FF | Floor Finish Works | 2010 | GR01 | 2010 | SMARTWORLD THE EDITION | H. S. OBEROI BUILDTECH PVT. LTD.MANISH SINGH | 9140000689 | 10 |  |  | 2026-06-10 | Finishing Work - T1 | AU | 1 | 0 | 115430682 | 136208204.76 | 0 | 0 | 115430682 | 0 | 0 | ZSER | 2026-04-03 | 2028-04-03
RE/0066-PRJ-T1-FIS-FF | Floor Finish Works | 2010 | GR01 | 2010 | SMARTWORLD THE EDITION | H. S. OBEROI BUILDTECH PVT. LTD.MANISH SINGH | 9140000689 | 20 |  |  | 2026-06-10 | Finishing Work - Lift Lobby-T1 | AU | 1 | 0 | 26590118.4 | 31376339.71 | 0 | 0 | 26590118.4 | 0 | 0 | ZSER | 2026-04-03 | 2028-04-03
RE/0066-PRJ-T1-FIS-LF | Lobby Furniture | 2010 | GR01 | 2010 |  |  |  | 0 | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
RE/0066-PRJ-T1-FIS-MI | Misc Finish Works | 2010 | GR01 | 2010 | SMARTWORLD THE EDITION | H. S. OBEROI BUILDTECH PVT. LTD.MANISH SINGH | 9140000561 | 40 |  |  | 2026-01-31 | Lead Apt 3.5+4.5 BHK Finishing -LOA | AU | 1 | 0 | 51537.5 | 60814.25 | 0 | 0 | 51537.5 | 0 | 0 | ZSER | 2026-01-16 | 2026-04-16
RE/0066-PRJ-T1-FIS-MI | Misc Finish Works | 2010 | GR01 | 2010 | SMARTWORLD THE EDITION | JJDJ CONSTRUCTION PVT. LTD. | 9140000602 | 10 |  |  | 2026-03-10 | Finishing Work - T1 | AU | 1 | 0 | 17369812 | 20496378.16 | 0 | 0 | 17369812 | 0 | 0 | ZSER | 2026-04-03 | 2028-04-03
RE/0066-PRJ-T1-FIS-MI | Misc Finish Works | 2010 | GR01 | 2010 | SMARTWORLD THE EDITION | JJDJ CONSTRUCTION PVT. LTD. | 9140000602 | 30 |  |  | 2026-03-10 | Incentive | AU | 1 | 15649288.53 | 15649288.53 | 18466160.47 | 0 | 0 | 15649288.53 | 0 | 0 | ZSER | 2026-04-03 | 2028-04-03
RE/0066-PRJ-T1-FIS-MI | Misc Finish Works | 2010 | GR01 | 2010 | SMARTWORLD THE EDITION | H. S. OBEROI BUILDTECH PVT. LTD.MANISH SINGH | 9140000689 | 10 |  |  | 2026-06-10 | Finishing Work - T1 | AU | 1 | 0 | 17369812 | 20496378.16 | 0 | 0 | 17369812 | 0 | 0 | ZSER | 2026-04-03 | 2028-04-03
RE/0066-PRJ-T1-FIS-MK | Modular Kitchen Works | 2010 | GR01 | 2010 |  |  |  | 0 | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
RE/0066-PRJ-T1-FIS-MS | MS works | 2010 | GR01 | 2010 | SMARTWORLD THE EDITION | H. S. OBEROI BUILDTECH PVT. LTD.MANISH SINGH | 9140000561 | 40 |  |  | 2026-01-31 | Lead Apt 3.5+4.5 BHK Finishing -LOA | AU | 1 | 0 | 65250 | 76995 | 0 | 0 | 65250 | 0 | 0 | ZSER | 2026-01-16 | 2026-04-16
RE/0066-PRJ-T1-FIS-MS | MS works | 2010 | GR01 | 2010 | SMARTWORLD THE EDITION | JJDJ CONSTRUCTION PVT. LTD. | 9140000602 | 10 |  |  | 2026-03-10 | Finishing Work - T1 | AU | 1 | 0 | 3068000 | 3620240 | 0 | 0 | 3068000 | 0 | 0 | ZSER | 2026-04-03 | 2028-04-03
RE/0066-PRJ-T1-FIS-MS | MS works | 2010 | GR01 | 2010 | SMARTWORLD THE EDITION | H. S. OBEROI BUILDTECH PVT. LTD.MANISH SINGH | 9140000689 | 10 |  |  | 2026-06-10 | Finishing Work - T1 | AU | 1 | 0 | 3068000 | 3620240 | 0 | 0 | 3068000 | 0 | 0 | ZSER | 2026-04-03 | 2028-04-03
RE/0066-PRJ-T1-FIS-WF | Wall Finish Works | 2010 | GR01 | 2010 | SMARTWORLD THE EDITION | H. S. OBEROI BUILDTECH PVT. LTD.MANISH SINGH | 9140000561 | 40 |  |  | 2026-01-31 | Lead Apt 3.5+4.5 BHK Finishing -LOA | AU | 1 | 0 | 1140276.8 | 1345526.62 | 0 | 0 | 1140276.8 | 0 | 0 | ZSER | 2026-01-16 | 2026-04-16
RE/0066-PRJ-T1-FIS-WF | Wall Finish Works | 2010 | GR01 | 2010 | SMARTWORLD THE EDITION | JJDJ CONSTRUCTION PVT. LTD. | 9140000602 | 10 |  |  | 2026-03-10 | Finishing Work - T1 | AU | 1 | 0 | 85943260 | 101413046.8 | 0 | 0 | 85943260 | 0 | 0 | ZSER | 2026-04-03 | 2028-04-03
RE/0066-PRJ-T1-FIS-WF | Wall Finish Works | 2010 | GR01 | 2010 | SMARTWORLD THE EDITION | JJDJ CONSTRUCTION PVT. LTD. | 9140000602 | 20 |  |  | 2026-03-10 | Finishing Work - Lift Lobby-T1 | AU | 1 | 0 | 18472969.66 | 21798104.2 | 0 | 0 | 18472969.66 | 0 | 0 | ZSER | 2026-04-03 | 2028-04-03
RE/0066-PRJ-T1-FIS-WF | Wall Finish Works | 2010 | GR01 | 2010 | SMARTWORLD THE EDITION | H. S. OBEROI BUILDTECH PVT. LTD.MANISH SINGH | 9140000689 | 10 |  |  | 2026-06-10 | Finishing Work - T1 | AU | 1 | 0 | 85943260 | 101413046.8 | 0 | 0 | 85943260 | 0 | 0 | ZSER | 2026-04-03 | 2028-04-03
RE/0066-PRJ-T1-FIS-WF | Wall Finish Works | 2010 | GR01 | 2010 | SMARTWORLD THE EDITION | H. S. OBEROI BUILDTECH PVT. LTD.MANISH SINGH | 9140000689 | 20 |  |  | 2026-06-10 | Finishing Work - Lift Lobby-T1 | AU | 1 | 0 | 18472969.66 | 21798104.2 | 0 | 0 | 18472969.66 | 0 | 0 | ZSER | 2026-04-03 | 2028-04-03
RE/0066-PRJ-T1-FIS-WO | Wood Work | 2010 | GR01 | 2010 | SMARTWORLD THE EDITION | H. S. OBEROI BUILDTECH PVT. LTD.MANISH SINGH | 9140000561 | 40 |  |  | 2026-01-31 | Lead Apt 3.5+4.5 BHK Finishing -LOA | AU | 1 | 0 | 197200.5 | 232696.59 | 0 | 0 | 197200.5 | 0 | 0 | ZSER | 2026-01-16 | 2026-04-16
RE/0066-PRJ-T1-MEP-EW-HE | High Side Electrical Works | 2010 | GR01 | 2010 | SMARTWORLD THE EDITION | Dehn India Pvt Ltd | 9140000379 | 10 |  |  | 2024-10-24 | Lightning Protection System for Basement | AU | 1 | 0 | 979507 | 1155818.26 | 144535.06 | 170551.37 | 834971.94 | 144535.08 | 170551.4 | ZSER | 2024-10-24 | 2027-08-23
RE/0066-PRJ-T1-MEP-EW-HE | High Side Electrical Works | 2010 | GR01 | 2010 | SMARTWORLD THE EDITION | SATKARTAR ELECTRICALS AND ELECTRONIPRIVATE LIMITED | 9140000677 | 10 |  |  | 2026-06-02 | Electrical Works Tower T1 | AU | 1 | 57350927.96 | 53600765.21 | 63248902.95 | 0 | 0 | 53600765.21 | 0 | 0 | ZSER | 2026-06-01 | 2028-02-01
RE/0066-PRJ-T1-MEP-EW-HE | High Side Electrical Works | 2010 | GR01 | 2010 | SMARTWORLD THE EDITION | TRIPLE A ENGINEERING PRIVATE LIMIT | 9140000688 | 10 |  |  | 2026-06-06 | Electrical Works Tower T1 | AU | 1 | 86257348.53 | 47226960.39 | 47226960.39 | 0 | 0 | 47226960.39 | 0 | 0 | ZSER | 2026-06-01 | 2028-02-01
RE/0066-PRJ-T1-MEP-EW-HE | High Side Electrical Works | 2010 | GR01 | 2010 | SMARTWORLD THE EDITION | TRIPLE A ENGINEERING PRIVATE LIMIT | 9140000688 | 40 |  |  | 2026-06-06 | Electrical Works Tower T4 | AU | 1 | 60790282.68 | 144.9 | 144.9 | 0 | 0 | 144.9 | 0 | 0 | ZSER | 2026-06-01 | 2028-02-01
RE/0066-PRJ-T1-MEP-EW-LE | Low Side Electrical Works | 2010 | GR01 | 2010 | SMARTWORLD THE EDITION | Shree Krishna Secauto Private Limit | 9110001835 | 10 |  |  | 2026-06-03 | Wiser Wifi Relay- 2 channel | NO | 5 | 4000 | 20000 | 23600 | 0 | 0 | 20000 | 0 | 0 | ZMAT
RE/0066-PRJ-T1-MEP-EW-LE | Low Side Electrical Works | 2010 | GR01 | 2010 | SMARTWORLD THE EDITION | Shree Krishna Secauto Private Limit | 9110001835 | 20 |  |  | 2026-06-03 | Wiser heavy load Relay-1 Channel | NO | 1 | 4200 | 4200 | 4956 | 0 | 0 | 4200 | 0 | 0 | ZMAT
RE/0066-PRJ-T1-MEP-EW-LE | Low Side Electrical Works | 2010 | GR01 | 2010 | SMARTWORLD THE EDITION | Shree Krishna Secauto Private Limit | 9110001835 | 30 |  |  | 2026-06-03 | Wiser IR Controller For AC | NO | 1 | 3800 | 3800 | 4484 | 0 | 0 | 3800 | 0 | 0 | ZMAT
RE/0066-PRJ-T1-MEP-EW-LE | Low Side Electrical Works | 2010 | GR01 | 2010 | SMARTWORLD THE EDITION | Shree Krishna Secauto Private Limit | 9110001835 | 40 |  |  | 2026-06-03 | Wiser Connected Switch-White | NO | 10 | 3240 | 32400 | 38232 | 0 | 0 | 32400 | 0 | 0 | ZMAT
RE/0066-PRJ-T1-MEP-EW-LE | Low Side Electrical Works | 2010 | GR01 | 2010 | SMARTWORLD THE EDITION | Shree Krishna Secauto Private Limit | 9110001835 | 50 |  |  | 2026-06-03 | Wiser Connected Fan Regulator-White | NO | 4 | 3500 | 14000 | 16520 | 0 | 0 | 14000 | 0 | 0 | ZMAT
RE/0066-PRJ-T1-MEP-EW-LE | Low Side Electrical Works | 2010 | GR01 | 2010 | SMARTWORLD THE EDITION | Shree Krishna Secauto Private Limit | 9110001835 | 60 |  |  | 2026-06-03 | Wiser IR Controller For AC | NO | 1 | 3800 | 3800 | 4484 | 0 | 0 | 3800 | 0 | 0 | ZMAT
RE/0066-PRJ-T1-MEP-EW-LE | Low Side Electrical Works | 2010 | GR01 | 2010 | SMARTWORLD THE EDITION | Shree Krishna Secauto Private Limit | 9110001835 | 70 |  |  | 2026-06-03 | 2M Plate | NO | 12 | 57.4 | 688.8 | 812.78 | 0 | 0 | 688.8 | 0 | 0 | ZMAT
RE/0066-PRJ-T1-MEP-EW-LE | Low Side Electrical Works | 2010 | GR01 | 2010 | SMARTWORLD THE EDITION | Shree Krishna Secauto Private Limit | 9110001835 | 80 |  |  | 2026-06-03 | 3M Plate | NO | 6 | 67.48 | 404.88 | 477.76 | 0 | 0 | 404.88 | 0 | 0 | ZMAT
RE/0066-PRJ-T1-MEP-EW-LE | Low Side Electrical Works | 2010 | GR01 | 2010 | SMARTWORLD THE EDITION | Shree Krishna Secauto Private Limit | 9110001835 | 90 |  |  | 2026-06-03 | 4M Plate | NO | 3 | 83.72 | 251.16 | 296.37 | 0 | 0 | 251.16 | 0 | 0 | ZMAT
RE/0066-PRJ-T1-MEP-EW-LE | Low Side Electrical Works | 2010 | GR01 | 2010 | SMARTWORLD THE EDITION | Shree Krishna Secauto Private Limit | 9110001835 | 100 |  |  | 2026-06-03 | 6M Plate | NO | 2 | 109.76 | 219.52 | 259.03 | 0 | 0 | 219.52 | 0 | 0 | ZMAT
RE/0066-PRJ-T1-MEP-EW-LE | Low Side Electrical Works | 2010 | GR01 | 2010 | SMARTWORLD THE EDITION | Shree Krishna Secauto Private Limit | 9110001835 | 110 |  |  | 2026-06-03 | 8M Plate | NO | 1 | 137.76 | 137.76 | 162.56 | 0 | 0 | 137.76 | 0 | 0 | ZMAT
RE/0066-PRJ-T1-MEP-EW-LE | Low Side Electrical Works | 2010 | GR01 | 2010 | SMARTWORLD THE EDITION | Shree Krishna Secauto Private Limit | 9110001835 | 120 |  |  | 2026-06-03 | 6A Switch | NO | 21 | 59.08 | 1240.68 | 1464 | 0 | 0 | 1240.68 | 0 | 0 | ZMAT
RE/0066-PRJ-T1-MEP-EW-LE | Low Side Electrical Works | 2010 | GR01 | 2010 | SMARTWORLD THE EDITION | Shree Krishna Secauto Private Limit | 9110001835 | 130 |  |  | 2026-06-03 | 6A Socket | NO | 8 | 99.68 | 797.44 | 940.98 | 0 | 0 | 797.44 | 0 | 0 | ZMAT
RE/0066-PRJ-T1-MEP-EW-LE | Low Side Electrical Works | 2010 | GR01 | 2010 | SMARTWORLD THE EDITION | Shree Krishna Secauto Private Limit | 9110001835 | 140 |  |  | 2026-06-03 | 16A Switch | NO | 5 | 92.12 | 460.6 | 543.51 | 0 | 0 | 460.6 | 0 | 0 | ZMAT
RE/0066-PRJ-T1-MEP-EW-LE | Low Side Electrical Works | 2010 | GR01 | 2010 | SMARTWORLD THE EDITION | Shree Krishna Secauto Private Limit | 9110001835 | 150 |  |  | 2026-06-03 | 16A Socket | NO | 5 | 147.56 | 737.8 | 870.6 | 0 | 0 | 737.8 | 0 | 0 | ZMAT
RE/0066-PRJ-T1-MEP-EW-LE | Low Side Electrical Works | 2010 | GR01 | 2010 | SMARTWORLD THE EDITION | Shree Krishna Secauto Private Limit | 9110001835 | 160 |  |  | 2026-06-03 | Fan Regulator | NO | 3 | 352.24 | 1056.72 | 1246.93 | 0 | 0 | 1056.72 | 0 | 0 | ZMAT
RE/0066-PRJ-T1-MEP-EW-LE | Low Side Electrical Works | 2010 | GR01 | 2010 | SMARTWORLD THE EDITION | Shree Krishna Secauto Private Limit | 9110001835 | 170 |  |  | 2026-06-03 | Blanking Plate | NO | 3 | 23.52 | 70.56 | 83.26 | 0 | 0 | 70.56 | 0 | 0 | ZMAT
RE/0066-PRJ-T1-MEP-EW-LE | Low Side Electrical Works | 2010 | GR01 | 2010 | SMARTWORLD THE EDITION | Shree Krishna Secauto Private Limit | 9110001835 | 180 |  |  | 2026-06-03 | 20A DP Switch | NO | 1 | 224 | 224 | 264.32 | 0 | 0 | 224 | 0 | 0 | ZMAT
RE/0066-PRJ-T1-MEP-EW-LE | Low Side Electrical Works | 2010 | GR01 | 2010 | SMARTWORLD THE EDITION | Shree Krishna Secauto Private Limit | 9110001835 | 190 |  |  | 2026-06-03 | TV Socket | NO | 3 | 89.04 | 267.12 | 315.2 | 0 | 0 | 267.12 | 0 | 0 | ZMAT
RE/0066-PRJ-T1-MEP-EW-LE | Low Side Electrical Works | 2010 | GR01 | 2010 | SMARTWORLD THE EDITION | Shree Krishna Secauto Private Limit | 9110001835 | 200 |  |  | 2026-06-03 | Data Socket | NO | 4 | 337.12 | 1348.48 | 1591.21 | 0 | 0 | 1348.48 | 0 | 0 | ZMAT
RE/0066-PRJ-T1-MEP-EW-LE | Low Side Electrical Works | 2010 | GR01 | 2010 | SMARTWORLD THE EDITION | Shree Krishna Secauto Private Limit | 9110001835 | 210 |  |  | 2026-06-03 | Tel Socket | NO | 2 | 92.12 | 184.24 | 217.4 | 0 | 0 | 184.24 | 0 | 0 | ZMAT
RE/0066-PRJ-T1-MEP-EW-LE | Low Side Electrical Works | 2010 | GR01 | 2010 | SMARTWORLD THE EDITION | Shree Krishna Secauto Private Limit | 9110001835 | 220 |  |  | 2026-06-03 | 1M Plate | NO | 6 | 51.6 | 309.6 | 365.33 | 0 | 0 | 309.6 | 0 | 0 | ZMAT
RE/0066-PRJ-T1-MEP-EW-LE | Low Side Electrical Works | 2010 | GR01 | 2010 | SMARTWORLD THE EDITION | Shree Krishna Secauto Private Limit | 9110001835 | 230 |  |  | 2026-06-03 | 2M Plate | NO | 3 | 51.6 | 154.8 | 182.66 | 0 | 0 | 154.8 | 0 | 0 | ZMAT
RE/0066-PRJ-T1-MEP-EW-LE | Low Side Electrical Works | 2010 | GR01 | 2010 | SMARTWORLD THE EDITION | Shree Krishna Secauto Private Limit | 9110001835 | 240 |  |  | 2026-06-03 | 3M Plate | NO | 5 | 66 | 330 | 389.4 | 0 | 0 | 330 | 0 | 0 | ZMAT
RE/0066-PRJ-T1-MEP-EW-LE | Low Side Electrical Works | 2010 | GR01 | 2010 | SMARTWORLD THE EDITION | Shree Krishna Secauto Private Limit | 9110001835 | 250 |  |  | 2026-06-03 | 6M Plate | NO | 1 | 96 | 96 | 113.28 | 0 | 0 | 96 | 0 | 0 | ZMAT
RE/0066-PRJ-T1-MEP-EW-LE | Low Side Electrical Works | 2010 | GR01 | 2010 | SMARTWORLD THE EDITION | Shree Krishna Secauto Private Limit | 9110001835 | 260 |  |  | 2026-06-03 | 8M Plate | NO | 2 | 126.6 | 253.2 | 298.78 | 0 | 0 | 253.2 | 0 | 0 | ZMAT
RE/0066-PRJ-T1-MEP-EW-LE | Low Side Electrical Works | 2010 | GR01 | 2010 | SMARTWORLD THE EDITION | Shree Krishna Secauto Private Limit | 9110001835 | 270 |  |  | 2026-06-03 | Bell Push | NO | 1 | 138.6 | 138.6 | 163.55 | 0 | 0 | 138.6 | 0 | 0 | ZMAT
RE/0066-PRJ-T1-MEP-EW-LE | Low Side Electrical Works | 2010 | GR01 | 2010 | SMARTWORLD THE EDITION | Shree Krishna Secauto Private Limit | 9110001835 | 280 |  |  | 2026-06-03 | 6A Switch | NO | 20 | 37.8 | 756 | 892.08 | 0 | 0 | 756 | 0 | 0 | ZMAT
RE/0066-PRJ-T1-MEP-EW-LE | Low Side Electrical Works | 2010 | GR01 | 2010 | SMARTWORLD THE EDITION | Shree Krishna Secauto Private Limit | 9110001835 | 290 |  |  | 2026-06-03 | 6A Socket | NO | 8 | 75.3 | 602.4 | 710.83 | 0 | 0 | 602.4 | 0 | 0 | ZMAT
RE/0066-PRJ-T1-MEP-EW-LE | Low Side Electrical Works | 2010 | GR01 | 2010 | SMARTWORLD THE EDITION | Shree Krishna Secauto Private Limit | 9110001835 | 300 |  |  | 2026-06-03 | 16A Switch | NO | 7 | 81.3 | 569.1 | 671.54 | 0 | 0 | 569.1 | 0 | 0 | ZMAT
RE/0066-PRJ-T1-MEP-EW-LE | Low Side Electrical Works | 2010 | GR01 | 2010 | SMARTWORLD THE EDITION | Shree Krishna Secauto Private Limit | 9110001835 | 310 |  |  | 2026-06-03 | 16A Socket | NO | 7 | 120.6 | 844.2 | 996.16 | 0 | 0 | 844.2 | 0 | 0 | ZMAT
RE/0066-PRJ-T1-MEP-EW-LE | Low Side Electrical Works | 2010 | GR01 | 2010 | SMARTWORLD THE EDITION | Shree Krishna Secauto Private Limit | 9110001835 | 320 |  |  | 2026-06-03 | Blanking Plate | NO | 1 | 18.6 | 18.6 | 21.95 | 0 | 0 | 18.6 | 0 | 0 | ZMAT
RE/0066-PRJ-T1-MEP-EW-LE | Low Side Electrical Works | 2010 | GR01 | 2010 | SMARTWORLD THE EDITION | Shree Krishna Secauto Private Limit | 9110001835 | 330 |  |  | 2026-06-03 | TV Socket | NO | 3 | 71.7 | 215.1 | 253.82 | 0 | 0 | 215.1 | 0 | 0 | ZMAT
RE/0066-PRJ-T1-MEP-EW-LE | Low Side Electrical Works | 2010 | GR01 | 2010 | SMARTWORLD THE EDITION | Shree Krishna Secauto Private Limit | 9110001835 | 340 |  |  | 2026-06-03 | Data Socket | NO | 3 | 271.2 | 813.6 | 960.05 | 0 | 0 | 813.6 | 0 | 0 | ZMAT
RE/0066-PRJ-T1-MEP-EW-LE | Low Side Electrical Works | 2010 | GR01 | 2010 | SMARTWORLD THE EDITION | Shree Krishna Secauto Private Limit | 9110001835 | 350 |  |  | 2026-06-03 | Tel Socket | NO | 1 | 74.7 | 74.7 | 88.15 | 0 | 0 | 74.7 | 0 | 0 | ZMAT
RE/0066-PRJ-T1-MEP-EW-LE | Low Side Electrical Works | 2010 | GR01 | 2010 | SMARTWORLD THE EDITION | Shree Krishna Secauto Private Limit | 9110001835 | 360 |  |  | 2026-06-03 | HDMI | NO | 1 | 452.1 | 452.1 | 533.48 | 0 | 0 | 452.1 | 0 | 0 | ZMAT
RE/0066-PRJ-T1-MEP-EW-LE | Low Side Electrical Works | 2010 | GR01 | 2010 | SMARTWORLD THE EDITION | Shree Krishna Secauto Private Limit | 9110001835 | 370 |  |  | 2026-06-03 | 2M Plate | NO | 7 | 57.4 | 401.8 | 474.12 | 0 | 0 | 401.8 | 0 | 0 | ZMAT
RE/0066-PRJ-T1-MEP-EW-LE | Low Side Electrical Works | 2010 | GR01 | 2010 | SMARTWORLD THE EDITION | Shree Krishna Secauto Private Limit | 9110001835 | 380 |  |  | 2026-06-03 | 3M Plate | NO | 3 | 67.48 | 202.44 | 238.88 | 0 | 0 | 202.44 | 0 | 0 | ZMAT
RE/0066-PRJ-T1-MEP-EW-LE | Low Side Electrical Works | 2010 | GR01 | 2010 | SMARTWORLD THE EDITION | Shree Krishna Secauto Private Limit | 9110001835 | 390 |  |  | 2026-06-03 | 4M Plate | NO | 1 | 83.72 | 83.72 | 98.79 | 0 | 0 | 83.72 | 0 | 0 | ZMAT
RE/0066-PRJ-T1-MEP-EW-LE | Low Side Electrical Works | 2010 | GR01 | 2010 | SMARTWORLD THE EDITION | Shree Krishna Secauto Private Limit | 9110001835 | 400 |  |  | 2026-06-03 | 6M Plate | NO | 1 | 109.76 | 109.76 | 129.52 | 0 | 0 | 109.76 | 0 | 0 | ZMAT
RE/0066-PRJ-T1-MEP-EW-LE | Low Side Electrical Works | 2010 | GR01 | 2010 | SMARTWORLD THE EDITION | Shree Krishna Secauto Private Limit | 9110001835 | 410 |  |  | 2026-06-03 | 6A Switch | NO | 11 | 59.08 | 649.88 | 766.86 | 0 | 0 | 649.88 | 0 | 0 | ZMAT
RE/0066-PRJ-T1-MEP-EW-LE | Low Side Electrical Works | 2010 | GR01 | 2010 | SMARTWORLD THE EDITION | Shree Krishna Secauto Private Limit | 9110001835 | 420 |  |  | 2026-06-03 | 6A Socket | NO | 4 | 99.68 | 398.72 | 470.49 | 0 | 0 | 398.72 | 0 | 0 | ZMAT
RE/0066-PRJ-T1-MEP-EW-LE | Low Side Electrical Works | 2010 | GR01 | 2010 | SMARTWORLD THE EDITION | Shree Krishna Secauto Private Limit | 9110001835 | 430 |  |  | 2026-06-03 | 16A Switch | NO | 4 | 92.12 | 368.48 | 434.81 | 0 | 0 | 368.48 | 0 | 0 | ZMAT
RE/0066-PRJ-T1-MEP-EW-LE | Low Side Electrical Works | 2010 | GR01 | 2010 | SMARTWORLD THE EDITION | Shree Krishna Secauto Private Limit | 9110001835 | 440 |  |  | 2026-06-03 | 16A Socket | NO | 4 | 147.56 | 590.24 | 696.48 | 0 | 0 | 590.24 | 0 | 0 | ZMAT
RE/0066-PRJ-T1-MEP-EW-LE | Low Side Electrical Works | 2010 | GR01 | 2010 | SMARTWORLD THE EDITION | Shree Krishna Secauto Private Limit | 9110001835 | 450 |  |  | 2026-06-03 | Fan Regulator | NO | 1 | 352.24 | 352.24 | 415.64 | 0 | 0 | 352.24 | 0 | 0 | ZMAT
RE/0066-PRJ-T1-MEP-EW-LE | Low Side Electrical Works | 2010 | GR01 | 2010 | SMARTWORLD THE EDITION | Shree Krishna Secauto Private Limit | 9110001835 | 460 |  |  | 2026-06-03 | Blanking Plate | NO | 2 | 23.52 | 47.04 | 55.51 | 0 | 0 | 47.04 | 0 | 0 | ZMAT
RE/0066-PRJ-T1-MEP-EW-LE | Low Side Electrical Works | 2010 | GR01 | 2010 | SMARTWORLD THE EDITION | Shree Krishna Secauto Private Limit | 9110001835 | 470 |  |  | 2026-06-03 | 20A DP Switch | NO | 1 | 224 | 224 | 264.32 | 0 | 0 | 224 | 0 | 0 | ZMAT
RE/0066-PRJ-T1-MEP-EW-LE | Low Side Electrical Works | 2010 | GR01 | 2010 | SMARTWORLD THE EDITION | Shree Krishna Secauto Private Limit | 9110001835 | 480 |  |  | 2026-06-03 | TV Socket | NO | 4 | 89.04 | 356.16 | 420.27 | 0 | 0 | 356.16 | 0 | 0 | ZMAT
RE/0066-PRJ-T1-MEP-EW-LE | Low Side Electrical Works | 2010 | GR01 | 2010 | SMARTWORLD THE EDITION | Shree Krishna Secauto Private Limit | 9110001835 | 490 |  |  | 2026-06-03 | Installation | NO | 1 | 5865 | 5865 | 6920.7 | 0 | 0 | 5865 | 0 | 0 | ZMAT
RE/0066-PRJ-T1-MEP-EW-LE | Low Side Electrical Works | 2010 | GR01 | 2010 | SMARTWORLD THE EDITION | CONVENIENT LIVING SOLUTIONS PRIVATELIMITED | 9110001841 | 10 |  |  | 2026-06-07 | Connected Switch - with Neutral - Wired | NO | 9 | 2993.22 | 26938.98 | 31788 | 0 | 0 | 26938.98 | 0 | 0 | ZMAT
RE/0066-PRJ-T1-MEP-EW-LE | Low Side Electrical Works | 2010 | GR01 | 2010 | SMARTWORLD THE EDITION | CONVENIENT LIVING SOLUTIONS PRIVATELIMITED | 9110001841 | 20 |  |  | 2026-06-07 | Fan Controller | NO | 3 | 2299.32 | 6897.96 | 8139.59 | 0 | 0 | 6897.96 | 0 | 0 | ZMAT
RE/0066-PRJ-T1-MEP-EW-LE | Low Side Electrical Works | 2010 | GR01 | 2010 | SMARTWORLD THE EDITION | CONVENIENT LIVING SOLUTIONS PRIVATELIMITED | 9110001841 | 30 |  |  | 2026-06-07 | Connected Switch | NO | 2 | 2993.22 | 5986.44 | 7064 | 0 | 0 | 5986.44 | 0 | 0 | ZMAT
RE/0066-PRJ-T1-MEP-EW-LE | Low Side Electrical Works | 2010 | GR01 | 2010 | SMARTWORLD THE EDITION | CONVENIENT LIVING SOLUTIONS PRIVATELIMITED | 9110001841 | 40 |  |  | 2026-06-07 | Contactor | NO | 2 | 1000 | 2000 | 2360 | 0 | 0 | 2000 | 0 | 0 | ZMAT
RE/0066-PRJ-T1-MEP-EW-LE | Low Side Electrical Works | 2010 | GR01 | 2010 | SMARTWORLD THE EDITION | CONVENIENT LIVING SOLUTIONS PRIVATELIMITED | 9110001841 | 50 |  |  | 2026-06-07 | Connected Switch | NO | 6 | 2993.22 | 17959.32 | 21192 | 0 | 0 | 17959.32 | 0 | 0 | ZMAT
RE/0066-PRJ-T1-MEP-EW-LE | Low Side Electrical Works | 2010 | GR01 | 2010 | SMARTWORLD THE EDITION | CONVENIENT LIVING SOLUTIONS PRIVATELIMITED | 9110001841 | 60 |  |  | 2026-06-07 | Fan Controller | NO | 1 | 2299.32 | 2299.32 | 2713.2 | 0 | 0 | 2299.32 | 0 | 0 | ZMAT
RE/0066-PRJ-T1-MEP-EW-LE | Low Side Electrical Works | 2010 | GR01 | 2010 | SMARTWORLD THE EDITION | CONVENIENT LIVING SOLUTIONS PRIVATELIMITED | 9110001841 | 70 |  |  | 2026-06-07 | Connected Switch | NO | 3 | 2993.22 | 8979.66 | 10596 | 0 | 0 | 8979.66 | 0 | 0 | ZMAT
RE/0066-PRJ-T1-MEP-EW-LE | Low Side Electrical Works | 2010 | GR01 | 2010 | SMARTWORLD THE EDITION | CONVENIENT LIVING SOLUTIONS PRIVATELIMITED | 9110001841 | 80 |  |  | 2026-06-07 | Contactor | NO | 3 | 1000 | 3000 | 3540 | 0 | 0 | 3000 | 0 | 0 | ZMAT
RE/0066-PRJ-T1-MEP-EW-LE | Low Side Electrical Works | 2010 | GR01 | 2010 | SMARTWORLD THE EDITION | CONVENIENT LIVING SOLUTIONS PRIVATELIMITED | 9110001841 | 90 |  |  | 2026-06-07 | Connected Switch | NO | 4 | 3141.18 | 12564.72 | 14826.37 | 0 | 0 | 12564.72 | 0 | 0 | ZMAT
RE/0066-PRJ-T1-MEP-EW-LE | Low Side Electrical Works | 2010 | GR01 | 2010 | SMARTWORLD THE EDITION | CONVENIENT LIVING SOLUTIONS PRIVATELIMITED | 9110001841 | 100 |  |  | 2026-06-07 | Connected Switch | NO | 1 | 2643.84 | 2643.84 | 3119.73 | 0 | 0 | 2643.84 | 0 | 0 | ZMAT
RE/0066-PRJ-T1-MEP-EW-LE | Low Side Electrical Works | 2010 | GR01 | 2010 | SMARTWORLD THE EDITION | CONVENIENT LIVING SOLUTIONS PRIVATELIMITED | 9110001841 | 110 |  |  | 2026-06-07 | Connected Switch | NO | 3 | 3141.18 | 9423.54 | 11119.78 | 0 | 0 | 9423.54 | 0 | 0 | ZMAT
RE/0066-PRJ-T1-MEP-EW-LE | Low Side Electrical Works | 2010 | GR01 | 2010 | SMARTWORLD THE EDITION | CONVENIENT LIVING SOLUTIONS PRIVATELIMITED | 9110001841 | 120 |  |  | 2026-06-07 | Contactor | NO | 3 | 1000 | 3000 | 3540 | 0 | 0 | 3000 | 0 | 0 | ZMAT
RE/0066-PRJ-T1-MEP-EW-LE | Low Side Electrical Works | 2010 | GR01 | 2010 | SMARTWORLD THE EDITION | CONVENIENT LIVING SOLUTIONS PRIVATELIMITED | 9110001841 | 130 |  |  | 2026-06-07 | Connected Switch | NO | 6 | 3141.18 | 18847.08 | 22239.55 | 0 | 0 | 18847.08 | 0 | 0 | ZMAT
RE/0066-PRJ-T1-MEP-EW-LE | Low Side Electrical Works | 2010 | GR01 | 2010 | SMARTWORLD THE EDITION | CONVENIENT LIVING SOLUTIONS PRIVATELIMITED | 9110001841 | 140 |  |  | 2026-06-07 | Fan Controller | NO | 1 | 2643.84 | 2643.84 | 3119.73 | 0 | 0 | 2643.84 | 0 | 0 | ZMAT
RE/0066-PRJ-T1-MEP-EW-LE | Low Side Electrical Works | 2010 | GR01 | 2010 | SMARTWORLD THE EDITION | CONVENIENT LIVING SOLUTIONS PRIVATELIMITED | 9110001841 | 150 |  |  | 2026-06-07 | Connected Switch | NO | 3 | 3141.18 | 9423.54 | 11119.78 | 0 | 0 | 9423.54 | 0 | 0 | ZMAT
RE/0066-PRJ-T1-MEP-EW-LE | Low Side Electrical Works | 2010 | GR01 | 2010 | SMARTWORLD THE EDITION | CONVENIENT LIVING SOLUTIONS PRIVATELIMITED | 9110001841 | 160 |  |  | 2026-06-07 | Contactor | NO | 3 | 1000 | 3000 | 3540 | 0 | 0 | 3000 | 0 | 0 | ZMAT
RE/0066-PRJ-T1-MEP-EW-LE | Low Side Electrical Works | 2010 | GR01 | 2010 | SMARTWORLD THE EDITION | CONVENIENT LIVING SOLUTIONS PRIVATELIMITED | 9110001841 | 170 |  |  | 2026-06-07 | Wireless Home Control | NO | 1 | 7609.14 | 7609.14 | 8978.79 | 0 | 0 | 7609.14 | 0 | 0 | ZMAT
RE/0066-PRJ-T1-MEP-EW-LE | Low Side Electrical Works | 2010 | GR01 | 2010 | SMARTWORLD THE EDITION | CONVENIENT LIVING SOLUTIONS PRIVATELIMITED | 9110001841 | 180 |  |  | 2026-06-07 | Wireless Home Control | NO | 1 | 6390.9 | 6390.9 | 7541.26 | 0 | 0 | 6390.9 | 0 | 0 | ZMAT
RE/0066-PRJ-T1-MEP-EW-LE | Low Side Electrical Works | 2010 | GR01 | 2010 | SMARTWORLD THE EDITION | CONVENIENT LIVING SOLUTIONS PRIVATELIMITED | 9110001841 | 190 |  |  | 2026-06-07 | Connected Switch | NO | 6 | 3141.18 | 18847.08 | 22239.55 | 0 | 0 | 18847.08 | 0 | 0 | ZMAT
RE/0066-PRJ-T1-MEP-EW-LE | Low Side Electrical Works | 2010 | GR01 | 2010 | SMARTWORLD THE EDITION | CONVENIENT LIVING SOLUTIONS PRIVATELIMITED | 9110001841 | 200 |  |  | 2026-06-07 | Fan Controller | NO | 1 | 2643.84 | 2643.84 | 3119.73 | 0 | 0 | 2643.84 | 0 | 0 | ZMAT
RE/0066-PRJ-T1-MEP-EW-LE | Low Side Electrical Works | 2010 | GR01 | 2010 | SMARTWORLD THE EDITION | CONVENIENT LIVING SOLUTIONS PRIVATELIMITED | 9110001841 | 210 |  |  | 2026-06-07 | Connected Switch | NO | 3 | 3141.18 | 9423.54 | 11119.78 | 0 | 0 | 9423.54 | 0 | 0 | ZMAT
RE/0066-PRJ-T1-MEP-EW-LE | Low Side Electrical Works | 2010 | GR01 | 2010 | SMARTWORLD THE EDITION | CONVENIENT LIVING SOLUTIONS PRIVATELIMITED | 9110001841 | 220 |  |  | 2026-06-07 | Wireless Home Control | NO | 1 | 7609.14 | 7609.14 | 8978.79 | 0 | 0 | 7609.14 | 0 | 0 | ZMAT
RE/0066-PRJ-T1-MEP-EW-LE | Low Side Electrical Works | 2010 | GR01 | 2010 | SMARTWORLD THE EDITION | CONVENIENT LIVING SOLUTIONS PRIVATELIMITED | 9110001841 | 230 |  |  | 2026-06-07 | Contactor | NO | 3 | 1000 | 3000 | 3540 | 0 | 0 | 3000 | 0 | 0 | ZMAT
RE/0066-PRJ-T1-MEP-EW-LE | Low Side Electrical Works | 2010 | GR01 | 2010 | SMARTWORLD THE EDITION | CONVENIENT LIVING SOLUTIONS PRIVATELIMITED | 9110001841 | 240 |  |  | 2026-06-07 | Connected Switch | NO | 6 | 2784.24 | 16705.44 | 19712.42 | 0 | 0 | 16705.44 | 0 | 0 | ZMAT
RE/0066-PRJ-T1-MEP-EW-LE | Low Side Electrical Works | 2010 | GR01 | 2010 | SMARTWORLD THE EDITION | CONVENIENT LIVING SOLUTIONS PRIVATELIMITED | 9110001841 | 250 |  |  | 2026-06-07 | Fan Controller | NO | 1 | 2345.22 | 2345.22 | 2767.36 | 0 | 0 | 2345.22 | 0 | 0 | ZMAT
RE/0066-PRJ-T1-MEP-EW-LE | Low Side Electrical Works | 2010 | GR01 | 2010 | SMARTWORLD THE EDITION | CONVENIENT LIVING SOLUTIONS PRIVATELIMITED | 9110001841 | 260 |  |  | 2026-06-07 | Connected Switch | NO | 3 | 2784.24 | 8352.72 | 9856.21 | 0 | 0 | 8352.72 | 0 | 0 | ZMAT
RE/0066-PRJ-T1-MEP-EW-LE | Low Side Electrical Works | 2010 | GR01 | 2010 | SMARTWORLD THE EDITION | CONVENIENT LIVING SOLUTIONS PRIVATELIMITED | 9110001841 | 270 |  |  | 2026-06-07 | Contactor | NO | 3 | 1000 | 3000 | 3540 | 0 | 0 | 3000 | 0 | 0 | ZMAT
RE/0066-PRJ-T1-MEP-EW-LE | Low Side Electrical Works | 2010 | GR01 | 2010 | SMARTWORLD THE EDITION | CONVENIENT LIVING SOLUTIONS PRIVATELIMITED | 9110001841 | 280 |  |  | 2026-06-07 | Wireless Home Control | NO | 1 | 5057.1 | 5057.1 | 5967.38 | 0 | 0 | 5057.1 | 0 | 0 | ZMAT
RE/0066-PRJ-T1-MEP-EW-LE | Low Side Electrical Works | 2010 | GR01 | 2010 | SMARTWORLD THE EDITION | CONVENIENT LIVING SOLUTIONS PRIVATELIMITED | 9110001841 | 290 |  |  | 2026-06-07 | Connected Switch | NO | 6 | 2729.7 | 16378.2 | 19326.28 | 0 | 0 | 16378.2 | 0 | 0 | ZMAT
RE/0066-PRJ-T1-MEP-EW-LE | Low Side Electrical Works | 2010 | GR01 | 2010 | SMARTWORLD THE EDITION | CONVENIENT LIVING SOLUTIONS PRIVATELIMITED | 9110001841 | 300 |  |  | 2026-06-07 | Fan Controller | NO | 1 | 2299.32 | 2299.32 | 2713.2 | 0 | 0 | 2299.32 | 0 | 0 | ZMAT
RE/0066-PRJ-T1-MEP-EW-LE | Low Side Electrical Works | 2010 | GR01 | 2010 | SMARTWORLD THE EDITION | CONVENIENT LIVING SOLUTIONS PRIVATELIMITED | 9110001841 | 310 |  |  | 2026-06-07 | Connected Switch | NO | 3 | 2729.7 | 8189.1 | 9663.14 | 0 | 0 | 8189.1 | 0 | 0 | ZMAT
RE/0066-PRJ-T1-MEP-EW-LE | Low Side Electrical Works | 2010 | GR01 | 2010 | SMARTWORLD THE EDITION | CONVENIENT LIVING SOLUTIONS PRIVATELIMITED | 9110001841 | 320 |  |  | 2026-06-07 | Contactor | NO | 3 | 1000 | 3000 | 3540 | 0 | 0 | 3000 | 0 | 0 | ZMAT
RE/0066-PRJ-T1-MEP-EW-LE | Low Side Electrical Works | 2010 | GR01 | 2010 | SMARTWORLD THE EDITION | CONVENIENT LIVING SOLUTIONS PRIVATELIMITED | 9110001841 | 330 |  |  | 2026-06-07 | Wireless Home Control | NO | 1 | 6617.7 | 6617.7 | 7808.89 | 0 | 0 | 6617.7 | 0 | 0 | ZMAT
RE/0066-PRJ-T1-MEP-EW-LE | Low Side Electrical Works | 2010 | GR01 | 2010 | SMARTWORLD THE EDITION | CONVENIENT LIVING SOLUTIONS PRIVATELIMITED | 9110001841 | 340 |  |  | 2026-06-07 | Connected Switch | NO | 6 | 2784.24 | 16705.44 | 19712.42 | 0 | 0 | 16705.44 | 0 | 0 | ZMAT
RE/0066-PRJ-T1-MEP-EW-LE | Low Side Electrical Works | 2010 | GR01 | 2010 | SMARTWORLD THE EDITION | CONVENIENT LIVING SOLUTIONS PRIVATELIMITED | 9110001841 | 350 |  |  | 2026-06-07 | Fan Controller | NO | 1 | 2345.22 | 2345.22 | 2767.36 | 0 | 0 | 2345.22 | 0 | 0 | ZMAT
RE/0066-PRJ-T1-MEP-EW-LE | Low Side Electrical Works | 2010 | GR01 | 2010 | SMARTWORLD THE EDITION | CONVENIENT LIVING SOLUTIONS PRIVATELIMITED | 9110001841 | 360 |  |  | 2026-06-07 | Connected Switch | NO | 3 | 2784.24 | 8352.72 | 9856.21 | 0 | 0 | 8352.72 | 0 | 0 | ZMAT
RE/0066-PRJ-T1-MEP-EW-LE | Low Side Electrical Works | 2010 | GR01 | 2010 | SMARTWORLD THE EDITION | CONVENIENT LIVING SOLUTIONS PRIVATELIMITED | 9110001841 | 370 |  |  | 2026-06-07 | Contactor | NO | 3 | 1000 | 3000 | 3540 | 0 | 0 | 3000 | 0 | 0 | ZMAT
RE/0066-PRJ-T1-MEP-EW-LE | Low Side Electrical Works | 2010 | GR01 | 2010 | SMARTWORLD THE EDITION | CONVENIENT LIVING SOLUTIONS PRIVATELIMITED | 9110001841 | 380 |  |  | 2026-06-07 | Wireless Home Control | NO | 1 | 5057.1 | 5057.1 | 5967.38 | 0 | 0 | 5057.1 | 0 | 0 | ZMAT
RE/0066-PRJ-T1-MEP-EW-LE | Low Side Electrical Works | 2010 | GR01 | 2010 | SMARTWORLD THE EDITION | CONVENIENT LIVING SOLUTIONS PRIVATELIMITED | 9110001841 | 390 |  |  | 2026-06-07 | Bell Push -6A - One Way - SP - 1 Module | NO | 11 | 73 | 803 | 947.54 | 0 | 0 | 803 | 0 | 0 | ZMAT
RE/0066-PRJ-T1-MEP-EW-LE | Low Side Electrical Works | 2010 | GR01 | 2010 | SMARTWORLD THE EDITION | CONVENIENT LIVING SOLUTIONS PRIVATELIMITED | 9110001841 | 400 |  |  | 2026-06-07 | Socket 6 Amp 3pin | NO | 6 | 108 | 648 | 764.64 | 0 | 0 | 648 | 0 | 0 | ZMAT
RE/0066-PRJ-T1-MEP-EW-LE | Low Side Electrical Works | 2010 | GR01 | 2010 | SMARTWORLD THE EDITION | CONVENIENT LIVING SOLUTIONS PRIVATELIMITED | 9110001841 | 410 |  |  | 2026-06-07 | 16A Switch | NO | 2 | 154 | 308 | 363.44 | 0 | 0 | 308 | 0 | 0 | ZMAT
RE/0066-PRJ-T1-MEP-EW-LE | Low Side Electrical Works | 2010 | GR01 | 2010 | SMARTWORLD THE EDITION | CONVENIENT LIVING SOLUTIONS PRIVATELIMITED | 9110001841 | 420 |  |  | 2026-06-07 | Socket Shuttered 6A/ 16A-3 Pin Combined | NO | 2 | 238 | 476 | 561.68 | 0 | 0 | 476 | 0 | 0 | ZMAT
RE/0066-PRJ-T1-MEP-EW-LE | Low Side Electrical Works | 2010 | GR01 | 2010 | SMARTWORLD THE EDITION | CONVENIENT LIVING SOLUTIONS PRIVATELIMITED | 9110001841 | 430 |  |  | 2026-06-07 | Telephone socket - RJ11-Jack - 1 Module | NO | 5 | 120 | 600 | 708 | 0 | 0 | 600 | 0 | 0 | ZMAT
RE/0066-PRJ-T1-MEP-EW-LE | Low Side Electrical Works | 2010 | GR01 | 2010 | SMARTWORLD THE EDITION | CONVENIENT LIVING SOLUTIONS PRIVATELIMITED | 9110001841 | 440 |  |  | 2026-06-07 | RJ 45 CAT6 Socket | NO | 3 | 184 | 552 | 651.36 | 0 | 0 | 552 | 0 | 0 | ZMAT
RE/0066-PRJ-T1-MEP-EW-LE | Low Side Electrical Works | 2010 | GR01 | 2010 | SMARTWORLD THE EDITION | CONVENIENT LIVING SOLUTIONS PRIVATELIMITED | 9110001841 | 450 |  |  | 2026-06-07 | TV Socket Co-axial - 1 Module | NO | 1 | 124 | 124 | 146.32 | 0 | 0 | 124 | 0 | 0 | ZMAT
RE/0066-PRJ-T1-MEP-EW-LE | Low Side Electrical Works | 2010 | GR01 | 2010 | SMARTWORLD THE EDITION | CONVENIENT LIVING SOLUTIONS PRIVATELIMITED | 9110001841 | 460 |  |  | 2026-06-07 | Cover Plate | NO | 5 | 102 | 510 | 601.8 | 0 | 0 | 510 | 0 | 0 | ZMAT
RE/0066-PRJ-T1-MEP-EW-LE | Low Side Electrical Works | 2010 | GR01 | 2010 | SMARTWORLD THE EDITION | CONVENIENT LIVING SOLUTIONS PRIVATELIMITED | 9110001841 | 470 |  |  | 2026-06-07 | Cover Plate | NO | 3 | 107 | 321 | 378.78 | 0 | 0 | 321 | 0 | 0 | ZMAT
RE/0066-PRJ-T1-MEP-EW-LE | Low Side Electrical Works | 2010 | GR01 | 2010 | SMARTWORLD THE EDITION | CONVENIENT LIVING SOLUTIONS PRIVATELIMITED | 9110001841 | 480 |  |  | 2026-06-07 | Cover Plate | NO | 5 | 116 | 580 | 684.4 | 0 | 0 | 580 | 0 | 0 | ZMAT
RE/0066-PRJ-T1-MEP-EW-LE | Low Side Electrical Works | 2010 | GR01 | 2010 | SMARTWORLD THE EDITION | CONVENIENT LIVING SOLUTIONS PRIVATELIMITED | 9110001841 | 490 |  |  | 2026-06-07 | Cover Plate | NO | 1 | 222 | 222 | 261.96 | 0 | 0 | 222 | 0 | 0 | ZMAT
RE/0066-PRJ-T1-MEP-EW-LE | Low Side Electrical Works | 2010 | GR01 | 2010 | SMARTWORLD THE EDITION | CONVENIENT LIVING SOLUTIONS PRIVATELIMITED | 9110001841 | 500 |  |  | 2026-06-07 | Cover Plate | NO | 2 | 242 | 484 | 571.12 | 0 | 0 | 484 | 0 | 0 | ZMAT
RE/0066-PRJ-T1-MEP-EW-LE | Low Side Electrical Works | 2010 | GR01 | 2010 | SMARTWORLD THE EDITION | CONVENIENT LIVING SOLUTIONS PRIVATELIMITED | 9110001841 | 510 |  |  | 2026-06-07 | Bell Push -6A - One Way - SP - 1 Module | NO | 8 | 73 | 584 | 689.12 | 0 | 0 | 584 | 0 | 0 | ZMAT
RE/0066-PRJ-T1-MEP-EW-LE | Low Side Electrical Works | 2010 | GR01 | 2010 | SMARTWORLD THE EDITION | CONVENIENT LIVING SOLUTIONS PRIVATELIMITED | 9110001841 | 520 |  |  | 2026-06-07 | Socket shuttered 6/16A 3 pin, 2 module | NO | 6 | 108 | 648 | 764.64 | 0 | 0 | 648 | 0 | 0 | ZMAT
RE/0066-PRJ-T1-MEP-EW-LE | Low Side Electrical Works | 2010 | GR01 | 2010 | SMARTWORLD THE EDITION | CONVENIENT LIVING SOLUTIONS PRIVATELIMITED | 9110001841 | 530 |  |  | 2026-06-07 | 16A Switch | NO | 2 | 154 | 308 | 363.44 | 0 | 0 | 308 | 0 | 0 | ZMAT
RE/0066-PRJ-T1-MEP-EW-LE | Low Side Electrical Works | 2010 | GR01 | 2010 | SMARTWORLD THE EDITION | CONVENIENT LIVING SOLUTIONS PRIVATELIMITED | 9110001841 | 540 |  |  | 2026-06-07 | Socket Shuttered 6A/ 16A-3 Pin Combined | NO | 2 | 238 | 476 | 561.68 | 0 | 0 | 476 | 0 | 0 | ZMAT
RE/0066-PRJ-T1-MEP-EW-LE | Low Side Electrical Works | 2010 | GR01 | 2010 | SMARTWORLD THE EDITION | CONVENIENT LIVING SOLUTIONS PRIVATELIMITED | 9110001841 | 550 |  |  | 2026-06-07 | Telephone socket - RJ11-Jack - 1 Module | NO | 1 | 184 | 184 | 217.12 | 0 | 0 | 184 | 0 | 0 | ZMAT
RE/0066-PRJ-T1-MEP-EW-LE | Low Side Electrical Works | 2010 | GR01 | 2010 | SMARTWORLD THE EDITION | CONVENIENT LIVING SOLUTIONS PRIVATELIMITED | 9110001841 | 560 |  |  | 2026-06-07 | RJ 45 CAT6 Socket | NO | 1 | 184 | 184 | 217.12 | 0 | 0 | 184 | 0 | 0 | ZMAT
RE/0066-PRJ-T1-MEP-EW-LE | Low Side Electrical Works | 2010 | GR01 | 2010 | SMARTWORLD THE EDITION | CONVENIENT LIVING SOLUTIONS PRIVATELIMITED | 9110001841 | 570 |  |  | 2026-06-07 | Blanking Plate | NO | 2 | 23 | 46 | 54.28 | 0 | 0 | 46 | 0 | 0 | ZMAT
RE/0066-PRJ-T1-MEP-EW-LE | Low Side Electrical Works | 2010 | GR01 | 2010 | SMARTWORLD THE EDITION | CONVENIENT LIVING SOLUTIONS PRIVATELIMITED | 9110001841 | 580 |  |  | 2026-06-07 | Cover Plate | NO | 1 | 102 | 102 | 120.36 | 0 | 0 | 102 | 0 | 0 | ZMAT
RE/0066-PRJ-T1-MEP-EW-LE | Low Side Electrical Works | 2010 | GR01 | 2010 | SMARTWORLD THE EDITION | CONVENIENT LIVING SOLUTIONS PRIVATELIMITED | 9110001841 | 590 |  |  | 2026-06-07 | Cover Plate | NO | 5 | 107 | 535 | 631.3 | 0 | 0 | 535 | 0 | 0 | ZMAT
RE/0066-PRJ-T1-MEP-EW-LE | Low Side Electrical Works | 2010 | GR01 | 2010 | SMARTWORLD THE EDITION | CONVENIENT LIVING SOLUTIONS PRIVATELIMITED | 9110001841 | 600 |  |  | 2026-06-07 | Cover Plate | NO | 2 | 116 | 232 | 273.76 | 0 | 0 | 232 | 0 | 0 | ZMAT
RE/0066-PRJ-T1-MEP-EW-LE | Low Side Electrical Works | 2010 | GR01 | 2010 | SMARTWORLD THE EDITION | CONVENIENT LIVING SOLUTIONS PRIVATELIMITED | 9110001841 | 610 |  |  | 2026-06-07 | Cover Plate | NO | 2 | 124 | 248 | 292.64 | 0 | 0 | 248 | 0 | 0 | ZMAT
RE/0066-PRJ-T1-MEP-EW-LE | Low Side Electrical Works | 2010 | GR01 | 2010 | SMARTWORLD THE EDITION | CONVENIENT LIVING SOLUTIONS PRIVATELIMITED | 9110001841 | 620 |  |  | 2026-06-07 | Cover Plate | NO | 2 | 222 | 444 | 523.92 | 0 | 0 | 444 | 0 | 0 | ZMAT
RE/0066-PRJ-T1-MEP-EW-LE | Low Side Electrical Works | 2010 | GR01 | 2010 | SMARTWORLD THE EDITION | CONVENIENT LIVING SOLUTIONS PRIVATELIMITED | 9110001841 | 630 |  |  | 2026-06-07 | Bell Push -6A - One Way - SP - 1 Module | NO | 6 | 96 | 576 | 679.68 | 0 | 0 | 576 | 0 | 0 | ZMAT
RE/0066-PRJ-T1-MEP-EW-LE | Low Side Electrical Works | 2010 | GR01 | 2010 | SMARTWORLD THE EDITION | CONVENIENT LIVING SOLUTIONS PRIVATELIMITED | 9110001841 | 640 |  |  | 2026-06-07 | Socket 6 Amp 3pin | NO | 2 | 137 | 274 | 323.32 | 0 | 0 | 274 | 0 | 0 | ZMAT
RE/0066-PRJ-T1-MEP-EW-LE | Low Side Electrical Works | 2010 | GR01 | 2010 | SMARTWORLD THE EDITION | CONVENIENT LIVING SOLUTIONS PRIVATELIMITED | 9110001841 | 650 |  |  | 2026-06-07 | 10A Switch | NO | 5 | 199 | 995 | 1174.1 | 0 | 0 | 995 | 0 | 0 | ZMAT
RE/0066-PRJ-T1-MEP-EW-LE | Low Side Electrical Works | 2010 | GR01 | 2010 | SMARTWORLD THE EDITION | CONVENIENT LIVING SOLUTIONS PRIVATELIMITED | 9110001841 | 660 |  |  | 2026-06-07 | Socket Shuttered 6A/ 16A-3 Pin Combined | NO | 5 | 270 | 1350 | 1593 | 0 | 0 | 1350 | 0 | 0 | ZMAT
RE/0066-PRJ-T1-MEP-EW-LE | Low Side Electrical Works | 2010 | GR01 | 2010 | SMARTWORLD THE EDITION | CONVENIENT LIVING SOLUTIONS PRIVATELIMITED | 9110001841 | 670 |  |  | 2026-06-07 | Socket | NO | 1 | 246 | 246 | 290.28 | 0 | 0 | 246 | 0 | 0 | ZMAT
RE/0066-PRJ-T1-MEP-EW-LE | Low Side Electrical Works | 2010 | GR01 | 2010 | SMARTWORLD THE EDITION | CONVENIENT LIVING SOLUTIONS PRIVATELIMITED | 9110001841 | 680 |  |  | 2026-06-07 | Blanking Plate | NO | 1 | 23 | 23 | 27.14 | 0 | 0 | 23 | 0 | 0 | ZMAT
RE/0066-PRJ-T1-MEP-EW-LE | Low Side Electrical Works | 2010 | GR01 | 2010 | SMARTWORLD THE EDITION | CONVENIENT LIVING SOLUTIONS PRIVATELIMITED | 9110001841 | 690 |  |  | 2026-06-07 | Cover Plate | NO | 6 | 183 | 1098 | 1295.64 | 0 | 0 | 1098 | 0 | 0 | ZMAT
RE/0066-PRJ-T1-MEP-EW-LE | Low Side Electrical Works | 2010 | GR01 | 2010 | SMARTWORLD THE EDITION | CONVENIENT LIVING SOLUTIONS PRIVATELIMITED | 9110001841 | 700 |  |  | 2026-06-07 | Cover Plate | NO | 2 | 197 | 394 | 464.92 | 0 | 0 | 394 | 0 | 0 | ZMAT
RE/0066-PRJ-T1-MEP-EW-LE | Low Side Electrical Works | 2010 | GR01 | 2010 | SMARTWORLD THE EDITION | CONVENIENT LIVING SOLUTIONS PRIVATELIMITED | 9110001841 | 710 |  |  | 2026-06-07 | Cover Plate | NO | 3 | 212 | 636 | 750.48 | 0 | 0 | 636 | 0 | 0 | ZMAT
RE/0066-PRJ-T1-MEP-EW-LE | Low Side Electrical Works | 2010 | GR01 | 2010 | SMARTWORLD THE EDITION | CONVENIENT LIVING SOLUTIONS PRIVATELIMITED | 9110001841 | 720 |  |  | 2026-06-07 | Switch - 6A-One Way- SP- 1 Module | NO | 9 | 96 | 864 | 1019.52 | 0 | 0 | 864 | 0 | 0 | ZMAT
RE/0066-PRJ-T1-MEP-EW-LE | Low Side Electrical Works | 2010 | GR01 | 2010 | SMARTWORLD THE EDITION | CONVENIENT LIVING SOLUTIONS PRIVATELIMITED | 9110001841 | 730 |  |  | 2026-06-07 | Socket shuttered 6/16A 3 pin, 2 module | NO | 6 | 137 | 822 | 969.96 | 0 | 0 | 822 | 0 | 0 | ZMAT
RE/0066-PRJ-T1-MEP-EW-LE | Low Side Electrical Works | 2010 | GR01 | 2010 | SMARTWORLD THE EDITION | CONVENIENT LIVING SOLUTIONS PRIVATELIMITED | 9110001841 | 740 |  |  | 2026-06-07 | 10A Switch | NO | 2 | 199 | 398 | 469.64 | 0 | 0 | 398 | 0 | 0 | ZMAT
RE/0066-PRJ-T1-MEP-EW-LE | Low Side Electrical Works | 2010 | GR01 | 2010 | SMARTWORLD THE EDITION | CONVENIENT LIVING SOLUTIONS PRIVATELIMITED | 9110001841 | 750 |  |  | 2026-06-07 | Socket Shuttered 6A/ 16A-3 Pin Combined | NO | 2 | 270 | 540 | 637.2 | 0 | 0 | 540 | 0 | 0 | ZMAT
RE/0066-PRJ-T1-MEP-EW-LE | Low Side Electrical Works | 2010 | GR01 | 2010 | SMARTWORLD THE EDITION | CONVENIENT LIVING SOLUTIONS PRIVATELIMITED | 9110001841 | 760 |  |  | 2026-06-07 | Blanking Plate | NO | 3 | 23 | 69 | 81.42 | 0 | 0 | 69 | 0 | 0 | ZMAT
RE/0066-PRJ-T1-MEP-EW-LE | Low Side Electrical Works | 2010 | GR01 | 2010 | SMARTWORLD THE EDITION | CONVENIENT LIVING SOLUTIONS PRIVATELIMITED | 9110001841 | 770 |  |  | 2026-06-07 | Socket | NO | 1 | 246 | 246 | 290.28 | 0 | 0 | 246 | 0 | 0 | ZMAT
RE/0066-PRJ-T1-MEP-EW-LE | Low Side Electrical Works | 2010 | GR01 | 2010 | SMARTWORLD THE EDITION | CONVENIENT LIVING SOLUTIONS PRIVATELIMITED | 9110001841 | 780 |  |  | 2026-06-07 | Socket | NO | 1 | 242 | 242 | 285.56 | 0 | 0 | 242 | 0 | 0 | ZMAT
RE/0066-PRJ-T1-MEP-EW-LE | Low Side Electrical Works | 2010 | GR01 | 2010 | SMARTWORLD THE EDITION | CONVENIENT LIVING SOLUTIONS PRIVATELIMITED | 9110001841 | 790 |  |  | 2026-06-07 | Cover Plate | NO | 2 | 174 | 348 | 410.64 | 0 | 0 | 348 | 0 | 0 | ZMAT
RE/0066-PRJ-T1-MEP-EW-LE | Low Side Electrical Works | 2010 | GR01 | 2010 | SMARTWORLD THE EDITION | CONVENIENT LIVING SOLUTIONS PRIVATELIMITED | 9110001841 | 800 |  |  | 2026-06-07 | Cover Plate | NO | 5 | 183 | 915 | 1079.7 | 0 | 0 | 915 | 0 | 0 | ZMAT
RE/0066-PRJ-T1-MEP-EW-LE | Low Side Electrical Works | 2010 | GR01 | 2010 | SMARTWORLD THE EDITION | CONVENIENT LIVING SOLUTIONS PRIVATELIMITED | 9110001841 | 810 |  |  | 2026-06-07 | Cover Plate | NO | 2 | 196 | 392 | 462.56 | 0 | 0 | 392 | 0 | 0 | ZMAT
RE/0066-PRJ-T1-MEP-EW-LE | Low Side Electrical Works | 2010 | GR01 | 2010 | SMARTWORLD THE EDITION | CONVENIENT LIVING SOLUTIONS PRIVATELIMITED | 9110001841 | 820 |  |  | 2026-06-07 | Cover Plate | NO | 2 | 221 | 442 | 521.56 | 0 | 0 | 442 | 0 | 0 | ZMAT
RE/0066-PRJ-T1-MEP-EW-LE | Low Side Electrical Works | 2010 | GR01 | 2010 | SMARTWORLD THE EDITION | CONVENIENT LIVING SOLUTIONS PRIVATELIMITED | 9110001841 | 830 |  |  | 2026-06-07 | Cover Plate | NO | 2 | 377 | 754 | 889.72 | 0 | 0 | 754 | 0 | 0 | ZMAT
RE/0066-PRJ-T1-MEP-EW-LE | Low Side Electrical Works | 2010 | GR01 | 2010 | SMARTWORLD THE EDITION | CONVENIENT LIVING SOLUTIONS PRIVATELIMITED | 9110001841 | 840 |  |  | 2026-06-07 | Switch - 6A-One Way- SP- 1 Module | NO | 8 | 96 | 768 | 906.24 | 0 | 0 | 768 | 0 | 0 | ZMAT
RE/0066-PRJ-T1-MEP-EW-LE | Low Side Electrical Works | 2010 | GR01 | 2010 | SMARTWORLD THE EDITION | CONVENIENT LIVING SOLUTIONS PRIVATELIMITED | 9110001841 | 850 |  |  | 2026-06-07 | Socket shuttered 6/16A 3 pin, 2 module | NO | 6 | 138 | 828 | 977.04 | 0 | 0 | 828 | 0 | 0 | ZMAT
RE/0066-PRJ-T1-MEP-EW-LE | Low Side Electrical Works | 2010 | GR01 | 2010 | SMARTWORLD THE EDITION | CONVENIENT LIVING SOLUTIONS PRIVATELIMITED | 9110001841 | 860 |  |  | 2026-06-07 | Socket shuttered 6/16A 3 pin, 2 module | NO | 2 | 199 | 398 | 469.64 | 0 | 0 | 398 | 0 | 0 | ZMAT
RE/0066-PRJ-T1-MEP-EW-LE | Low Side Electrical Works | 2010 | GR01 | 2010 | SMARTWORLD THE EDITION | CONVENIENT LIVING SOLUTIONS PRIVATELIMITED | 9110001841 | 870 |  |  | 2026-06-07 | 6/16A - Socket | NO | 2 | 270 | 540 | 637.2 | 0 | 0 | 540 | 0 | 0 | ZMAT
RE/0066-PRJ-T1-MEP-EW-LE | Low Side Electrical Works | 2010 | GR01 | 2010 | SMARTWORLD THE EDITION | CONVENIENT LIVING SOLUTIONS PRIVATELIMITED | 9110001841 | 880 |  |  | 2026-06-07 | Blanking Plate | NO | 2 | 23 | 46 | 54.28 | 0 | 0 | 46 | 0 | 0 | ZMAT
RE/0066-PRJ-T1-MEP-EW-LE | Low Side Electrical Works | 2010 | GR01 | 2010 | SMARTWORLD THE EDITION | CONVENIENT LIVING SOLUTIONS PRIVATELIMITED | 9110001841 | 890 |  |  | 2026-06-07 | Socket | NO | 1 | 297 | 297 | 350.46 | 0 | 0 | 297 | 0 | 0 | ZMAT
RE/0066-PRJ-T1-MEP-EW-LE | Low Side Electrical Works | 2010 | GR01 | 2010 | SMARTWORLD THE EDITION | CONVENIENT LIVING SOLUTIONS PRIVATELIMITED | 9110001841 | 900 |  |  | 2026-06-07 | Socket | NO | 1 | 146 | 146 | 172.28 | 0 | 0 | 146 | 0 | 0 | ZMAT
RE/0066-PRJ-T1-MEP-EW-LE | Low Side Electrical Works | 2010 | GR01 | 2010 | SMARTWORLD THE EDITION | CONVENIENT LIVING SOLUTIONS PRIVATELIMITED | 9110001841 | 910 |  |  | 2026-06-07 | Cover Plate | NO | 1 | 157 | 157 | 185.26 | 0 | 0 | 157 | 0 | 0 | ZMAT
RE/0066-PRJ-T1-MEP-EW-LE | Low Side Electrical Works | 2010 | GR01 | 2010 | SMARTWORLD THE EDITION | CONVENIENT LIVING SOLUTIONS PRIVATELIMITED | 9110001841 | 920 |  |  | 2026-06-07 | Cover Plate | NO | 5 | 163 | 815 | 961.7 | 0 | 0 | 815 | 0 | 0 | ZMAT
RE/0066-PRJ-T1-MEP-EW-LE | Low Side Electrical Works | 2010 | GR01 | 2010 | SMARTWORLD THE EDITION | CONVENIENT LIVING SOLUTIONS PRIVATELIMITED | 9110001841 | 930 |  |  | 2026-06-07 | Cover Plate | NO | 2 | 176 | 352 | 415.36 | 0 | 0 | 352 | 0 | 0 | ZMAT
RE/0066-PRJ-T1-MEP-EW-LE | Low Side Electrical Works | 2010 | GR01 | 2010 | SMARTWORLD THE EDITION | CONVENIENT LIVING SOLUTIONS PRIVATELIMITED | 9110001841 | 940 |  |  | 2026-06-07 | Cover Plate | NO | 2 | 200 | 400 | 472 | 0 | 0 | 400 | 0 | 0 | ZMAT
RE/0066-PRJ-T1-MEP-EW-LE | Low Side Electrical Works | 2010 | GR01 | 2010 | SMARTWORLD THE EDITION | CONVENIENT LIVING SOLUTIONS PRIVATELIMITED | 9110001841 | 950 |  |  | 2026-06-07 | Cover Plate | NO | 2 | 344 | 688 | 811.84 | 0 | 0 | 688 | 0 | 0 | ZMAT
RE/0066-PRJ-T1-MEP-EW-LE | Low Side Electrical Works | 2010 | GR01 | 2010 | SMARTWORLD THE EDITION | CONVENIENT LIVING SOLUTIONS PRIVATELIMITED | 9110001841 | 960 |  |  | 2026-06-07 | 10A Switch | NO | 9 | 136 | 1224 | 1444.32 | 0 | 0 | 1224 | 0 | 0 | ZMAT
RE/0066-PRJ-T1-MEP-EW-LE | Low Side Electrical Works | 2010 | GR01 | 2010 | SMARTWORLD THE EDITION | CONVENIENT LIVING SOLUTIONS PRIVATELIMITED | 9110001841 | 970 |  |  | 2026-06-07 | Socket shuttered 6/16A 3 pin, 2 module | NO | 6 | 191 | 1146 | 1352.28 | 0 | 0 | 1146 | 0 | 0 | ZMAT
RE/0066-PRJ-T1-MEP-EW-LE | Low Side Electrical Works | 2010 | GR01 | 2010 | SMARTWORLD THE EDITION | CONVENIENT LIVING SOLUTIONS PRIVATELIMITED | 9110001841 | 980 |  |  | 2026-06-07 | 16A Switch | NO | 2 | 217 | 434 | 512.12 | 0 | 0 | 434 | 0 | 0 | ZMAT
RE/0066-PRJ-T1-MEP-EW-LE | Low Side Electrical Works | 2010 | GR01 | 2010 | SMARTWORLD THE EDITION | CONVENIENT LIVING SOLUTIONS PRIVATELIMITED | 9110001841 | 990 |  |  | 2026-06-07 | Socket Shuttered 6A/ 16A-3 Pin Combined | NO | 2 | 387 | 774 | 913.32 | 0 | 0 | 774 | 0 | 0 | ZMAT
RE/0066-PRJ-T1-MEP-EW-LE | Low Side Electrical Works | 2010 | GR01 | 2010 | SMARTWORLD THE EDITION | CONVENIENT LIVING SOLUTIONS PRIVATELIMITED | 9110001841 | 1000 |  |  | 2026-06-07 | Blanking Plate | NO | 3 | 39 | 117 | 138.06 | 0 | 0 | 117 | 0 | 0 | ZMAT
RE/0066-PRJ-T1-MEP-EW-LE | Low Side Electrical Works | 2010 | GR01 | 2010 | SMARTWORLD THE EDITION | CONVENIENT LIVING SOLUTIONS PRIVATELIMITED | 9110001841 | 1010 |  |  | 2026-06-07 | Socket | NO | 1 | 205 | 205 | 241.9 | 0 | 0 | 205 | 0 | 0 | ZMAT
RE/0066-PRJ-T1-MEP-EW-LE | Low Side Electrical Works | 2010 | GR01 | 2010 | SMARTWORLD THE EDITION | CONVENIENT LIVING SOLUTIONS PRIVATELIMITED | 9110001841 | 1020 |  |  | 2026-06-07 | Cover Plate | NO | 2 | 246 | 492 | 580.56 | 0 | 0 | 492 | 0 | 0 | ZMAT
RE/0066-PRJ-T1-MEP-EW-LE | Low Side Electrical Works | 2010 | GR01 | 2010 | SMARTWORLD THE EDITION | CONVENIENT LIVING SOLUTIONS PRIVATELIMITED | 9110001841 | 1030 |  |  | 2026-06-07 | Cover Plate | NO | 5 | 254 | 1270 | 1498.6 | 0 | 0 | 1270 | 0 | 0 | ZMAT
RE/0066-PRJ-T1-MEP-EW-LE | Low Side Electrical Works | 2010 | GR01 | 2010 | SMARTWORLD THE EDITION | CONVENIENT LIVING SOLUTIONS PRIVATELIMITED | 9110001841 | 1040 |  |  | 2026-06-07 | Cover Plate | NO | 2 | 295 | 590 | 696.2 | 0 | 0 | 590 | 0 | 0 | ZMAT
RE/0066-PRJ-T1-MEP-EW-LE | Low Side Electrical Works | 2010 | GR01 | 2010 | SMARTWORLD THE EDITION | CONVENIENT LIVING SOLUTIONS PRIVATELIMITED | 9110001841 | 1050 |  |  | 2026-06-07 | Cover Plate | NO | 2 | 338 | 676 | 797.68 | 0 | 0 | 676 | 0 | 0 | ZMAT
RE/0066-PRJ-T1-MEP-EW-LE | Low Side Electrical Works | 2010 | GR01 | 2010 | SMARTWORLD THE EDITION | CONVENIENT LIVING SOLUTIONS PRIVATELIMITED | 9110001841 | 1060 |  |  | 2026-06-07 | Cover Plate | NO | 2 | 465 | 930 | 1097.4 | 0 | 0 | 930 | 0 | 0 | ZMAT
RE/0066-PRJ-T1-MEP-EW-LE | Low Side Electrical Works | 2010 | GR01 | 2010 | SMARTWORLD THE EDITION | CONVENIENT LIVING SOLUTIONS PRIVATELIMITED | 9110001841 | 1070 |  |  | 2026-06-07 | Switch - 6A-One Way- SP- 1 Module | NO | 8 | 82 | 656 | 774.08 | 0 | 0 | 656 | 0 | 0 | ZMAT
RE/0066-PRJ-T1-MEP-EW-LE | Low Side Electrical Works | 2010 | GR01 | 2010 | SMARTWORLD THE EDITION | CONVENIENT LIVING SOLUTIONS PRIVATELIMITED | 9110001841 | 1080 |  |  | 2026-06-07 | Socket shuttered 6/16A 3 pin, 2 module | NO | 5 | 116 | 580 | 684.4 | 0 | 0 | 580 | 0 | 0 | ZMAT
RE/0066-PRJ-T1-MEP-EW-LE | Low Side Electrical Works | 2010 | GR01 | 2010 | SMARTWORLD THE EDITION | CONVENIENT LIVING SOLUTIONS PRIVATELIMITED | 9110001841 | 1090 |  |  | 2026-06-07 | 10A Switch | NO | 2 | 176 | 352 | 415.36 | 0 | 0 | 352 | 0 | 0 | ZMAT
RE/0066-PRJ-T1-MEP-EW-LE | Low Side Electrical Works | 2010 | GR01 | 2010 | SMARTWORLD THE EDITION | CONVENIENT LIVING SOLUTIONS PRIVATELIMITED | 9110001841 | 1100 |  |  | 2026-06-07 | Socket Shuttered 6A/ 16A-3 Pin Combined | NO | 2 | 236 | 472 | 556.96 | 0 | 0 | 472 | 0 | 0 | ZMAT
RE/0066-PRJ-T1-MEP-EW-LE | Low Side Electrical Works | 2010 | GR01 | 2010 | SMARTWORLD THE EDITION | CONVENIENT LIVING SOLUTIONS PRIVATELIMITED | 9110001841 | 1110 |  |  | 2026-06-07 | Blanking Plate | NO | 2 | 23 | 46 | 54.28 | 0 | 0 | 46 | 0 | 0 | ZMAT
RE/0066-PRJ-T1-MEP-EW-LE | Low Side Electrical Works | 2010 | GR01 | 2010 | SMARTWORLD THE EDITION | CONVENIENT LIVING SOLUTIONS PRIVATELIMITED | 9110001841 | 1120 |  |  | 2026-06-07 | Socket | NO | 1 | 122 | 122 | 143.96 | 0 | 0 | 122 | 0 | 0 | ZMAT
RE/0066-PRJ-T1-MEP-EW-LE | Low Side Electrical Works | 2010 | GR01 | 2010 | SMARTWORLD THE EDITION | CONVENIENT LIVING SOLUTIONS PRIVATELIMITED | 9110001841 | 1130 |  |  | 2026-06-07 | Socket | NO | 1 | 246 | 246 | 290.28 | 0 | 0 | 246 | 0 | 0 | ZMAT
RE/0066-PRJ-T1-MEP-EW-LE | Low Side Electrical Works | 2010 | GR01 | 2010 | SMARTWORLD THE EDITION | CONVENIENT LIVING SOLUTIONS PRIVATELIMITED | 9110001841 | 1140 |  |  | 2026-06-07 | 10A Switch | NO | 1 | 387 | 387 | 456.66 | 0 | 0 | 387 | 0 | 0 | ZMAT
RE/0066-PRJ-T1-MEP-EW-LE | Low Side Electrical Works | 2010 | GR01 | 2010 | SMARTWORLD THE EDITION | CONVENIENT LIVING SOLUTIONS PRIVATELIMITED | 9110001841 | 1150 |  |  | 2026-06-07 | Cover Plate | NO | 5 | 111 | 555 | 654.9 | 0 | 0 | 555 | 0 | 0 | ZMAT
RE/0066-PRJ-T1-MEP-EW-LE | Low Side Electrical Works | 2010 | GR01 | 2010 | SMARTWORLD THE EDITION | CONVENIENT LIVING SOLUTIONS PRIVATELIMITED | 9110001841 | 1160 |  |  | 2026-06-07 | Cover Plate | NO | 2 | 125 | 250 | 295 | 0 | 0 | 250 | 0 | 0 | ZMAT
RE/0066-PRJ-T1-MEP-EW-LE | Low Side Electrical Works | 2010 | GR01 | 2010 | SMARTWORLD THE EDITION | CONVENIENT LIVING SOLUTIONS PRIVATELIMITED | 9110001841 | 1170 |  |  | 2026-06-07 | Cover Plate | NO | 2 | 161 | 322 | 379.96 | 0 | 0 | 322 | 0 | 0 | ZMAT
RE/0066-PRJ-T1-MEP-EW-LE | Low Side Electrical Works | 2010 | GR01 | 2010 | SMARTWORLD THE EDITION | CONVENIENT LIVING SOLUTIONS PRIVATELIMITED | 9110001841 | 1180 |  |  | 2026-06-07 | Cover Plate | NO | 1 | 100 | 100 | 118 | 0 | 0 | 100 | 0 | 0 | ZMAT
RE/0066-PRJ-T1-MEP-EW-LE | Low Side Electrical Works | 2010 | GR01 | 2010 | SMARTWORLD THE EDITION | CONVENIENT LIVING SOLUTIONS PRIVATELIMITED | 9110001841 | 1190 |  |  | 2026-06-07 | Cover Plate | NO | 1 | 264 | 264 | 311.52 | 0 | 0 | 264 | 0 | 0 | ZMAT
RE/0066-PRJ-T1-MEP-EW-LE | Low Side Electrical Works | 2010 | GR01 | 2010 | SMARTWORLD THE EDITION | CONVENIENT LIVING SOLUTIONS PRIVATELIMITED | 9110001841 | 1200 |  |  | 2026-06-07 | 10A Switch | NO | 8 | 136 | 1088 | 1283.84 | 0 | 0 | 1088 | 0 | 0 | ZMAT
RE/0066-PRJ-T1-MEP-EW-LE | Low Side Electrical Works | 2010 | GR01 | 2010 | SMARTWORLD THE EDITION | CONVENIENT LIVING SOLUTIONS PRIVATELIMITED | 9110001841 | 1210 |  |  | 2026-06-07 | Socket shuttered 6/16A 3 pin, 2 module | NO | 5 | 132 | 660 | 778.8 | 0 | 0 | 660 | 0 | 0 | ZMAT
RE/0066-PRJ-T1-MEP-EW-LE | Low Side Electrical Works | 2010 | GR01 | 2010 | SMARTWORLD THE EDITION | CONVENIENT LIVING SOLUTIONS PRIVATELIMITED | 9110001841 | 1220 |  |  | 2026-06-07 | 16A Switch | NO | 2 | 217 | 434 | 512.12 | 0 | 0 | 434 | 0 | 0 | ZMAT
RE/0066-PRJ-T1-MEP-EW-LE | Low Side Electrical Works | 2010 | GR01 | 2010 | SMARTWORLD THE EDITION | CONVENIENT LIVING SOLUTIONS PRIVATELIMITED | 9110001841 | 1230 |  |  | 2026-06-07 | Socket Shuttered 6A/ 16A-3 Pin Combined | NO | 2 | 268 | 536 | 632.48 | 0 | 0 | 536 | 0 | 0 | ZMAT
RE/0066-PRJ-T1-MEP-EW-LE | Low Side Electrical Works | 2010 | GR01 | 2010 | SMARTWORLD THE EDITION | CONVENIENT LIVING SOLUTIONS PRIVATELIMITED | 9110001841 | 1240 |  |  | 2026-06-07 | Blanking Plate | NO | 2 | 39 | 78 | 92.04 | 0 | 0 | 78 | 0 | 0 | ZMAT
RE/0066-PRJ-T1-MEP-EW-LE | Low Side Electrical Works | 2010 | GR01 | 2010 | SMARTWORLD THE EDITION | CONVENIENT LIVING SOLUTIONS PRIVATELIMITED | 9110001841 | 1250 |  |  | 2026-06-07 | Socket | NO | 1 | 205 | 205 | 241.9 | 0 | 0 | 205 | 0 | 0 | ZMAT
RE/0066-PRJ-T1-MEP-EW-LE | Low Side Electrical Works | 2010 | GR01 | 2010 | SMARTWORLD THE EDITION | CONVENIENT LIVING SOLUTIONS PRIVATELIMITED | 9110001841 | 1260 |  |  | 2026-06-07 | Cover Plate | NO | 2 | 170 | 340 | 401.2 | 0 | 0 | 340 | 0 | 0 | ZMAT
RE/0066-PRJ-T1-MEP-EW-LE | Low Side Electrical Works | 2010 | GR01 | 2010 | SMARTWORLD THE EDITION | CONVENIENT LIVING SOLUTIONS PRIVATELIMITED | 9110001841 | 1270 |  |  | 2026-06-07 | Cover Plate | NO | 5 | 176 | 880 | 1038.4 | 0 | 0 | 880 | 0 | 0 | ZMAT
RE/0066-PRJ-T1-MEP-EW-LE | Low Side Electrical Works | 2010 | GR01 | 2010 | SMARTWORLD THE EDITION | CONVENIENT LIVING SOLUTIONS PRIVATELIMITED | 9110001841 | 1280 |  |  | 2026-06-07 | Cover Plate | NO | 2 | 204 | 408 | 481.44 | 0 | 0 | 408 | 0 | 0 | ZMAT
RE/0066-PRJ-T1-MEP-EW-LE | Low Side Electrical Works | 2010 | GR01 | 2010 | SMARTWORLD THE EDITION | CONVENIENT LIVING SOLUTIONS PRIVATELIMITED | 9110001841 | 1290 |  |  | 2026-06-07 | Cover Plate | NO | 2 | 233 | 466 | 549.88 | 0 | 0 | 466 | 0 | 0 | ZMAT
RE/0066-PRJ-T1-MEP-EW-LE | Low Side Electrical Works | 2010 | GR01 | 2010 | SMARTWORLD THE EDITION | CONVENIENT LIVING SOLUTIONS PRIVATELIMITED | 9110001841 | 1300 |  |  | 2026-06-07 | Cover Plate | NO | 2 | 321 | 642 | 757.56 | 0 | 0 | 642 | 0 | 0 | ZMAT
RE/0066-PRJ-T1-MEP-EW-LE | Low Side Electrical Works | 2010 | GR01 | 2010 | SMARTWORLD THE EDITION | CONVENIENT LIVING SOLUTIONS PRIVATELIMITED | 9110001841 | 1310 |  |  | 2026-06-07 | Installation | NO | 1 | 22390 | 22390 | 26420.2 | 0 | 0 | 22390 | 0 | 0 | ZMAT
RE/0066-PRJ-T1-MEP-EW-LE | Low Side Electrical Works | 2010 | GR01 | 2010 | SMARTWORLD THE EDITION | Ahluwalia Contracts India Limited | 9140000321 | 140 |  |  | 2024-07-20 | CONDUITING | AU | 1 | 0 | 21002227.87 | 24782628.89 | 4206638.05 | 4963832.9 | 16795589.82 | 3581626.01 | 4226318.69 | ZSER | 2024-07-15 | 2027-01-14
RE/0066-PRJ-T1-MEP-EW-LE | Low Side Electrical Works | 2010 | GR01 | 2010 | SMARTWORLD THE EDITION | SATKARTAR ELECTRICALS AND ELECTRONIPRIVATE LIMITED | 9140000677 | 10 |  |  | 2026-06-02 | Electrical Works Tower T1 | AU | 1 | 0 | 3750162.75 | 4425192.05 | 0 | 0 | 3750162.75 | 0 | 0 | ZSER | 2026-06-01 | 2028-02-01
RE/0066-PRJ-T1-MEP-EW-LE | Low Side Electrical Works | 2010 | GR01 | 2010 | SMARTWORLD THE EDITION | TRIPLE A ENGINEERING PRIVATE LIMIT | 9140000688 | 10 |  |  | 2026-06-06 | Electrical Works Tower T1 | AU | 1 | 0 | 38294992.34 | 38294992.34 | 0 | 0 | 38294992.34 | 0 | 0 | ZSER | 2026-06-01 | 2028-02-01
RE/0066-PRJ-T1-MEP-EW-LS | Light Fixtures Supply | 2010 | GR01 | 2010 | SMARTWORLD THE EDITION | JAINSONS LIGHTS COAnubhav Jain | 9110001673 | 10 |  |  | 2026-04-07 | F-50 Dual wall Light | NO | 26 | 2880 | 74880 | 88358.4 | 74880 | 88358.4 | 0 | 74880 | 88358.4 | ZMAT
RE/0066-PRJ-T1-MEP-EW-LS | Light Fixtures Supply | 2010 | GR01 | 2010 | SMARTWORLD THE EDITION | JAINSONS LIGHTS COAnubhav Jain | 9110001673 | 20 |  |  | 2026-04-07 | Mirror Light | NO | 7 | 2880 | 20160 | 23788.8 | 20160 | 23788.8 | 0 | 20160 | 23788.8 | ZMAT
RE/0066-PRJ-T1-MEP-EW-LS | Light Fixtures Supply | 2010 | GR01 | 2010 | SMARTWORLD THE EDITION | JAINSONS LIGHTS COAnubhav Jain | 9110001673 | 30 |  |  | 2026-04-07 | LED Bulbs | NO | 52 | 150 | 7800 | 9204 | 7800 | 9204 | 0 | 7800 | 9204 | ZMAT
RE/0066-PRJ-T1-MEP-FF | Fire Fighting Work | 2010 | GR01 | 2010 | SMARTWORLD THE EDITION | Jagrati Civil Constructions Pvt Ltd | 9140000633 | 220 |  |  | 2026-04-15 | FF-FIRE HYDRANT & EQUIPMENT SUPPLY- T1 | AU | 1 | 3205680 | 3205680 | 3782702.4 | 0 | 0 | 3205680 | 0 | 0 | ZSER | 2026-04-08 | 2028-01-31
RE/0066-PRJ-T1-MEP-FF | Fire Fighting Work | 2010 | GR01 | 2010 | SMARTWORLD THE EDITION | Jagrati Civil Constructions Pvt Ltd | 9140000633 | 270 |  |  | 2026-04-15 | FF-AUTOMATIC SPRINKLER & WATER Supply-T1 | AU | 1 | 18319831.38 | 18319831.38 | 21617401.03 | 0 | 0 | 18319831.38 | 0 | 0 | ZSER | 2026-04-08 | 2028-01-31
RE/0066-PRJ-T1-MEP-FF | Fire Fighting Work | 2010 | GR01 | 2010 | SMARTWORLD THE EDITION | Jagrati Civil Constructions Pvt Ltd | 9140000633 | 320 |  |  | 2026-04-15 | FF-PORTABLE FIRE EXTINGUISHERS Supply-T1 | AU | 1 | 354500 | 354500 | 418310 | 0 | 0 | 354500 | 0 | 0 | ZSER | 2026-04-08 | 2028-01-31
RE/0066-PRJ-T1-MEP-HV-HS | High Side | 2010 | GR01 | 2010 | SMARTWORLD THE EDITION | Pahuja Aircon Pvt LtdVinay Malik | 9140000557 | 50 |  |  | 2026-01-29 | HVAC -Lead Apartment ( 3.5+4.5 +Comm)PO | AU | 1 | 1459855.9 | 870833.92 | 1027584.03 | 744488.14 | 878496 | 126345.78 | 0 | 0 | ZSER | 2026-01-20 | 2026-03-21
RE/0066-PRJ-T1-MEP-HV-LS | Low Side | 2010 | GR01 | 2010 | SMARTWORLD THE EDITION | Pahuja Aircon Pvt LtdVinay Malik | 9140000557 | 50 |  |  | 2026-01-29 | HVAC -Lead Apartment ( 3.5+4.5 +Comm)PO | AU | 1 | 0 | 589021.98 | 695045.94 | 0 | 0 | 589021.98 | 0 | 0 | ZSER | 2026-01-20 | 2026-03-21
RE/0066-PRJ-T1-MEP-LT | Lifts | 2010 | GR01 | 2010 |  |  |  | 0 | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
RE/0066-PRJ-T1-MEP-PB-FS | Fixtures Supply | 2010 | GR01 | 2010 | SMARTWORLD THE EDITION | DA MARINA CONCEPTS LLPSAHIL CHAUDHARY | 9110001656 | 10 |  |  | 2026-03-31 | Supply of Bath Tub ( Jacuzzi) | NO | 1 | 249150 | 249150 | 293997 | 249150 | 293997 | 0 | 249150 | 293997 | ZMAT | 2026-02-16 | 2026-03-16
RE/0066-PRJ-T1-MEP-PB-IP | Internal Plumbing | 2010 | GR01 | 2010 | SMARTWORLD THE EDITION | Jagrati Civil Constructions Pvt Ltd | 9140000633 | 10 |  |  | 2026-04-15 | SANITARY FIXTURES & FITTINGS INST. T-1 | AU | 1 | 4621950 | 4621950 | 5453901 | 0 | 0 | 4621950 | 0 | 0 | ZSER | 2026-04-08 | 2028-01-31
RE/0066-PRJ-T1-MEP-PB-IP | Internal Plumbing | 2010 | GR01 | 2010 | SMARTWORLD THE EDITION | Jagrati Civil Constructions Pvt Ltd | 9140000633 | 60 |  |  | 2026-04-15 | INTERNAL DRAINAGE SUPPLY(SOIL, WASTE T-1 | AU | 1 | 15093208.8 | 15093208.8 | 17809986.38 | 0 | 0 | 15093208.8 | 0 | 0 | ZSER | 2026-04-08 | 2028-01-31
RE/0066-PRJ-T1-MEP-PB-IP | Internal Plumbing | 2010 | GR01 | 2010 | SMARTWORLD THE EDITION | Jagrati Civil Constructions Pvt Ltd | 9140000633 | 110 |  |  | 2026-04-15 | DOMESTIC AND FLUSHING WATER SUPPLY T-1 | AU | 1 | 17052178.43 | 17052178.43 | 20121570.55 | 0 | 0 | 17052178.43 | 0 | 0 | ZSER | 2026-04-08 | 2028-01-31
RE/0066-PRJ-T1-MEP-PB-IP | Internal Plumbing | 2010 | GR01 | 2010 | SMARTWORLD THE EDITION | Jagrati Civil Constructions Pvt Ltd | 9140000633 | 160 |  |  | 2026-04-15 | MISCELLANEOUS ITEMS FOR TERRACE WATER-T1 | AU | 1 | 376700 | 376700 | 444506 | 0 | 0 | 376700 | 0 | 0 | ZSER | 2026-04-08 | 2028-01-31
RE/0066-PRJ-T1-MEP-PB-JC | JACUZZI | 2010 | GR01 | 2010 |  |  |  | 0 | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
RE/0066-PRJ-T1-MEP-PN | PNG Gas Pipe Line | 2010 | GR01 | 2010 |  |  |  | 0 | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
RE/0066-PRJ-T2-CIV-CC-LA | Concrete Labour | 2010 | GR01 | 2010 |  |  |  | 0 | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
RE/0066-PRJ-T2-CIV-CC-SL | Concrete Supply & Labour | 2010 | GR01 | 2010 | SMARTWORLD THE EDITION | Ahluwalia Contracts India Limited | 9140000321 | 20 |  |  | 2024-07-20 | REINFORCED CEMENT CONCRETE-I part A | AU | 1 | 0 | 104595526.51 | 123422721.28 | 85835969.25 | 101286443.72 | 18759557.26 | 57854136.24 | 68267880.76 | ZSER | 2024-07-15 | 2027-01-14
RE/0066-PRJ-T2-CIV-CC-SL | Concrete Supply & Labour | 2010 | GR01 | 2010 | SMARTWORLD THE EDITION | Ahluwalia Contracts India Limited | 9140000321 | 30 |  |  | 2024-07-20 | REINFORCED CEMENT CONCRETE-I Part B | AU | 1 | 0 | 83259983.83 | 98246780.92 | 40662548.52 | 47981807.25 | 42597435.31 | 34916100.35 | 41200998.41 | ZSER | 2024-07-15 | 2027-01-14
RE/0066-PRJ-T2-CIV-CC-SL | Concrete Supply & Labour | 2010 | GR01 | 2010 | SMARTWORLD THE EDITION | Ahluwalia Contracts India Limited | 9140000321 | 40 |  |  | 2024-07-20 | REINFORCED CEMENT CONCRETE-I Part C | AU | 1 | 0 | 110667972.97 | 130588208.1 | 34354902.03 | 40538784.39 | 76313070.94 | 29721675.64 | 35071577.25 | ZSER | 2024-07-15 | 2027-01-14
RE/0066-PRJ-T2-CIV-CC-SL | Concrete Supply & Labour | 2010 | GR01 | 2010 | SMARTWORLD THE EDITION | Ahluwalia Contracts India Limited | 9140000321 | 180 |  |  | 2024-07-20 | SUBSTITUTE ITEM | AU | 1 | 0 | 1266038.72 | 1493925.69 | 953935.86 | 1125644.32 | 312102.86 | 953935.86 | 1125644.32 | ZSER | 2024-07-15 | 2027-01-14
RE/0066-PRJ-T2-CIV-CC-SU | Concrete Supply | 2010 | GR01 | 2010 |  |  |  | 0 | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
RE/0066-PRJ-T2-CIV-EW | Earthwork | 2010 | GR01 | 2010 | SMARTWORLD THE EDITION | Ahluwalia Contracts India Limited | 9140000321 | 10 |  |  | 2024-07-20 | SITE DEVLOPMENT AND EARTH WORK | AU | 1 | 0 | 1474182 | 1739534.76 | 429738.81 | 507091.79 | 1044443.19 | 429738.81 | 507091.79 | ZSER | 2024-07-15 | 2027-01-14
RE/0066-PRJ-T2-CIV-MS | Misc Structure Works | 2010 | GR01 | 2010 | SMARTWORLD THE EDITION | Ahluwalia Contracts India Limited | 9140000321 | 100 |  |  | 2024-07-20 | STRUCTURAL STEEL WORKS | AU | 1 | 0 | 35910322.32 | 42374180.34 | 3070650.27 | 3623367.32 | 32839672.05 | 2402175.51 | 2834567.1 | ZSER | 2024-07-15 | 2027-01-14
RE/0066-PRJ-T2-CIV-MS | Misc Structure Works | 2010 | GR01 | 2010 | SMARTWORLD THE EDITION | Ahluwalia Contracts India Limited | 9140000321 | 130 |  |  | 2024-07-20 | INTERNAL & EXTERNAL PLASTERING | AU | 1 | 0 | 607320 | 716637.6 | 0 | 0 | 607320 | 0 | 0 | ZSER | 2024-07-15 | 2027-01-14
RE/0066-PRJ-T2-CIV-MS | Misc Structure Works | 2010 | GR01 | 2010 | SMARTWORLD THE EDITION | Ahluwalia Contracts India Limited | 9140000321 | 160 |  |  | 2024-07-20 | Amed-Monthly rental payment to M/S ACIL | AU | 1 | 0 | 1230377.3 | 1451845.21 | 154479.6 | 182285.93 | 1075897.7 | 0 | 0 | ZSER | 2024-07-15 | 2027-01-14
RE/0066-PRJ-T2-CIV-MW | Masonry Works | 2010 | GR01 | 2010 | SMARTWORLD THE EDITION | Ahluwalia Contracts India Limited | 9140000321 | 90 |  |  | 2024-07-20 | MASONARY WORKS | AU | 1 | 0 | 8702363.87 | 10268789.37 | 1133181.36 | 1337154.01 | 7569182.51 | 1133181.36 | 1337154.01 | ZSER | 2024-07-15 | 2027-01-14
RE/0066-PRJ-T2-CIV-MW | Masonry Works | 2010 | GR01 | 2010 | SMARTWORLD THE EDITION | SNA ASSOCIATES INDIA PRIVATE LIMITPraful Asatkar | 9140000604 | 10 |  |  | 2026-03-10 | Finishing Work -T2 | AU | 1 | 299773018.22 | 1912000 | 2256160 | 0 | 0 | 1912000 | 0 | 0 | ZSER | 2026-04-03 | 2028-04-03
RE/0066-PRJ-T2-CIV-PW-IP | Internal Plaster | 2010 | GR01 | 2010 | SMARTWORLD THE EDITION | Ahluwalia Contracts India Limited | 9140000321 | 130 |  |  | 2024-07-20 | INTERNAL & EXTERNAL PLASTERING | AU | 1 | 0 | 6775115 | 7994635.7 | 0 | 0 | 6775115 | 0 | 0 | ZSER | 2024-07-15 | 2027-01-14
RE/0066-PRJ-T2-CIV-PW-XP | External Plaster | 2010 | GR01 | 2010 | SMARTWORLD THE EDITION | Ahluwalia Contracts India Limited | 9140000321 | 130 |  |  | 2024-07-20 | INTERNAL & EXTERNAL PLASTERING | AU | 1 | 0 | 225900 | 266562 | 0 | 0 | 225900 | 0 | 0 | ZSER | 2024-07-15 | 2027-01-14
RE/0066-PRJ-T2-CIV-RS-LA | Reinforcement Labour | 2010 | GR01 | 2010 | SMARTWORLD THE EDITION | Ahluwalia Contracts India Limited | 9140000321 | 70 |  |  | 2024-07-20 | REINFORCEMENT STEEL Installation Part A | AU | 1 | 0 | 140802078 | 166146452.04 | 59936553.7 | 70725133.37 | 80865524.3 | 55163702.19 | 65093168.59 | ZSER | 2024-07-15 | 2027-01-14
RE/0066-PRJ-T2-CIV-RS-LA | Reinforcement Labour | 2010 | GR01 | 2010 | SMARTWORLD THE EDITION | Ahluwalia Contracts India Limited | 9140000321 | 80 |  |  | 2024-07-20 | REINFORCEMENT STEEL Installation Part B | AU | 1 | 0 | 12352887.89 | 14576407.71 | 3875089 | 4572605.02 | 8477798.89 | 3635599 | 4290006.82 | ZSER | 2024-07-15 | 2027-01-14
RE/0066-PRJ-T2-CIV-RS-SU | Reinforcement Supply | 2010 | GR01 | 2010 | SMARTWORLD THE EDITION | JINDAL STEEL LIMITEDMr Robin Taneja | 9110000725 | 50 |  |  | 2024-10-10 | Fe 550D TMT Steel 16MM | TO | 4.2 | 53500 | 224700 | 265146 | 224700 | 265146 | 0 | 224700 | 265146 | ZMAT | 2025-01-20 | 2025-03-20
RE/0066-PRJ-T2-CIV-RS-SU | Reinforcement Supply | 2010 | GR01 | 2010 | SMARTWORLD THE EDITION | JINDAL STEEL LIMITEDMr Robin Taneja | 9110000725 | 140 |  |  | 2024-10-10 | Fe 550D TMT Steel 32MM | TO | 38.66 | 53500 | 2068310 | 2440605.8 | 2068310 | 2440605.8 | 0 | 2068310 | 2440605.8 | ZMAT | 2025-01-20 | 2025-03-20
RE/0066-PRJ-T2-CIV-RS-SU | Reinforcement Supply | 2010 | GR01 | 2010 | SMARTWORLD THE EDITION | Carna Corporation Pvt LtdVISHWANATH | 9110000726 | 20 |  |  | 2024-10-11 | Fe 550D TMT Steel 10 MM | TO | 74 | 54250 | 4014500 | 4737110 | 4014500 | 4737110 | 0 | 4014499.68 | 4737109.69 | ZMAT | 2024-10-11 | 2024-11-11
RE/0066-PRJ-T2-CIV-RS-SU | Reinforcement Supply | 2010 | GR01 | 2010 | SMARTWORLD THE EDITION | Northern Steel and General MillsPrivate Limited | 9110000774 | 20 |  |  | 2024-11-15 | Steel Re-bar TMT 16 mm Dia. FE-550D | TO | 22.5 | 54500 | 1226250 | 1446975 | 1318355 | 1555658.9 | 92105 | 1318355 | 1555658.9 | ZMAT | 2025-01-20 | 2025-03-20
RE/0066-PRJ-T2-CIV-RS-SU | Reinforcement Supply | 2010 | GR01 | 2010 | SMARTWORLD THE EDITION | Northern Steel and General MillsPrivate Limited | 9110000774 | 70 |  |  | 2024-11-15 | Steel Re-bar TMT 20 mm Dia. FE-550D | TO | 8 | 54500 | 436000 | 514480 | 436000 | 514480 | 0 | 436000 | 514480 | ZMAT | 2025-01-20 | 2025-03-20
RE/0066-PRJ-T2-CIV-RS-SU | Reinforcement Supply | 2010 | GR01 | 2010 | SMARTWORLD THE EDITION | Northern Steel and General MillsPrivate Limited | 9110000774 | 140 |  |  | 2024-11-15 | Steel Re-bar TMT 25 mm Dia. FE-550D | TO | 4 | 54500 | 218000 | 257240 | 218000 | 257240 | 0 | 218000 | 257240 | ZMAT | 2025-01-20 | 2025-03-20
RE/0066-PRJ-T2-CIV-RS-SU | Reinforcement Supply | 2010 | GR01 | 2010 | SMARTWORLD THE EDITION | Jindal Steel Limited | 9110000777 | 20 |  |  | 2024-11-15 | Steel Re-bar TMT 20 mm Dia. FE-550D | TO | 8.5 | 54500 | 463250 | 546635 | 463250 | 546635 | 0 | 463250 | 546635 | ZMAT | 2025-01-20 | 2025-03-20
RE/0066-PRJ-T2-CIV-RS-SU | Reinforcement Supply | 2010 | GR01 | 2010 | SMARTWORLD THE EDITION | Jindal Steel Limited | 9110000777 | 90 |  |  | 2024-11-15 | Steel Re-bar TMT 25 mm Dia. FE-550D | TO | 3 | 54500 | 163500 | 192930 | 163500 | 192930 | 0 | 163500 | 192930 | ZMAT | 2025-01-20 | 2025-03-20
RE/0066-PRJ-T2-CIV-RS-SU | Reinforcement Supply | 2010 | GR01 | 2010 | SMARTWORLD THE EDITION | Jindal Steel Limited | 9110000777 | 160 |  |  | 2024-11-15 | Steel Re-bar TMT 32 mm Dia. FE-550D | TO | 27 | 54500 | 1471500 | 1736370 | 1471500 | 1736370 | 0 | 1471500 | 1736370 | ZMAT | 2025-01-20 | 2025-03-20
RE/0066-PRJ-T2-CIV-RS-SU | Reinforcement Supply | 2010 | GR01 | 2010 | SMARTWORLD THE EDITION | Carna Corporation Pvt LtdVISHWANATH | 9110000779 | 20 |  |  | 2024-11-16 | Steel Re-bar TMT 20 mm Dia. FE-550D | TO | 9 | 54500 | 490500 | 578790 | 490500 | 578790 | 0 | 490500 | 578790 | ZMAT | 2025-01-20 | 2025-03-20
RE/0066-PRJ-T2-CIV-RS-SU | Reinforcement Supply | 2010 | GR01 | 2010 | SMARTWORLD THE EDITION | Carna Corporation Pvt LtdVISHWANATH | 9110000779 | 90 |  |  | 2024-11-16 | Steel Re-bar TMT 25 mm Dia. FE-550D | TO | 5 | 54500 | 272500 | 321550 | 272500 | 321550 | 0 | 272500 | 321550 | ZMAT | 2025-01-20 | 2025-03-20
RE/0066-PRJ-T2-CIV-RS-SU | Reinforcement Supply | 2010 | GR01 | 2010 | SMARTWORLD THE EDITION | Carna Corporation Pvt LtdVISHWANATH | 9110000779 | 160 |  |  | 2024-11-16 | Steel Re-bar TMT 32 mm Dia. FE-550D | TO | 87 | 54500 | 4741500 | 5594970 | 4741500 | 5594970 | 0 | 4741500.5 | 5594970.49 | ZMAT | 2025-01-20 | 2025-03-20
RE/0066-PRJ-T2-CIV-RS-SU | Reinforcement Supply | 2010 | GR01 | 2010 | SMARTWORLD THE EDITION | Ram Niwas & SonsDeepak gupta | 9110000782 | 10 |  |  | 2024-11-16 | Steel Re-bar TMT 08 mm Dia. FE-550D | TO | 15 | 52500 | 787500 | 929250 | 787500 | 929250 | 0 | 787500 | 929250.11 | ZMAT | 2024-11-16 | 2024-12-15
RE/0066-PRJ-T2-CIV-RS-SU | Reinforcement Supply | 2010 | GR01 | 2010 | SMARTWORLD THE EDITION | Rashtriya Ispat Nigam Ltd | 9110000790 | 30 |  |  | 2024-11-29 | Fe 550D TMT Steel Coil 10MM | TO | 51 | 54450 | 2776950 | 3276801 | 2776950 | 3276801 | 0 | 2776950 | 3276801 | ZMAT | 2024-11-29 | 2024-12-28
RE/0066-PRJ-T2-CIV-RS-SU | Reinforcement Supply | 2010 | GR01 | 2010 | SMARTWORLD THE EDITION | Rashtriya Ispat Nigam Ltd | 9110000790 | 100 |  |  | 2024-11-29 | Fe 550D TMT Steel Coil 12MM | TO | 16 | 53950 | 863200 | 1018576 | 727785.5 | 858786.89 | 135414.5 | 727785.5 | 858786.9 | ZMAT | 2024-11-29 | 2024-12-28
RE/0066-PRJ-T2-CIV-RS-SU | Reinforcement Supply | 2010 | GR01 | 2010 | SMARTWORLD THE EDITION | Jindal Steel Limited | 9110000820 | 20 |  |  | 2024-10-10 | Fe 550D TMT Steel 12MM | TO | 24 | 53500 | 1284000 | 1515120 | 1254254 | 1480019.72 | 29746 | 1254254 | 1480019.72 | ZMAT | 2025-01-20 | 2025-03-20
RE/0066-PRJ-T2-CIV-RS-SU | Reinforcement Supply | 2010 | GR01 | 2010 | SMARTWORLD THE EDITION | Jindal Steel Limited | 9110000820 | 50 |  |  | 2024-10-10 | Fe 550D TMT Steel 16MM | TO | 5.4 | 53500 | 288900 | 340902 | 288900 | 340902 | 0 | 288900 | 340902 | ZMAT | 2025-01-20 | 2025-03-20
RE/0066-PRJ-T2-CIV-RS-SU | Reinforcement Supply | 2010 | GR01 | 2010 | SMARTWORLD THE EDITION | Jindal Steel Limited | 9110000820 | 80 |  |  | 2024-10-10 | Fe 550D TMT Steel 20MM | TO | 41.25 | 53500 | 2206875 | 2604112.5 | 2206875 | 2604112.5 | 0 | 2206875 | 2604112.5 | ZMAT | 2025-01-20 | 2025-03-20
RE/0066-PRJ-T2-CIV-RS-SU | Reinforcement Supply | 2010 | GR01 | 2010 | SMARTWORLD THE EDITION | Jindal Steel Limited | 9110000820 | 110 |  |  | 2024-10-10 | Fe 550D TMT Steel 25MM | TO | 99.25 | 53500 | 5309875 | 6265652.5 | 5309875 | 6265652.5 | 0 | 5309875 | 6265652.5 | ZMAT | 2025-01-20 | 2025-03-20
RE/0066-PRJ-T2-CIV-RS-SU | Reinforcement Supply | 2010 | GR01 | 2010 | SMARTWORLD THE EDITION | Jindal Steel Limited | 9110000820 | 140 |  |  | 2024-10-10 | Fe 550D TMT Steel 32MM | TO | 611.62 | 53500 | 32721670 | 38611570.6 | 32543247.5 | 38401032.05 | 178422.5 | 32543247.5 | 38401032.05 | ZMAT | 2025-01-20 | 2025-03-20
RE/0066-PRJ-T2-CIV-RS-SU | Reinforcement Supply | 2010 | GR01 | 2010 | SMARTWORLD THE EDITION | Carna Corporation Pvt LtdVISHWANATH | 9110000837 | 20 |  |  | 2025-01-09 | Steel Re-bar TMT 08 mm Dia. FE-550D | TO | 8 | 51400 | 411200 | 485216 | 411200 | 485216 | 0 | 411200 | 485216 | ZMAT | 2025-01-20 | 2025-03-20
RE/0066-PRJ-T2-CIV-RS-SU | Reinforcement Supply | 2010 | GR01 | 2010 | SMARTWORLD THE EDITION | Ram Niwas & SonsDeepak gupta | 9110000862 | 40 |  |  | 2025-02-15 | Steel Re-bar TMT 10 mm Dia. FE-550D | TO | 39 | 50200 | 1957800 | 2310204 | 1697210.95 | 2002708.92 | 260589.05 | 1957800 | 2310204 | ZMAT
RE/0066-PRJ-T2-CIV-RS-SU | Reinforcement Supply | 2010 | GR01 | 2010 | SMARTWORLD THE EDITION | Jindal Steel Limited | 9110000886 | 20 |  |  | 2025-03-12 | Steel Re-bar TMT 12 mm Dia. FE-550D | TO | 50 | 54750 | 2737500 | 3230250 | 2737500 | 3230250 | 0 | 2737500 | 3230250 | ZMAT
RE/0066-PRJ-T2-CIV-RS-SU | Reinforcement Supply | 2010 | GR01 | 2010 | SMARTWORLD THE EDITION | Jindal Steel Limited | 9110000886 | 80 |  |  | 2025-03-12 | Steel Re-bar TMT 16 mm Dia. FE-550D | TO | 25 | 54750 | 1368750 | 1615125 | 1368750 | 1615125 | 0 | 1368750 | 1615125 | ZMAT
RE/0066-PRJ-T2-CIV-RS-SU | Reinforcement Supply | 2010 | GR01 | 2010 | SMARTWORLD THE EDITION | Jindal Steel Limited | 9110000886 | 140 |  |  | 2025-03-12 | Steel Re-bar TMT 20 mm Dia. FE-550D | TO | 30 | 54750 | 1642500 | 1938150 | 1642500 | 1938150 | 0 | 1642500 | 1938150 | ZMAT
RE/0066-PRJ-T2-CIV-RS-SU | Reinforcement Supply | 2010 | GR01 | 2010 | SMARTWORLD THE EDITION | Ram Niwas & SonsDeepak gupta | 9110000887 | 20 |  |  | 2025-03-12 | Steel Re-bar TMT 10 mm Dia. FE-550D | TO | 10.5 | 52900 | 555450 | 655431 | 529000 | 624220 | 26450 | 529000 | 624220 | ZMAT
RE/0066-PRJ-T2-CIV-RS-SU | Reinforcement Supply | 2010 | GR01 | 2010 | SMARTWORLD THE EDITION | Carna Corporation Pvt LtdVISHWANATH | 9110000889 | 20 |  |  | 2025-03-12 | Steel Re-bar TMT 10 mm Dia. FE-550D | TO | 4.5 | 55500 | 249750 | 294705 | 249750 | 294705 | 0 | 249750 | 294705 | ZMAT
RE/0066-PRJ-T2-CIV-RS-SU | Reinforcement Supply | 2010 | GR01 | 2010 | SMARTWORLD THE EDITION | Rashtriya Ispat Nigam Ltd | 9110000961 | 20 |  |  | 2025-04-08 | Fe 550D TMT Steel Coil 10MM | TO | 9 | 58750 | 528750 | 623925 | 528750 | 623925 | 0 | 528750 | 623925 | ZMAT
RE/0066-PRJ-T2-CIV-RS-SU | Reinforcement Supply | 2010 | GR01 | 2010 | SMARTWORLD THE EDITION | Rashtriya Ispat Nigam Ltd | 9110000961 | 90 |  |  | 2025-04-08 | Fe 550D TMT Steel Coil 08MM | TO | 9 | 60000 | 540000 | 637200 | 540000 | 637200 | 0 | 540000 | 637200 | ZMAT
RE/0066-PRJ-T2-CIV-RS-SU | Reinforcement Supply | 2010 | GR01 | 2010 | SMARTWORLD THE EDITION | Vikrant Ispat Udyog | 9110000966 | 20 |  |  | 2025-04-09 | Fe 550D TMT Steel Coil 10MM | TO | 3 | 64250 | 192750 | 227445 | 192750 | 227445 | 0 | 192750 | 227445 | ZMAT
RE/0066-PRJ-T2-CIV-RS-SU | Reinforcement Supply | 2010 | GR01 | 2010 | SMARTWORLD THE EDITION | Vikrant Ispat Udyog | 9110000966 | 90 |  |  | 2025-04-09 | Fe 550D TMT Steel Coil 08MM | TO | 3 | 65750 | 197250 | 232755 | 197250 | 232755 | 0 | 197250 | 232755 | ZMAT
RE/0066-PRJ-T2-CIV-RS-SU | Reinforcement Supply | 2010 | GR01 | 2010 | SMARTWORLD THE EDITION | JINDAL STEEL LIMITEDMr Robin Taneja | 9110000991 | 180 |  |  | 2025-04-17 | Steel Re-bar TMT 25 mm Dia. FE-550D | TO | 8 | 57750 | 462000 | 545160 | 462000 | 545160 | 0 | 462000 | 545160 | ZMAT
RE/0066-PRJ-T2-CIV-RS-SU | Reinforcement Supply | 2010 | GR01 | 2010 | SMARTWORLD THE EDITION | Ram Niwas & SonsDeepak gupta | 9110000992 | 40 |  |  | 2025-04-17 | Steel Re-bar TMT 10 mm Dia. FE-550D | TO | 40 | 56000 | 2240000 | 2643200 | 2208640 | 2606195.2 | 31360 | 2208640 | 2606195.2 | ZMAT
RE/0066-PRJ-T2-CIV-RS-SU | Reinforcement Supply | 2010 | GR01 | 2010 | SMARTWORLD THE EDITION | Sapcon Steels Private Limited | 9110000999 | 40 |  |  | 2025-04-18 | Fe 550D TMT Steel Coil 10MM | TO | 40 | 58250 | 2330000 | 2749400 | 2330000 | 2749400 | 0 | 2330000 | 2749400 | ZMAT | 2025-04-11 | 2025-04-30
RE/0066-PRJ-T2-CIV-RS-SU | Reinforcement Supply | 2010 | GR01 | 2010 | SMARTWORLD THE EDITION | Sapcon Steels Private Limited | 9110001009 | 20 |  |  | 2025-04-28 | Steel Re-bar TMT 32 mm Dia. FE-550D | TO | 11 | 57000 | 627000 | 739860 | 399000 | 470820 | 228000 | 399000 | 470820 | ZMAT
RE/0066-PRJ-T2-CIV-RS-SU | Reinforcement Supply | 2010 | GR01 | 2010 | SMARTWORLD THE EDITION | Jindal Steel Limited | 9110001055 | 20 |  |  | 2025-05-17 | Steel Re-bar TMT 20 mm Dia. FE-550D | TO | 10 | 54850 | 548500 | 647230 | 548500 | 647230 | 0 | 548500 | 647230 | ZMAT | 2025-05-29 | 2025-06-29
RE/0066-PRJ-T2-CIV-RS-SU | Reinforcement Supply | 2010 | GR01 | 2010 | SMARTWORLD THE EDITION | Jindal Steel Limited | 9110001055 | 90 |  |  | 2025-05-17 | Steel Re-bar TMT 25 mm Dia. FE-550D | TO | 33 | 54850 | 1810050 | 2135859 | 1810050 | 2135859 | 0 | 1810050 | 2135859 | ZMAT | 2025-05-29 | 2025-06-29
RE/0066-PRJ-T2-CIV-RS-SU | Reinforcement Supply | 2010 | GR01 | 2010 | SMARTWORLD THE EDITION | Jindal Steel Limited | 9110001055 | 160 |  |  | 2025-05-17 | Steel Re-bar TMT 32 mm Dia. FE-550D | TO | 10 | 54850 | 548500 | 647230 | 548500 | 647230 | 0 | 548500 | 647230 | ZMAT | 2025-05-29 | 2025-06-29
RE/0066-PRJ-T2-CIV-RS-SU | Reinforcement Supply | 2010 | GR01 | 2010 | SMARTWORLD THE EDITION | Jindal Steel Limited | 9110001073 | 30 |  |  | 2025-05-27 | Steel Re-bar TMT 12 mm Dia. FE-550D | TO | 10 | 57750 | 577500 | 681450 | 577500 | 681450 | 0 | 577500 | 681450 | ZMAT
RE/0066-PRJ-T2-CIV-RS-SU | Reinforcement Supply | 2010 | GR01 | 2010 | SMARTWORLD THE EDITION | Jindal Steel Limited | 9110001073 | 100 |  |  | 2025-05-27 | Steel Re-bar TMT 16 mm Dia. FE-550D | TO | 15 | 57750 | 866250 | 1022175 | 866250 | 1022175 | 0 | 866250 | 1022175 | ZMAT
RE/0066-PRJ-T2-CIV-RS-SU | Reinforcement Supply | 2010 | GR01 | 2010 | SMARTWORLD THE EDITION | Jindal Steel Limited | 9110001073 | 180 |  |  | 2025-05-27 | Steel Re-bar TMT 25 mm Dia. FE-550D | TO | 2 | 57750 | 115500 | 136290 | 115500 | 136290 | 0 | 115500 | 136290 | ZMAT
RE/0066-PRJ-T2-CIV-RS-SU | Reinforcement Supply | 2010 | GR01 | 2010 | SMARTWORLD THE EDITION | JINDAL STEEL LIMITEDMr Robin Taneja | 9110001079 | 20 |  |  | 2025-05-29 | Steel Re-bar TMT 25 mm Dia. FE-550D | TO | 12 | 54850 | 658200 | 776676 | 658200 | 776676 | 0 | 658200 | 776676 | ZMAT | 2025-05-29 | 2025-06-29
RE/0066-PRJ-T2-CIV-RS-SU | Reinforcement Supply | 2010 | GR01 | 2010 | SMARTWORLD THE EDITION | Ram Niwas & SonsDeepak gupta | 9110001126 | 20 |  |  | 2025-06-20 | Steel Re-bar TMT 08 mm Dia. FE-550D | TO | 10 | 51000 | 510000 | 601800 | 510000 | 601800 | 0 | 510000 | 601800 | ZMAT | 2025-06-20 | 2025-07-20
RE/0066-PRJ-T2-CIV-RS-SU | Reinforcement Supply | 2010 | GR01 | 2010 | SMARTWORLD THE EDITION | Jindal Steel Limited | 9110001127 | 20 |  |  | 2025-06-20 | Steel Re-bar TMT 12 mm Dia. FE-550D | TO | 30 | 50600 | 1518000 | 1791240 | 1518000 | 1791240 | 0 | 1518000 | 1791240 | ZMAT | 2025-06-20 | 2025-07-20
RE/0066-PRJ-T2-CIV-RS-SU | Reinforcement Supply | 2010 | GR01 | 2010 | SMARTWORLD THE EDITION | Jindal Steel Limited | 9110001127 | 100 |  |  | 2025-06-20 | Steel Re-bar TMT 16 mm Dia. FE-550D | TO | 25 | 50600 | 1265000 | 1492700 | 1265000 | 1492700 | 0 | 1265000 | 1492700 | ZMAT | 2025-06-20 | 2025-07-20
RE/0066-PRJ-T2-CIV-RS-SU | Reinforcement Supply | 2010 | GR01 | 2010 | SMARTWORLD THE EDITION | Jindal Steel Limited | 9110001127 | 180 |  |  | 2025-06-20 | Steel Re-bar TMT 20 mm Dia. FE-550D | TO | 15 | 50600 | 759000 | 895620 | 759000 | 895620 | 0 | 759000 | 895620 | ZMAT | 2025-06-20 | 2025-07-20
RE/0066-PRJ-T2-CIV-RS-SU | Reinforcement Supply | 2010 | GR01 | 2010 | SMARTWORLD THE EDITION | Jindal Steel Limited | 9110001127 | 250 |  |  | 2025-06-20 | Steel Re-bar TMT 25 mm Dia. FE-550D | TO | 20 | 50600 | 1012000 | 1194160 | 1012000 | 1194160 | 0 | 1012000 | 1194160 | ZMAT | 2025-06-20 | 2025-07-20
RE/0066-PRJ-T2-CIV-RS-SU | Reinforcement Supply | 2010 | GR01 | 2010 | SMARTWORLD THE EDITION | Jindal Steel Limited | 9110001127 | 330 |  |  | 2025-06-20 | Steel Re-bar TMT 32 mm Dia. FE-550D | TO | 10 | 50600 | 506000 | 597080 | 506000 | 597080 | 0 | 506000 | 597080 | ZMAT | 2025-06-20 | 2025-07-20
RE/0066-PRJ-T2-CIV-RS-SU | Reinforcement Supply | 2010 | GR01 | 2010 | SMARTWORLD THE EDITION | Jindal Steel Limited | 9110001162 | 20 |  |  | 2025-07-17 | Steel Re-bar TMT 10 mm Dia. FE-550D | TO | 40 | 47500 | 1900000 | 2242000 | 0 | 0 | 1900000 | 0 | 0 | ZMAT | 2025-07-17 | 2025-08-17
RE/0066-PRJ-T2-CIV-RS-SU | Reinforcement Supply | 2010 | GR01 | 2010 | SMARTWORLD THE EDITION | Jindal Steel Limited | 9110001162 | 100 |  |  | 2025-07-17 | Steel Re-bar TMT 12 mm Dia. FE-550D | TO | 15 | 46500 | 697500 | 823050 | 0 | 0 | 697500 | 0 | 0 | ZMAT | 2025-07-17 | 2025-08-17
RE/0066-PRJ-T2-CIV-RS-SU | Reinforcement Supply | 2010 | GR01 | 2010 | SMARTWORLD THE EDITION | Jindal Steel Limited | 9110001162 | 180 |  |  | 2025-07-17 | Steel Re-bar TMT 16 mm Dia. FE-550D | TO | 5 | 46500 | 232500 | 274350 | 0 | 0 | 232500 | 0 | 0 | ZMAT | 2025-07-17 | 2025-08-17
RE/0066-PRJ-T2-CIV-RS-SU | Reinforcement Supply | 2010 | GR01 | 2010 | SMARTWORLD THE EDITION | Jindal Steel Limited | 9110001162 | 240 |  |  | 2025-07-17 | Steel Re-bar TMT 20 mm Dia. FE-550D | TO | 5 | 46500 | 232500 | 274350 | 0 | 0 | 232500 | 0 | 0 | ZMAT | 2025-07-17 | 2025-08-17
RE/0066-PRJ-T2-CIV-RS-SU | Reinforcement Supply | 2010 | GR01 | 2010 | SMARTWORLD THE EDITION | Jindal Steel Limited | 9110001162 | 310 |  |  | 2025-07-17 | Steel Re-bar TMT 25 mm Dia. FE-550D | TO | 5 | 46500 | 232500 | 274350 | 0 | 0 | 232500 | 0 | 0 | ZMAT | 2025-07-17 | 2025-08-17
RE/0066-PRJ-T2-CIV-RS-SU | Reinforcement Supply | 2010 | GR01 | 2010 | SMARTWORLD THE EDITION | Jindal Steel Limited | 9110001162 | 390 |  |  | 2025-07-17 | Steel Re-bar TMT 32 mm Dia. FE-550D | TO | 5 | 46500 | 232500 | 274350 | 0 | 0 | 232500 | 0 | 0 | ZMAT | 2025-07-17 | 2025-08-17
RE/0066-PRJ-T2-CIV-RS-SU | Reinforcement Supply | 2010 | GR01 | 2010 | SMARTWORLD THE EDITION | Rashtriya Ispat Nigam Ltd | 9110001212 | 20 |  |  | 2025-08-14 | Steel Re-bar TMT 08 mm Dia. FE-550D | TO | 10 | 49300 | 493000 | 581740 | 493000 | 581740 | 0 | 493000 | 581740 | ZMAT | 2025-08-14 | 2025-09-14
RE/0066-PRJ-T2-CIV-RS-SU | Reinforcement Supply | 2010 | GR01 | 2010 | SMARTWORLD THE EDITION | Rashtriya Ispat Nigam Ltd | 9110001212 | 80 |  |  | 2025-08-14 | Steel Re-bar TMT 10 mm Dia. FE-550D | TO | 55 | 47800 | 2629000 | 3102220 | 2629000 | 3102220 | 0 | 2629000 | 3102220 | ZMAT | 2025-08-14 | 2025-09-14
RE/0066-PRJ-T2-CIV-RS-SU | Reinforcement Supply | 2010 | GR01 | 2010 | SMARTWORLD THE EDITION | Jindal Steel Limited | 9110001213 | 20 |  |  | 2025-08-14 | Steel Re-bar TMT 12 mm Dia. FE-550D | TO | 35 | 47000 | 1645000 | 1941100 | 1645000 | 1941100 | 0 | 1645000 | 1941100 | ZMAT | 2025-08-14 | 2025-09-14
RE/0066-PRJ-T2-CIV-RS-SU | Reinforcement Supply | 2010 | GR01 | 2010 | SMARTWORLD THE EDITION | Jindal Steel Limited | 9110001213 | 80 |  |  | 2025-08-14 | Steel Re-bar TMT 16 mm Dia. FE-550D | TO | 15 | 47000 | 705000 | 831900 | 705000 | 831900 | 0 | 705000 | 831900 | ZMAT | 2025-08-14 | 2025-09-14
RE/0066-PRJ-T2-CIV-RS-SU | Reinforcement Supply | 2010 | GR01 | 2010 | SMARTWORLD THE EDITION | Jindal Steel Limited | 9110001213 | 140 |  |  | 2025-08-14 | Steel Re-bar TMT 20 mm Dia. FE-550D | TO | 15 | 47000 | 705000 | 831900 | 705000 | 831900 | 0 | 705000 | 831900 | ZMAT | 2025-08-14 | 2025-09-14
RE/0066-PRJ-T2-CIV-RS-SU | Reinforcement Supply | 2010 | GR01 | 2010 | SMARTWORLD THE EDITION | Jindal Steel Limited | 9110001213 | 200 |  |  | 2025-08-14 | Steel Re-bar TMT 25 mm Dia. FE-550D | TO | 20 | 47000 | 940000 | 1109200 | 940000 | 1109200 | 0 | 940000 | 1109200 | ZMAT | 2025-08-14 | 2025-09-14
RE/0066-PRJ-T2-CIV-RS-SU | Reinforcement Supply | 2010 | GR01 | 2010 | SMARTWORLD THE EDITION | Jindal Steel Limited | 9110001213 | 260 |  |  | 2025-08-14 | Steel Re-bar TMT 32 mm Dia. FE-550D | TO | 20 | 47000 | 940000 | 1109200 | 940000 | 1109200 | 0 | 940000 | 1109200 | ZMAT | 2025-08-14 | 2025-09-14
RE/0066-PRJ-T2-CIV-RS-SU | Reinforcement Supply | 2010 | GR01 | 2010 | SMARTWORLD THE EDITION | Steel Authority Of India LTD | 9110001280 | 30 |  |  | 2025-09-18 | Steel Re-bar TMT 12 mm Dia. FE-550D | TO | 25.74 | 46260 | 1190732.4 | 1405064.23 | 1190732.4 | 1405064.23 | 0 | 1190732.4 | 1405064.24 | ZMAT | 2025-09-18 | 2025-10-18
RE/0066-PRJ-T2-CIV-RS-SU | Reinforcement Supply | 2010 | GR01 | 2010 | SMARTWORLD THE EDITION | Steel Authority Of India LTD | 9110001280 | 90 |  |  | 2025-09-18 | Steel Re-bar TMT 16 mm Dia. FE-550D | TO | 20 | 46260 | 925200 | 1091736 | 925199.99 | 1091735.99 | 0.01 | 925200 | 1091736.02 | ZMAT | 2025-09-18 | 2025-10-18
RE/0066-PRJ-T2-CIV-RS-SU | Reinforcement Supply | 2010 | GR01 | 2010 | SMARTWORLD THE EDITION | Steel Authority Of India LTD | 9110001280 | 150 |  |  | 2025-09-18 | Steel Re-bar TMT 20 mm Dia. FE-550D | TO | 24.59 | 46260 | 1137533.4 | 1342289.41 | 1137533.4 | 1342289.41 | 0 | 1137533.4 | 1342289.42 | ZMAT | 2025-09-18 | 2025-10-18
RE/0066-PRJ-T2-CIV-RS-SU | Reinforcement Supply | 2010 | GR01 | 2010 | SMARTWORLD THE EDITION | Steel Authority Of India LTD | 9110001280 | 210 |  |  | 2025-09-18 | Steel Re-bar TMT 25 mm Dia. FE-550D | TO | 13 | 46260 | 601380 | 709628.4 | 601380 | 709628.4 | 0 | 601380 | 709628.4 | ZMAT | 2025-09-18 | 2025-10-18
RE/0066-PRJ-T2-CIV-RS-SU | Reinforcement Supply | 2010 | GR01 | 2010 | SMARTWORLD THE EDITION | Steel Authority Of India LTD | 9110001280 | 270 |  |  | 2025-09-18 | Steel Re-bar TMT 32 mm Dia. FE-550D | TO | 12.75 | 46260 | 589815 | 695981.7 | 589815 | 695981.7 | 0 | 589815 | 695981.7 | ZMAT | 2025-09-18 | 2025-10-18
RE/0066-PRJ-T2-CIV-RS-SU | Reinforcement Supply | 2010 | GR01 | 2010 | SMARTWORLD THE EDITION | Steel Authority Of India LTD | 9110001280 | 300 |  |  | 2025-09-18 | Steel Re-bar TMT 10 mm Dia. FE-550D | TO | 15.8 | 47260 | 746708 | 881115.44 | 746708 | 881115.44 | 0 | 746708 | 881115.44 | ZMAT | 2025-09-18 | 2025-10-18
RE/0066-PRJ-T2-CIV-RS-SU | Reinforcement Supply | 2010 | GR01 | 2010 | SMARTWORLD THE EDITION | Ram Niwas & SonsDeepak gupta | 9110001305 | 80 |  |  | 2025-10-09 | Steel Re-bar TMT 10 mm Dia. FE-550D | TO | 29 | 46500 | 1348500 | 1591230 | 1341525 | 1582999.5 | 6975 | 1341525 | 1582999.5 | ZMAT | 2025-10-09 | 2025-11-08
RE/0066-PRJ-T2-CIV-RS-SU | Reinforcement Supply | 2010 | GR01 | 2010 | SMARTWORLD THE EDITION | Jindal Steel Limited | 9110001307 | 20 |  |  | 2025-10-09 | Steel Re-bar TMT 12 mm Dia. FE-550D | TO | 5 | 46500 | 232500 | 274350 | 232500 | 274350 | 0 | 232500 | 274350 | ZMAT | 2025-10-09 | 2025-11-08
RE/0066-PRJ-T2-CIV-RS-SU | Reinforcement Supply | 2010 | GR01 | 2010 | SMARTWORLD THE EDITION | Jindal Steel Limited | 9110001307 | 80 |  |  | 2025-10-09 | Steel Re-bar TMT 16 mm Dia. FE-550D | TO | 20 | 46500 | 930000 | 1097400 | 930000 | 1097400 | 0 | 930000 | 1097400 | ZMAT | 2025-10-09 | 2025-11-08
RE/0066-PRJ-T2-CIV-RS-SU | Reinforcement Supply | 2010 | GR01 | 2010 | SMARTWORLD THE EDITION | Jindal Steel Limited | 9110001307 | 140 |  |  | 2025-10-09 | Steel Re-bar TMT 20 mm Dia. FE-550D | TO | 20 | 46500 | 930000 | 1097400 | 930000 | 1097400 | 0 | 930000 | 1097400 | ZMAT | 2025-10-09 | 2025-11-08
RE/0066-PRJ-T2-CIV-RS-SU | Reinforcement Supply | 2010 | GR01 | 2010 | SMARTWORLD THE EDITION | Jindal Steel Limited | 9110001307 | 200 |  |  | 2025-10-09 | Steel Re-bar TMT 25 mm Dia. FE-550D | TO | 16 | 46500 | 744000 | 877920 | 744000 | 877920 | 0 | 744000 | 877920 | ZMAT | 2025-10-09 | 2025-11-08
RE/0066-PRJ-T2-CIV-RS-SU | Reinforcement Supply | 2010 | GR01 | 2010 | SMARTWORLD THE EDITION | Jindal Steel Limited | 9110001307 | 260 |  |  | 2025-10-09 | Steel Re-bar TMT 32 mm Dia. FE-550D | TO | 16 | 46500 | 744000 | 877920 | 744000 | 877920 | 0 | 744000 | 877920 | ZMAT | 2025-10-09 | 2025-11-08
RE/0066-PRJ-T2-CIV-RS-SU | Reinforcement Supply | 2010 | GR01 | 2010 | SMARTWORLD THE EDITION | Jindal Steel Limited | 9110001361 | 20 |  |  | 2025-11-07 | Steel Re-bar TMT 12 mm Dia. FE-550D | TO | 34 | 46100 | 1567400 | 1849532 | 1567400 | 1849532 | 0 | 1567400 | 1849532 | ZMAT | 2025-11-07 | 2025-12-07
RE/0066-PRJ-T2-CIV-RS-SU | Reinforcement Supply | 2010 | GR01 | 2010 | SMARTWORLD THE EDITION | Jindal Steel Limited | 9110001361 | 80 |  |  | 2025-11-07 | Steel Re-bar TMT 16 mm Dia. FE-550D | TO | 25 | 46100 | 1152500 | 1359950 | 1152500 | 1359950 | 0 | 1152500 | 1359950 | ZMAT | 2025-11-07 | 2025-12-07
RE/0066-PRJ-T2-CIV-RS-SU | Reinforcement Supply | 2010 | GR01 | 2010 | SMARTWORLD THE EDITION | Jindal Steel Limited | 9110001361 | 140 |  |  | 2025-11-07 | Steel Re-bar TMT 20 mm Dia. FE-550D | TO | 8 | 46100 | 368800 | 435184 | 368800 | 435184 | 0 | 368800 | 435184 | ZMAT | 2025-11-07 | 2025-12-07
RE/0066-PRJ-T2-CIV-RS-SU | Reinforcement Supply | 2010 | GR01 | 2010 | SMARTWORLD THE EDITION | Jindal Steel Limited | 9110001361 | 200 |  |  | 2025-11-07 | Steel Re-bar TMT 25 mm Dia. FE-550D | TO | 30 | 46100 | 1383000 | 1631940 | 1383000 | 1631940 | 0 | 1383000 | 1631940 | ZMAT | 2025-11-07 | 2025-12-07
RE/0066-PRJ-T2-CIV-RS-SU | Reinforcement Supply | 2010 | GR01 | 2010 | SMARTWORLD THE EDITION | Jindal Steel Limited | 9110001361 | 260 |  |  | 2025-11-07 | Steel Re-bar TMT 32 mm Dia. FE-550D | TO | 8 | 46100 | 368800 | 435184 | 368800 | 435184 | 0 | 368800 | 435184 | ZMAT | 2025-11-07 | 2025-12-07
RE/0066-PRJ-T2-CIV-RS-SU | Reinforcement Supply | 2010 | GR01 | 2010 | SMARTWORLD THE EDITION | Ram Niwas & SonsDeepak gupta | 9110001362 | 20 |  |  | 2025-11-07 | Steel Re-bar TMT 08 mm Dia. FE-550D | TO | 2.5 | 46900 | 117250 | 138355 | 117250 | 138355 | 0 | 117250 | 138355 | ZMAT | 2025-11-07 | 2025-12-07
RE/0066-PRJ-T2-CIV-RS-SU | Reinforcement Supply | 2010 | GR01 | 2010 | SMARTWORLD THE EDITION | Ram Niwas & SonsDeepak gupta | 9110001362 | 70 |  |  | 2025-11-07 | Steel Re-bar TMT 10 mm Dia. FE-550D | TO | 38.5 | 45900 | 1767150 | 2085237 | 1767150 | 2085237 | 0 | 1767150 | 2085237 | ZMAT | 2025-11-07 | 2025-12-07
RE/0066-PRJ-T2-CIV-RS-SU | Reinforcement Supply | 2010 | GR01 | 2010 | SMARTWORLD THE EDITION | Ram Niwas & SonsDeepak gupta | 9110001421 | 20 |  |  | 2025-12-10 | Steel Re-bar TMT 10 mm Dia. FE-550D | TO | 35 | 46500 | 1627500 | 1920450 | 1623780 | 1916060.4 | 3720 | 1623780 | 1916060.4 | ZMAT | 2025-12-10 | 2026-01-10
RE/0066-PRJ-T2-CIV-RS-SU | Reinforcement Supply | 2010 | GR01 | 2010 | SMARTWORLD THE EDITION | Jindal Steel Limited | 9110001422 | 20 |  |  | 2025-12-10 | Steel Re-bar TMT 12 mm Dia. FE-550D | TO | 20 | 46400 | 928000 | 1095040 | 928000 | 1095040 | 0 | 928000 | 1095040 | ZMAT | 2025-12-10 | 2026-01-10
RE/0066-PRJ-T2-CIV-RS-SU | Reinforcement Supply | 2010 | GR01 | 2010 | SMARTWORLD THE EDITION | Jindal Steel Limited | 9110001422 | 80 |  |  | 2025-12-10 | Steel Re-bar TMT 16 mm Dia. FE-550D | TO | 18 | 46400 | 835200 | 985536 | 835200 | 985536 | 0 | 835200 | 985536 | ZMAT | 2025-12-10 | 2026-01-10
RE/0066-PRJ-T2-CIV-RS-SU | Reinforcement Supply | 2010 | GR01 | 2010 | SMARTWORLD THE EDITION | Jindal Steel Limited | 9110001422 | 140 |  |  | 2025-12-10 | Steel Re-bar TMT 20 mm Dia. FE-550D | TO | 13 | 46400 | 603200 | 711776 | 603200 | 711776 | 0 | 603200 | 711776 | ZMAT | 2025-12-10 | 2026-01-10
RE/0066-PRJ-T2-CIV-RS-SU | Reinforcement Supply | 2010 | GR01 | 2010 | SMARTWORLD THE EDITION | Jindal Steel Limited | 9110001422 | 200 |  |  | 2025-12-10 | Steel Re-bar TMT 25 mm Dia. FE-550D | TO | 15 | 46400 | 696000 | 821280 | 696000 | 821280 | 0 | 696000 | 821280 | ZMAT | 2025-12-10 | 2026-01-10
RE/0066-PRJ-T2-CIV-RS-SU | Reinforcement Supply | 2010 | GR01 | 2010 | SMARTWORLD THE EDITION | Ram Niwas & SonsDeepak gupta | 9110001471 | 80 |  |  | 2026-01-12 | Steel Re-bar TMT 10 mm Dia. FE-550D | TO | 8 | 51000 | 408000 | 481440 | 374850 | 442323 | 33150 | 374850 | 442323 | ZMAT | 2026-01-12 | 2026-02-12
RE/0066-PRJ-T2-CIV-RS-SU | Reinforcement Supply | 2010 | GR01 | 2010 | SMARTWORLD THE EDITION | ESL STEEL LIMITED | 9110001481 | 20 |  |  | 2026-01-12 | Steel Re-bar TMT 12 mm Dia. FE-550D | TO | 42 | 51800 | 2175600 | 2567208 | 2160060 | 2548870.8 | 15540 | 2160060 | 2548870.8 | ZMAT | 2026-01-12 | 2026-02-12
RE/0066-PRJ-T2-CIV-RS-SU | Reinforcement Supply | 2010 | GR01 | 2010 | SMARTWORLD THE EDITION | ESL STEEL LIMITED | 9110001481 | 80 |  |  | 2026-01-12 | Steel Re-bar TMT 16 mm Dia. FE-550D | TO | 2 | 51800 | 103600 | 122248 | 103600 | 122248 | 0 | 103600 | 122248 | ZMAT | 2026-01-12 | 2026-02-12
RE/0066-PRJ-T2-CIV-RS-SU | Reinforcement Supply | 2010 | GR01 | 2010 | SMARTWORLD THE EDITION | ESL STEEL LIMITED | 9110001481 | 140 |  |  | 2026-01-12 | Steel Re-bar TMT 20 mm Dia. FE-550D | TO | 25 | 51800 | 1295000 | 1528100 | 1295000 | 1528100 | 0 | 1295000 | 1528100 | ZMAT | 2026-01-12 | 2026-02-12
RE/0066-PRJ-T2-CIV-RS-SU | Reinforcement Supply | 2010 | GR01 | 2010 | SMARTWORLD THE EDITION | ESL STEEL LIMITED | 9110001481 | 200 |  |  | 2026-01-12 | Steel Re-bar TMT 25 mm Dia. FE-550D | TO | 8 | 51800 | 414400 | 488992 | 414400 | 488992 | 0 | 414400 | 488992 | ZMAT | 2026-01-12 | 2026-02-12
RE/0066-PRJ-T2-CIV-RS-SU | Reinforcement Supply | 2010 | GR01 | 2010 | SMARTWORLD THE EDITION | Ram Niwas & SonsDeepak gupta | 9110001541 | 80 |  |  | 2026-02-07 | Steel Re-bar TMT 10 mm Dia. FE-550D | TO | 11 | 54300 | 597300 | 704814 | 597300 | 704814 | 0 | 597300 | 704814 | ZMAT | 2026-02-07 | 2026-03-31
RE/0066-PRJ-T2-CIV-RS-SU | Reinforcement Supply | 2010 | GR01 | 2010 | SMARTWORLD THE EDITION | Petropol India LimitedSANJAY GUPTA | 9110001546 | 80 |  |  | 2026-02-07 | Steel Re-bar TMT 10 mm Dia. FE-550D | TO | 15 | 54300 | 814500 | 961110 | 814500 | 961110 | 0 | 814500 | 961110 | ZMAT | 2026-02-07 | 2026-03-31
RE/0066-PRJ-T2-CIV-RS-SU | Reinforcement Supply | 2010 | GR01 | 2010 | SMARTWORLD THE EDITION | Jindal Steel Limited | 9110001551 | 20 |  |  | 2026-02-07 | Steel Re-bar TMT 12 mm Dia. FE-550D | TO | 27 | 58500 | 1579500 | 1863810 | 1577745 | 1861739.1 | 1755 | 1577745 | 1861739.1 | ZMAT | 2026-02-07 | 2026-03-07
RE/0066-PRJ-T2-CIV-RS-SU | Reinforcement Supply | 2010 | GR01 | 2010 | SMARTWORLD THE EDITION | Jindal Steel Limited | 9110001551 | 80 |  |  | 2026-02-07 | Steel Re-bar TMT 16 mm Dia. FE-550D | TO | 30 | 58500 | 1755000 | 2070900 | 1737450 | 2050191 | 17550 | 1737450 | 2050191 | ZMAT | 2026-02-07 | 2026-03-07
RE/0066-PRJ-T2-CIV-RS-SU | Reinforcement Supply | 2010 | GR01 | 2010 | SMARTWORLD THE EDITION | Jindal Steel Limited | 9110001551 | 140 |  |  | 2026-02-07 | Steel Re-bar TMT 20 mm Dia. FE-550D | TO | 13 | 58500 | 760500 | 897390 | 744120 | 878061.6 | 16380 | 744120 | 878061.6 | ZMAT | 2026-02-07 | 2026-03-07
RE/0066-PRJ-T2-CIV-RS-SU | Reinforcement Supply | 2010 | GR01 | 2010 | SMARTWORLD THE EDITION | Jindal Steel Limited | 9110001551 | 200 |  |  | 2026-02-07 | Steel Re-bar TMT 25 mm Dia. FE-550D | TO | 20 | 58500 | 1170000 | 1380600 | 1169415 | 1379909.7 | 585 | 1169415 | 1379909.7 | ZMAT | 2026-02-07 | 2026-03-07
RE/0066-PRJ-T2-CIV-RS-SU | Reinforcement Supply | 2010 | GR01 | 2010 | SMARTWORLD THE EDITION | Jindal Steel Limited | 9110001557 | 20 |  |  | 2026-02-10 | Steel Re-bar TMT 12 mm Dia. FE-550D | TO | 26 | 58500 | 1521000 | 1794780 | 1515150 | 1787877 | 5850 | 1515150 | 1787877 | ZMAT | 2026-02-10 | 2026-03-10
RE/0066-PRJ-T2-CIV-RS-SU | Reinforcement Supply | 2010 | GR01 | 2010 | SMARTWORLD THE EDITION | Jindal Steel Limited | 9110001557 | 80 |  |  | 2026-02-10 | Steel Re-bar TMT 25 mm Dia. FE-550D | TO | 49 | 58500 | 2866500 | 3382470 | 2865915 | 3381779.7 | 585 | 2865915 | 3381779.7 | ZMAT | 2026-02-10 | 2026-03-10
RE/0066-PRJ-T2-CIV-RS-SU | Reinforcement Supply | 2010 | GR01 | 2010 | SMARTWORLD THE EDITION | Jindal Steel Limited | 9110001557 | 140 |  |  | 2026-02-10 | Steel Re-bar TMT 32 mm Dia. FE-550D | TO | 15 | 58500 | 877500 | 1035450 | 877500 | 1035450 | 0 | 877500 | 1035450 | ZMAT | 2026-02-10 | 2026-03-10
RE/0066-PRJ-T2-CIV-RS-SU | Reinforcement Supply | 2010 | GR01 | 2010 | SMARTWORLD THE EDITION | Ram Niwas & SonsDeepak gupta | 9110001607 | 20 |  |  | 2026-03-11 | Steel Re-bar TMT 10 mm Dia. FE-550D | TO | 37 | 55800 | 2064600 | 2436228 | 2064600 | 2436228 | 0 | 2064600 | 2436228 | ZMAT | 2026-03-11 | 2026-04-11
RE/0066-PRJ-T2-CIV-RS-SU | Reinforcement Supply | 2010 | GR01 | 2010 | SMARTWORLD THE EDITION | ESL STEEL LIMITED | 9110001613 | 20 |  |  | 2026-03-11 | Steel Re-bar TMT 12 mm Dia. FE-550D | TO | 37 | 58250 | 2155250 | 2543195 | 2155250.01 | 2543195.01 | 0.01 | 2155250 | 2543195.01 | ZMAT | 2026-03-11 | 2026-04-11
RE/0066-PRJ-T2-CIV-RS-SU | Reinforcement Supply | 2010 | GR01 | 2010 | SMARTWORLD THE EDITION | ESL STEEL LIMITED | 9110001613 | 80 |  |  | 2026-03-11 | Steel Re-bar TMT 16 mm Dia. FE-550D | TO | 30 | 58250 | 1747500 | 2062050 | 1747500 | 2062050 | 0 | 1747500 | 2062050 | ZMAT | 2026-03-11 | 2026-04-11
RE/0066-PRJ-T2-CIV-RS-SU | Reinforcement Supply | 2010 | GR01 | 2010 | SMARTWORLD THE EDITION | ESL STEEL LIMITED | 9110001613 | 140 |  |  | 2026-03-11 | Steel Re-bar TMT 20 mm Dia. FE-550D | TO | 27 | 58250 | 1572750 | 1855845 | 1572750 | 1855845 | 0 | 1572750 | 1855845 | ZMAT | 2026-03-11 | 2026-04-11
RE/0066-PRJ-T2-CIV-RS-SU | Reinforcement Supply | 2010 | GR01 | 2010 | SMARTWORLD THE EDITION | ESL STEEL LIMITED | 9110001613 | 200 |  |  | 2026-03-11 | Steel Re-bar TMT 25 mm Dia. FE-550D | TO | 25 | 58250 | 1456250 | 1718375 | 1456250 | 1718375 | 0 | 1456250 | 1718375 | ZMAT | 2026-03-11 | 2026-04-11
RE/0066-PRJ-T2-CIV-RS-SU | Reinforcement Supply | 2010 | GR01 | 2010 | SMARTWORLD THE EDITION | Ram Niwas & SonsDeepak gupta | 9110001691 | 80 |  |  | 2026-04-10 | Steel Re-bar TMT 10 mm Dia. FE-550D | TO | 8 | 59800 | 478400 | 564512 | 478400 | 564512 | 0 | 478400 | 564512 | ZMAT | 2026-04-10 | 2026-05-10
RE/0066-PRJ-T2-CIV-RS-SU | Reinforcement Supply | 2010 | GR01 | 2010 | SMARTWORLD THE EDITION | ESL STEEL LIMITED | 9110001698 | 20 |  |  | 2026-04-10 | Steel Re-bar TMT 12 mm Dia. FE-550D | TO | 43 | 60500 | 2601500 | 3069770 | 2601500 | 3069770 | 0 | 2601500 | 3069770 | ZMAT | 2026-04-10 | 2026-05-10
RE/0066-PRJ-T2-CIV-RS-SU | Reinforcement Supply | 2010 | GR01 | 2010 | SMARTWORLD THE EDITION | ESL STEEL LIMITED | 9110001698 | 80 |  |  | 2026-04-10 | Steel Re-bar TMT 16 mm Dia. FE-550D | TO | 8.5 | 60500 | 514250 | 606815 | 526350 | 621093 | 12100 | 526350 | 621093 | ZMAT | 2026-04-10 | 2026-05-10
RE/0066-PRJ-T2-CIV-RS-SU | Reinforcement Supply | 2010 | GR01 | 2010 | SMARTWORLD THE EDITION | ESL STEEL LIMITED | 9110001698 | 140 |  |  | 2026-04-10 | Steel Re-bar TMT 20 mm Dia. FE-550D | TO | 14 | 60500 | 847000 | 999460 | 847000 | 999460 | 0 | 847000 | 999460 | ZMAT | 2026-04-10 | 2026-05-10
RE/0066-PRJ-T2-CIV-RS-SU | Reinforcement Supply | 2010 | GR01 | 2010 | SMARTWORLD THE EDITION | ESL STEEL LIMITED | 9110001698 | 200 |  |  | 2026-04-10 | Steel Re-bar TMT 25 mm Dia. FE-550D | TO | 25 | 60500 | 1512500 | 1784750 | 1512500 | 1784750 | 0 | 1512500 | 1784750 | ZMAT | 2026-04-10 | 2026-05-10
RE/0066-PRJ-T2-CIV-RS-SU | Reinforcement Supply | 2010 | GR01 | 2010 | SMARTWORLD THE EDITION | ESL STEEL LIMITED | 9110001698 | 260 |  |  | 2026-04-10 | Steel Re-bar TMT 32 mm Dia. FE-550D | TO | 7 | 60500 | 423500 | 499730 | 423500 | 499730 | 0 | 423500 | 499730 | ZMAT | 2026-04-10 | 2026-05-10
RE/0066-PRJ-T2-CIV-RS-SU | Reinforcement Supply | 2010 | GR01 | 2010 | SMARTWORLD THE EDITION | Petropol India LimitedSANJAY GUPTA | 9110001791 | 80 |  |  | 2026-05-11 | Steel Re-bar TMT 10 mm Dia. FE-550D | TO | 4 | 54700 | 218800 | 258184 | 218800 | 258184 | 0 | 218800 | 258184 | ZMAT | 2026-05-11 | 2026-06-11
RE/0066-PRJ-T2-CIV-RS-SU | Reinforcement Supply | 2010 | GR01 | 2010 | SMARTWORLD THE EDITION | Jindal Steel Limited | 9110001796 | 20 |  |  | 2026-05-11 | Steel Re-bar TMT 12 mm Dia. FE-550D | TO | 33 | 57200 | 1887600 | 2227368 | 1887600 | 2227368 | 0 | 0 | 0 | ZMAT | 2026-05-11 | 2026-06-11
RE/0066-PRJ-T2-CIV-RS-SU | Reinforcement Supply | 2010 | GR01 | 2010 | SMARTWORLD THE EDITION | Jindal Steel Limited | 9110001796 | 80 |  |  | 2026-05-11 | Steel Re-bar TMT 16 mm Dia. FE-550D | TO | 3 | 57200 | 171600 | 202488 | 85800 | 101244 | 85800 | 0 | 0 | ZMAT | 2026-05-11 | 2026-06-11
RE/0066-PRJ-T2-CIV-RS-SU | Reinforcement Supply | 2010 | GR01 | 2010 | SMARTWORLD THE EDITION | Jindal Steel Limited | 9110001796 | 140 |  |  | 2026-05-11 | Steel Re-bar TMT 20 mm Dia. FE-550D | TO | 29 | 57200 | 1658800 | 1957384 | 1658800 | 1957384 | 0 | 0 | 0 | ZMAT | 2026-05-11 | 2026-06-11
RE/0066-PRJ-T2-CIV-RS-SU | Reinforcement Supply | 2010 | GR01 | 2010 | SMARTWORLD THE EDITION | Jindal Steel Limited | 9110001796 | 200 |  |  | 2026-05-11 | Steel Re-bar TMT 25 mm Dia. FE-550D | TO | 13 | 57200 | 743600 | 877448 | 743600 | 877448 | 0 | 0 | 0 | ZMAT | 2026-05-11 | 2026-06-11
RE/0066-PRJ-T2-CIV-RS-SU | Reinforcement Supply | 2010 | GR01 | 2010 | SMARTWORLD THE EDITION | Jindal Steel Limited | 9110001796 | 260 |  |  | 2026-05-11 | Steel Re-bar TMT 32 mm Dia. FE-550D | TO | 4 | 57200 | 228800 | 269984 | 228800 | 269984 | 0 | 0 | 0 | ZMAT | 2026-05-11 | 2026-06-11
RE/0066-PRJ-T2-CIV-SW-AS | Aluminum Shuttering | 2010 | GR01 | 2010 | SMARTWORLD THE EDITION | Ahluwalia Contracts India Limited | 9140000321 | 50 |  |  | 2024-07-20 | CENTERING & SHUTTERING Part A | AU | 1 | 0 | 160754359.04 | 189690143.67 | 37294279.6 | 44007249.93 | 123460079.44 | 29832755.73 | 35202651.76 | ZSER | 2024-07-15 | 2027-01-14
RE/0066-PRJ-T2-CIV-SW-CS | Conventional Shuttering | 2010 | GR01 | 2010 | SMARTWORLD THE EDITION | Ahluwalia Contracts India Limited | 9140000321 | 50 |  |  | 2024-07-20 | CENTERING & SHUTTERING Part A | AU | 1 | 0 | 17864325.52 | 21079904.11 | 15195818.71 | 17931066.08 | 2668506.81 | 15195818.76 | 17931066.14 | ZSER | 2024-07-15 | 2027-01-14
RE/0066-PRJ-T2-CIV-SW-SO | Shuttering Other | 2010 | GR01 | 2010 |  |  |  | 0 | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
RE/0066-PRJ-T2-CIV-WP | Waterproofing Works | 2010 | GR01 | 2010 | SMARTWORLD THE EDITION | Ahluwalia Contracts India Limited | 9140000321 | 110 |  |  | 2024-07-20 | FLOORING | AU | 1 | 0 | 1433 | 1690.94 | 0 | 0 | 1433 | 0 | 0 | ZSER | 2024-07-15 | 2027-01-14
RE/0066-PRJ-T2-CIV-WP | Waterproofing Works | 2010 | GR01 | 2010 | SMARTWORLD THE EDITION | Ahluwalia Contracts India Limited | 9140000321 | 120 |  |  | 2024-07-20 | WATER-PROOFING WORKS | AU | 1 | 0 | 18463180.04 | 21786552.45 | 440146.86 | 519373.3 | 18023033.18 | 440146.86 | 519373.3 | ZSER | 2024-07-15 | 2027-01-14
RE/0066-PRJ-T2-FAC-EF | Elevation Feature | 2010 | GR01 | 2010 | SMARTWORLD THE EDITION | Ahluwalia Contracts India Limited | 9140000321 | 100 |  |  | 2024-07-20 | STRUCTURAL STEEL WORKS | AU | 1 | 0 | 0.01 | 0.01 | 0 | 0 | 0.01 | 0 | 0 | ZSER | 2024-07-15 | 2027-01-14
RE/0066-PRJ-T2-FAC-EP | External Paint | 2010 | GR01 | 2010 | SMARTWORLD THE EDITION | Ahluwalia Contracts India Limited | 9140000321 | 160 |  |  | 2024-07-20 | Amed-Monthly rental payment to M/S ACIL | AU | 1 | 0 | 4753600 | 5609248 | 0 | 0 | 4753600 | 0 | 0 | ZSER | 2024-07-15 | 2027-01-14
RE/0066-PRJ-T2-FAC-GL | Glazing Works | 2010 | GR01 | 2010 |  |  |  | 0 | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
RE/0066-PRJ-T2-FAC-RA | Railing Works | 2010 | GR01 | 2010 |  |  |  | 0 | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
RE/0066-PRJ-T2-FIS-CF | Ceiling Finish Works | 2010 | GR01 | 2010 | SMARTWORLD THE EDITION | SNA ASSOCIATES INDIA PRIVATE LIMITPraful Asatkar | 9140000604 | 10 |  |  | 2026-03-10 | Finishing Work -T2 | AU | 1 | 0 | 76049264.22 | 89738131.78 | 0 | 0 | 76049264.22 | 0 | 0 | ZSER | 2026-04-03 | 2028-04-03
RE/0066-PRJ-T2-FIS-CF | Ceiling Finish Works | 2010 | GR01 | 2010 | SMARTWORLD THE EDITION | SNA ASSOCIATES INDIA PRIVATE LIMITPraful Asatkar | 9140000604 | 20 |  |  | 2026-03-10 | Finishing Work - Lift Lobby-T2 | AU | 1 | 46230888.06 | 1167800 | 1378004 | 0 | 0 | 1167800 | 0 | 0 | ZSER | 2026-04-03 | 2028-04-03
RE/0066-PRJ-T2-FIS-DW | Door Works | 2010 | GR01 | 2010 |  |  |  | 0 | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
RE/0066-PRJ-T2-FIS-FF | Floor Finish Works | 2010 | GR01 | 2010 | SMARTWORLD THE EDITION | Ahluwalia Contracts India Limited | 9140000321 | 110 |  |  | 2024-07-20 | FLOORING | AU | 1 | 0 | 9803437.89 | 11568056.71 | 0 | 0 | 9803437.89 | 0 | 0 | ZSER | 2024-07-15 | 2027-01-14
RE/0066-PRJ-T2-FIS-FF | Floor Finish Works | 2010 | GR01 | 2010 | SMARTWORLD THE EDITION | SNA ASSOCIATES INDIA PRIVATE LIMITPraful Asatkar | 9140000604 | 10 |  |  | 2026-03-10 | Finishing Work -T2 | AU | 1 | 0 | 115430682 | 136208204.76 | 0 | 0 | 115430682 | 0 | 0 | ZSER | 2026-04-03 | 2028-04-03
RE/0066-PRJ-T2-FIS-FF | Floor Finish Works | 2010 | GR01 | 2010 | SMARTWORLD THE EDITION | SNA ASSOCIATES INDIA PRIVATE LIMITPraful Asatkar | 9140000604 | 20 |  |  | 2026-03-10 | Finishing Work - Lift Lobby-T2 | AU | 1 | 0 | 26590118.4 | 31376339.71 | 0 | 0 | 26590118.4 | 0 | 0 | ZSER | 2026-04-03 | 2028-04-03
RE/0066-PRJ-T2-FIS-LF | Lobby Furniture | 2010 | GR01 | 2010 |  |  |  | 0 | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
RE/0066-PRJ-T2-FIS-MI | Misc Finish Works | 2010 | GR01 | 2010 | SMARTWORLD THE EDITION | SNA ASSOCIATES INDIA PRIVATE LIMITPraful Asatkar | 9140000604 | 10 |  |  | 2026-03-10 | Finishing Work -T2 | AU | 1 | 0 | 17369812 | 20496378.16 | 0 | 0 | 17369812 | 0 | 0 | ZSER | 2026-04-03 | 2028-04-03
RE/0066-PRJ-T2-FIS-MK | Modular Kitchen Works | 2010 | GR01 | 2010 |  |  |  | 0 | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
RE/0066-PRJ-T2-FIS-MW | MS works | 2010 | GR01 | 2010 | SMARTWORLD THE EDITION | SNA ASSOCIATES INDIA PRIVATE LIMITPraful Asatkar | 9140000604 | 10 |  |  | 2026-03-10 | Finishing Work -T2 | AU | 1 | 0 | 3068000 | 3620240 | 0 | 0 | 3068000 | 0 | 0 | ZSER | 2026-04-03 | 2028-04-03
RE/0066-PRJ-T2-FIS-WF | Wall Finish Works | 2010 | GR01 | 2010 | SMARTWORLD THE EDITION | SNA ASSOCIATES INDIA PRIVATE LIMITPraful Asatkar | 9140000604 | 10 |  |  | 2026-03-10 | Finishing Work -T2 | AU | 1 | 0 | 85943260 | 101413046.8 | 0 | 0 | 85943260 | 0 | 0 | ZSER | 2026-04-03 | 2028-04-03
RE/0066-PRJ-T2-FIS-WF | Wall Finish Works | 2010 | GR01 | 2010 | SMARTWORLD THE EDITION | SNA ASSOCIATES INDIA PRIVATE LIMITPraful Asatkar | 9140000604 | 20 |  |  | 2026-03-10 | Finishing Work - Lift Lobby-T2 | AU | 1 | 0 | 18472969.66 | 21798104.2 | 0 | 0 | 18472969.66 | 0 | 0 | ZSER | 2026-04-03 | 2028-04-03
RE/0066-PRJ-T2-FIS-WO | Wood Work | 2010 | GR01 | 2010 |  |  |  | 0 | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
RE/0066-PRJ-T2-MEP-EW-HE | High Side Electrical Works | 2010 | GR01 | 2010 | SMARTWORLD THE EDITION | Dehn India Pvt Ltd | 9140000379 | 10 |  |  | 2024-10-24 | Lightning Protection System for Basement | AU | 1 | 0 | 922389 | 1088419.02 | 144535.06 | 170551.37 | 777853.94 | 144535.08 | 170551.4 | ZSER | 2024-10-24 | 2027-08-23
RE/0066-PRJ-T2-MEP-EW-HE | High Side Electrical Works | 2010 | GR01 | 2010 | SMARTWORLD THE EDITION | SATKARTAR ELECTRICALS AND ELECTRONIPRIVATE LIMITED | 9140000677 | 20 |  |  | 2026-06-02 | Electrical Works Tower T2 | AU | 1 | 25044843.01 | 21206117.01 | 25023218.07 | 0 | 0 | 21206117.01 | 0 | 0 | ZSER | 2026-06-01 | 2028-02-01
RE/0066-PRJ-T2-MEP-EW-HE | High Side Electrical Works | 2010 | GR01 | 2010 | SMARTWORLD THE EDITION | TRIPLE A ENGINEERING PRIVATE LIMIT | 9140000688 | 20 |  |  | 2026-06-06 | Electrical Works Tower T2 | AU | 1 | 56963214.84 | 19666293.5 | 19666293.5 | 0 | 0 | 19666293.5 | 0 | 0 | ZSER | 2026-06-01 | 2028-02-01
RE/0066-PRJ-T2-MEP-EW-LE | Low Side Electrical Works | 2010 | GR01 | 2010 | SMARTWORLD THE EDITION | Ahluwalia Contracts India Limited | 9140000321 | 140 |  |  | 2024-07-20 | CONDUITING | AU | 1 | 0 | 20121741.87 | 23743655.41 | 545734.65 | 643966.89 | 19576007.22 | 395004.21 | 466104.97 | ZSER | 2024-07-15 | 2027-01-14
RE/0066-PRJ-T2-MEP-EW-LE | Low Side Electrical Works | 2010 | GR01 | 2010 | SMARTWORLD THE EDITION | SATKARTAR ELECTRICALS AND ELECTRONIPRIVATE LIMITED | 9140000677 | 20 |  |  | 2026-06-02 | Electrical Works Tower T2 | AU | 1 | 0 | 3838726 | 4529696.68 | 0 | 0 | 3838726 | 0 | 0 | ZSER | 2026-06-01 | 2028-02-01
RE/0066-PRJ-T2-MEP-EW-LE | Low Side Electrical Works | 2010 | GR01 | 2010 | SMARTWORLD THE EDITION | TRIPLE A ENGINEERING PRIVATE LIMIT | 9140000688 | 20 |  |  | 2026-06-06 | Electrical Works Tower T2 | AU | 1 | 0 | 37296921.34 | 37296921.34 | 0 | 0 | 37296921.34 | 0 | 0 | ZSER | 2026-06-01 | 2028-02-01
RE/0066-PRJ-T2-MEP-EW-LS | Light Fixtures Supply | 2010 | GR01 | 2010 |  |  |  | 0 | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
RE/0066-PRJ-T2-MEP-FF | Fire Fighting Work | 2010 | GR01 | 2010 | SMARTWORLD THE EDITION | Jagrati Civil Constructions Pvt Ltd | 9140000633 | 240 |  |  | 2026-04-15 | FF-FIRE HYDRANT & EQUIPMENT SUPPLY- T2 | AU | 1 | 3205680 | 3205680 | 3782702.4 | 0 | 0 | 3205680 | 0 | 0 | ZSER | 2026-04-08 | 2028-01-31
RE/0066-PRJ-T2-MEP-FF | Fire Fighting Work | 2010 | GR01 | 2010 | SMARTWORLD THE EDITION | Jagrati Civil Constructions Pvt Ltd | 9140000633 | 290 |  |  | 2026-04-15 | FF-AUTOMATIC SPRINKLER & WATER Supply-T2 | AU | 1 | 17451680.56 | 17451680.56 | 20592983.06 | 0 | 0 | 17451680.56 | 0 | 0 | ZSER | 2026-04-08 | 2028-01-31
RE/0066-PRJ-T2-MEP-FF | Fire Fighting Work | 2010 | GR01 | 2010 | SMARTWORLD THE EDITION | Jagrati Civil Constructions Pvt Ltd | 9140000633 | 340 |  |  | 2026-04-15 | FF-PORTABLE FIRE EXTINGUISHERS Supply-T2 | AU | 1 | 357000 | 357000 | 421260 | 0 | 0 | 357000 | 0 | 0 | ZSER | 2026-04-08 | 2028-01-31
RE/0066-PRJ-T2-MEP-HV-HS | High Side | 2010 | GR01 | 2010 |  |  |  | 0 | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
RE/0066-PRJ-T2-MEP-HV-LS | Low Side | 2010 | GR01 | 2010 |  |  |  | 0 | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
RE/0066-PRJ-T2-MEP-LT | Lifts | 2010 | GR01 | 2010 |  |  |  | 0 | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
RE/0066-PRJ-T2-MEP-PB-FS | Fixtures Supply | 2010 | GR01 | 2010 |  |  |  | 0 | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
RE/0066-PRJ-T2-MEP-PB-IP | Internal Plumbing | 2010 | GR01 | 2010 | SMARTWORLD THE EDITION | Jagrati Civil Constructions Pvt Ltd | 9140000633 | 30 |  |  | 2026-04-15 | SANITARY FIXTURES & FITTINGS INST. T-2 | AU | 1 | 4447825 | 4447825 | 5248433.5 | 0 | 0 | 4447825 | 0 | 0 | ZSER | 2026-04-08 | 2028-01-31
RE/0066-PRJ-T2-MEP-PB-IP | Internal Plumbing | 2010 | GR01 | 2010 | SMARTWORLD THE EDITION | Jagrati Civil Constructions Pvt Ltd | 9140000633 | 80 |  |  | 2026-04-15 | INTERNAL DRAINAGE SUPPLY(SOIL, WASTE T-2 | AU | 1 | 14003403.63 | 14003403.63 | 16524016.28 | 0 | 0 | 14003403.63 | 0 | 0 | ZSER | 2026-04-08 | 2028-01-31
RE/0066-PRJ-T2-MEP-PB-IP | Internal Plumbing | 2010 | GR01 | 2010 | SMARTWORLD THE EDITION | Jagrati Civil Constructions Pvt Ltd | 9140000633 | 130 |  |  | 2026-04-15 | DOMESTIC AND FLUSHING WATER SUPPLY T-2 | AU | 1 | 16024565.99 | 16024565.99 | 18908987.87 | 0 | 0 | 16024565.99 | 0 | 0 | ZSER | 2026-04-08 | 2028-01-31
RE/0066-PRJ-T2-MEP-PB-IP | Internal Plumbing | 2010 | GR01 | 2010 | SMARTWORLD THE EDITION | Jagrati Civil Constructions Pvt Ltd | 9140000633 | 180 |  |  | 2026-04-15 | MISCELLANEOUS ITEMS FOR TERRACE WATER-T2 | AU | 1 | 376700 | 376700 | 444506 | 0 | 0 | 376700 | 0 | 0 | ZSER | 2026-04-08 | 2028-01-31
RE/0066-PRJ-T2-MEP-PB-JC | JACUZZI | 2010 | GR01 | 2010 |  |  |  | 0 | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
RE/0066-PRJ-T2-MEP-PN | PNG Gas Pipe Line | 2010 | GR01 | 2010 |  |  |  | 0 | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
RE/0066-PRJ-T3-CIV-CC-LA | Concrete Labour | 2010 | GR01 | 2010 |  |  |  | 0 | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
RE/0066-PRJ-T3-CIV-CC-SL | Concrete Supply & Labour | 2010 | GR01 | 2010 | SMARTWORLD THE EDITION | Ahluwalia Contracts India Limited | 9140000321 | 20 |  |  | 2024-07-20 | REINFORCED CEMENT CONCRETE-I part A | AU | 1 | 0 | 107152066.68 | 126439438.68 | 57534150.09 | 67890297.11 | 49617916.59 | 57534150.14 | 67890297.16 | ZSER | 2024-07-15 | 2027-01-14
RE/0066-PRJ-T3-CIV-CC-SL | Concrete Supply & Labour | 2010 | GR01 | 2010 | SMARTWORLD THE EDITION | Ahluwalia Contracts India Limited | 9140000321 | 30 |  |  | 2024-07-20 | REINFORCED CEMENT CONCRETE-I Part B | AU | 1 | 0 | 83259983.83 | 98246780.92 | 33815626.96 | 39902439.81 | 49444356.87 | 27200180.79 | 32096213.33 | ZSER | 2024-07-15 | 2027-01-14
RE/0066-PRJ-T3-CIV-CC-SL | Concrete Supply & Labour | 2010 | GR01 | 2010 | SMARTWORLD THE EDITION | Ahluwalia Contracts India Limited | 9140000321 | 40 |  |  | 2024-07-20 | REINFORCED CEMENT CONCRETE-I Part C | AU | 1 | 0 | 110667972.97 | 130588208.1 | 30308630.33 | 35764183.79 | 80359342.64 | 25673510.41 | 30294742.28 | ZSER | 2024-07-15 | 2027-01-14
RE/0066-PRJ-T3-CIV-CC-SL | Concrete Supply & Labour | 2010 | GR01 | 2010 | SMARTWORLD THE EDITION | Ahluwalia Contracts India Limited | 9140000321 | 180 |  |  | 2024-07-20 | SUBSTITUTE ITEM | AU | 1 | 0 | 1266038.72 | 1493925.69 | 976715.25 | 1152524 | 289323.47 | 976715.25 | 1152524 | ZSER | 2024-07-15 | 2027-01-14
RE/0066-PRJ-T3-CIV-CC-SU | Concrete Supply | 2010 | GR01 | 2010 |  |  |  | 0 | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
RE/0066-PRJ-T3-CIV-EW | Earthwork | 2010 | GR01 | 2010 | SMARTWORLD THE EDITION | Ahluwalia Contracts India Limited | 9140000321 | 10 |  |  | 2024-07-20 | SITE DEVLOPMENT AND EARTH WORK | AU | 1 | 0 | 1471574 | 1736457.32 | 28542909.9 | 33680633.68 | 27071335.9 | 561076.85 | 662070.68 | ZSER | 2024-07-15 | 2027-01-14
RE/0066-PRJ-T3-CIV-MS | Misc Structure Works | 2010 | GR01 | 2010 | SMARTWORLD THE EDITION | Ahluwalia Contracts India Limited | 9140000321 | 100 |  |  | 2024-07-20 | STRUCTURAL STEEL WORKS | AU | 1 | 0 | 35979692.22 | 42456036.82 | 2232737.2 | 2634629.9 | 33746955.02 | 1650072.57 | 1947085.63 | ZSER | 2024-07-15 | 2027-01-14
RE/0066-PRJ-T3-CIV-MS | Misc Structure Works | 2010 | GR01 | 2010 | SMARTWORLD THE EDITION | Ahluwalia Contracts India Limited | 9140000321 | 130 |  |  | 2024-07-20 | INTERNAL & EXTERNAL PLASTERING | AU | 1 | 0 | 607320 | 716637.6 | 0 | 0 | 607320 | 0 | 0 | ZSER | 2024-07-15 | 2027-01-14
RE/0066-PRJ-T3-CIV-MS | Misc Structure Works | 2010 | GR01 | 2010 | SMARTWORLD THE EDITION | Ahluwalia Contracts India Limited | 9140000321 | 160 |  |  | 2024-07-20 | Amed-Monthly rental payment to M/S ACIL | AU | 1 | 0 | 1230377.3 | 1451845.21 | 93990.6 | 110908.91 | 1136386.7 | 0 | 0 | ZSER | 2024-07-15 | 2027-01-14
RE/0066-PRJ-T3-CIV-MW | Masonry Works | 2010 | GR01 | 2010 | SMARTWORLD THE EDITION | Ahluwalia Contracts India Limited | 9140000321 | 90 |  |  | 2024-07-20 | MASONARY WORKS | AU | 1 | 0 | 8702363.87 | 10268789.37 | 1106509.04 | 1305680.67 | 7595854.83 | 1106509.04 | 1305680.67 | ZSER | 2024-07-15 | 2027-01-14
RE/0066-PRJ-T3-CIV-PW-IP | Internal Plaster | 2010 | GR01 | 2010 | SMARTWORLD THE EDITION | Ahluwalia Contracts India Limited | 9140000321 | 130 |  |  | 2024-07-20 | INTERNAL & EXTERNAL PLASTERING | AU | 1 | 0 | 6654569 | 7852391.42 | 0 | 0 | 6654569 | 0 | 0 | ZSER | 2024-07-15 | 2027-01-14
RE/0066-PRJ-T3-CIV-PW-XP | External Plaster | 2010 | GR01 | 2010 | SMARTWORLD THE EDITION | Ahluwalia Contracts India Limited | 9140000321 | 130 |  |  | 2024-07-20 | INTERNAL & EXTERNAL PLASTERING | AU | 1 | 0 | 225900 | 266562 | 0 | 0 | 225900 | 0 | 0 | ZSER | 2024-07-15 | 2027-01-14
RE/0066-PRJ-T3-CIV-RS-LA | Reinforcement Labour | 2010 | GR01 | 2010 | SMARTWORLD THE EDITION | Ahluwalia Contracts India Limited | 9140000321 | 70 |  |  | 2024-07-20 | REINFORCEMENT STEEL Installation Part A | AU | 1 | 0 | 140633003 | 165946943.54 | 55368667.03 | 65335027.1 | 85264335.97 | 50558796.72 | 59659380.13 | ZSER | 2024-07-15 | 2027-01-14
RE/0066-PRJ-T3-CIV-RS-LA | Reinforcement Labour | 2010 | GR01 | 2010 | SMARTWORLD THE EDITION | Ahluwalia Contracts India Limited | 9140000321 | 80 |  |  | 2024-07-20 | REINFORCEMENT STEEL Installation Part B | AU | 1 | 0 | 12337669.45 | 14558449.95 | 3439605.72 | 4058734.75 | 8898063.73 | 3158012 | 3726454.16 | ZSER | 2024-07-15 | 2027-01-14
RE/0066-PRJ-T3-CIV-RS-SU | Reinforcement Supply | 2010 | GR01 | 2010 | SMARTWORLD THE EDITION | Northern Steel and General MillsPrivate Limited | 9110000774 | 80 |  |  | 2024-11-15 | Steel Re-bar TMT 20 mm Dia. FE-550D | TO | 9 | 54500 | 490500 | 578790 | 490500 | 578790 | 0 | 490500 | 578790 | ZMAT | 2025-01-20 | 2025-03-20
RE/0066-PRJ-T3-CIV-RS-SU | Reinforcement Supply | 2010 | GR01 | 2010 | SMARTWORLD THE EDITION | Northern Steel and General MillsPrivate Limited | 9110000774 | 150 |  |  | 2024-11-15 | Steel Re-bar TMT 25 mm Dia. FE-550D | TO | 39.5 | 54500 | 2152750 | 2540245 | 2152750 | 2540245 | 0 | 2152750 | 2540245 | ZMAT | 2025-01-20 | 2025-03-20
RE/0066-PRJ-T3-CIV-RS-SU | Reinforcement Supply | 2010 | GR01 | 2010 | SMARTWORLD THE EDITION | Jindal Steel Limited | 9110000777 | 30 |  |  | 2024-11-15 | Steel Re-bar TMT 20 mm Dia. FE-550D | TO | 11.5 | 54500 | 626750 | 739565 | 626750 | 739565 | 0 | 626750 | 739565 | ZMAT | 2025-01-20 | 2025-03-20
RE/0066-PRJ-T3-CIV-RS-SU | Reinforcement Supply | 2010 | GR01 | 2010 | SMARTWORLD THE EDITION | Jindal Steel Limited | 9110000777 | 100 |  |  | 2024-11-15 | Steel Re-bar TMT 25 mm Dia. FE-550D | TO | 29 | 54500 | 1580500 | 1864990 | 1580500 | 1864990 | 0 | 1580500 | 1864990 | ZMAT | 2025-01-20 | 2025-03-20
RE/0066-PRJ-T3-CIV-RS-SU | Reinforcement Supply | 2010 | GR01 | 2010 | SMARTWORLD THE EDITION | Jindal Steel Limited | 9110000777 | 170 |  |  | 2024-11-15 | Steel Re-bar TMT 32 mm Dia. FE-550D | TO | 131 | 54500 | 7139500 | 8424610 | 7135249 | 8419593.82 | 4251 | 7135249 | 8419593.82 | ZMAT | 2025-01-20 | 2025-03-20
RE/0066-PRJ-T3-CIV-RS-SU | Reinforcement Supply | 2010 | GR01 | 2010 | SMARTWORLD THE EDITION | Carna Corporation Pvt LtdVISHWANATH | 9110000779 | 30 |  |  | 2024-11-16 | Steel Re-bar TMT 20 mm Dia. FE-550D | TO | 11 | 54500 | 599500 | 707410 | 599500 | 707410 | 0 | 599499.9 | 707409.89 | ZMAT | 2025-01-20 | 2025-03-20
RE/0066-PRJ-T3-CIV-RS-SU | Reinforcement Supply | 2010 | GR01 | 2010 | SMARTWORLD THE EDITION | Carna Corporation Pvt LtdVISHWANATH | 9110000779 | 100 |  |  | 2024-11-16 | Steel Re-bar TMT 25 mm Dia. FE-550D | TO | 31 | 54500 | 1689500 | 1993610 | 1689500 | 1993610 | 0 | 1689500 | 1993610.03 | ZMAT | 2025-01-20 | 2025-03-20
RE/0066-PRJ-T3-CIV-RS-SU | Reinforcement Supply | 2010 | GR01 | 2010 | SMARTWORLD THE EDITION | Carna Corporation Pvt LtdVISHWANATH | 9110000779 | 170 |  |  | 2024-11-16 | Steel Re-bar TMT 32 mm Dia. FE-550D | TO | 418 | 54500 | 22781000 | 26881580 | 22781000 | 26881580 | 0 | 22780999.5 | 26881579.51 | ZMAT | 2025-01-20 | 2025-03-20
RE/0066-PRJ-T3-CIV-RS-SU | Reinforcement Supply | 2010 | GR01 | 2010 | SMARTWORLD THE EDITION | Rashtriya Ispat Nigam Ltd | 9110000790 | 40 |  |  | 2024-11-29 | Fe 550D TMT Steel Coil 10MM | TO | 4 | 54450 | 217800 | 257004 | 217800 | 257004 | 0 | 217800 | 257004 | ZMAT | 2024-11-29 | 2024-12-28
RE/0066-PRJ-T3-CIV-RS-SU | Reinforcement Supply | 2010 | GR01 | 2010 | SMARTWORLD THE EDITION | Rashtriya Ispat Nigam Ltd | 9110000790 | 110 |  |  | 2024-11-29 | Fe 550D TMT Steel Coil 12MM | TO | 8 | 53950 | 431600 | 509288 | 323700 | 381966 | 107900 | 323700 | 381966 | ZMAT | 2024-11-29 | 2024-12-28
RE/0066-PRJ-T3-CIV-RS-SU | Reinforcement Supply | 2010 | GR01 | 2010 | SMARTWORLD THE EDITION | Carna Corporation Pvt LtdVISHWANATH | 9110000837 | 30 |  |  | 2025-01-09 | Steel Re-bar TMT 08 mm Dia. FE-550D | TO | 1 | 51400 | 51400 | 60652 | 51400 | 60652 | 0 | 51400 | 60652 | ZMAT | 2025-01-20 | 2025-03-20
RE/0066-PRJ-T3-CIV-RS-SU | Reinforcement Supply | 2010 | GR01 | 2010 | SMARTWORLD THE EDITION | Carna Corporation Pvt LtdVISHWANATH | 9110000837 | 60 |  |  | 2025-01-09 | Steel Re-bar TMT 10 mm Dia. FE-550D | TO | 44 | 50150 | 2206600 | 2603788 | 2377110 | 2804989.8 | 170510 | 2377110 | 2804989.8 | ZMAT | 2025-01-20 | 2025-03-20
RE/0066-PRJ-T3-CIV-RS-SU | Reinforcement Supply | 2010 | GR01 | 2010 | SMARTWORLD THE EDITION | Jindal Steel Limited | 9110000859 | 10 |  |  | 2025-02-15 | Steel Re-bar TMT 12 mm Dia. FE-550D | TO | 29 | 50900 | 1476100 | 1741798 | 1250932.2 | 1476100 | 225167.8 | 1476100 | 1741798 | ZMAT
RE/0066-PRJ-T3-CIV-RS-SU | Reinforcement Supply | 2010 | GR01 | 2010 | SMARTWORLD THE EDITION | Jindal Steel Limited | 9110000859 | 30 |  |  | 2025-02-15 | Steel Re-bar TMT 16 mm Dia. FE-550D | TO | 42 | 50900 | 2137800 | 2522604 | 1811694.92 | 2137800 | 326105.08 | 2137800 | 2522604 | ZMAT
RE/0066-PRJ-T3-CIV-RS-SU | Reinforcement Supply | 2010 | GR01 | 2010 | SMARTWORLD THE EDITION | Jindal Steel Limited | 9110000859 | 60 |  |  | 2025-02-15 | Steel Re-bar TMT 20 mm Dia. FE-550D | TO | 17 | 50900 | 865300 | 1021054 | 578922.8 | 683128.9 | 286377.2 | 683128.9 | 806092.1 | ZMAT
RE/0066-PRJ-T3-CIV-RS-SU | Reinforcement Supply | 2010 | GR01 | 2010 | SMARTWORLD THE EDITION | Ram Niwas & SonsDeepak gupta | 9110000862 | 10 |  |  | 2025-02-15 | Steel Re-bar TMT 08 mm Dia. FE-550D | TO | 7.5 | 51200 | 384000 | 453120 | 390144 | 460369.92 | 6144 | 390144 | 460369.92 | ZMAT
RE/0066-PRJ-T3-CIV-RS-SU | Reinforcement Supply | 2010 | GR01 | 2010 | SMARTWORLD THE EDITION | Ram Niwas & SonsDeepak gupta | 9110000862 | 50 |  |  | 2025-02-15 | Steel Re-bar TMT 10 mm Dia. FE-550D | TO | 60 | 50200 | 3012000 | 3554160 | 3012000 | 3554160 | 0 | 3012000 | 3554160 | ZMAT
RE/0066-PRJ-T3-CIV-RS-SU | Reinforcement Supply | 2010 | GR01 | 2010 | SMARTWORLD THE EDITION | PRAGYAN METALS PRIVATE LIMITED | 9110000868 | 10 |  |  | 2025-02-18 | Steel Re-bar TMT 16 mm Dia. FE-550D | TO | 30 | 50900 | 1527000 | 1801860 | 1294067.8 | 1527000 | 232932.2 | 1527000 | 1801860 | ZMAT
RE/0066-PRJ-T3-CIV-RS-SU | Reinforcement Supply | 2010 | GR01 | 2010 | SMARTWORLD THE EDITION | Jindal Steel Limited | 9110000886 | 30 |  |  | 2025-03-12 | Steel Re-bar TMT 12 mm Dia. FE-550D | TO | 15 | 54750 | 821250 | 969075 | 882898.5 | 1041820.23 | 61648.5 | 882898.5 | 1041820.23 | ZMAT
RE/0066-PRJ-T3-CIV-RS-SU | Reinforcement Supply | 2010 | GR01 | 2010 | SMARTWORLD THE EDITION | Jindal Steel Limited | 9110000886 | 90 |  |  | 2025-03-12 | Steel Re-bar TMT 16 mm Dia. FE-550D | TO | 25 | 54750 | 1368750 | 1615125 | 1368750 | 1615125 | 0 | 1368750 | 1615125 | ZMAT
RE/0066-PRJ-T3-CIV-RS-SU | Reinforcement Supply | 2010 | GR01 | 2010 | SMARTWORLD THE EDITION | Jindal Steel Limited | 9110000886 | 150 |  |  | 2025-03-12 | Steel Re-bar TMT 20 mm Dia. FE-550D | TO | 20 | 54750 | 1095000 | 1292100 | 1095000.01 | 1292100.01 | 0.01 | 1095000 | 1292100.01 | ZMAT
RE/0066-PRJ-T3-CIV-RS-SU | Reinforcement Supply | 2010 | GR01 | 2010 | SMARTWORLD THE EDITION | Ram Niwas & SonsDeepak gupta | 9110000887 | 30 |  |  | 2025-03-12 | Steel Re-bar TMT 10 mm Dia. FE-550D | TO | 10.5 | 52900 | 555450 | 655431 | 575023 | 678527.14 | 19573 | 575023 | 678527.14 | ZMAT
RE/0066-PRJ-T3-CIV-RS-SU | Reinforcement Supply | 2010 | GR01 | 2010 | SMARTWORLD THE EDITION | Carna Corporation Pvt LtdVISHWANATH | 9110000889 | 30 |  |  | 2025-03-12 | Steel Re-bar TMT 10 mm Dia. FE-550D | TO | 4.5 | 55500 | 249750 | 294705 | 249750 | 294705 | 0 | 249750 | 294705 | ZMAT
RE/0066-PRJ-T3-CIV-RS-SU | Reinforcement Supply | 2010 | GR01 | 2010 | SMARTWORLD THE EDITION | Rashtriya Ispat Nigam Ltd | 9110000961 | 30 |  |  | 2025-04-08 | Fe 550D TMT Steel Coil 10MM | TO | 9 | 58750 | 528750 | 623925 | 528750 | 623925 | 0 | 528750 | 623925 | ZMAT
RE/0066-PRJ-T3-CIV-RS-SU | Reinforcement Supply | 2010 | GR01 | 2010 | SMARTWORLD THE EDITION | Rashtriya Ispat Nigam Ltd | 9110000961 | 100 |  |  | 2025-04-08 | Fe 550D TMT Steel Coil 08MM | TO | 9 | 60000 | 540000 | 637200 | 540000 | 637200 | 0 | 540000 | 637200 | ZMAT
RE/0066-PRJ-T3-CIV-RS-SU | Reinforcement Supply | 2010 | GR01 | 2010 | SMARTWORLD THE EDITION | Vikrant Ispat Udyog | 9110000966 | 30 |  |  | 2025-04-09 | Fe 550D TMT Steel Coil 10MM | TO | 3 | 64250 | 192750 | 227445 | 192750 | 227445 | 0 | 192750 | 227445 | ZMAT
RE/0066-PRJ-T3-CIV-RS-SU | Reinforcement Supply | 2010 | GR01 | 2010 | SMARTWORLD THE EDITION | Vikrant Ispat Udyog | 9110000966 | 100 |  |  | 2025-04-09 | Fe 550D TMT Steel Coil 08MM | TO | 3 | 65750 | 197250 | 232755 | 197250 | 232755 | 0 | 197250 | 232755 | ZMAT
RE/0066-PRJ-T3-CIV-RS-SU | Reinforcement Supply | 2010 | GR01 | 2010 | SMARTWORLD THE EDITION | Ram Niwas & SonsDeepak gupta | 9110000992 | 50 |  |  | 2025-04-17 | Steel Re-bar TMT 10 mm Dia. FE-550D | TO | 10 | 56000 | 560000 | 660800 | 560000 | 660800 | 0 | 560000 | 660800 | ZMAT
RE/0066-PRJ-T3-CIV-RS-SU | Reinforcement Supply | 2010 | GR01 | 2010 | SMARTWORLD THE EDITION | Petropol India LimitedSANJAY GUPTA | 9110000993 | 10 |  |  | 2025-04-17 | Steel Re-bar TMT 10 mm Dia. FE-550D | TO | 30 | 56000 | 1680000 | 1982400 | 1848000 | 2180640 | 168000 | 1848000 | 2180640 | ZMAT | 2025-04-17 | 2025-04-30
RE/0066-PRJ-T3-CIV-RS-SU | Reinforcement Supply | 2010 | GR01 | 2010 | SMARTWORLD THE EDITION | Sapcon Steels Private Limited | 9110000999 | 50 |  |  | 2025-04-18 | Fe 550D TMT Steel Coil 10MM | TO | 40 | 58250 | 2330000 | 2749400 | 2330000 | 2749400 | 0 | 2330000 | 2749400 | ZMAT | 2025-04-11 | 2025-04-30
RE/0066-PRJ-T3-CIV-RS-SU | Reinforcement Supply | 2010 | GR01 | 2010 | SMARTWORLD THE EDITION | Sapcon Steels Private Limited | 9110001009 | 30 |  |  | 2025-04-28 | Steel Re-bar TMT 32 mm Dia. FE-550D | TO | 11 | 57000 | 627000 | 739860 | 399000 | 470820 | 228000 | 399000 | 470820 | ZMAT
RE/0066-PRJ-T3-CIV-RS-SU | Reinforcement Supply | 2010 | GR01 | 2010 | SMARTWORLD THE EDITION | Jindal Steel Limited | 9110001055 | 30 |  |  | 2025-05-17 | Steel Re-bar TMT 20 mm Dia. FE-550D | TO | 10 | 54850 | 548500 | 647230 | 548500 | 647230 | 0 | 548500 | 647230 | ZMAT | 2025-05-29 | 2025-06-29
RE/0066-PRJ-T3-CIV-RS-SU | Reinforcement Supply | 2010 | GR01 | 2010 | SMARTWORLD THE EDITION | Jindal Steel Limited | 9110001055 | 100 |  |  | 2025-05-17 | Steel Re-bar TMT 25 mm Dia. FE-550D | TO | 33 | 54850 | 1810050 | 2135859 | 1810050 | 2135859 | 0 | 1810050 | 2135859 | ZMAT | 2025-05-29 | 2025-06-29
RE/0066-PRJ-T3-CIV-RS-SU | Reinforcement Supply | 2010 | GR01 | 2010 | SMARTWORLD THE EDITION | Jindal Steel Limited | 9110001055 | 170 |  |  | 2025-05-17 | Steel Re-bar TMT 32 mm Dia. FE-550D | TO | 15 | 54850 | 822750 | 970845 | 739542.55 | 872660.21 | 83207.45 | 739542.55 | 872660.21 | ZMAT | 2025-05-29 | 2025-06-29
RE/0066-PRJ-T3-CIV-RS-SU | Reinforcement Supply | 2010 | GR01 | 2010 | SMARTWORLD THE EDITION | Jindal Steel Limited | 9110001073 | 40 |  |  | 2025-05-27 | Steel Re-bar TMT 12 mm Dia. FE-550D | TO | 10 | 57750 | 577500 | 681450 | 577500 | 681450 | 0 | 577500 | 681450 | ZMAT
RE/0066-PRJ-T3-CIV-RS-SU | Reinforcement Supply | 2010 | GR01 | 2010 | SMARTWORLD THE EDITION | Jindal Steel Limited | 9110001073 | 110 |  |  | 2025-05-27 | Steel Re-bar TMT 16 mm Dia. FE-550D | TO | 20 | 57750 | 1155000 | 1362900 | 1155000 | 1362900 | 0 | 1155000 | 1362900 | ZMAT
RE/0066-PRJ-T3-CIV-RS-SU | Reinforcement Supply | 2010 | GR01 | 2010 | SMARTWORLD THE EDITION | JINDAL STEEL LIMITEDMr Robin Taneja | 9110001079 | 30 |  |  | 2025-05-29 | Steel Re-bar TMT 25 mm Dia. FE-550D | TO | 12 | 54850 | 658200 | 776676 | 658200 | 776676 | 0 | 658200 | 776676 | ZMAT | 2025-05-29 | 2025-06-29
RE/0066-PRJ-T3-CIV-RS-SU | Reinforcement Supply | 2010 | GR01 | 2010 | SMARTWORLD THE EDITION | Ram Niwas & SonsDeepak gupta | 9110001126 | 30 |  |  | 2025-06-20 | Steel Re-bar TMT 08 mm Dia. FE-550D | TO | 10 | 51000 | 510000 | 601800 | 510000 | 601800 | 0 | 510000 | 601800 | ZMAT | 2025-06-20 | 2025-07-20
RE/0066-PRJ-T3-CIV-RS-SU | Reinforcement Supply | 2010 | GR01 | 2010 | SMARTWORLD THE EDITION | Jindal Steel Limited | 9110001127 | 30 |  |  | 2025-06-20 | Steel Re-bar TMT 12 mm Dia. FE-550D | TO | 30 | 50600 | 1518000 | 1791240 | 1518000 | 1791240 | 0 | 1518000 | 1791240 | ZMAT | 2025-06-20 | 2025-07-20
RE/0066-PRJ-T3-CIV-RS-SU | Reinforcement Supply | 2010 | GR01 | 2010 | SMARTWORLD THE EDITION | Jindal Steel Limited | 9110001127 | 110 |  |  | 2025-06-20 | Steel Re-bar TMT 16 mm Dia. FE-550D | TO | 25 | 50600 | 1265000 | 1492700 | 1265000 | 1492700 | 0 | 1265000 | 1492700 | ZMAT | 2025-06-20 | 2025-07-20
RE/0066-PRJ-T3-CIV-RS-SU | Reinforcement Supply | 2010 | GR01 | 2010 | SMARTWORLD THE EDITION | Jindal Steel Limited | 9110001127 | 190 |  |  | 2025-06-20 | Steel Re-bar TMT 20 mm Dia. FE-550D | TO | 15 | 50600 | 759000 | 895620 | 759000 | 895620 | 0 | 759000 | 895620 | ZMAT | 2025-06-20 | 2025-07-20
RE/0066-PRJ-T3-CIV-RS-SU | Reinforcement Supply | 2010 | GR01 | 2010 | SMARTWORLD THE EDITION | Jindal Steel Limited | 9110001127 | 260 |  |  | 2025-06-20 | Steel Re-bar TMT 25 mm Dia. FE-550D | TO | 20 | 50600 | 1012000 | 1194160 | 1012000 | 1194160 | 0 | 1012000 | 1194160 | ZMAT | 2025-06-20 | 2025-07-20
RE/0066-PRJ-T3-CIV-RS-SU | Reinforcement Supply | 2010 | GR01 | 2010 | SMARTWORLD THE EDITION | Jindal Steel Limited | 9110001127 | 340 |  |  | 2025-06-20 | Steel Re-bar TMT 32 mm Dia. FE-550D | TO | 10 | 50600 | 506000 | 597080 | 506000 | 597080 | 0 | 506000 | 597080 | ZMAT | 2025-06-20 | 2025-07-20
RE/0066-PRJ-T3-CIV-RS-SU | Reinforcement Supply | 2010 | GR01 | 2010 | SMARTWORLD THE EDITION | Jindal Steel Limited | 9110001162 | 30 |  |  | 2025-07-17 | Steel Re-bar TMT 10 mm Dia. FE-550D | TO | 40 | 47500 | 1900000 | 2242000 | 0 | 0 | 1900000 | 0 | 0 | ZMAT | 2025-07-17 | 2025-08-17
RE/0066-PRJ-T3-CIV-RS-SU | Reinforcement Supply | 2010 | GR01 | 2010 | SMARTWORLD THE EDITION | Jindal Steel Limited | 9110001162 | 110 |  |  | 2025-07-17 | Steel Re-bar TMT 12 mm Dia. FE-550D | TO | 15 | 46500 | 697500 | 823050 | 0 | 0 | 697500 | 0 | 0 | ZMAT | 2025-07-17 | 2025-08-17
RE/0066-PRJ-T3-CIV-RS-SU | Reinforcement Supply | 2010 | GR01 | 2010 | SMARTWORLD THE EDITION | Jindal Steel Limited | 9110001162 | 190 |  |  | 2025-07-17 | Steel Re-bar TMT 16 mm Dia. FE-550D | TO | 5 | 46500 | 232500 | 274350 | 0 | 0 | 232500 | 0 | 0 | ZMAT | 2025-07-17 | 2025-08-17
RE/0066-PRJ-T3-CIV-RS-SU | Reinforcement Supply | 2010 | GR01 | 2010 | SMARTWORLD THE EDITION | Jindal Steel Limited | 9110001162 | 250 |  |  | 2025-07-17 | Steel Re-bar TMT 20 mm Dia. FE-550D | TO | 5 | 46500 | 232500 | 274350 | 0 | 0 | 232500 | 0 | 0 | ZMAT | 2025-07-17 | 2025-08-17
RE/0066-PRJ-T3-CIV-RS-SU | Reinforcement Supply | 2010 | GR01 | 2010 | SMARTWORLD THE EDITION | Jindal Steel Limited | 9110001162 | 320 |  |  | 2025-07-17 | Steel Re-bar TMT 25 mm Dia. FE-550D | TO | 5 | 46500 | 232500 | 274350 | 0 | 0 | 232500 | 0 | 0 | ZMAT | 2025-07-17 | 2025-08-17
RE/0066-PRJ-T3-CIV-RS-SU | Reinforcement Supply | 2010 | GR01 | 2010 | SMARTWORLD THE EDITION | Jindal Steel Limited | 9110001162 | 400 |  |  | 2025-07-17 | Steel Re-bar TMT 32 mm Dia. FE-550D | TO | 5 | 46500 | 232500 | 274350 | 0 | 0 | 232500 | 0 | 0 | ZMAT | 2025-07-17 | 2025-08-17
RE/0066-PRJ-T3-CIV-RS-SU | Reinforcement Supply | 2010 | GR01 | 2010 | SMARTWORLD THE EDITION | Rashtriya Ispat Nigam Ltd | 9110001212 | 30 |  |  | 2025-08-14 | Steel Re-bar TMT 08 mm Dia. FE-550D | TO | 10 | 49300 | 493000 | 581740 | 493000 | 581740 | 0 | 493000 | 581740 | ZMAT | 2025-08-14 | 2025-09-14
RE/0066-PRJ-T3-CIV-RS-SU | Reinforcement Supply | 2010 | GR01 | 2010 | SMARTWORLD THE EDITION | Rashtriya Ispat Nigam Ltd | 9110001212 | 90 |  |  | 2025-08-14 | Steel Re-bar TMT 10 mm Dia. FE-550D | TO | 55 | 47800 | 2629000 | 3102220 | 2629000 | 3102220 | 0 | 2629000 | 3102220 | ZMAT | 2025-08-14 | 2025-09-14
RE/0066-PRJ-T3-CIV-RS-SU | Reinforcement Supply | 2010 | GR01 | 2010 | SMARTWORLD THE EDITION | Jindal Steel Limited | 9110001213 | 30 |  |  | 2025-08-14 | Steel Re-bar TMT 12 mm Dia. FE-550D | TO | 35 | 47000 | 1645000 | 1941100 | 1645000 | 1941100 | 0 | 1645000 | 1941100 | ZMAT | 2025-08-14 | 2025-09-14
RE/0066-PRJ-T3-CIV-RS-SU | Reinforcement Supply | 2010 | GR01 | 2010 | SMARTWORLD THE EDITION | Jindal Steel Limited | 9110001213 | 90 |  |  | 2025-08-14 | Steel Re-bar TMT 16 mm Dia. FE-550D | TO | 15 | 47000 | 705000 | 831900 | 705000 | 831900 | 0 | 705000 | 831900 | ZMAT | 2025-08-14 | 2025-09-14
RE/0066-PRJ-T3-CIV-RS-SU | Reinforcement Supply | 2010 | GR01 | 2010 | SMARTWORLD THE EDITION | Jindal Steel Limited | 9110001213 | 150 |  |  | 2025-08-14 | Steel Re-bar TMT 20 mm Dia. FE-550D | TO | 15 | 47000 | 705000 | 831900 | 705000 | 831900 | 0 | 705000 | 831900 | ZMAT | 2025-08-14 | 2025-09-14
RE/0066-PRJ-T3-CIV-RS-SU | Reinforcement Supply | 2010 | GR01 | 2010 | SMARTWORLD THE EDITION | Jindal Steel Limited | 9110001213 | 210 |  |  | 2025-08-14 | Steel Re-bar TMT 25 mm Dia. FE-550D | TO | 20 | 47000 | 940000 | 1109200 | 940000 | 1109200 | 0 | 940000 | 1109200 | ZMAT | 2025-08-14 | 2025-09-14
RE/0066-PRJ-T3-CIV-RS-SU | Reinforcement Supply | 2010 | GR01 | 2010 | SMARTWORLD THE EDITION | Jindal Steel Limited | 9110001213 | 270 |  |  | 2025-08-14 | Steel Re-bar TMT 32 mm Dia. FE-550D | TO | 20 | 47000 | 940000 | 1109200 | 940000 | 1109200 | 0 | 940000 | 1109200 | ZMAT | 2025-08-14 | 2025-09-14
RE/0066-PRJ-T3-CIV-RS-SU | Reinforcement Supply | 2010 | GR01 | 2010 | SMARTWORLD THE EDITION | Steel Authority Of India LTD | 9110001280 | 40 |  |  | 2025-09-18 | Steel Re-bar TMT 12 mm Dia. FE-550D | TO | 26.1 | 46260 | 1207386 | 1424715.48 | 1207386 | 1424715.48 | 0 | 1207386 | 1424715.48 | ZMAT | 2025-09-18 | 2025-10-18
RE/0066-PRJ-T3-CIV-RS-SU | Reinforcement Supply | 2010 | GR01 | 2010 | SMARTWORLD THE EDITION | Steel Authority Of India LTD | 9110001280 | 100 |  |  | 2025-09-18 | Steel Re-bar TMT 16 mm Dia. FE-550D | TO | 20 | 46260 | 925200 | 1091736 | 925200 | 1091736 | 0 | 925200 | 1091736 | ZMAT | 2025-09-18 | 2025-10-18
RE/0066-PRJ-T3-CIV-RS-SU | Reinforcement Supply | 2010 | GR01 | 2010 | SMARTWORLD THE EDITION | Steel Authority Of India LTD | 9110001280 | 160 |  |  | 2025-09-18 | Steel Re-bar TMT 20 mm Dia. FE-550D | TO | 24.7 | 46260 | 1142622 | 1348293.96 | 1142622 | 1348293.96 | 0 | 1142622 | 1348293.96 | ZMAT | 2025-09-18 | 2025-10-18
RE/0066-PRJ-T3-CIV-RS-SU | Reinforcement Supply | 2010 | GR01 | 2010 | SMARTWORLD THE EDITION | Steel Authority Of India LTD | 9110001280 | 220 |  |  | 2025-09-18 | Steel Re-bar TMT 25 mm Dia. FE-550D | TO | 13 | 46260 | 601380 | 709628.4 | 601380 | 709628.4 | 0 | 601380 | 709628.4 | ZMAT | 2025-09-18 | 2025-10-18
RE/0066-PRJ-T3-CIV-RS-SU | Reinforcement Supply | 2010 | GR01 | 2010 | SMARTWORLD THE EDITION | Steel Authority Of India LTD | 9110001280 | 280 |  |  | 2025-09-18 | Steel Re-bar TMT 32 mm Dia. FE-550D | TO | 10.8 | 46260 | 499608 | 589537.44 | 499608 | 589537.44 | 0 | 499608 | 589537.44 | ZMAT | 2025-09-18 | 2025-10-18
RE/0066-PRJ-T3-CIV-RS-SU | Reinforcement Supply | 2010 | GR01 | 2010 | SMARTWORLD THE EDITION | Steel Authority Of India LTD | 9110001280 | 310 |  |  | 2025-09-18 | Steel Re-bar TMT 10 mm Dia. FE-550D | TO | 16.4 | 47260 | 775064 | 914575.52 | 775064 | 914575.52 | 0 | 775064 | 914575.52 | ZMAT | 2025-09-18 | 2025-10-18
RE/0066-PRJ-T3-CIV-RS-SU | Reinforcement Supply | 2010 | GR01 | 2010 | SMARTWORLD THE EDITION | Ram Niwas & SonsDeepak gupta | 9110001305 | 30 |  |  | 2025-10-09 | Steel Re-bar TMT 08 mm Dia. FE-550D | TO | 6 | 47500 | 285000 | 336300 | 285000 | 336300 | 0 | 285000 | 336300 | ZMAT | 2025-10-09 | 2025-11-08
RE/0066-PRJ-T3-CIV-RS-SU | Reinforcement Supply | 2010 | GR01 | 2010 | SMARTWORLD THE EDITION | Ram Niwas & SonsDeepak gupta | 9110001305 | 90 |  |  | 2025-10-09 | Steel Re-bar TMT 10 mm Dia. FE-550D | TO | 28 | 46500 | 1302000 | 1536360 | 1295025 | 1528129.5 | 6975 | 1295025 | 1528129.5 | ZMAT | 2025-10-09 | 2025-11-08
RE/0066-PRJ-T3-CIV-RS-SU | Reinforcement Supply | 2010 | GR01 | 2010 | SMARTWORLD THE EDITION | Jindal Steel Limited | 9110001307 | 30 |  |  | 2025-10-09 | Steel Re-bar TMT 12 mm Dia. FE-550D | TO | 5 | 46500 | 232500 | 274350 | 232500 | 274350 | 0 | 232500 | 274350 | ZMAT | 2025-10-09 | 2025-11-08
RE/0066-PRJ-T3-CIV-RS-SU | Reinforcement Supply | 2010 | GR01 | 2010 | SMARTWORLD THE EDITION | Jindal Steel Limited | 9110001307 | 90 |  |  | 2025-10-09 | Steel Re-bar TMT 16 mm Dia. FE-550D | TO | 20 | 46500 | 930000 | 1097400 | 930000 | 1097400 | 0 | 930000 | 1097400 | ZMAT | 2025-10-09 | 2025-11-08
RE/0066-PRJ-T3-CIV-RS-SU | Reinforcement Supply | 2010 | GR01 | 2010 | SMARTWORLD THE EDITION | Jindal Steel Limited | 9110001307 | 150 |  |  | 2025-10-09 | Steel Re-bar TMT 20 mm Dia. FE-550D | TO | 20 | 46500 | 930000 | 1097400 | 930000 | 1097400 | 0 | 930000 | 1097400 | ZMAT | 2025-10-09 | 2025-11-08
RE/0066-PRJ-T3-CIV-RS-SU | Reinforcement Supply | 2010 | GR01 | 2010 | SMARTWORLD THE EDITION | Jindal Steel Limited | 9110001307 | 210 |  |  | 2025-10-09 | Steel Re-bar TMT 25 mm Dia. FE-550D | TO | 17 | 46500 | 790500 | 932790 | 790500 | 932790 | 0 | 790500 | 932790 | ZMAT | 2025-10-09 | 2025-11-08
RE/0066-PRJ-T3-CIV-RS-SU | Reinforcement Supply | 2010 | GR01 | 2010 | SMARTWORLD THE EDITION | Jindal Steel Limited | 9110001307 | 270 |  |  | 2025-10-09 | Steel Re-bar TMT 32 mm Dia. FE-550D | TO | 17 | 46500 | 790500 | 932790 | 790500 | 932790 | 0 | 790500 | 932790 | ZMAT | 2025-10-09 | 2025-11-08
RE/0066-PRJ-T3-CIV-RS-SU | Reinforcement Supply | 2010 | GR01 | 2010 | SMARTWORLD THE EDITION | Jindal Steel Limited | 9110001361 | 30 |  |  | 2025-11-07 | Steel Re-bar TMT 12 mm Dia. FE-550D | TO | 33 | 46100 | 1521300 | 1795134 | 1521300 | 1795134 | 0 | 1521300 | 1795134 | ZMAT | 2025-11-07 | 2025-12-07
RE/0066-PRJ-T3-CIV-RS-SU | Reinforcement Supply | 2010 | GR01 | 2010 | SMARTWORLD THE EDITION | Jindal Steel Limited | 9110001361 | 90 |  |  | 2025-11-07 | Steel Re-bar TMT 16 mm Dia. FE-550D | TO | 25 | 46100 | 1152500 | 1359950 | 1152500 | 1359950 | 0 | 1152500 | 1359950 | ZMAT | 2025-11-07 | 2025-12-07
RE/0066-PRJ-T3-CIV-RS-SU | Reinforcement Supply | 2010 | GR01 | 2010 | SMARTWORLD THE EDITION | Jindal Steel Limited | 9110001361 | 150 |  |  | 2025-11-07 | Steel Re-bar TMT 20 mm Dia. FE-550D | TO | 8 | 46100 | 368800 | 435184 | 368800 | 435184 | 0 | 368800 | 435184 | ZMAT | 2025-11-07 | 2025-12-07
RE/0066-PRJ-T3-CIV-RS-SU | Reinforcement Supply | 2010 | GR01 | 2010 | SMARTWORLD THE EDITION | Jindal Steel Limited | 9110001361 | 210 |  |  | 2025-11-07 | Steel Re-bar TMT 25 mm Dia. FE-550D | TO | 30 | 46100 | 1383000 | 1631940 | 1383000 | 1631940 | 0 | 1383000 | 1631940 | ZMAT | 2025-11-07 | 2025-12-07
RE/0066-PRJ-T3-CIV-RS-SU | Reinforcement Supply | 2010 | GR01 | 2010 | SMARTWORLD THE EDITION | Jindal Steel Limited | 9110001361 | 270 |  |  | 2025-11-07 | Steel Re-bar TMT 32 mm Dia. FE-550D | TO | 8 | 46100 | 368800 | 435184 | 368800 | 435184 | 0 | 368800 | 435184 | ZMAT | 2025-11-07 | 2025-12-07
RE/0066-PRJ-T3-CIV-RS-SU | Reinforcement Supply | 2010 | GR01 | 2010 | SMARTWORLD THE EDITION | Ram Niwas & SonsDeepak gupta | 9110001362 | 30 |  |  | 2025-11-07 | Steel Re-bar TMT 08 mm Dia. FE-550D | TO | 2.5 | 46900 | 117250 | 138355 | 117250 | 138355 | 0 | 117250 | 138355 | ZMAT | 2025-11-07 | 2025-12-07
RE/0066-PRJ-T3-CIV-RS-SU | Reinforcement Supply | 2010 | GR01 | 2010 | SMARTWORLD THE EDITION | Ram Niwas & SonsDeepak gupta | 9110001362 | 80 |  |  | 2025-11-07 | Steel Re-bar TMT 10 mm Dia. FE-550D | TO | 38.5 | 45900 | 1767150 | 2085237 | 1767150 | 2085237 | 0 | 1767150 | 2085237 | ZMAT | 2025-11-07 | 2025-12-07
RE/0066-PRJ-T3-CIV-RS-SU | Reinforcement Supply | 2010 | GR01 | 2010 | SMARTWORLD THE EDITION | Ram Niwas & SonsDeepak gupta | 9110001421 | 30 |  |  | 2025-12-10 | Steel Re-bar TMT 10 mm Dia. FE-550D | TO | 22 | 46500 | 1023000 | 1207140 | 1018350 | 1201653 | 4650 | 1018350 | 1201653 | ZMAT | 2025-12-10 | 2026-01-10
RE/0066-PRJ-T3-CIV-RS-SU | Reinforcement Supply | 2010 | GR01 | 2010 | SMARTWORLD THE EDITION | Ram Niwas & SonsDeepak gupta | 9110001421 | 90 |  |  | 2025-12-10 | Steel Re-bar TMT 08 mm Dia. FE-550D | TO | 12 | 47500 | 570000 | 672600 | 567625 | 669797.5 | 2375 | 567625 | 669797.5 | ZMAT | 2025-12-10 | 2026-01-10
RE/0066-PRJ-T3-CIV-RS-SU | Reinforcement Supply | 2010 | GR01 | 2010 | SMARTWORLD THE EDITION | Jindal Steel Limited | 9110001422 | 30 |  |  | 2025-12-10 | Steel Re-bar TMT 12 mm Dia. FE-550D | TO | 20 | 46400 | 928000 | 1095040 | 928000 | 1095040 | 0 | 928000 | 1095040 | ZMAT | 2025-12-10 | 2026-01-10
RE/0066-PRJ-T3-CIV-RS-SU | Reinforcement Supply | 2010 | GR01 | 2010 | SMARTWORLD THE EDITION | Jindal Steel Limited | 9110001422 | 90 |  |  | 2025-12-10 | Steel Re-bar TMT 16 mm Dia. FE-550D | TO | 18 | 46400 | 835200 | 985536 | 835200 | 985536 | 0 | 835200 | 985536 | ZMAT | 2025-12-10 | 2026-01-10
RE/0066-PRJ-T3-CIV-RS-SU | Reinforcement Supply | 2010 | GR01 | 2010 | SMARTWORLD THE EDITION | Jindal Steel Limited | 9110001422 | 150 |  |  | 2025-12-10 | Steel Re-bar TMT 20 mm Dia. FE-550D | TO | 13 | 46400 | 603200 | 711776 | 603200 | 711776 | 0 | 603200 | 711776 | ZMAT | 2025-12-10 | 2026-01-10
RE/0066-PRJ-T3-CIV-RS-SU | Reinforcement Supply | 2010 | GR01 | 2010 | SMARTWORLD THE EDITION | Jindal Steel Limited | 9110001422 | 210 |  |  | 2025-12-10 | Steel Re-bar TMT 25 mm Dia. FE-550D | TO | 15 | 46400 | 696000 | 821280 | 696000 | 821280 | 0 | 696000 | 821280 | ZMAT | 2025-12-10 | 2026-01-10
RE/0066-PRJ-T3-CIV-RS-SU | Reinforcement Supply | 2010 | GR01 | 2010 | SMARTWORLD THE EDITION | Ram Niwas & SonsDeepak gupta | 9110001471 | 30 |  |  | 2026-01-12 | Steel Re-bar TMT 08 mm Dia. FE-550D | TO | 10 | 52000 | 520000 | 613600 | 495560 | 584760.8 | 24440 | 495560 | 584760.8 | ZMAT | 2026-01-12 | 2026-02-12
RE/0066-PRJ-T3-CIV-RS-SU | Reinforcement Supply | 2010 | GR01 | 2010 | SMARTWORLD THE EDITION | ESL STEEL LIMITED | 9110001481 | 30 |  |  | 2026-01-12 | Steel Re-bar TMT 12 mm Dia. FE-550D | TO | 42 | 51800 | 2175600 | 2567208 | 2134678 | 2518920.04 | 40922 | 2134678 | 2518920.04 | ZMAT | 2026-01-12 | 2026-02-12
RE/0066-PRJ-T3-CIV-RS-SU | Reinforcement Supply | 2010 | GR01 | 2010 | SMARTWORLD THE EDITION | ESL STEEL LIMITED | 9110001481 | 90 |  |  | 2026-01-12 | Steel Re-bar TMT 16 mm Dia. FE-550D | TO | 2 | 51800 | 103600 | 122248 | 103600 | 122248 | 0 | 103600 | 122248 | ZMAT | 2026-01-12 | 2026-02-12
RE/0066-PRJ-T3-CIV-RS-SU | Reinforcement Supply | 2010 | GR01 | 2010 | SMARTWORLD THE EDITION | ESL STEEL LIMITED | 9110001481 | 150 |  |  | 2026-01-12 | Steel Re-bar TMT 20 mm Dia. FE-550D | TO | 25 | 51800 | 1295000 | 1528100 | 1322298.6 | 1560312.35 | 27298.6 | 1322298.6 | 1560312.35 | ZMAT | 2026-01-12 | 2026-02-12
RE/0066-PRJ-T3-CIV-RS-SU | Reinforcement Supply | 2010 | GR01 | 2010 | SMARTWORLD THE EDITION | ESL STEEL LIMITED | 9110001481 | 210 |  |  | 2026-01-12 | Steel Re-bar TMT 25 mm Dia. FE-550D | TO | 8 | 51800 | 414400 | 488992 | 414400 | 488992 | 0 | 414400 | 488992 | ZMAT | 2026-01-12 | 2026-02-12
RE/0066-PRJ-T3-CIV-RS-SU | Reinforcement Supply | 2010 | GR01 | 2010 | SMARTWORLD THE EDITION | Ram Niwas & SonsDeepak gupta | 9110001541 | 30 |  |  | 2026-02-07 | Steel Re-bar TMT 08 mm Dia. FE-550D | TO | 7 | 55300 | 387100 | 456778 | 385994 | 455472.92 | 1106 | 385994 | 455472.92 | ZMAT | 2026-02-07 | 2026-03-31
RE/0066-PRJ-T3-CIV-RS-SU | Reinforcement Supply | 2010 | GR01 | 2010 | SMARTWORLD THE EDITION | Ram Niwas & SonsDeepak gupta | 9110001541 | 90 |  |  | 2026-02-07 | Steel Re-bar TMT 10 mm Dia. FE-550D | TO | 12 | 54300 | 651600 | 768888 | 651600 | 768888 | 0 | 651600 | 768888 | ZMAT | 2026-02-07 | 2026-03-31
RE/0066-PRJ-T3-CIV-RS-SU | Reinforcement Supply | 2010 | GR01 | 2010 | SMARTWORLD THE EDITION | Petropol India LimitedSANJAY GUPTA | 9110001546 | 30 |  |  | 2026-02-07 | Steel Re-bar TMT 08 mm Dia. FE-550D | TO | 7 | 55300 | 387100 | 456778 | 387100 | 456778 | 0 | 387100 | 456778 | ZMAT | 2026-02-07 | 2026-03-31
RE/0066-PRJ-T3-CIV-RS-SU | Reinforcement Supply | 2010 | GR01 | 2010 | SMARTWORLD THE EDITION | Petropol India LimitedSANJAY GUPTA | 9110001546 | 90 |  |  | 2026-02-07 | Steel Re-bar TMT 10 mm Dia. FE-550D | TO | 15 | 54300 | 814500 | 961110 | 810699 | 956624.82 | 3801 | 810699 | 956624.82 | ZMAT | 2026-02-07 | 2026-03-31
RE/0066-PRJ-T3-CIV-RS-SU | Reinforcement Supply | 2010 | GR01 | 2010 | SMARTWORLD THE EDITION | Jindal Steel Limited | 9110001551 | 30 |  |  | 2026-02-07 | Steel Re-bar TMT 12 mm Dia. FE-550D | TO | 27 | 58500 | 1579500 | 1863810 | 1578330 | 1862429.4 | 1170 | 1578330 | 1862429.4 | ZMAT | 2026-02-07 | 2026-03-07
RE/0066-PRJ-T3-CIV-RS-SU | Reinforcement Supply | 2010 | GR01 | 2010 | SMARTWORLD THE EDITION | Jindal Steel Limited | 9110001551 | 90 |  |  | 2026-02-07 | Steel Re-bar TMT 16 mm Dia. FE-550D | TO | 30 | 58500 | 1755000 | 2070900 | 1747512 | 2062064.16 | 7488 | 1747512 | 2062064.16 | ZMAT | 2026-02-07 | 2026-03-07
RE/0066-PRJ-T3-CIV-RS-SU | Reinforcement Supply | 2010 | GR01 | 2010 | SMARTWORLD THE EDITION | Jindal Steel Limited | 9110001551 | 150 |  |  | 2026-02-07 | Steel Re-bar TMT 20 mm Dia. FE-550D | TO | 3 | 58500 | 175500 | 207090 | 0 | 0 | 175500 | 0 | 0 | ZMAT | 2026-02-07 | 2026-03-07
RE/0066-PRJ-T3-CIV-RS-SU | Reinforcement Supply | 2010 | GR01 | 2010 | SMARTWORLD THE EDITION | Jindal Steel Limited | 9110001551 | 210 |  |  | 2026-02-07 | Steel Re-bar TMT 25 mm Dia. FE-550D | TO | 20 | 58500 | 1170000 | 1380600 | 1076458.5 | 1270221.03 | 93541.5 | 1076458.5 | 1270221.03 | ZMAT | 2026-02-07 | 2026-03-07
RE/0066-PRJ-T3-CIV-RS-SU | Reinforcement Supply | 2010 | GR01 | 2010 | SMARTWORLD THE EDITION | Jindal Steel Limited | 9110001557 | 30 |  |  | 2026-02-10 | Steel Re-bar TMT 12 mm Dia. FE-550D | TO | 27 | 58500 | 1579500 | 1863810 | 1567800 | 1850004 | 11700 | 1567800 | 1850004 | ZMAT | 2026-02-10 | 2026-03-10
RE/0066-PRJ-T3-CIV-RS-SU | Reinforcement Supply | 2010 | GR01 | 2010 | SMARTWORLD THE EDITION | Jindal Steel Limited | 9110001557 | 90 |  |  | 2026-02-10 | Steel Re-bar TMT 25 mm Dia. FE-550D | TO | 48 | 58500 | 2808000 | 3313440 | 2805309 | 3310264.62 | 2691 | 2805309 | 3310264.62 | ZMAT | 2026-02-10 | 2026-03-10
RE/0066-PRJ-T3-CIV-RS-SU | Reinforcement Supply | 2010 | GR01 | 2010 | SMARTWORLD THE EDITION | Jindal Steel Limited | 9110001557 | 150 |  |  | 2026-02-10 | Steel Re-bar TMT 32 mm Dia. FE-550D | TO | 15 | 58500 | 877500 | 1035450 | 877500 | 1035450 | 0 | 877500 | 1035450 | ZMAT | 2026-02-10 | 2026-03-10
RE/0066-PRJ-T3-CIV-RS-SU | Reinforcement Supply | 2010 | GR01 | 2010 | SMARTWORLD THE EDITION | Petropol India LimitedSANJAY GUPTA | 9110001558 | 30 |  |  | 2026-02-10 | Steel Re-bar TMT 08 mm Dia. FE-550D | TO | 18 | 55300 | 995400 | 1174572 | 990423 | 1168699.14 | 4977 | 990423 | 1168699.14 | ZMAT | 2026-02-10 | 2026-03-10
RE/0066-PRJ-T3-CIV-RS-SU | Reinforcement Supply | 2010 | GR01 | 2010 | SMARTWORLD THE EDITION | Ram Niwas & SonsDeepak gupta | 9110001607 | 30 |  |  | 2026-03-11 | Steel Re-bar TMT 10 mm Dia. FE-550D | TO | 37 | 55800 | 2064600 | 2436228 | 2064600 | 2436228 | 0 | 2064600 | 2436228 | ZMAT | 2026-03-11 | 2026-04-11
RE/0066-PRJ-T3-CIV-RS-SU | Reinforcement Supply | 2010 | GR01 | 2010 | SMARTWORLD THE EDITION | Ram Niwas & SonsDeepak gupta | 9110001607 | 90 |  |  | 2026-03-11 | Steel Re-bar TMT 08 mm Dia. FE-550D | TO | 30 | 56800 | 1704000 | 2010720 | 1643224 | 1939004.32 | 60776 | 1643224 | 1939004.32 | ZMAT | 2026-03-11 | 2026-04-11
RE/0066-PRJ-T3-CIV-RS-SU | Reinforcement Supply | 2010 | GR01 | 2010 | SMARTWORLD THE EDITION | ESL STEEL LIMITED | 9110001613 | 30 |  |  | 2026-03-11 | Steel Re-bar TMT 12 mm Dia. FE-550D | TO | 37 | 58250 | 2155250 | 2543195 | 2155250 | 2543195 | 0 | 2155250 | 2543195 | ZMAT | 2026-03-11 | 2026-04-11
RE/0066-PRJ-T3-CIV-RS-SU | Reinforcement Supply | 2010 | GR01 | 2010 | SMARTWORLD THE EDITION | ESL STEEL LIMITED | 9110001613 | 90 |  |  | 2026-03-11 | Steel Re-bar TMT 16 mm Dia. FE-550D | TO | 30 | 58250 | 1747500 | 2062050 | 1747500 | 2062050 | 0 | 1747500 | 2062050 | ZMAT | 2026-03-11 | 2026-04-11
RE/0066-PRJ-T3-CIV-RS-SU | Reinforcement Supply | 2010 | GR01 | 2010 | SMARTWORLD THE EDITION | ESL STEEL LIMITED | 9110001613 | 150 |  |  | 2026-03-11 | Steel Re-bar TMT 20 mm Dia. FE-550D | TO | 27 | 58250 | 1572750 | 1855845 | 1572750 | 1855845 | 0 | 1572750 | 1855845 | ZMAT | 2026-03-11 | 2026-04-11
RE/0066-PRJ-T3-CIV-RS-SU | Reinforcement Supply | 2010 | GR01 | 2010 | SMARTWORLD THE EDITION | ESL STEEL LIMITED | 9110001613 | 210 |  |  | 2026-03-11 | Steel Re-bar TMT 25 mm Dia. FE-550D | TO | 25 | 58250 | 1456250 | 1718375 | 1456250 | 1718375 | 0 | 1456250 | 1718375 | ZMAT | 2026-03-11 | 2026-04-11
RE/0066-PRJ-T3-CIV-RS-SU | Reinforcement Supply | 2010 | GR01 | 2010 | SMARTWORLD THE EDITION | Ram Niwas & SonsDeepak gupta | 9110001691 | 30 |  |  | 2026-04-10 | Steel Re-bar TMT 08 mm Dia. FE-550D | TO | 33 | 60800 | 2006400 | 2367552 | 2006400 | 2367552 | 0 | 2006400 | 2367552 | ZMAT | 2026-04-10 | 2026-05-10
RE/0066-PRJ-T3-CIV-RS-SU | Reinforcement Supply | 2010 | GR01 | 2010 | SMARTWORLD THE EDITION | Ram Niwas & SonsDeepak gupta | 9110001691 | 90 |  |  | 2026-04-10 | Steel Re-bar TMT 10 mm Dia. FE-550D | TO | 8 | 59800 | 478400 | 564512 | 478400 | 564512 | 0 | 478400 | 564512 | ZMAT | 2026-04-10 | 2026-05-10
RE/0066-PRJ-T3-CIV-RS-SU | Reinforcement Supply | 2010 | GR01 | 2010 | SMARTWORLD THE EDITION | ESL STEEL LIMITED | 9110001698 | 30 |  |  | 2026-04-10 | Steel Re-bar TMT 12 mm Dia. FE-550D | TO | 43 | 60500 | 2601500 | 3069770 | 2601500 | 3069770 | 0 | 2601500 | 3069770 | ZMAT | 2026-04-10 | 2026-05-10
RE/0066-PRJ-T3-CIV-RS-SU | Reinforcement Supply | 2010 | GR01 | 2010 | SMARTWORLD THE EDITION | ESL STEEL LIMITED | 9110001698 | 90 |  |  | 2026-04-10 | Steel Re-bar TMT 16 mm Dia. FE-550D | TO | 8.5 | 60500 | 514250 | 606815 | 526350 | 621093 | 12100 | 526350 | 621093 | ZMAT | 2026-04-10 | 2026-05-10
RE/0066-PRJ-T3-CIV-RS-SU | Reinforcement Supply | 2010 | GR01 | 2010 | SMARTWORLD THE EDITION | ESL STEEL LIMITED | 9110001698 | 150 |  |  | 2026-04-10 | Steel Re-bar TMT 20 mm Dia. FE-550D | TO | 13 | 60500 | 786500 | 928070 | 786500 | 928070 | 0 | 786500 | 928070 | ZMAT | 2026-04-10 | 2026-05-10
RE/0066-PRJ-T3-CIV-RS-SU | Reinforcement Supply | 2010 | GR01 | 2010 | SMARTWORLD THE EDITION | ESL STEEL LIMITED | 9110001698 | 210 |  |  | 2026-04-10 | Steel Re-bar TMT 25 mm Dia. FE-550D | TO | 25 | 60500 | 1512500 | 1784750 | 1512500 | 1784750 | 0 | 1512500 | 1784750 | ZMAT | 2026-04-10 | 2026-05-10
RE/0066-PRJ-T3-CIV-RS-SU | Reinforcement Supply | 2010 | GR01 | 2010 | SMARTWORLD THE EDITION | ESL STEEL LIMITED | 9110001698 | 270 |  |  | 2026-04-10 | Steel Re-bar TMT 32 mm Dia. FE-550D | TO | 7 | 60500 | 423500 | 499730 | 423500 | 499730 | 0 | 423500 | 499730 | ZMAT | 2026-04-10 | 2026-05-10
RE/0066-PRJ-T3-CIV-RS-SU | Reinforcement Supply | 2010 | GR01 | 2010 | SMARTWORLD THE EDITION | Petropol India LimitedSANJAY GUPTA | 9110001791 | 30 |  |  | 2026-05-11 | Steel Re-bar TMT 08 mm Dia. FE-550D | TO | 53 | 55700 | 2952100 | 3483478 | 2952100 | 3483478 | 0 | 2952100 | 3483478 | ZMAT | 2026-05-11 | 2026-06-11
RE/0066-PRJ-T3-CIV-RS-SU | Reinforcement Supply | 2010 | GR01 | 2010 | SMARTWORLD THE EDITION | Petropol India LimitedSANJAY GUPTA | 9110001791 | 90 |  |  | 2026-05-11 | Steel Re-bar TMT 10 mm Dia. FE-550D | TO | 4 | 54700 | 218800 | 258184 | 218800 | 258184 | 0 | 218800 | 258184 | ZMAT | 2026-05-11 | 2026-06-11
RE/0066-PRJ-T3-CIV-RS-SU | Reinforcement Supply | 2010 | GR01 | 2010 | SMARTWORLD THE EDITION | Jindal Steel Limited | 9110001796 | 30 |  |  | 2026-05-11 | Steel Re-bar TMT 12 mm Dia. FE-550D | TO | 33 | 57200 | 1887600 | 2227368 | 1887600 | 2227368 | 0 | 0 | 0 | ZMAT | 2026-05-11 | 2026-06-11
RE/0066-PRJ-T3-CIV-RS-SU | Reinforcement Supply | 2010 | GR01 | 2010 | SMARTWORLD THE EDITION | Jindal Steel Limited | 9110001796 | 90 |  |  | 2026-05-11 | Steel Re-bar TMT 16 mm Dia. FE-550D | TO | 3 | 57200 | 171600 | 202488 | 85800 | 101244 | 85800 | 0 | 0 | ZMAT | 2026-05-11 | 2026-06-11
RE/0066-PRJ-T3-CIV-RS-SU | Reinforcement Supply | 2010 | GR01 | 2010 | SMARTWORLD THE EDITION | Jindal Steel Limited | 9110001796 | 150 |  |  | 2026-05-11 | Steel Re-bar TMT 20 mm Dia. FE-550D | TO | 29 | 57200 | 1658800 | 1957384 | 1658800 | 1957384 | 0 | 0 | 0 | ZMAT | 2026-05-11 | 2026-06-11
RE/0066-PRJ-T3-CIV-RS-SU | Reinforcement Supply | 2010 | GR01 | 2010 | SMARTWORLD THE EDITION | Jindal Steel Limited | 9110001796 | 210 |  |  | 2026-05-11 | Steel Re-bar TMT 25 mm Dia. FE-550D | TO | 13 | 57200 | 743600 | 877448 | 743600 | 877448 | 0 | 0 | 0 | ZMAT | 2026-05-11 | 2026-06-11
RE/0066-PRJ-T3-CIV-RS-SU | Reinforcement Supply | 2010 | GR01 | 2010 | SMARTWORLD THE EDITION | Jindal Steel Limited | 9110001796 | 270 |  |  | 2026-05-11 | Steel Re-bar TMT 32 mm Dia. FE-550D | TO | 4 | 57200 | 228800 | 269984 | 228800 | 269984 | 0 | 0 | 0 | ZMAT | 2026-05-11 | 2026-06-11
RE/0066-PRJ-T3-CIV-SW-AS | Aluminum Shuttering | 2010 | GR01 | 2010 | SMARTWORLD THE EDITION | Ahluwalia Contracts India Limited | 9140000321 | 50 |  |  | 2024-07-20 | CENTERING & SHUTTERING Part A | AU | 1 | 0 | 160754359.04 | 189690143.67 | 28349033.92 | 33451860.03 | 132405325.12 | 21260880.69 | 25087839.21 | ZSER | 2024-07-15 | 2027-01-14
RE/0066-PRJ-T3-CIV-SW-CS | Conventional Shuttering | 2010 | GR01 | 2010 | SMARTWORLD THE EDITION | Ahluwalia Contracts India Limited | 9140000321 | 50 |  |  | 2024-07-20 | CENTERING & SHUTTERING Part A | AU | 1 | 0 | 17822822.3 | 21030930.31 | 15673403.21 | 18494615.79 | 2149419.09 | 15673403.25 | 18494615.83 | ZSER | 2024-07-15 | 2027-01-14
RE/0066-PRJ-T3-CIV-SW-SO | Shuttering Other | 2010 | GR01 | 2010 |  |  |  | 0 | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
RE/0066-PRJ-T3-CIV-WP | Waterproofing Works | 2010 | GR01 | 2010 | SMARTWORLD THE EDITION | Ahluwalia Contracts India Limited | 9140000321 | 110 |  |  | 2024-07-20 | FLOORING | AU | 1 | 0 | 1433 | 1690.94 | 0 | 0 | 1433 | 0 | 0 | ZSER | 2024-07-15 | 2027-01-14
RE/0066-PRJ-T3-CIV-WP | Waterproofing Works | 2010 | GR01 | 2010 | SMARTWORLD THE EDITION | Ahluwalia Contracts India Limited | 9140000321 | 120 |  |  | 2024-07-20 | WATER-PROOFING WORKS | AU | 1 | 0 | 18474150.04 | 21799497.05 | 440146.86 | 519373.3 | 18034003.18 | 440146.86 | 519373.3 | ZSER | 2024-07-15 | 2027-01-14
RE/0066-PRJ-T3-FAC-EF | Elevation Feature | 2010 | GR01 | 2010 | SMARTWORLD THE EDITION | Ahluwalia Contracts India Limited | 9140000321 | 100 |  |  | 2024-07-20 | STRUCTURAL STEEL WORKS | AU | 1 | 0 | 0.01 | 0.01 | 0 | 0 | 0.01 | 0 | 0 | ZSER | 2024-07-15 | 2027-01-14
RE/0066-PRJ-T3-FAC-EP | External Paint | 2010 | GR01 | 2010 | SMARTWORLD THE EDITION | Ahluwalia Contracts India Limited | 9140000321 | 160 |  |  | 2024-07-20 | Amed-Monthly rental payment to M/S ACIL | AU | 1 | 0 | 4753600 | 5609248 | 0 | 0 | 4753600 | 0 | 0 | ZSER | 2024-07-15 | 2027-01-14
RE/0066-PRJ-T3-FAC-GL | Glazing Works | 2010 | GR01 | 2010 |  |  |  | 0 | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
RE/0066-PRJ-T3-FAC-RA | Railing Works | 2010 | GR01 | 2010 |  |  |  | 0 | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
RE/0066-PRJ-T3-FIS-CF | Ceiling Finish Works | 2010 | GR01 | 2010 |  |  |  | 0 | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
RE/0066-PRJ-T3-FIS-DW | Door Works | 2010 | GR01 | 2010 |  |  |  | 0 | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
RE/0066-PRJ-T3-FIS-FF | Floor Finish Works | 2010 | GR01 | 2010 | SMARTWORLD THE EDITION | Ahluwalia Contracts India Limited | 9140000321 | 110 |  |  | 2024-07-20 | FLOORING | AU | 1 | 0 | 9803437.89 | 11568056.71 | 0 | 0 | 9803437.89 | 0 | 0 | ZSER | 2024-07-15 | 2027-01-14
RE/0066-PRJ-T3-FIS-LF | Lobby Furniture | 2010 | GR01 | 2010 |  |  |  | 0 | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
RE/0066-PRJ-T3-FIS-MD | Modular Kitchen Works | 2010 | GR01 | 2010 |  |  |  | 0 | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
RE/0066-PRJ-T3-FIS-MF | Misc Finish Works | 2010 | GR01 | 2010 |  |  |  | 0 | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
RE/0066-PRJ-T3-FIS-MW | MS works | 2010 | GR01 | 2010 |  |  |  | 0 | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
RE/0066-PRJ-T3-FIS-WF | Wall Finish Works | 2010 | GR01 | 2010 |  |  |  | 0 | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
RE/0066-PRJ-T3-FIS-WO | Wood Work | 2010 | GR01 | 2010 |  |  |  | 0 | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
RE/0066-PRJ-T3-MEP-EW-HE | High Side Electrical Works | 2010 | GR01 | 2010 | SMARTWORLD THE EDITION | Dehn India Pvt Ltd | 9140000379 | 10 |  |  | 2024-10-24 | Lightning Protection System for Basement | AU | 1 | 0 | 922389 | 1088419.02 | 144535.06 | 170551.37 | 777853.94 | 144535.08 | 170551.4 | ZSER | 2024-10-24 | 2027-08-23
RE/0066-PRJ-T3-MEP-EW-HE | High Side Electrical Works | 2010 | GR01 | 2010 | SMARTWORLD THE EDITION | SATKARTAR ELECTRICALS AND ELECTRONIPRIVATE LIMITED | 9140000677 | 30 |  |  | 2026-06-02 | Electrical Works Tower T3 | AU | 1 | 18570917.92 | 14868927.92 | 17545334.95 | 0 | 0 | 14868927.92 | 0 | 0 | ZSER | 2026-06-01 | 2028-02-01
RE/0066-PRJ-T3-MEP-EW-HE | High Side Electrical Works | 2010 | GR01 | 2010 | SMARTWORLD THE EDITION | TRIPLE A ENGINEERING PRIVATE LIMIT | 9140000688 | 30 |  |  | 2026-06-06 | Electrical Works Tower T3 | AU | 1 | 50668654.85 | 13548994.71 | 13548994.71 | 0 | 0 | 13548994.71 | 0 | 0 | ZSER | 2026-06-01 | 2028-02-01
RE/0066-PRJ-T3-MEP-EW-LE | Low Side Electrical Works | 2010 | GR01 | 2010 | SMARTWORLD THE EDITION | Ahluwalia Contracts India Limited | 9140000321 | 140 |  |  | 2024-07-20 | CONDUITING | AU | 1 | 0 | 20097712.87 | 23715301.19 | 877036.35 | 1034902.89 | 19220676.52 | 575060.19 | 678571.03 | ZSER | 2024-07-15 | 2027-01-14
RE/0066-PRJ-T3-MEP-EW-LE | Low Side Electrical Works | 2010 | GR01 | 2010 | SMARTWORLD THE EDITION | SATKARTAR ELECTRICALS AND ELECTRONIPRIVATE LIMITED | 9140000677 | 30 |  |  | 2026-06-02 | Electrical Works Tower T3 | AU | 1 | 0 | 3701990 | 4368348.2 | 0 | 0 | 3701990 | 0 | 0 | ZSER | 2026-06-01 | 2028-02-01
RE/0066-PRJ-T3-MEP-EW-LE | Low Side Electrical Works | 2010 | GR01 | 2010 | SMARTWORLD THE EDITION | TRIPLE A ENGINEERING PRIVATE LIMIT | 9140000688 | 30 |  |  | 2026-06-06 | Electrical Works Tower T3 | AU | 1 | 0 | 37119660.14 | 37119660.14 | 0 | 0 | 37119660.14 | 0 | 0 | ZSER | 2026-06-01 | 2028-02-01
RE/0066-PRJ-T3-MEP-EW-LS | Light Fixtures Supply | 2010 | GR01 | 2010 |  |  |  | 0 | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
RE/0066-PRJ-T3-MEP-FF | Fire Fighting Work | 2010 | GR01 | 2010 | SMARTWORLD THE EDITION | Jagrati Civil Constructions Pvt Ltd | 9140000633 | 250 |  |  | 2026-04-15 | FF-FIRE HYDRANT & EQUIPMENT SUPPLY- T3 | AU | 1 | 3205680 | 3205680 | 3782702.4 | 0 | 0 | 3205680 | 0 | 0 | ZSER | 2026-04-08 | 2028-01-31
RE/0066-PRJ-T3-MEP-FF | Fire Fighting Work | 2010 | GR01 | 2010 | SMARTWORLD THE EDITION | Jagrati Civil Constructions Pvt Ltd | 9140000633 | 300 |  |  | 2026-04-15 | FF-AUTOMATIC SPRINKLER & WATER Supply-T3 | AU | 1 | 17451681.38 | 17451681.38 | 20592984.03 | 0 | 0 | 17451681.38 | 0 | 0 | ZSER | 2026-04-08 | 2028-01-31
RE/0066-PRJ-T3-MEP-FF | Fire Fighting Work | 2010 | GR01 | 2010 | SMARTWORLD THE EDITION | Jagrati Civil Constructions Pvt Ltd | 9140000633 | 350 |  |  | 2026-04-15 | FF-PORTABLE FIRE EXTINGUISHERS Supply-T3 | AU | 1 | 357000 | 357000 | 421260 | 0 | 0 | 357000 | 0 | 0 | ZSER | 2026-04-08 | 2028-01-31
RE/0066-PRJ-T3-MEP-HV-HS | High Side | 2010 | GR01 | 2010 |  |  |  | 0 | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
RE/0066-PRJ-T3-MEP-HV-LS | Low Side | 2010 | GR01 | 2010 |  |  |  | 0 | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
RE/0066-PRJ-T3-MEP-LT | Lifts | 2010 | GR01 | 2010 |  |  |  | 0 | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
RE/0066-PRJ-T3-MEP-PB-FS | Fixtures Supply | 2010 | GR01 | 2010 |  |  |  | 0 | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
RE/0066-PRJ-T3-MEP-PB-IP | Internal Plumbing | 2010 | GR01 | 2010 | SMARTWORLD THE EDITION | Jagrati Civil Constructions Pvt Ltd | 9140000633 | 40 |  |  | 2026-04-15 | SANITARY FIXTURES & FITTINGS INST. T-3 | AU | 1 | 4447825 | 4447825 | 5248433.5 | 0 | 0 | 4447825 | 0 | 0 | ZSER | 2026-04-08 | 2028-01-31
RE/0066-PRJ-T3-MEP-PB-IP | Internal Plumbing | 2010 | GR01 | 2010 | SMARTWORLD THE EDITION | Jagrati Civil Constructions Pvt Ltd | 9140000633 | 90 |  |  | 2026-04-15 | INTERNAL DRAINAGE SUPPLY(SOIL, WASTE T-3 | AU | 1 | 14003403.63 | 14003403.63 | 16524016.28 | 0 | 0 | 14003403.63 | 0 | 0 | ZSER | 2026-04-08 | 2028-01-31
RE/0066-PRJ-T3-MEP-PB-IP | Internal Plumbing | 2010 | GR01 | 2010 | SMARTWORLD THE EDITION | Jagrati Civil Constructions Pvt Ltd | 9140000633 | 140 |  |  | 2026-04-15 | DOMESTIC AND FLUSHING WATER SUPPLY T-3 | AU | 1 | 16024565.99 | 16024565.99 | 18908987.87 | 0 | 0 | 16024565.99 | 0 | 0 | ZSER | 2026-04-08 | 2028-01-31
RE/0066-PRJ-T3-MEP-PB-IP | Internal Plumbing | 2010 | GR01 | 2010 | SMARTWORLD THE EDITION | Jagrati Civil Constructions Pvt Ltd | 9140000633 | 190 |  |  | 2026-04-15 | MISCELLANEOUS ITEMS FOR TERRACE WATER-T3 | AU | 1 | 376700 | 376700 | 444506 | 0 | 0 | 376700 | 0 | 0 | ZSER | 2026-04-08 | 2028-01-31
RE/0066-PRJ-T3-MEP-PB-JC | JACUZZI | 2010 | GR01 | 2010 |  |  |  | 0 | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
RE/0066-PRJ-T3-MEP-PN | PNG Gas Pipe Line | 2010 | GR01 | 2010 |  |  |  | 0 | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
RE/0066-PRJ-T4-CIV-CC-LA | Concrete Labour | 2010 | GR01 | 2010 |  |  |  | 0 | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
RE/0066-PRJ-T4-CIV-CC-SL | Concrete Supply & Labour | 2010 | GR01 | 2010 | SMARTWORLD THE EDITION | Ahluwalia Contracts India Limited | 9140000321 | 20 |  |  | 2024-07-20 | REINFORCED CEMENT CONCRETE-I part A | AU | 1 | 0 | 112357982.58 | 132582419.44 | 59992036.45 | 70790603.01 | 52365946.13 | 59992036.51 | 70790603.08 | ZSER | 2024-07-15 | 2027-01-14
RE/0066-PRJ-T4-CIV-CC-SL | Concrete Supply & Labour | 2010 | GR01 | 2010 | SMARTWORLD THE EDITION | Ahluwalia Contracts India Limited | 9140000321 | 30 |  |  | 2024-07-20 | REINFORCED CEMENT CONCRETE-I Part B | AU | 1 | 0 | 88774726.87 | 104754177.71 | 37705579.37 | 44492583.66 | 51069147.5 | 30414934.03 | 35889622.16 | ZSER | 2024-07-15 | 2027-01-14
RE/0066-PRJ-T4-CIV-CC-SL | Concrete Supply & Labour | 2010 | GR01 | 2010 | SMARTWORLD THE EDITION | Ahluwalia Contracts India Limited | 9140000321 | 40 |  |  | 2024-07-20 | REINFORCED CEMENT CONCRETE-I Part C | AU | 1 | 0 | 115756630.82 | 136592824.37 | 32868263.64 | 38784551.1 | 82888367.18 | 27256324.14 | 32162462.48 | ZSER | 2024-07-15 | 2027-01-14
RE/0066-PRJ-T4-CIV-CC-SL | Concrete Supply & Labour | 2010 | GR01 | 2010 | SMARTWORLD THE EDITION | Ahluwalia Contracts India Limited | 9140000321 | 180 |  |  | 2024-07-20 | SUBSTITUTE ITEM | AU | 1 | 0 | 1266038.72 | 1493925.69 | 861485.37 | 1016552.74 | 404553.35 | 857532.68 | 1011888.56 | ZSER | 2024-07-15 | 2027-01-14
RE/0066-PRJ-T4-CIV-CC-SU | Concrete Supply | 2010 | GR01 | 2010 |  |  |  | 0 | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
RE/0066-PRJ-T4-CIV-EW | Earthwork | 2010 | GR01 | 2010 | SMARTWORLD THE EDITION | Ahluwalia Contracts India Limited | 9140000321 | 10 |  |  | 2024-07-20 | SITE DEVLOPMENT AND EARTH WORK | AU | 1 | 0 | 1497014 | 1766476.52 | 324307.49 | 382682.84 | 1172706.51 | 324307.49 | 382682.84 | ZSER | 2024-07-15 | 2027-01-14
RE/0066-PRJ-T4-CIV-MS | Misc Structure Works | 2010 | GR01 | 2010 | SMARTWORLD THE EDITION | Ahluwalia Contracts India Limited | 9140000321 | 100 |  |  | 2024-07-20 | STRUCTURAL STEEL WORKS | AU | 1 | 0 | 37828694.68 | 44637859.72 | 2989937.77 | 3528126.57 | 34838756.91 | 2166475.45 | 2556441.03 | ZSER | 2024-07-15 | 2027-01-14
RE/0066-PRJ-T4-CIV-MS | Misc Structure Works | 2010 | GR01 | 2010 | SMARTWORLD THE EDITION | Ahluwalia Contracts India Limited | 9140000321 | 130 |  |  | 2024-07-20 | INTERNAL & EXTERNAL PLASTERING | AU | 1 | 0 | 607320 | 716637.6 | 0 | 0 | 607320 | 0 | 0 | ZSER | 2024-07-15 | 2027-01-14
RE/0066-PRJ-T4-CIV-MS | Misc Structure Works | 2010 | GR01 | 2010 | SMARTWORLD THE EDITION | Ahluwalia Contracts India Limited | 9140000321 | 160 |  |  | 2024-07-20 | Amed-Monthly rental payment to M/S ACIL | AU | 1 | 0 | 1230377.3 | 1451845.21 | 238512.79 | 281445.09 | 991864.51 | 0 | 0 | ZSER | 2024-07-15 | 2027-01-14
RE/0066-PRJ-T4-CIV-MW | Masonry Works | 2010 | GR01 | 2010 | SMARTWORLD THE EDITION | Ahluwalia Contracts India Limited | 9140000321 | 90 |  |  | 2024-07-20 | MASONARY WORKS | AU | 1 | 0 | 8702363.87 | 10268789.37 | 1133181.36 | 1337154.01 | 7569182.51 | 1133181.36 | 1337154.01 | ZSER | 2024-07-15 | 2027-01-14
RE/0066-PRJ-T4-CIV-PW-IP | Internal Plaster | 2010 | GR01 | 2010 | SMARTWORLD THE EDITION | Ahluwalia Contracts India Limited | 9140000321 | 130 |  |  | 2024-07-20 | INTERNAL & EXTERNAL PLASTERING | AU | 1 | 0 | 7172048 | 8463016.64 | 0 | 0 | 7172048 | 0 | 0 | ZSER | 2024-07-15 | 2027-01-14
RE/0066-PRJ-T4-CIV-PW-XP | External Plaster | 2010 | GR01 | 2010 | SMARTWORLD THE EDITION | Ahluwalia Contracts India Limited | 9140000321 | 130 |  |  | 2024-07-20 | INTERNAL & EXTERNAL PLASTERING | AU | 1 | 0 | 225900 | 266562 | 0 | 0 | 225900 | 0 | 0 | ZSER | 2024-07-15 | 2027-01-14
RE/0066-PRJ-T4-CIV-RS-LA | Reinforcement Labour | 2010 | GR01 | 2010 | SMARTWORLD THE EDITION | Ahluwalia Contracts India Limited | 9140000321 | 70 |  |  | 2024-07-20 | REINFORCEMENT STEEL Installation Part A | AU | 1 | 0 | 147752692 | 174348176.56 | 62298705.69 | 73512472.72 | 85453986.31 | 56910143.39 | 67153969.2 | ZSER | 2024-07-15 | 2027-01-14
RE/0066-PRJ-T4-CIV-RS-LA | Reinforcement Labour | 2010 | GR01 | 2010 | SMARTWORLD THE EDITION | Ahluwalia Contracts India Limited | 9140000321 | 80 |  |  | 2024-07-20 | REINFORCEMENT STEEL Installation Part B | AU | 1 | 0 | 12987413.89 | 15325148.39 | 4527343.71 | 5342265.58 | 8460070.18 | 4217973 | 4977208.14 | ZSER | 2024-07-15 | 2027-01-14
RE/0066-PRJ-T4-CIV-RS-SU | Reinforcement Supply | 2010 | GR01 | 2010 | SMARTWORLD THE EDITION | Northern Steel and General MillsPrivate Limited | 9110000774 | 90 |  |  | 2024-11-15 | Steel Re-bar TMT 20 mm Dia. FE-550D | TO | 9 | 54500 | 490500 | 578790 | 490500 | 578790 | 0 | 490500 | 578790 | ZMAT | 2025-01-20 | 2025-03-20
RE/0066-PRJ-T4-CIV-RS-SU | Reinforcement Supply | 2010 | GR01 | 2010 | SMARTWORLD THE EDITION | Northern Steel and General MillsPrivate Limited | 9110000774 | 160 |  |  | 2024-11-15 | Steel Re-bar TMT 25 mm Dia. FE-550D | TO | 39.5 | 54500 | 2152750 | 2540245 | 2152750 | 2540245 | 0 | 2152750 | 2540245 | ZMAT | 2025-01-20 | 2025-03-20
RE/0066-PRJ-T4-CIV-RS-SU | Reinforcement Supply | 2010 | GR01 | 2010 | SMARTWORLD THE EDITION | Jindal Steel Limited | 9110000777 | 40 |  |  | 2024-11-15 | Steel Re-bar TMT 20 mm Dia. FE-550D | TO | 11.5 | 54500 | 626750 | 739565 | 626750 | 739565 | 0 | 626750 | 739565 | ZMAT | 2025-01-20 | 2025-03-20
RE/0066-PRJ-T4-CIV-RS-SU | Reinforcement Supply | 2010 | GR01 | 2010 | SMARTWORLD THE EDITION | Jindal Steel Limited | 9110000777 | 110 |  |  | 2024-11-15 | Steel Re-bar TMT 25 mm Dia. FE-550D | TO | 29 | 54500 | 1580500 | 1864990 | 1580500 | 1864990 | 0 | 1580500 | 1864990 | ZMAT | 2025-01-20 | 2025-03-20
RE/0066-PRJ-T4-CIV-RS-SU | Reinforcement Supply | 2010 | GR01 | 2010 | SMARTWORLD THE EDITION | Jindal Steel Limited | 9110000777 | 180 |  |  | 2024-11-15 | Steel Re-bar TMT 32 mm Dia. FE-550D | TO | 131 | 54500 | 7139500 | 8424610 | 7139500 | 8424610 | 0 | 7139500 | 8424610 | ZMAT | 2025-01-20 | 2025-03-20
RE/0066-PRJ-T4-CIV-RS-SU | Reinforcement Supply | 2010 | GR01 | 2010 | SMARTWORLD THE EDITION | Carna Corporation Pvt LtdVISHWANATH | 9110000779 | 40 |  |  | 2024-11-16 | Steel Re-bar TMT 20 mm Dia. FE-550D | TO | 11 | 54500 | 599500 | 707410 | 599500 | 707410 | 0 | 599500 | 707410 | ZMAT | 2025-01-20 | 2025-03-20
RE/0066-PRJ-T4-CIV-RS-SU | Reinforcement Supply | 2010 | GR01 | 2010 | SMARTWORLD THE EDITION | Carna Corporation Pvt LtdVISHWANATH | 9110000779 | 110 |  |  | 2024-11-16 | Steel Re-bar TMT 25 mm Dia. FE-550D | TO | 31 | 54500 | 1689500 | 1993610 | 1689500 | 1993610 | 0 | 1689500 | 1993610 | ZMAT | 2025-01-20 | 2025-03-20
RE/0066-PRJ-T4-CIV-RS-SU | Reinforcement Supply | 2010 | GR01 | 2010 | SMARTWORLD THE EDITION | Carna Corporation Pvt LtdVISHWANATH | 9110000779 | 180 |  |  | 2024-11-16 | Steel Re-bar TMT 32 mm Dia. FE-550D | TO | 370.89 | 54500 | 20213505 | 23851935.9 | 20213505 | 23851935.9 | 0 | 20213505 | 23851935.9 | ZMAT | 2025-01-20 | 2025-03-20
RE/0066-PRJ-T4-CIV-RS-SU | Reinforcement Supply | 2010 | GR01 | 2010 | SMARTWORLD THE EDITION | Rashtriya Ispat Nigam Ltd | 9110000790 | 50 |  |  | 2024-11-29 | Fe 550D TMT Steel Coil 10MM | TO | 4 | 54450 | 217800 | 257004 | 226512 | 267284.16 | 8712 | 226512 | 267284.16 | ZMAT | 2024-11-29 | 2024-12-28
RE/0066-PRJ-T4-CIV-RS-SU | Reinforcement Supply | 2010 | GR01 | 2010 | SMARTWORLD THE EDITION | Rashtriya Ispat Nigam Ltd | 9110000790 | 120 |  |  | 2024-11-29 | Fe 550D TMT Steel Coil 12MM | TO | 8 | 53950 | 431600 | 509288 | 323700 | 381966 | 107900 | 323700 | 381966 | ZMAT | 2024-11-29 | 2024-12-28
RE/0066-PRJ-T4-CIV-RS-SU | Reinforcement Supply | 2010 | GR01 | 2010 | SMARTWORLD THE EDITION | Carna Corporation Pvt LtdVISHWANATH | 9110000837 | 40 |  |  | 2025-01-09 | Steel Re-bar TMT 08 mm Dia. FE-550D | TO | 1 | 51400 | 51400 | 60652 | 51400 | 60652 | 0 | 51400 | 60652 | ZMAT | 2025-01-20 | 2025-03-20
RE/0066-PRJ-T4-CIV-RS-SU | Reinforcement Supply | 2010 | GR01 | 2010 | SMARTWORLD THE EDITION | Carna Corporation Pvt LtdVISHWANATH | 9110000837 | 70 |  |  | 2025-01-09 | Steel Re-bar TMT 10 mm Dia. FE-550D | TO | 44 | 50150 | 2206600 | 2603788 | 2352887.55 | 2776407.31 | 146287.55 | 2352887.55 | 2776407.31 | ZMAT | 2025-01-20 | 2025-03-20
RE/0066-PRJ-T4-CIV-RS-SU | Reinforcement Supply | 2010 | GR01 | 2010 | SMARTWORLD THE EDITION | Jindal Steel Limited | 9110000859 | 20 |  |  | 2025-02-15 | Steel Re-bar TMT 12 mm Dia. FE-550D | TO | 30 | 50900 | 1527000 | 1801860 | 1277201.78 | 1507098.1 | 249798.22 | 1507098.1 | 1778375.76 | ZMAT
RE/0066-PRJ-T4-CIV-RS-SU | Reinforcement Supply | 2010 | GR01 | 2010 | SMARTWORLD THE EDITION | Jindal Steel Limited | 9110000859 | 40 |  |  | 2025-02-15 | Steel Re-bar TMT 16 mm Dia. FE-550D | TO | 42 | 50900 | 2137800 | 2522604 | 1823945.42 | 2152255.6 | 313854.58 | 2152255.6 | 2539661.61 | ZMAT
RE/0066-PRJ-T4-CIV-RS-SU | Reinforcement Supply | 2010 | GR01 | 2010 | SMARTWORLD THE EDITION | Jindal Steel Limited | 9110000859 | 70 |  |  | 2025-02-15 | Steel Re-bar TMT 20 mm Dia. FE-550D | TO | 22 | 50900 | 1119800 | 1321364 | 862711.86 | 1018000 | 257088.14 | 1018000 | 1201240 | ZMAT
RE/0066-PRJ-T4-CIV-RS-SU | Reinforcement Supply | 2010 | GR01 | 2010 | SMARTWORLD THE EDITION | Ram Niwas & SonsDeepak gupta | 9110000862 | 20 |  |  | 2025-02-15 | Steel Re-bar TMT 08 mm Dia. FE-550D | TO | 7.5 | 51200 | 384000 | 453120 | 385536 | 454932.48 | 1536 | 385536 | 454932.48 | ZMAT
RE/0066-PRJ-T4-CIV-RS-SU | Reinforcement Supply | 2010 | GR01 | 2010 | SMARTWORLD THE EDITION | Ram Niwas & SonsDeepak gupta | 9110000862 | 60 |  |  | 2025-02-15 | Steel Re-bar TMT 10 mm Dia. FE-550D | TO | 60 | 50200 | 3012000 | 3554160 | 3012000 | 3554160 | 0 | 3012000 | 3554160 | ZMAT
RE/0066-PRJ-T4-CIV-RS-SU | Reinforcement Supply | 2010 | GR01 | 2010 | SMARTWORLD THE EDITION | PRAGYAN METALS PRIVATE LIMITED | 9110000868 | 20 |  |  | 2025-02-18 | Steel Re-bar TMT 16 mm Dia. FE-550D | TO | 34 | 50900 | 1730600 | 2042108 | 1466610.17 | 1730600 | 263989.83 | 1730600 | 2042108.02 | ZMAT
RE/0066-PRJ-T4-CIV-RS-SU | Reinforcement Supply | 2010 | GR01 | 2010 | SMARTWORLD THE EDITION | Jindal Steel Limited | 9110000886 | 40 |  |  | 2025-03-12 | Steel Re-bar TMT 12 mm Dia. FE-550D | TO | 15 | 54750 | 821250 | 969075 | 876000 | 1033680 | 54750 | 876000 | 1033680 | ZMAT
RE/0066-PRJ-T4-CIV-RS-SU | Reinforcement Supply | 2010 | GR01 | 2010 | SMARTWORLD THE EDITION | Jindal Steel Limited | 9110000886 | 100 |  |  | 2025-03-12 | Steel Re-bar TMT 16 mm Dia. FE-550D | TO | 25 | 54750 | 1368750 | 1615125 | 1368750 | 1615125 | 0 | 1368750 | 1615125 | ZMAT
RE/0066-PRJ-T4-CIV-RS-SU | Reinforcement Supply | 2010 | GR01 | 2010 | SMARTWORLD THE EDITION | Jindal Steel Limited | 9110000886 | 160 |  |  | 2025-03-12 | Steel Re-bar TMT 20 mm Dia. FE-550D | TO | 20 | 54750 | 1095000 | 1292100 | 1095000.01 | 1292100.01 | 0.01 | 1095000 | 1292100.01 | ZMAT
RE/0066-PRJ-T4-CIV-RS-SU | Reinforcement Supply | 2010 | GR01 | 2010 | SMARTWORLD THE EDITION | Ram Niwas & SonsDeepak gupta | 9110000887 | 40 |  |  | 2025-03-12 | Steel Re-bar TMT 10 mm Dia. FE-550D | TO | 10.5 | 52900 | 555450 | 655431 | 555450 | 655431 | 0 | 555450 | 655431 | ZMAT
RE/0066-PRJ-T4-CIV-RS-SU | Reinforcement Supply | 2010 | GR01 | 2010 | SMARTWORLD THE EDITION | Carna Corporation Pvt LtdVISHWANATH | 9110000889 | 40 |  |  | 2025-03-12 | Steel Re-bar TMT 10 mm Dia. FE-550D | TO | 4.5 | 55500 | 249750 | 294705 | 249750 | 294705 | 0 | 249750 | 294705 | ZMAT
RE/0066-PRJ-T4-CIV-RS-SU | Reinforcement Supply | 2010 | GR01 | 2010 | SMARTWORLD THE EDITION | Rashtriya Ispat Nigam Ltd | 9110000961 | 40 |  |  | 2025-04-08 | Fe 550D TMT Steel Coil 10MM | TO | 9 | 58750 | 528750 | 623925 | 528750 | 623925 | 0 | 528750 | 623925 | ZMAT
RE/0066-PRJ-T4-CIV-RS-SU | Reinforcement Supply | 2010 | GR01 | 2010 | SMARTWORLD THE EDITION | Rashtriya Ispat Nigam Ltd | 9110000961 | 110 |  |  | 2025-04-08 | Fe 550D TMT Steel Coil 08MM | TO | 9 | 60000 | 540000 | 637200 | 540000 | 637200 | 0 | 540000 | 637200 | ZMAT
RE/0066-PRJ-T4-CIV-RS-SU | Reinforcement Supply | 2010 | GR01 | 2010 | SMARTWORLD THE EDITION | Vikrant Ispat Udyog | 9110000966 | 40 |  |  | 2025-04-09 | Fe 550D TMT Steel Coil 10MM | TO | 3 | 64250 | 192750 | 227445 | 192750 | 227445 | 0 | 192750 | 227445 | ZMAT
RE/0066-PRJ-T4-CIV-RS-SU | Reinforcement Supply | 2010 | GR01 | 2010 | SMARTWORLD THE EDITION | Vikrant Ispat Udyog | 9110000966 | 110 |  |  | 2025-04-09 | Fe 550D TMT Steel Coil 08MM | TO | 3 | 65750 | 197250 | 232755 | 197250 | 232755 | 0 | 197250 | 232755 | ZMAT
RE/0066-PRJ-T4-CIV-RS-SU | Reinforcement Supply | 2010 | GR01 | 2010 | SMARTWORLD THE EDITION | Petropol India LimitedSANJAY GUPTA | 9110000993 | 20 |  |  | 2025-04-17 | Steel Re-bar TMT 10 mm Dia. FE-550D | TO | 40 | 56000 | 2240000 | 2643200 | 2124640 | 2507075.2 | 115360 | 2124640 | 2507075.2 | ZMAT | 2025-04-17 | 2025-04-30
RE/0066-PRJ-T4-CIV-RS-SU | Reinforcement Supply | 2010 | GR01 | 2010 | SMARTWORLD THE EDITION | Sapcon Steels Private Limited | 9110000999 | 60 |  |  | 2025-04-18 | Fe 550D TMT Steel Coil 10MM | TO | 40 | 58250 | 2330000 | 2749400 | 2330000 | 2749400 | 0 | 2330000 | 2749400 | ZMAT | 2025-04-11 | 2025-04-30
RE/0066-PRJ-T4-CIV-RS-SU | Reinforcement Supply | 2010 | GR01 | 2010 | SMARTWORLD THE EDITION | Sapcon Steels Private Limited | 9110001009 | 40 |  |  | 2025-04-28 | Steel Re-bar TMT 32 mm Dia. FE-550D | TO | 11 | 57000 | 627000 | 739860 | 399000 | 470820 | 228000 | 399000 | 470820 | ZMAT
RE/0066-PRJ-T4-CIV-RS-SU | Reinforcement Supply | 2010 | GR01 | 2010 | SMARTWORLD THE EDITION | Jindal Steel Limited | 9110001055 | 40 |  |  | 2025-05-17 | Steel Re-bar TMT 20 mm Dia. FE-550D | TO | 10 | 54850 | 548500 | 647230 | 548500 | 647230 | 0 | 548500 | 647230 | ZMAT | 2025-05-29 | 2025-06-29
RE/0066-PRJ-T4-CIV-RS-SU | Reinforcement Supply | 2010 | GR01 | 2010 | SMARTWORLD THE EDITION | Jindal Steel Limited | 9110001055 | 110 |  |  | 2025-05-17 | Steel Re-bar TMT 25 mm Dia. FE-550D | TO | 33 | 54850 | 1810050 | 2135859 | 1864900 | 2200582 | 54850 | 1864900 | 2200582 | ZMAT | 2025-05-29 | 2025-06-29
RE/0066-PRJ-T4-CIV-RS-SU | Reinforcement Supply | 2010 | GR01 | 2010 | SMARTWORLD THE EDITION | Jindal Steel Limited | 9110001055 | 180 |  |  | 2025-05-17 | Steel Re-bar TMT 32 mm Dia. FE-550D | TO | 15 | 54850 | 822750 | 970845 | 822750 | 970845 | 0 | 822750 | 970845 | ZMAT | 2025-05-29 | 2025-06-29
RE/0066-PRJ-T4-CIV-RS-SU | Reinforcement Supply | 2010 | GR01 | 2010 | SMARTWORLD THE EDITION | Jindal Steel Limited | 9110001073 | 50 |  |  | 2025-05-27 | Steel Re-bar TMT 12 mm Dia. FE-550D | TO | 10 | 57750 | 577500 | 681450 | 577500 | 681450 | 0 | 577500 | 681450 | ZMAT
RE/0066-PRJ-T4-CIV-RS-SU | Reinforcement Supply | 2010 | GR01 | 2010 | SMARTWORLD THE EDITION | Jindal Steel Limited | 9110001073 | 120 |  |  | 2025-05-27 | Steel Re-bar TMT 16 mm Dia. FE-550D | TO | 20 | 57750 | 1155000 | 1362900 | 1155000.01 | 1362900.01 | 0.01 | 1155000 | 1362900.01 | ZMAT
RE/0066-PRJ-T4-CIV-RS-SU | Reinforcement Supply | 2010 | GR01 | 2010 | SMARTWORLD THE EDITION | JINDAL STEEL LIMITEDMr Robin Taneja | 9110001079 | 40 |  |  | 2025-05-29 | Steel Re-bar TMT 25 mm Dia. FE-550D | TO | 12 | 54850 | 658200 | 776676 | 658200 | 776676 | 0 | 658200 | 776676 | ZMAT | 2025-05-29 | 2025-06-29
RE/0066-PRJ-T4-CIV-RS-SU | Reinforcement Supply | 2010 | GR01 | 2010 | SMARTWORLD THE EDITION | Ram Niwas & SonsDeepak gupta | 9110001126 | 40 |  |  | 2025-06-20 | Steel Re-bar TMT 08 mm Dia. FE-550D | TO | 10 | 51000 | 510000 | 601800 | 510000 | 601800 | 0 | 510000 | 601800 | ZMAT | 2025-06-20 | 2025-07-20
RE/0066-PRJ-T4-CIV-RS-SU | Reinforcement Supply | 2010 | GR01 | 2010 | SMARTWORLD THE EDITION | Jindal Steel Limited | 9110001127 | 40 |  |  | 2025-06-20 | Steel Re-bar TMT 12 mm Dia. FE-550D | TO | 30 | 50600 | 1518000 | 1791240 | 1518000 | 1791240 | 0 | 1518000 | 1791240 | ZMAT | 2025-06-20 | 2025-07-20
RE/0066-PRJ-T4-CIV-RS-SU | Reinforcement Supply | 2010 | GR01 | 2010 | SMARTWORLD THE EDITION | Jindal Steel Limited | 9110001127 | 120 |  |  | 2025-06-20 | Steel Re-bar TMT 16 mm Dia. FE-550D | TO | 25 | 50600 | 1265000 | 1492700 | 1265000 | 1492700 | 0 | 1265000 | 1492700 | ZMAT | 2025-06-20 | 2025-07-20
RE/0066-PRJ-T4-CIV-RS-SU | Reinforcement Supply | 2010 | GR01 | 2010 | SMARTWORLD THE EDITION | Jindal Steel Limited | 9110001127 | 200 |  |  | 2025-06-20 | Steel Re-bar TMT 20 mm Dia. FE-550D | TO | 15 | 50600 | 759000 | 895620 | 759000 | 895620 | 0 | 759000 | 895620 | ZMAT | 2025-06-20 | 2025-07-20
RE/0066-PRJ-T4-CIV-RS-SU | Reinforcement Supply | 2010 | GR01 | 2010 | SMARTWORLD THE EDITION | Jindal Steel Limited | 9110001127 | 270 |  |  | 2025-06-20 | Steel Re-bar TMT 25 mm Dia. FE-550D | TO | 20 | 50600 | 1012000 | 1194160 | 1012000 | 1194160 | 0 | 1012000 | 1194160 | ZMAT | 2025-06-20 | 2025-07-20
RE/0066-PRJ-T4-CIV-RS-SU | Reinforcement Supply | 2010 | GR01 | 2010 | SMARTWORLD THE EDITION | Jindal Steel Limited | 9110001127 | 350 |  |  | 2025-06-20 | Steel Re-bar TMT 32 mm Dia. FE-550D | TO | 10 | 50600 | 506000 | 597080 | 549971.4 | 648966.25 | 43971.4 | 549971.4 | 648966.25 | ZMAT | 2025-06-20 | 2025-07-20
RE/0066-PRJ-T4-CIV-RS-SU | Reinforcement Supply | 2010 | GR01 | 2010 | SMARTWORLD THE EDITION | Jindal Steel Limited | 9110001162 | 40 |  |  | 2025-07-17 | Steel Re-bar TMT 10 mm Dia. FE-550D | TO | 40 | 47500 | 1900000 | 2242000 | 0 | 0 | 1900000 | 0 | 0 | ZMAT | 2025-07-17 | 2025-08-17
RE/0066-PRJ-T4-CIV-RS-SU | Reinforcement Supply | 2010 | GR01 | 2010 | SMARTWORLD THE EDITION | Jindal Steel Limited | 9110001162 | 120 |  |  | 2025-07-17 | Steel Re-bar TMT 12 mm Dia. FE-550D | TO | 15 | 46500 | 697500 | 823050 | 0 | 0 | 697500 | 0 | 0 | ZMAT | 2025-07-17 | 2025-08-17
RE/0066-PRJ-T4-CIV-RS-SU | Reinforcement Supply | 2010 | GR01 | 2010 | SMARTWORLD THE EDITION | Jindal Steel Limited | 9110001162 | 200 |  |  | 2025-07-17 | Steel Re-bar TMT 16 mm Dia. FE-550D | TO | 5 | 46500 | 232500 | 274350 | 0 | 0 | 232500 | 0 | 0 | ZMAT | 2025-07-17 | 2025-08-17
RE/0066-PRJ-T4-CIV-RS-SU | Reinforcement Supply | 2010 | GR01 | 2010 | SMARTWORLD THE EDITION | Jindal Steel Limited | 9110001162 | 260 |  |  | 2025-07-17 | Steel Re-bar TMT 20 mm Dia. FE-550D | TO | 5 | 46500 | 232500 | 274350 | 0 | 0 | 232500 | 0 | 0 | ZMAT | 2025-07-17 | 2025-08-17
RE/0066-PRJ-T4-CIV-RS-SU | Reinforcement Supply | 2010 | GR01 | 2010 | SMARTWORLD THE EDITION | Jindal Steel Limited | 9110001162 | 330 |  |  | 2025-07-17 | Steel Re-bar TMT 25 mm Dia. FE-550D | TO | 5 | 46500 | 232500 | 274350 | 0 | 0 | 232500 | 0 | 0 | ZMAT | 2025-07-17 | 2025-08-17
RE/0066-PRJ-T4-CIV-RS-SU | Reinforcement Supply | 2010 | GR01 | 2010 | SMARTWORLD THE EDITION | Jindal Steel Limited | 9110001162 | 410 |  |  | 2025-07-17 | Steel Re-bar TMT 32 mm Dia. FE-550D | TO | 5 | 46500 | 232500 | 274350 | 0 | 0 | 232500 | 0 | 0 | ZMAT | 2025-07-17 | 2025-08-17
RE/0066-PRJ-T4-CIV-RS-SU | Reinforcement Supply | 2010 | GR01 | 2010 | SMARTWORLD THE EDITION | Steel Authority Of India LTD | 9110001194 | 20 |  |  | 2025-08-06 | Steel Re-bar TMT 32 mm Dia. FE-550D | TO | 0.1 | 0.1 | 0.01 | 0.01 | 0 | 0 | 0.01 | 0 | 0 | ZMAT | 2025-08-05 | 2025-09-05
RE/0066-PRJ-T4-CIV-RS-SU | Reinforcement Supply | 2010 | GR01 | 2010 | SMARTWORLD THE EDITION | Rashtriya Ispat Nigam Ltd | 9110001212 | 40 |  |  | 2025-08-14 | Steel Re-bar TMT 08 mm Dia. FE-550D | TO | 10 | 49300 | 493000 | 581740 | 493000 | 581740 | 0 | 493000 | 581740 | ZMAT | 2025-08-14 | 2025-09-14
RE/0066-PRJ-T4-CIV-RS-SU | Reinforcement Supply | 2010 | GR01 | 2010 | SMARTWORLD THE EDITION | Rashtriya Ispat Nigam Ltd | 9110001212 | 100 |  |  | 2025-08-14 | Steel Re-bar TMT 10 mm Dia. FE-550D | TO | 55 | 47800 | 2629000 | 3102220 | 2629000 | 3102220 | 0 | 2629000 | 3102220 | ZMAT | 2025-08-14 | 2025-09-14
RE/0066-PRJ-T4-CIV-RS-SU | Reinforcement Supply | 2010 | GR01 | 2010 | SMARTWORLD THE EDITION | Jindal Steel Limited | 9110001213 | 40 |  |  | 2025-08-14 | Steel Re-bar TMT 12 mm Dia. FE-550D | TO | 35 | 47000 | 1645000 | 1941100 | 1610784 | 1900725.12 | 34216 | 1610784 | 1900725.12 | ZMAT | 2025-08-14 | 2025-09-14
RE/0066-PRJ-T4-CIV-RS-SU | Reinforcement Supply | 2010 | GR01 | 2010 | SMARTWORLD THE EDITION | Jindal Steel Limited | 9110001213 | 100 |  |  | 2025-08-14 | Steel Re-bar TMT 16 mm Dia. FE-550D | TO | 10 | 47000 | 470000 | 554600 | 470000 | 554600 | 0 | 470000 | 554600 | ZMAT | 2025-08-14 | 2025-09-14
RE/0066-PRJ-T4-CIV-RS-SU | Reinforcement Supply | 2010 | GR01 | 2010 | SMARTWORLD THE EDITION | Jindal Steel Limited | 9110001213 | 160 |  |  | 2025-08-14 | Steel Re-bar TMT 20 mm Dia. FE-550D | TO | 10 | 47000 | 470000 | 554600 | 470000 | 554600 | 0 | 470000 | 554600 | ZMAT | 2025-08-14 | 2025-09-14
RE/0066-PRJ-T4-CIV-RS-SU | Reinforcement Supply | 2010 | GR01 | 2010 | SMARTWORLD THE EDITION | Jindal Steel Limited | 9110001213 | 220 |  |  | 2025-08-14 | Steel Re-bar TMT 25 mm Dia. FE-550D | TO | 20 | 47000 | 940000 | 1109200 | 905596 | 1068603.28 | 34404 | 905596 | 1068603.28 | ZMAT | 2025-08-14 | 2025-09-14
RE/0066-PRJ-T4-CIV-RS-SU | Reinforcement Supply | 2010 | GR01 | 2010 | SMARTWORLD THE EDITION | Jindal Steel Limited | 9110001213 | 280 |  |  | 2025-08-14 | Steel Re-bar TMT 32 mm Dia. FE-550D | TO | 20 | 47000 | 940000 | 1109200 | 940000 | 1109200 | 0 | 940000 | 1109200 | ZMAT | 2025-08-14 | 2025-09-14
RE/0066-PRJ-T4-CIV-RS-SU | Reinforcement Supply | 2010 | GR01 | 2010 | SMARTWORLD THE EDITION | STEEL AUTHORITY OF INDIA LIMITED | 9110001272 | 20 |  |  | 2025-09-13 | Steel Re-bar TMT 32 mm Dia. FE-550D | TO | 60 | 48760 | 2925600 | 3452208 | 2815890 | 3322750.2 | 109710 | 2815890 | 3322750.2 | ZMAT
RE/0066-PRJ-T4-CIV-RS-SU | Reinforcement Supply | 2010 | GR01 | 2010 | SMARTWORLD THE EDITION | Steel Authority Of India LTD | 9110001280 | 50 |  |  | 2025-09-18 | Steel Re-bar TMT 12 mm Dia. FE-550D | TO | 27 | 46260 | 1249020 | 1473843.6 | 1249020 | 1473843.6 | 0 | 1249020 | 1473843.61 | ZMAT | 2025-09-18 | 2025-10-18
RE/0066-PRJ-T4-CIV-RS-SU | Reinforcement Supply | 2010 | GR01 | 2010 | SMARTWORLD THE EDITION | Steel Authority Of India LTD | 9110001280 | 110 |  |  | 2025-09-18 | Steel Re-bar TMT 16 mm Dia. FE-550D | TO | 20 | 46260 | 925200 | 1091736 | 925200 | 1091736 | 0 | 925200 | 1091736 | ZMAT | 2025-09-18 | 2025-10-18
RE/0066-PRJ-T4-CIV-RS-SU | Reinforcement Supply | 2010 | GR01 | 2010 | SMARTWORLD THE EDITION | Steel Authority Of India LTD | 9110001280 | 170 |  |  | 2025-09-18 | Steel Re-bar TMT 20 mm Dia. FE-550D | TO | 25 | 46260 | 1156500 | 1364670 | 1156500.01 | 1364670.01 | 0.01 | 1156500 | 1364670.01 | ZMAT | 2025-09-18 | 2025-10-18
RE/0066-PRJ-T4-CIV-RS-SU | Reinforcement Supply | 2010 | GR01 | 2010 | SMARTWORLD THE EDITION | Steel Authority Of India LTD | 9110001280 | 230 |  |  | 2025-09-18 | Steel Re-bar TMT 25 mm Dia. FE-550D | TO | 13 | 46260 | 601380 | 709628.4 | 601380 | 709628.4 | 0 | 601380 | 709628.41 | ZMAT | 2025-09-18 | 2025-10-18
RE/0066-PRJ-T4-CIV-RS-SU | Reinforcement Supply | 2010 | GR01 | 2010 | SMARTWORLD THE EDITION | Steel Authority Of India LTD | 9110001280 | 290 |  |  | 2025-09-18 | Steel Re-bar TMT 32 mm Dia. FE-550D | TO | 11.25 | 46260 | 520425 | 614101.5 | 520425 | 614101.5 | 0 | 520425 | 614101.5 | ZMAT | 2025-09-18 | 2025-10-18
RE/0066-PRJ-T4-CIV-RS-SU | Reinforcement Supply | 2010 | GR01 | 2010 | SMARTWORLD THE EDITION | Steel Authority Of India LTD | 9110001280 | 320 |  |  | 2025-09-18 | Steel Re-bar TMT 10 mm Dia. FE-550D | TO | 16.68 | 47260 | 788296.8 | 930190.22 | 788296.8 | 930190.22 | 0 | 788296.8 | 930190.23 | ZMAT | 2025-09-18 | 2025-10-18
RE/0066-PRJ-T4-CIV-RS-SU | Reinforcement Supply | 2010 | GR01 | 2010 | SMARTWORLD THE EDITION | Ram Niwas & SonsDeepak gupta | 9110001305 | 40 |  |  | 2025-10-09 | Steel Re-bar TMT 08 mm Dia. FE-550D | TO | 6 | 47500 | 285000 | 336300 | 285000 | 336300 | 0 | 285000 | 336300 | ZMAT | 2025-10-09 | 2025-11-08
RE/0066-PRJ-T4-CIV-RS-SU | Reinforcement Supply | 2010 | GR01 | 2010 | SMARTWORLD THE EDITION | Ram Niwas & SonsDeepak gupta | 9110001305 | 100 |  |  | 2025-10-09 | Steel Re-bar TMT 10 mm Dia. FE-550D | TO | 28 | 46500 | 1302000 | 1536360 | 1086705 | 1282311.9 | 215295 | 1086705 | 1282311.9 | ZMAT | 2025-10-09 | 2025-11-08
RE/0066-PRJ-T4-CIV-RS-SU | Reinforcement Supply | 2010 | GR01 | 2010 | SMARTWORLD THE EDITION | Jindal Steel Limited | 9110001307 | 40 |  |  | 2025-10-09 | Steel Re-bar TMT 12 mm Dia. FE-550D | TO | 5 | 46500 | 232500 | 274350 | 232500 | 274350 | 0 | 232500 | 274350 | ZMAT | 2025-10-09 | 2025-11-08
RE/0066-PRJ-T4-CIV-RS-SU | Reinforcement Supply | 2010 | GR01 | 2010 | SMARTWORLD THE EDITION | Jindal Steel Limited | 9110001307 | 100 |  |  | 2025-10-09 | Steel Re-bar TMT 16 mm Dia. FE-550D | TO | 20 | 46500 | 930000 | 1097400 | 335404.5 | 395777.31 | 594595.5 | 335404.5 | 395777.31 | ZMAT | 2025-10-09 | 2025-11-08
RE/0066-PRJ-T4-CIV-RS-SU | Reinforcement Supply | 2010 | GR01 | 2010 | SMARTWORLD THE EDITION | Jindal Steel Limited | 9110001307 | 160 |  |  | 2025-10-09 | Steel Re-bar TMT 20 mm Dia. FE-550D | TO | 20 | 46500 | 930000 | 1097400 | 1000819.5 | 1180967.01 | 70819.5 | 1000819.5 | 1180967.01 | ZMAT | 2025-10-09 | 2025-11-08
RE/0066-PRJ-T4-CIV-RS-SU | Reinforcement Supply | 2010 | GR01 | 2010 | SMARTWORLD THE EDITION | Jindal Steel Limited | 9110001307 | 220 |  |  | 2025-10-09 | Steel Re-bar TMT 25 mm Dia. FE-550D | TO | 17 | 46500 | 790500 | 932790 | 790500 | 932790 | 0 | 790500 | 932790 | ZMAT | 2025-10-09 | 2025-11-08
RE/0066-PRJ-T4-CIV-RS-SU | Reinforcement Supply | 2010 | GR01 | 2010 | SMARTWORLD THE EDITION | Jindal Steel Limited | 9110001307 | 280 |  |  | 2025-10-09 | Steel Re-bar TMT 32 mm Dia. FE-550D | TO | 17 | 46500 | 790500 | 932790 | 790500 | 932790 | 0 | 790500 | 932790 | ZMAT | 2025-10-09 | 2025-11-08
RE/0066-PRJ-T4-CIV-RS-SU | Reinforcement Supply | 2010 | GR01 | 2010 | SMARTWORLD THE EDITION | Jindal Steel Limited | 9110001361 | 40 |  |  | 2025-11-07 | Steel Re-bar TMT 12 mm Dia. FE-550D | TO | 33 | 46100 | 1521300 | 1795134 | 1521300 | 1795134 | 0 | 1521300 | 1795134 | ZMAT | 2025-11-07 | 2025-12-07
RE/0066-PRJ-T4-CIV-RS-SU | Reinforcement Supply | 2010 | GR01 | 2010 | SMARTWORLD THE EDITION | Jindal Steel Limited | 9110001361 | 100 |  |  | 2025-11-07 | Steel Re-bar TMT 16 mm Dia. FE-550D | TO | 25 | 46100 | 1152500 | 1359950 | 1162964.69 | 1372298.34 | 10464.69 | 1162964.7 | 1372298.34 | ZMAT | 2025-11-07 | 2025-12-07
RE/0066-PRJ-T4-CIV-RS-SU | Reinforcement Supply | 2010 | GR01 | 2010 | SMARTWORLD THE EDITION | Jindal Steel Limited | 9110001361 | 160 |  |  | 2025-11-07 | Steel Re-bar TMT 20 mm Dia. FE-550D | TO | 8 | 46100 | 368800 | 435184 | 368800 | 435184 | 0 | 368800 | 435184 | ZMAT | 2025-11-07 | 2025-12-07
RE/0066-PRJ-T4-CIV-RS-SU | Reinforcement Supply | 2010 | GR01 | 2010 | SMARTWORLD THE EDITION | Jindal Steel Limited | 9110001361 | 220 |  |  | 2025-11-07 | Steel Re-bar TMT 25 mm Dia. FE-550D | TO | 30 | 46100 | 1383000 | 1631940 | 1383000 | 1631940 | 0 | 1383000 | 1631940 | ZMAT | 2025-11-07 | 2025-12-07
RE/0066-PRJ-T4-CIV-RS-SU | Reinforcement Supply | 2010 | GR01 | 2010 | SMARTWORLD THE EDITION | Jindal Steel Limited | 9110001361 | 280 |  |  | 2025-11-07 | Steel Re-bar TMT 32 mm Dia. FE-550D | TO | 8 | 46100 | 368800 | 435184 | 368800 | 435184 | 0 | 368800 | 435184 | ZMAT | 2025-11-07 | 2025-12-07
RE/0066-PRJ-T4-CIV-RS-SU | Reinforcement Supply | 2010 | GR01 | 2010 | SMARTWORLD THE EDITION | Ram Niwas & SonsDeepak gupta | 9110001362 | 40 |  |  | 2025-11-07 | Steel Re-bar TMT 08 mm Dia. FE-550D | TO | 2.5 | 46900 | 117250 | 138355 | 117250 | 138355 | 0 | 117250 | 138355 | ZMAT | 2025-11-07 | 2025-12-07
RE/0066-PRJ-T4-CIV-RS-SU | Reinforcement Supply | 2010 | GR01 | 2010 | SMARTWORLD THE EDITION | Ram Niwas & SonsDeepak gupta | 9110001362 | 90 |  |  | 2025-11-07 | Steel Re-bar TMT 10 mm Dia. FE-550D | TO | 38.13 | 45900 | 1750167 | 2065197.06 | 1649187 | 1946040.66 | 100980 | 1649187 | 1946040.66 | ZMAT | 2025-11-07 | 2025-12-07
RE/0066-PRJ-T4-CIV-RS-SU | Reinforcement Supply | 2010 | GR01 | 2010 | SMARTWORLD THE EDITION | Ram Niwas & SonsDeepak gupta | 9110001421 | 40 |  |  | 2025-12-10 | Steel Re-bar TMT 10 mm Dia. FE-550D | TO | 22 | 46500 | 1023000 | 1207140 | 1020675 | 1204396.5 | 2325 | 1020675 | 1204396.5 | ZMAT | 2025-12-10 | 2026-01-10
RE/0066-PRJ-T4-CIV-RS-SU | Reinforcement Supply | 2010 | GR01 | 2010 | SMARTWORLD THE EDITION | Ram Niwas & SonsDeepak gupta | 9110001421 | 100 |  |  | 2025-12-10 | Steel Re-bar TMT 08 mm Dia. FE-550D | TO | 12 | 47500 | 570000 | 672600 | 570000 | 672600 | 0 | 570000 | 672600 | ZMAT | 2025-12-10 | 2026-01-10
RE/0066-PRJ-T4-CIV-RS-SU | Reinforcement Supply | 2010 | GR01 | 2010 | SMARTWORLD THE EDITION | Jindal Steel Limited | 9110001422 | 40 |  |  | 2025-12-10 | Steel Re-bar TMT 12 mm Dia. FE-550D | TO | 20 | 46400 | 928000 | 1095040 | 928000 | 1095040 | 0 | 928000 | 1095040 | ZMAT | 2025-12-10 | 2026-01-10
RE/0066-PRJ-T4-CIV-RS-SU | Reinforcement Supply | 2010 | GR01 | 2010 | SMARTWORLD THE EDITION | Jindal Steel Limited | 9110001422 | 100 |  |  | 2025-12-10 | Steel Re-bar TMT 16 mm Dia. FE-550D | TO | 18 | 46400 | 835200 | 985536 | 825131.2 | 973654.82 | 10068.8 | 825131.2 | 973654.82 | ZMAT | 2025-12-10 | 2026-01-10
RE/0066-PRJ-T4-CIV-RS-SU | Reinforcement Supply | 2010 | GR01 | 2010 | SMARTWORLD THE EDITION | Jindal Steel Limited | 9110001422 | 160 |  |  | 2025-12-10 | Steel Re-bar TMT 20 mm Dia. FE-550D | TO | 13 | 46400 | 603200 | 711776 | 603200 | 711776 | 0 | 603200 | 711776 | ZMAT | 2025-12-10 | 2026-01-10
RE/0066-PRJ-T4-CIV-RS-SU | Reinforcement Supply | 2010 | GR01 | 2010 | SMARTWORLD THE EDITION | Jindal Steel Limited | 9110001422 | 220 |  |  | 2025-12-10 | Steel Re-bar TMT 25 mm Dia. FE-550D | TO | 15 | 46400 | 696000 | 821280 | 696000 | 821280 | 0 | 696000 | 821280 | ZMAT | 2025-12-10 | 2026-01-10
RE/0066-PRJ-T4-CIV-RS-SU | Reinforcement Supply | 2010 | GR01 | 2010 | SMARTWORLD THE EDITION | Ram Niwas & SonsDeepak gupta | 9110001471 | 40 |  |  | 2026-01-12 | Steel Re-bar TMT 08 mm Dia. FE-550D | TO | 10 | 52000 | 520000 | 613600 | 520000 | 613600 | 0 | 520000 | 613600 | ZMAT | 2026-01-12 | 2026-02-12
RE/0066-PRJ-T4-CIV-RS-SU | Reinforcement Supply | 2010 | GR01 | 2010 | SMARTWORLD THE EDITION | ESL STEEL LIMITED | 9110001481 | 40 |  |  | 2026-01-12 | Steel Re-bar TMT 12 mm Dia. FE-550D | TO | 42 | 51800 | 2175600 | 2567208 | 1915253.2 | 2259998.78 | 260346.8 | 1915253.2 | 2259998.78 | ZMAT | 2026-01-12 | 2026-02-12
RE/0066-PRJ-T4-CIV-RS-SU | Reinforcement Supply | 2010 | GR01 | 2010 | SMARTWORLD THE EDITION | ESL STEEL LIMITED | 9110001481 | 100 |  |  | 2026-01-12 | Steel Re-bar TMT 16 mm Dia. FE-550D | TO | 2 | 51800 | 103600 | 122248 | 103600 | 122248 | 0 | 103600 | 122248 | ZMAT | 2026-01-12 | 2026-02-12
RE/0066-PRJ-T4-CIV-RS-SU | Reinforcement Supply | 2010 | GR01 | 2010 | SMARTWORLD THE EDITION | ESL STEEL LIMITED | 9110001481 | 160 |  |  | 2026-01-12 | Steel Re-bar TMT 20 mm Dia. FE-550D | TO | 25 | 51800 | 1295000 | 1528100 | 1295000 | 1528100 | 0 | 1295000 | 1528100 | ZMAT | 2026-01-12 | 2026-02-12
RE/0066-PRJ-T4-CIV-RS-SU | Reinforcement Supply | 2010 | GR01 | 2010 | SMARTWORLD THE EDITION | ESL STEEL LIMITED | 9110001481 | 220 |  |  | 2026-01-12 | Steel Re-bar TMT 25 mm Dia. FE-550D | TO | 8 | 51800 | 414400 | 488992 | 414400 | 488992 | 0 | 414400 | 488992 | ZMAT | 2026-01-12 | 2026-02-12
RE/0066-PRJ-T4-CIV-RS-SU | Reinforcement Supply | 2010 | GR01 | 2010 | SMARTWORLD THE EDITION | Ram Niwas & SonsDeepak gupta | 9110001541 | 40 |  |  | 2026-02-07 | Steel Re-bar TMT 08 mm Dia. FE-550D | TO | 7 | 55300 | 387100 | 456778 | 386547 | 456125.46 | 553 | 386547 | 456125.46 | ZMAT | 2026-02-07 | 2026-03-31
RE/0066-PRJ-T4-CIV-RS-SU | Reinforcement Supply | 2010 | GR01 | 2010 | SMARTWORLD THE EDITION | Ram Niwas & SonsDeepak gupta | 9110001541 | 100 |  |  | 2026-02-07 | Steel Re-bar TMT 10 mm Dia. FE-550D | TO | 12 | 54300 | 651600 | 768888 | 648342 | 765043.56 | 3258 | 648342 | 765043.56 | ZMAT | 2026-02-07 | 2026-03-31
RE/0066-PRJ-T4-CIV-RS-SU | Reinforcement Supply | 2010 | GR01 | 2010 | SMARTWORLD THE EDITION | Petropol India LimitedSANJAY GUPTA | 9110001546 | 40 |  |  | 2026-02-07 | Steel Re-bar TMT 08 mm Dia. FE-550D | TO | 7 | 55300 | 387100 | 456778 | 387100 | 456778 | 0 | 387100 | 456778 | ZMAT | 2026-02-07 | 2026-03-31
RE/0066-PRJ-T4-CIV-RS-SU | Reinforcement Supply | 2010 | GR01 | 2010 | SMARTWORLD THE EDITION | Petropol India LimitedSANJAY GUPTA | 9110001546 | 100 |  |  | 2026-02-07 | Steel Re-bar TMT 10 mm Dia. FE-550D | TO | 15 | 54300 | 814500 | 961110 | 811785 | 957906.3 | 2715 | 811785 | 957906.3 | ZMAT | 2026-02-07 | 2026-03-31
RE/0066-PRJ-T4-CIV-RS-SU | Reinforcement Supply | 2010 | GR01 | 2010 | SMARTWORLD THE EDITION | Jindal Steel Limited | 9110001551 | 40 |  |  | 2026-02-07 | Steel Re-bar TMT 12 mm Dia. FE-550D | TO | 27 | 58500 | 1579500 | 1863810 | 1573650 | 1856907 | 5850 | 1573650 | 1856907 | ZMAT | 2026-02-07 | 2026-03-07
RE/0066-PRJ-T4-CIV-RS-SU | Reinforcement Supply | 2010 | GR01 | 2010 | SMARTWORLD THE EDITION | Jindal Steel Limited | 9110001551 | 100 |  |  | 2026-02-07 | Steel Re-bar TMT 16 mm Dia. FE-550D | TO | 30 | 58500 | 1755000 | 2070900 | 1749150 | 2063997 | 5850 | 1749150 | 2063997 | ZMAT | 2026-02-07 | 2026-03-07
RE/0066-PRJ-T4-CIV-RS-SU | Reinforcement Supply | 2010 | GR01 | 2010 | SMARTWORLD THE EDITION | Jindal Steel Limited | 9110001551 | 160 |  |  | 2026-02-07 | Steel Re-bar TMT 20 mm Dia. FE-550D | TO | 3 | 58500 | 175500 | 207090 | 0 | 0 | 175500 | 0 | 0 | ZMAT | 2026-02-07 | 2026-03-07
RE/0066-PRJ-T4-CIV-RS-SU | Reinforcement Supply | 2010 | GR01 | 2010 | SMARTWORLD THE EDITION | Jindal Steel Limited | 9110001551 | 220 |  |  | 2026-02-07 | Steel Re-bar TMT 25 mm Dia. FE-550D | TO | 20 | 58500 | 1170000 | 1380600 | 1169415 | 1379909.7 | 585 | 1169415 | 1379909.7 | ZMAT | 2026-02-07 | 2026-03-07
RE/0066-PRJ-T4-CIV-RS-SU | Reinforcement Supply | 2010 | GR01 | 2010 | SMARTWORLD THE EDITION | Jindal Steel Limited | 9110001557 | 40 |  |  | 2026-02-10 | Steel Re-bar TMT 12 mm Dia. FE-550D | TO | 27 | 58500 | 1579500 | 1863810 | 1564290 | 1845862.2 | 15210 | 1564290 | 1845862.2 | ZMAT | 2026-02-10 | 2026-03-10
RE/0066-PRJ-T4-CIV-RS-SU | Reinforcement Supply | 2010 | GR01 | 2010 | SMARTWORLD THE EDITION | Jindal Steel Limited | 9110001557 | 100 |  |  | 2026-02-10 | Steel Re-bar TMT 25 mm Dia. FE-550D | TO | 48 | 58500 | 2808000 | 3313440 | 2802442.5 | 3306882.15 | 5557.5 | 2802442.5 | 3306882.15 | ZMAT | 2026-02-10 | 2026-03-10
RE/0066-PRJ-T4-CIV-RS-SU | Reinforcement Supply | 2010 | GR01 | 2010 | SMARTWORLD THE EDITION | Jindal Steel Limited | 9110001557 | 160 |  |  | 2026-02-10 | Steel Re-bar TMT 32 mm Dia. FE-550D | TO | 15 | 58500 | 877500 | 1035450 | 913360.5 | 1077765.39 | 35860.5 | 913360.5 | 1077765.39 | ZMAT | 2026-02-10 | 2026-03-10
RE/0066-PRJ-T4-CIV-RS-SU | Reinforcement Supply | 2010 | GR01 | 2010 | SMARTWORLD THE EDITION | Petropol India LimitedSANJAY GUPTA | 9110001558 | 40 |  |  | 2026-02-10 | Steel Re-bar TMT 08 mm Dia. FE-550D | TO | 18 | 55300 | 995400 | 1174572 | 994847 | 1173919.46 | 553 | 994847 | 1173919.46 | ZMAT | 2026-02-10 | 2026-03-10
RE/0066-PRJ-T4-CIV-RS-SU | Reinforcement Supply | 2010 | GR01 | 2010 | SMARTWORLD THE EDITION | Ram Niwas & SonsDeepak gupta | 9110001607 | 40 |  |  | 2026-03-11 | Steel Re-bar TMT 10 mm Dia. FE-550D | TO | 37 | 55800 | 2064600 | 2436228 | 2064600 | 2436228 | 0 | 2064600 | 2436228 | ZMAT | 2026-03-11 | 2026-04-11
RE/0066-PRJ-T4-CIV-RS-SU | Reinforcement Supply | 2010 | GR01 | 2010 | SMARTWORLD THE EDITION | Ram Niwas & SonsDeepak gupta | 9110001607 | 100 |  |  | 2026-03-11 | Steel Re-bar TMT 08 mm Dia. FE-550D | TO | 30 | 56800 | 1704000 | 2010720 | 1704000 | 2010720 | 0 | 1704000 | 2010720 | ZMAT | 2026-03-11 | 2026-04-11
RE/0066-PRJ-T4-CIV-RS-SU | Reinforcement Supply | 2010 | GR01 | 2010 | SMARTWORLD THE EDITION | ESL STEEL LIMITED | 9110001613 | 40 |  |  | 2026-03-11 | Steel Re-bar TMT 12 mm Dia. FE-550D | TO | 37 | 58250 | 2155250 | 2543195 | 2156997.51 | 2545257.06 | 1747.51 | 2156997.5 | 2545257.06 | ZMAT | 2026-03-11 | 2026-04-11
RE/0066-PRJ-T4-CIV-RS-SU | Reinforcement Supply | 2010 | GR01 | 2010 | SMARTWORLD THE EDITION | ESL STEEL LIMITED | 9110001613 | 100 |  |  | 2026-03-11 | Steel Re-bar TMT 16 mm Dia. FE-550D | TO | 30 | 58250 | 1747500 | 2062050 | 1747500 | 2062050 | 0 | 1747500 | 2062050 | ZMAT | 2026-03-11 | 2026-04-11
RE/0066-PRJ-T4-CIV-RS-SU | Reinforcement Supply | 2010 | GR01 | 2010 | SMARTWORLD THE EDITION | ESL STEEL LIMITED | 9110001613 | 160 |  |  | 2026-03-11 | Steel Re-bar TMT 20 mm Dia. FE-550D | TO | 27 | 58250 | 1572750 | 1855845 | 1572750 | 1855845 | 0 | 1572750 | 1855845 | ZMAT | 2026-03-11 | 2026-04-11
RE/0066-PRJ-T4-CIV-RS-SU | Reinforcement Supply | 2010 | GR01 | 2010 | SMARTWORLD THE EDITION | ESL STEEL LIMITED | 9110001613 | 220 |  |  | 2026-03-11 | Steel Re-bar TMT 25 mm Dia. FE-550D | TO | 25 | 58250 | 1456250 | 1718375 | 1456250 | 1718375 | 0 | 1456250 | 1718375 | ZMAT | 2026-03-11 | 2026-04-11
RE/0066-PRJ-T4-CIV-RS-SU | Reinforcement Supply | 2010 | GR01 | 2010 | SMARTWORLD THE EDITION | Ram Niwas & SonsDeepak gupta | 9110001691 | 40 |  |  | 2026-04-10 | Steel Re-bar TMT 08 mm Dia. FE-550D | TO | 33 | 60800 | 2006400 | 2367552 | 2006400 | 2367552 | 0 | 2006400 | 2367552 | ZMAT | 2026-04-10 | 2026-05-10
RE/0066-PRJ-T4-CIV-RS-SU | Reinforcement Supply | 2010 | GR01 | 2010 | SMARTWORLD THE EDITION | Ram Niwas & SonsDeepak gupta | 9110001691 | 100 |  |  | 2026-04-10 | Steel Re-bar TMT 10 mm Dia. FE-550D | TO | 8 | 59800 | 478400 | 564512 | 478400 | 564512 | 0 | 478400 | 564512 | ZMAT | 2026-04-10 | 2026-05-10
RE/0066-PRJ-T4-CIV-RS-SU | Reinforcement Supply | 2010 | GR01 | 2010 | SMARTWORLD THE EDITION | ESL STEEL LIMITED | 9110001698 | 40 |  |  | 2026-04-10 | Steel Re-bar TMT 12 mm Dia. FE-550D | TO | 43 | 60500 | 2601500 | 3069770 | 2587464 | 3053207.52 | 14036 | 2587464 | 3053207.52 | ZMAT | 2026-04-10 | 2026-05-10
RE/0066-PRJ-T4-CIV-RS-SU | Reinforcement Supply | 2010 | GR01 | 2010 | SMARTWORLD THE EDITION | ESL STEEL LIMITED | 9110001698 | 100 |  |  | 2026-04-10 | Steel Re-bar TMT 16 mm Dia. FE-550D | TO | 8.5 | 60500 | 514250 | 606815 | 526350 | 621093 | 12100 | 526350 | 621093 | ZMAT | 2026-04-10 | 2026-05-10
RE/0066-PRJ-T4-CIV-RS-SU | Reinforcement Supply | 2010 | GR01 | 2010 | SMARTWORLD THE EDITION | ESL STEEL LIMITED | 9110001698 | 160 |  |  | 2026-04-10 | Steel Re-bar TMT 20 mm Dia. FE-550D | TO | 13 | 60500 | 786500 | 928070 | 786500 | 928070 | 0 | 786500 | 928070 | ZMAT | 2026-04-10 | 2026-05-10
RE/0066-PRJ-T4-CIV-RS-SU | Reinforcement Supply | 2010 | GR01 | 2010 | SMARTWORLD THE EDITION | ESL STEEL LIMITED | 9110001698 | 220 |  |  | 2026-04-10 | Steel Re-bar TMT 25 mm Dia. FE-550D | TO | 25 | 60500 | 1512500 | 1784750 | 1512500 | 1784750 | 0 | 1512500 | 1784750 | ZMAT | 2026-04-10 | 2026-05-10
RE/0066-PRJ-T4-CIV-RS-SU | Reinforcement Supply | 2010 | GR01 | 2010 | SMARTWORLD THE EDITION | ESL STEEL LIMITED | 9110001698 | 280 |  |  | 2026-04-10 | Steel Re-bar TMT 32 mm Dia. FE-550D | TO | 7 | 60500 | 423500 | 499730 | 423500 | 499730 | 0 | 423500 | 499730 | ZMAT | 2026-04-10 | 2026-05-10
RE/0066-PRJ-T4-CIV-RS-SU | Reinforcement Supply | 2010 | GR01 | 2010 | SMARTWORLD THE EDITION | Petropol India LimitedSANJAY GUPTA | 9110001791 | 40 |  |  | 2026-05-11 | Steel Re-bar TMT 08 mm Dia. FE-550D | TO | 53 | 55700 | 2952100 | 3483478 | 2934276 | 3462445.68 | 17824 | 2934276 | 3462445.68 | ZMAT | 2026-05-11 | 2026-06-11
RE/0066-PRJ-T4-CIV-RS-SU | Reinforcement Supply | 2010 | GR01 | 2010 | SMARTWORLD THE EDITION | Petropol India LimitedSANJAY GUPTA | 9110001791 | 100 |  |  | 2026-05-11 | Steel Re-bar TMT 10 mm Dia. FE-550D | TO | 4 | 54700 | 218800 | 258184 | 218800 | 258184 | 0 | 218800 | 258184 | ZMAT | 2026-05-11 | 2026-06-11
RE/0066-PRJ-T4-CIV-RS-SU | Reinforcement Supply | 2010 | GR01 | 2010 | SMARTWORLD THE EDITION | Jindal Steel Limited | 9110001796 | 40 |  |  | 2026-05-11 | Steel Re-bar TMT 12 mm Dia. FE-550D | TO | 33 | 57200 | 1887600 | 2227368 | 1887600 | 2227368 | 0 | 0 | 0 | ZMAT | 2026-05-11 | 2026-06-11
RE/0066-PRJ-T4-CIV-RS-SU | Reinforcement Supply | 2010 | GR01 | 2010 | SMARTWORLD THE EDITION | Jindal Steel Limited | 9110001796 | 100 |  |  | 2026-05-11 | Steel Re-bar TMT 16 mm Dia. FE-550D | TO | 3 | 57200 | 171600 | 202488 | 85800 | 101244 | 85800 | 0 | 0 | ZMAT | 2026-05-11 | 2026-06-11
RE/0066-PRJ-T4-CIV-RS-SU | Reinforcement Supply | 2010 | GR01 | 2010 | SMARTWORLD THE EDITION | Jindal Steel Limited | 9110001796 | 160 |  |  | 2026-05-11 | Steel Re-bar TMT 20 mm Dia. FE-550D | TO | 29 | 57200 | 1658800 | 1957384 | 1658800 | 1957384 | 0 | 0 | 0 | ZMAT | 2026-05-11 | 2026-06-11
RE/0066-PRJ-T4-CIV-RS-SU | Reinforcement Supply | 2010 | GR01 | 2010 | SMARTWORLD THE EDITION | Jindal Steel Limited | 9110001796 | 220 |  |  | 2026-05-11 | Steel Re-bar TMT 25 mm Dia. FE-550D | TO | 13 | 57200 | 743600 | 877448 | 743600 | 877448 | 0 | 0 | 0 | ZMAT | 2026-05-11 | 2026-06-11
RE/0066-PRJ-T4-CIV-RS-SU | Reinforcement Supply | 2010 | GR01 | 2010 | SMARTWORLD THE EDITION | Jindal Steel Limited | 9110001796 | 280 |  |  | 2026-05-11 | Steel Re-bar TMT 32 mm Dia. FE-550D | TO | 3 | 57200 | 171600 | 202488 | 147404.4 | 173937.19 | 24195.6 | 0 | 0 | ZMAT | 2026-05-11 | 2026-06-11
RE/0066-PRJ-T4-CIV-SW-AS | Aluminum Shuttering | 2010 | GR01 | 2010 | SMARTWORLD THE EDITION | Ahluwalia Contracts India Limited | 9140000321 | 60 |  |  | 2024-07-20 | CENTERING & SHUTTERING Part B | AU | 1 | 0 | 166845866.85 | 196878122.88 | 31962244.01 | 37715447.93 | 134883622.84 | 23971683.01 | 28286585.95 | ZSER | 2024-07-15 | 2027-01-14
RE/0066-PRJ-T4-CIV-SW-CS | Conventional Shuttering | 2010 | GR01 | 2010 | SMARTWORLD THE EDITION | Ahluwalia Contracts India Limited | 9140000321 | 50 |  |  | 2024-07-20 | CENTERING & SHUTTERING Part A | AU | 1 | 0 | 18288880.44 | 21580878.92 | 15982353.89 | 18859177.59 | 2306526.55 | 15982353.96 | 18859177.67 | ZSER | 2024-07-15 | 2027-01-14
RE/0066-PRJ-T4-CIV-SW-SO | Shuttering Other | 2010 | GR01 | 2010 |  |  |  | 0 | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
RE/0066-PRJ-T4-CIV-WP | Waterproofing Works | 2010 | GR01 | 2010 | SMARTWORLD THE EDITION | Ahluwalia Contracts India Limited | 9140000321 | 110 |  |  | 2024-07-20 | FLOORING | AU | 1 | 0 | 1433 | 1690.94 | 0 | 0 | 1433 | 0 | 0 | ZSER | 2024-07-15 | 2027-01-14
RE/0066-PRJ-T4-CIV-WP | Waterproofing Works | 2010 | GR01 | 2010 | SMARTWORLD THE EDITION | Ahluwalia Contracts India Limited | 9140000321 | 120 |  |  | 2024-07-20 | WATER-PROOFING WORKS | AU | 1 | 0 | 18999762.04 | 22419719.21 | 440146.86 | 519373.3 | 18559615.18 | 440146.86 | 519373.3 | ZSER | 2024-07-15 | 2027-01-14
RE/0066-PRJ-T4-FAC-EL | Elevation Feature | 2010 | GR01 | 2010 | SMARTWORLD THE EDITION | Ahluwalia Contracts India Limited | 9140000321 | 100 |  |  | 2024-07-20 | STRUCTURAL STEEL WORKS | AU | 1 | 0 | 0.01 | 0.01 | 0 | 0 | 0.01 | 0 | 0 | ZSER | 2024-07-15 | 2027-01-14
RE/0066-PRJ-T4-FAC-EP | External Paint | 2010 | GR01 | 2010 | SMARTWORLD THE EDITION | Ahluwalia Contracts India Limited | 9140000321 | 160 |  |  | 2024-07-20 | Amed-Monthly rental payment to M/S ACIL | AU | 1 | 0 | 4866880 | 5742918.4 | 0 | 0 | 4866880 | 0 | 0 | ZSER | 2024-07-15 | 2027-01-14
RE/0066-PRJ-T4-FAC-GL | Glazing Works | 2010 | GR01 | 2010 |  |  |  | 0 | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
RE/0066-PRJ-T4-FAC-RA | Railing Works | 2010 | GR01 | 2010 |  |  |  | 0 | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
RE/0066-PRJ-T4-FIS-CF | Ceiling Finish Works | 2010 | GR01 | 2010 |  |  |  | 0 | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
RE/0066-PRJ-T4-FIS-DW | Door Works | 2010 | GR01 | 2010 |  |  |  | 0 | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
RE/0066-PRJ-T4-FIS-FF | Floor Finish Works | 2010 | GR01 | 2010 | SMARTWORLD THE EDITION | Ahluwalia Contracts India Limited | 9140000321 | 110 |  |  | 2024-07-20 | FLOORING | AU | 1 | 0 | 10332769.24 | 12192667.7 | 0 | 0 | 10332769.24 | 0 | 0 | ZSER | 2024-07-15 | 2027-01-14
RE/0066-PRJ-T4-FIS-LF | Lobby Furniture | 2010 | GR01 | 2010 |  |  |  | 0 | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
RE/0066-PRJ-T4-FIS-MD | Modular Kitchen Works | 2010 | GR01 | 2010 |  |  |  | 0 | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
RE/0066-PRJ-T4-FIS-MF | Misc Finish Works | 2010 | GR01 | 2010 |  |  |  | 0 | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
RE/0066-PRJ-T4-FIS-MW | MS works | 2010 | GR01 | 2010 |  |  |  | 0 | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
RE/0066-PRJ-T4-FIS-WF | Wall Finish Works | 2010 | GR01 | 2010 |  |  |  | 0 | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
RE/0066-PRJ-T4-FIS-WO | Wood Work | 2010 | GR01 | 2010 |  |  |  | 0 | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
RE/0066-PRJ-T4-MEP-EW-HE | High Side Electrical Works | 2010 | GR01 | 2010 | SMARTWORLD THE EDITION | Dehn India Pvt Ltd | 9140000379 | 10 |  |  | 2024-10-24 | Lightning Protection System for Basement | AU | 1 | 0 | 984074 | 1161207.32 | 144535.06 | 170551.37 | 839538.94 | 144535.08 | 170551.4 | ZSER | 2024-10-24 | 2027-08-23
RE/0066-PRJ-T4-MEP-EW-HE | High Side Electrical Works | 2010 | GR01 | 2010 | SMARTWORLD THE EDITION | SATKARTAR ELECTRICALS AND ELECTRONIPRIVATE LIMITED | 9140000677 | 40 |  |  | 2026-06-02 | Electrical Works Tower T4 | AU | 1 | 30519112.54 | 26231622.54 | 30953314.6 | 0 | 0 | 26231622.54 | 0 | 0 | ZSER | 2026-06-01 | 2028-02-01
RE/0066-PRJ-T4-MEP-EW-HE | High Side Electrical Works | 2010 | GR01 | 2010 | SMARTWORLD THE EDITION | TRIPLE A ENGINEERING PRIVATE LIMIT | 9140000688 | 10 |  |  | 2026-06-06 | Electrical Works Tower T1 | AU | 1 | 0 | 659395.8 | 659395.8 | 0 | 0 | 659395.8 | 0 | 0 | ZSER | 2026-06-01 | 2028-02-01
RE/0066-PRJ-T4-MEP-EW-HE | High Side Electrical Works | 2010 | GR01 | 2010 | SMARTWORLD THE EDITION | TRIPLE A ENGINEERING PRIVATE LIMIT | 9140000688 | 40 |  |  | 2026-06-06 | Electrical Works Tower T4 | AU | 1 | 0 | 22404102.94 | 22404102.94 | 0 | 0 | 22404102.94 | 0 | 0 | ZSER | 2026-06-01 | 2028-02-01
RE/0066-PRJ-T4-MEP-EW-LE | Low Side Electrical Works | 2010 | GR01 | 2010 | SMARTWORLD THE EDITION | Ahluwalia Contracts India Limited | 9140000321 | 140 |  |  | 2024-07-20 | CONDUITING | AU | 1 | 0 | 21154341.87 | 24962123.41 | 3438397.45 | 4057308.99 | 17715944.42 | 1989338.57 | 2347419.51 | ZSER | 2024-07-15 | 2027-01-14
RE/0066-PRJ-T4-MEP-EW-LE | Low Side Electrical Works | 2010 | GR01 | 2010 | SMARTWORLD THE EDITION | SATKARTAR ELECTRICALS AND ELECTRONIPRIVATE LIMITED | 9140000677 | 40 |  |  | 2026-06-02 | Electrical Works Tower T4 | AU | 1 | 0 | 4287490 | 5059238.2 | 0 | 0 | 4287490 | 0 | 0 | ZSER | 2026-06-01 | 2028-02-01
RE/0066-PRJ-T4-MEP-EW-LE | Low Side Electrical Works | 2010 | GR01 | 2010 | SMARTWORLD THE EDITION | TRIPLE A ENGINEERING PRIVATE LIMIT | 9140000688 | 10 |  |  | 2026-06-06 | Electrical Works Tower T1 | AU | 1 | 0 | 76000 | 76000 | 0 | 0 | 76000 | 0 | 0 | ZSER | 2026-06-01 | 2028-02-01
RE/0066-PRJ-T4-MEP-EW-LE | Low Side Electrical Works | 2010 | GR01 | 2010 | SMARTWORLD THE EDITION | TRIPLE A ENGINEERING PRIVATE LIMIT | 9140000688 | 40 |  |  | 2026-06-06 | Electrical Works Tower T4 | AU | 1 | 0 | 38386034.84 | 38386034.84 | 0 | 0 | 38386034.84 | 0 | 0 | ZSER | 2026-06-01 | 2028-02-01
RE/0066-PRJ-T4-MEP-EW-LS | Light Fixtures Supply | 2010 | GR01 | 2010 |  |  |  | 0 | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
RE/0066-PRJ-T4-MEP-FF | Fire Fighting Work | 2010 | GR01 | 2010 | SMARTWORLD THE EDITION | Jagrati Civil Constructions Pvt Ltd | 9140000633 | 230 |  |  | 2026-04-15 | FF-FIRE HYDRANT & EQUIPMENT SUPPLY- T4 | AU | 1 | 3205680 | 3205680 | 3782702.4 | 0 | 0 | 3205680 | 0 | 0 | ZSER | 2026-04-08 | 2028-01-31
RE/0066-PRJ-T4-MEP-FF | Fire Fighting Work | 2010 | GR01 | 2010 | SMARTWORLD THE EDITION | Jagrati Civil Constructions Pvt Ltd | 9140000633 | 280 |  |  | 2026-04-15 | FF-AUTOMATIC SPRINKLER & WATER Supply-T4 | AU | 1 | 18319831.38 | 18319831.38 | 21617401.03 | 0 | 0 | 18319831.38 | 0 | 0 | ZSER | 2026-04-08 | 2028-01-31
RE/0066-PRJ-T4-MEP-FF | Fire Fighting Work | 2010 | GR01 | 2010 | SMARTWORLD THE EDITION | Jagrati Civil Constructions Pvt Ltd | 9140000633 | 330 |  |  | 2026-04-15 | FF-PORTABLE FIRE EXTINGUISHERS Supply-T4 | AU | 1 | 354500 | 354500 | 418310 | 0 | 0 | 354500 | 0 | 0 | ZSER | 2026-04-08 | 2028-01-31
RE/0066-PRJ-T4-MEP-HV-HS | High Side | 2010 | GR01 | 2010 |  |  |  | 0 | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
RE/0066-PRJ-T4-MEP-HV-LS | Low Side | 2010 | GR01 | 2010 |  |  |  | 0 | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
RE/0066-PRJ-T4-MEP-LT | Lifts | 2010 | GR01 | 2010 |  |  |  | 0 | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
RE/0066-PRJ-T4-MEP-PB-IP | Internal Plumbing | 2010 | GR01 | 2010 | SMARTWORLD THE EDITION | Jagrati Civil Constructions Pvt Ltd | 9140000633 | 20 |  |  | 2026-04-15 | SANITARY FIXTURES & FITTINGS INST. T-4 | AU | 1 | 4621950 | 4621950 | 5453901 | 0 | 0 | 4621950 | 0 | 0 | ZSER | 2026-04-08 | 2028-01-31
RE/0066-PRJ-T4-MEP-PB-IP | Internal Plumbing | 2010 | GR01 | 2010 | SMARTWORLD THE EDITION | Jagrati Civil Constructions Pvt Ltd | 9140000633 | 70 |  |  | 2026-04-15 | INTERNAL DRAINAGE SUPPLY(SOIL, WASTE T-4 | AU | 1 | 15093203.07 | 15093203.07 | 17809979.62 | 0 | 0 | 15093203.07 | 0 | 0 | ZSER | 2026-04-08 | 2028-01-31
RE/0066-PRJ-T4-MEP-PB-IP | Internal Plumbing | 2010 | GR01 | 2010 | SMARTWORLD THE EDITION | Jagrati Civil Constructions Pvt Ltd | 9140000633 | 120 |  |  | 2026-04-15 | DOMESTIC AND FLUSHING WATER SUPPLY T-4 | AU | 1 | 17052183.67 | 17052183.67 | 20121576.73 | 0 | 0 | 17052183.67 | 0 | 0 | ZSER | 2026-04-08 | 2028-01-31
RE/0066-PRJ-T4-MEP-PB-IP | Internal Plumbing | 2010 | GR01 | 2010 | SMARTWORLD THE EDITION | Jagrati Civil Constructions Pvt Ltd | 9140000633 | 170 |  |  | 2026-04-15 | MISCELLANEOUS ITEMS FOR TERRACE WATER-T4 | AU | 1 | 376700 | 376700 | 444506 | 0 | 0 | 376700 | 0 | 0 | ZSER | 2026-04-08 | 2028-01-31
RE/0066-PRJ-T4-MEP-PB-JA | JACUZZI | 2010 | GR01 | 2010 |  |  |  | 0 | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
RE/0066-PRJ-T4-MEP-PB-PS | Fixtures Supply | 2010 | GR01 | 2010 |  |  |  | 0 | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
RE/0066-PRJ-T4-MEP-PN | PNG Gas Pipe Line | 2010 | GR01 | 2010 |  |  |  | 0 | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
RE/0066-PRJ-T5-CIV-CC-LA | Concrete Labour | 2010 | GR01 | 2010 |  |  |  | 0 | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
RE/0066-PRJ-T5-CIV-CC-SL | Concrete Supply & Labour | 2010 | GR01 | 2010 | SMARTWORLD THE EDITION | Ahluwalia Contracts India Limited | 9140000321 | 20 |  |  | 2024-07-20 | REINFORCED CEMENT CONCRETE-I part A | AU | 1 | 0 | 114356201.09 | 134940317.29 | 62071494.75 | 73244363.8 | 52284706.34 | 62071494.79 | 73244363.85 | ZSER | 2024-07-15 | 2027-01-14
RE/0066-PRJ-T5-CIV-CC-SL | Concrete Supply & Labour | 2010 | GR01 | 2010 | SMARTWORLD THE EDITION | Ahluwalia Contracts India Limited | 9140000321 | 30 |  |  | 2024-07-20 | REINFORCED CEMENT CONCRETE-I Part B | AU | 1 | 0 | 87484504.36 | 103231715.14 | 53729911.78 | 63401295.9 | 33754592.58 | 46254768.08 | 54580626.34 | ZSER | 2024-07-15 | 2027-01-14
RE/0066-PRJ-T5-CIV-CC-SL | Concrete Supply & Labour | 2010 | GR01 | 2010 | SMARTWORLD THE EDITION | Ahluwalia Contracts India Limited | 9140000321 | 40 |  |  | 2024-07-20 | REINFORCED CEMENT CONCRETE-I Part C | AU | 1 | 0 | 117487570.12 | 138635332.74 | 46207793.36 | 54525196.16 | 71279776.76 | 38201289.74 | 45077521.89 | ZSER | 2024-07-15 | 2027-01-14
RE/0066-PRJ-T5-CIV-CC-SL | Concrete Supply & Labour | 2010 | GR01 | 2010 | SMARTWORLD THE EDITION | Ahluwalia Contracts India Limited | 9140000321 | 180 |  |  | 2024-07-20 | SUBSTITUTE ITEM | AU | 1 | 0 | 1266038.72 | 1493925.69 | 1050319.08 | 1239376.52 | 215719.64 | 1050319.08 | 1239376.52 | ZSER | 2024-07-15 | 2027-01-14
RE/0066-PRJ-T5-CIV-CC-SU | Concrete Supply | 2010 | GR01 | 2010 |  |  |  | 0 | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
RE/0066-PRJ-T5-CIV-EW | Earthwork | 2010 | GR01 | 2010 | SMARTWORLD THE EDITION | Ahluwalia Contracts India Limited | 9140000321 | 10 |  |  | 2024-07-20 | SITE DEVLOPMENT AND EARTH WORK | AU | 1 | 0 | 1496781 | 1766201.58 | 754630.33 | 890463.79 | 742150.67 | 754630.33 | 890463.79 | ZSER | 2024-07-15 | 2027-01-14
RE/0066-PRJ-T5-CIV-MS | Misc Structure Works | 2010 | GR01 | 2010 | SMARTWORLD THE EDITION | Ahluwalia Contracts India Limited | 9140000321 | 100 |  |  | 2024-07-20 | STRUCTURAL STEEL WORKS | AU | 1 | 0 | 38574653.06 | 45518090.61 | 5695271.89 | 6720420.83 | 32879381.17 | 4330461.97 | 5109945.13 | ZSER | 2024-07-15 | 2027-01-14
RE/0066-PRJ-T5-CIV-MS | Misc Structure Works | 2010 | GR01 | 2010 | SMARTWORLD THE EDITION | Ahluwalia Contracts India Limited | 9140000321 | 130 |  |  | 2024-07-20 | INTERNAL & EXTERNAL PLASTERING | AU | 1 | 0 | 607320 | 716637.6 | 0 | 0 | 607320 | 0 | 0 | ZSER | 2024-07-15 | 2027-01-14
RE/0066-PRJ-T5-CIV-MS | Misc Structure Works | 2010 | GR01 | 2010 | SMARTWORLD THE EDITION | Ahluwalia Contracts India Limited | 9140000321 | 160 |  |  | 2024-07-20 | Amed-Monthly rental payment to M/S ACIL | AU | 1 | 0 | 1230377.3 | 1451845.21 | 443589.1 | 523435.14 | 786788.2 | 0 | 0 | ZSER | 2024-07-15 | 2027-01-14
RE/0066-PRJ-T5-CIV-MW | Masonry Works | 2010 | GR01 | 2010 | SMARTWORLD THE EDITION | Ahluwalia Contracts India Limited | 9140000321 | 90 |  |  | 2024-07-20 | MASONARY WORKS | AU | 1 | 0 | 8721464.77 | 10291328.43 | 1200254.41 | 1416300.2 | 7521210.36 | 1200254.41 | 1416300.2 | ZSER | 2024-07-15 | 2027-01-14
RE/0066-PRJ-T5-CIV-MW | Masonry Works | 2010 | GR01 | 2010 | SMARTWORLD THE EDITION | ANIMESH BUILDTECH INDIA PRIVATE LIMSunil kumar pandey | 9140000603 | 10 |  |  | 2026-03-10 | Finishing Work -T5 | AU | 1 | 299773018.22 | 1912000 | 2256160 | 0 | 0 | 1912000 | 0 | 0 | ZSER | 2026-04-14 | 2028-04-13
RE/0066-PRJ-T5-CIV-PW-IP | Internal Plaster | 2010 | GR01 | 2010 | SMARTWORLD THE EDITION | Ahluwalia Contracts India Limited | 9140000321 | 130 |  |  | 2024-07-20 | INTERNAL & EXTERNAL PLASTERING | AU | 1 | 0 | 7118735.46 | 8400107.84 | 0 | 0 | 7118735.46 | 0 | 0 | ZSER | 2024-07-15 | 2027-01-14
RE/0066-PRJ-T5-CIV-PW-XP | External Plaster | 2010 | GR01 | 2010 | SMARTWORLD THE EDITION | Ahluwalia Contracts India Limited | 9140000321 | 130 |  |  | 2024-07-20 | INTERNAL & EXTERNAL PLASTERING | AU | 1 | 0 | 251000 | 296180 | 0 | 0 | 251000 | 0 | 0 | ZSER | 2024-07-15 | 2027-01-14
RE/0066-PRJ-T5-CIV-RS-LA | Reinforcement Labour | 2010 | GR01 | 2010 | SMARTWORLD THE EDITION | Ahluwalia Contracts India Limited | 9140000321 | 70 |  |  | 2024-07-20 | REINFORCEMENT STEEL Installation Part A | AU | 1 | 0 | 33633149 | 39687115.82 | 32526116.31 | 38380817.24 | 1107032.69 | 32526116.33 | 38380817.27 | ZSER | 2024-07-15 | 2027-01-14
RE/0066-PRJ-T5-CIV-RS-LA | Reinforcement Labour | 2010 | GR01 | 2010 | SMARTWORLD THE EDITION | Ahluwalia Contracts India Limited | 9140000321 | 80 |  |  | 2024-07-20 | REINFORCEMENT STEEL Installation Part B | AU | 1 | 0 | 129654971.89 | 152992866.83 | 47639051.67 | 56214080.97 | 82015920.22 | 41442283.26 | 48901894.25 | ZSER | 2024-07-15 | 2027-01-14
RE/0066-PRJ-T5-CIV-RS-SU | Reinforcement Supply | 2010 | GR01 | 2010 | SMARTWORLD THE EDITION | Carna Corporation Pvt LtdVISHWANATH | 9110000657 | 10 |  |  | 2024-08-03 | Fe 550D TMT Steel 8 MM dia. | TO | 2.5 | 52500 | 131250 | 154875 | 131250 | 154875 | 0 | 131250 | 154875.02 | ZMAT | 2024-08-03 | 2024-09-03
RE/0066-PRJ-T5-CIV-RS-SU | Reinforcement Supply | 2010 | GR01 | 2010 | SMARTWORLD THE EDITION | Carna Corporation Pvt LtdVISHWANATH | 9110000657 | 20 |  |  | 2024-08-03 | Fe 550D TMT Steel 10 MM dia. | TO | 4.5 | 51250 | 230625 | 272137.5 | 230625 | 272137.5 | 0 | 230625 | 272138.03 | ZMAT | 2024-08-03 | 2024-09-03
RE/0066-PRJ-T5-CIV-RS-SU | Reinforcement Supply | 2010 | GR01 | 2010 | SMARTWORLD THE EDITION | Carna Corporation Pvt LtdVISHWANATH | 9110000657 | 30 |  |  | 2024-08-03 | Fe 550D TMT Steel 12 MM dia. | TO | 64.5 | 50500 | 3257250 | 3843555 | 3237050 | 3819719 | 20200 | 3237050 | 3819718.4 | ZMAT | 2024-08-03 | 2024-09-03
RE/0066-PRJ-T5-CIV-RS-SU | Reinforcement Supply | 2010 | GR01 | 2010 | SMARTWORLD THE EDITION | Carna Corporation Pvt LtdVISHWANATH | 9110000657 | 40 |  |  | 2024-08-03 | Fe 550D TMT Steel 16 MM dia. | TO | 22 | 50500 | 1111000 | 1310980 | 1111000 | 1310980 | 0 | 1111000 | 1310980.13 | ZMAT | 2024-08-03 | 2024-09-03
RE/0066-PRJ-T5-CIV-RS-SU | Reinforcement Supply | 2010 | GR01 | 2010 | SMARTWORLD THE EDITION | Carna Corporation Pvt LtdVISHWANATH | 9110000657 | 50 |  |  | 2024-08-03 | Fe 550D TMT Steel 20 MM dia. | TO | 10 | 50500 | 505000 | 595900 | 482275 | 569084.5 | 22725 | 482275 | 569085 | ZMAT | 2024-08-03 | 2024-09-03
RE/0066-PRJ-T5-CIV-RS-SU | Reinforcement Supply | 2010 | GR01 | 2010 | SMARTWORLD THE EDITION | Carna Corporation Pvt LtdVISHWANATH | 9110000657 | 60 |  |  | 2024-08-03 | Fe 550D TMT Steel 25 MM dai. | TO | 117.5 | 50500 | 5933750 | 7001825 | 5933750 | 7001825 | 0 | 5933750 | 7001824.66 | ZMAT | 2024-08-03 | 2024-09-03
RE/0066-PRJ-T5-CIV-RS-SU | Reinforcement Supply | 2010 | GR01 | 2010 | SMARTWORLD THE EDITION | Carna Corporation Pvt LtdVISHWANATH | 9110000657 | 70 |  |  | 2024-08-03 | Fe 550D TMT Steel 32 MM dia. | TO | 588.5 | 50500 | 29719250 | 35068715 | 29719250 | 35068715 | 0 | 29719250 | 35068715.89 | ZMAT | 2024-08-03 | 2024-09-03
RE/0066-PRJ-T5-CIV-RS-SU | Reinforcement Supply | 2010 | GR01 | 2010 | SMARTWORLD THE EDITION | Carna Corporation Pvt LtdVISHWANATH | 9110000708 | 20 |  |  | 2024-09-23 | Fe 550D TMT Steel 8 MM dia. | TO | 7.5 | 50250 | 376875 | 444712.5 | 376875 | 444712.5 | 0 | 376875 | 444712.53 | ZMAT | 2024-09-23 | 2024-10-22
RE/0066-PRJ-T5-CIV-RS-SU | Reinforcement Supply | 2010 | GR01 | 2010 | SMARTWORLD THE EDITION | Carna Corporation Pvt LtdVISHWANATH | 9110000708 | 40 |  |  | 2024-09-23 | Fe 550D TMT Steel 10 MM dia. | TO | 7.5 | 49000 | 367500 | 433650 | 390334 | 460594.12 | 22834 | 390334 | 460594.12 | ZMAT | 2024-09-23 | 2024-10-22
RE/0066-PRJ-T5-CIV-RS-SU | Reinforcement Supply | 2010 | GR01 | 2010 | SMARTWORLD THE EDITION | Carna Corporation Pvt LtdVISHWANATH | 9110000708 | 60 |  |  | 2024-09-23 | Fe 550D TMT Steel 12 MM dia. | TO | 15.5 | 48250 | 747875 | 882492.5 | 605055 | 713964.9 | 142820 | 605055 | 713964.62 | ZMAT | 2024-09-23 | 2024-10-22
RE/0066-PRJ-T5-CIV-RS-SU | Reinforcement Supply | 2010 | GR01 | 2010 | SMARTWORLD THE EDITION | Carna Corporation Pvt LtdVISHWANATH | 9110000708 | 80 |  |  | 2024-09-23 | Fe 550D TMT Steel 16 MM dia. | TO | 15 | 48250 | 723750 | 854025 | 416783.5 | 491804.53 | 306966.5 | 416783.5 | 491804.53 | ZMAT | 2024-09-23 | 2024-10-22
RE/0066-PRJ-T5-CIV-RS-SU | Reinforcement Supply | 2010 | GR01 | 2010 | SMARTWORLD THE EDITION | Carna Corporation Pvt LtdVISHWANATH | 9110000708 | 100 |  |  | 2024-09-23 | Fe 550D TMT Steel 20 MM dia. | TO | 27 | 48250 | 1302750 | 1537245 | 1425449.75 | 1682030.71 | 122699.75 | 1425449.75 | 1682030.31 | ZMAT | 2024-09-23 | 2024-10-22
RE/0066-PRJ-T5-CIV-RS-SU | Reinforcement Supply | 2010 | GR01 | 2010 | SMARTWORLD THE EDITION | Carna Corporation Pvt LtdVISHWANATH | 9110000708 | 120 |  |  | 2024-09-23 | Fe 550D TMT Steel 25 MM dia. | TO | 15 | 48250 | 723750 | 854025 | 719648.75 | 849185.53 | 4101.25 | 719648.75 | 849185.87 | ZMAT | 2024-09-23 | 2024-10-22
RE/0066-PRJ-T5-CIV-RS-SU | Reinforcement Supply | 2010 | GR01 | 2010 | SMARTWORLD THE EDITION | Carna Corporation Pvt LtdVISHWANATH | 9110000708 | 140 |  |  | 2024-09-23 | Fe 550D TMT Steel 32 MM dia. | TO | 100 | 48250 | 4825000 | 5693500 | 4886036.25 | 5765522.78 | 61036.25 | 4886036.25 | 5765522.86 | ZMAT | 2024-09-23 | 2024-10-22
RE/0066-PRJ-T5-CIV-RS-SU | Reinforcement Supply | 2010 | GR01 | 2010 | SMARTWORLD THE EDITION | Carna Corporation Pvt LtdVISHWANATH | 9110000709 | 50 |  |  | 2024-09-23 | Fe 550D TMT Steel 8 MM | TO | 17.5 | 50250 | 879375 | 1037662.5 | 846210.01 | 998527.81 | 33164.99 | 846210 | 998527.89 | ZMAT | 2024-09-23 | 2024-10-22
RE/0066-PRJ-T5-CIV-RS-SU | Reinforcement Supply | 2010 | GR01 | 2010 | SMARTWORLD THE EDITION | Carna Corporation Pvt LtdVISHWANATH | 9110000709 | 60 |  |  | 2024-09-23 | Fe 550D TMT Steel 10 MM | TO | 70 | 49000 | 3430000 | 4047400 | 3376149 | 3983855.82 | 53851 | 3376149 | 3983855.77 | ZMAT | 2024-09-23 | 2024-10-22
RE/0066-PRJ-T5-CIV-RS-SU | Reinforcement Supply | 2010 | GR01 | 2010 | SMARTWORLD THE EDITION | Carna Corporation Pvt LtdVISHWANATH | 9110000709 | 70 |  |  | 2024-09-23 | Fe 550D TMT Steel 16 MM | TO | 17.5 | 48250 | 844375 | 996362.5 | 851612.5 | 1004902.75 | 7237.5 | 851612.5 | 1004902.85 | ZMAT | 2024-09-23 | 2024-10-22
RE/0066-PRJ-T5-CIV-RS-SU | Reinforcement Supply | 2010 | GR01 | 2010 | SMARTWORLD THE EDITION | Carna Corporation Pvt LtdVISHWANATH | 9110000709 | 80 |  |  | 2024-09-23 | Fe 550D TMT Steel 20 MM | TO | 20 | 48250 | 965000 | 1138700 | 1057157.5 | 1247445.85 | 92157.5 | 1057157.5 | 1247445.83 | ZMAT | 2024-09-23 | 2024-10-22
RE/0066-PRJ-T5-CIV-RS-SU | Reinforcement Supply | 2010 | GR01 | 2010 | SMARTWORLD THE EDITION | Northern Steel and General MillsPrivate Limited | 9110000774 | 30 |  |  | 2024-11-15 | Steel Re-bar TMT 16 mm Dia. FE-550D | TO | 18 | 54500 | 981000 | 1157580 | 981000 | 1157580 | 0 | 981000 | 1157580 | ZMAT | 2025-01-20 | 2025-03-20
RE/0066-PRJ-T5-CIV-RS-SU | Reinforcement Supply | 2010 | GR01 | 2010 | SMARTWORLD THE EDITION | Northern Steel and General MillsPrivate Limited | 9110000774 | 100 |  |  | 2024-11-15 | Steel Re-bar TMT 20 mm Dia. FE-550D | TO | 3.5 | 54500 | 190750 | 225085 | 190750 | 225085 | 0 | 190750 | 225085 | ZMAT | 2025-01-20 | 2025-03-20
RE/0066-PRJ-T5-CIV-RS-SU | Reinforcement Supply | 2010 | GR01 | 2010 | SMARTWORLD THE EDITION | Northern Steel and General MillsPrivate Limited | 9110000774 | 170 |  |  | 2024-11-15 | Steel Re-bar TMT 25 mm Dia. FE-550D | TO | 15.5 | 54500 | 844750 | 996805 | 844750 | 996805 | 0 | 844750 | 996805 | ZMAT | 2025-01-20 | 2025-03-20
RE/0066-PRJ-T5-CIV-RS-SU | Reinforcement Supply | 2010 | GR01 | 2010 | SMARTWORLD THE EDITION | Jindal Steel Limited | 9110000777 | 50 |  |  | 2024-11-15 | Steel Re-bar TMT 20 mm Dia. FE-550D | TO | 4 | 54500 | 218000 | 257240 | 218000 | 257240 | 0 | 218000 | 257240 | ZMAT | 2025-01-20 | 2025-03-20
RE/0066-PRJ-T5-CIV-RS-SU | Reinforcement Supply | 2010 | GR01 | 2010 | SMARTWORLD THE EDITION | Jindal Steel Limited | 9110000777 | 120 |  |  | 2024-11-15 | Steel Re-bar TMT 25 mm Dia. FE-550D | TO | 11.5 | 54500 | 626750 | 739565 | 626750 | 739565 | 0 | 626750 | 739565 | ZMAT | 2025-01-20 | 2025-03-20
RE/0066-PRJ-T5-CIV-RS-SU | Reinforcement Supply | 2010 | GR01 | 2010 | SMARTWORLD THE EDITION | Jindal Steel Limited | 9110000777 | 190 |  |  | 2024-11-15 | Steel Re-bar TMT 32 mm Dia. FE-550D | TO | 8 | 54500 | 436000 | 514480 | 436000 | 514480 | 0 | 436000 | 514480 | ZMAT | 2025-01-20 | 2025-03-20
RE/0066-PRJ-T5-CIV-RS-SU | Reinforcement Supply | 2010 | GR01 | 2010 | SMARTWORLD THE EDITION | Carna Corporation Pvt LtdVISHWANATH | 9110000779 | 50 |  |  | 2024-11-16 | Steel Re-bar TMT 20 mm Dia. FE-550D | TO | 5 | 54500 | 272500 | 321550 | 272500 | 321550 | 0 | 272500 | 321550 | ZMAT | 2025-01-20 | 2025-03-20
RE/0066-PRJ-T5-CIV-RS-SU | Reinforcement Supply | 2010 | GR01 | 2010 | SMARTWORLD THE EDITION | Carna Corporation Pvt LtdVISHWANATH | 9110000779 | 120 |  |  | 2024-11-16 | Steel Re-bar TMT 25 mm Dia. FE-550D | TO | 12 | 54500 | 654000 | 771720 | 689806.5 | 813971.67 | 35806.5 | 689806.5 | 813971.67 | ZMAT | 2025-01-20 | 2025-03-20
RE/0066-PRJ-T5-CIV-RS-SU | Reinforcement Supply | 2010 | GR01 | 2010 | SMARTWORLD THE EDITION | Ram Niwas & SonsDeepak gupta | 9110000782 | 20 |  |  | 2024-11-16 | Steel Re-bar TMT 08 mm Dia. FE-550D | TO | 9 | 52500 | 472500 | 557550 | 472500 | 557550 | 0 | 472500 | 557550.07 | ZMAT | 2024-11-16 | 2024-12-15
RE/0066-PRJ-T5-CIV-RS-SU | Reinforcement Supply | 2010 | GR01 | 2010 | SMARTWORLD THE EDITION | Rashtriya Ispat Nigam Ltd | 9110000790 | 60 |  |  | 2024-11-29 | Fe 550D TMT Steel Coil 10MM | TO | 37 | 54450 | 2014650 | 2377287 | 2014650 | 2377287 | 0 | 2014650 | 2377287 | ZMAT | 2024-11-29 | 2024-12-28
RE/0066-PRJ-T5-CIV-RS-SU | Reinforcement Supply | 2010 | GR01 | 2010 | SMARTWORLD THE EDITION | Rashtriya Ispat Nigam Ltd | 9110000790 | 130 |  |  | 2024-11-29 | Fe 550D TMT Steel Coil 12MM | TO | 16 | 53950 | 863200 | 1018576 | 803315.5 | 947912.29 | 59884.5 | 803315.5 | 947912.3 | ZMAT | 2024-11-29 | 2024-12-28
RE/0066-PRJ-T5-CIV-RS-SU | Reinforcement Supply | 2010 | GR01 | 2010 | SMARTWORLD THE EDITION | Carna Corporation Pvt LtdVISHWANATH | 9110000837 | 80 |  |  | 2025-01-09 | Steel Re-bar TMT 10 mm Dia. FE-550D | TO | 30 | 50150 | 1504500 | 1775310 | 1554650 | 1834487 | 50150 | 1554650 | 1834487 | ZMAT | 2025-01-20 | 2025-03-20
RE/0066-PRJ-T5-CIV-RS-SU | Reinforcement Supply | 2010 | GR01 | 2010 | SMARTWORLD THE EDITION | Ram Niwas & SonsDeepak gupta | 9110000862 | 70 |  |  | 2025-02-15 | Steel Re-bar TMT 10 mm Dia. FE-550D | TO | 27 | 50200 | 1355400 | 1599372 | 1355400 | 1599372 | 0 | 1355400 | 1599372 | ZMAT
RE/0066-PRJ-T5-CIV-RS-SU | Reinforcement Supply | 2010 | GR01 | 2010 | SMARTWORLD THE EDITION | Jindal Steel Limited | 9110000886 | 50 |  |  | 2025-03-12 | Steel Re-bar TMT 12 mm Dia. FE-550D | TO | 50 | 54750 | 2737500 | 3230250 | 2737500 | 3230250 | 0 | 2737500 | 3230250 | ZMAT
RE/0066-PRJ-T5-CIV-RS-SU | Reinforcement Supply | 2010 | GR01 | 2010 | SMARTWORLD THE EDITION | Jindal Steel Limited | 9110000886 | 110 |  |  | 2025-03-12 | Steel Re-bar TMT 16 mm Dia. FE-550D | TO | 30 | 54750 | 1642500 | 1938150 | 1642500 | 1938150 | 0 | 1642500 | 1938150 | ZMAT
RE/0066-PRJ-T5-CIV-RS-SU | Reinforcement Supply | 2010 | GR01 | 2010 | SMARTWORLD THE EDITION | Jindal Steel Limited | 9110000886 | 170 |  |  | 2025-03-12 | Steel Re-bar TMT 20 mm Dia. FE-550D | TO | 40 | 54750 | 2190000 | 2584200 | 2190000 | 2584200 | 0 | 2190000 | 2584200 | ZMAT
RE/0066-PRJ-T5-CIV-RS-SU | Reinforcement Supply | 2010 | GR01 | 2010 | SMARTWORLD THE EDITION | Jindal Steel Limited | 9110000886 | 190 |  |  | 2025-03-12 | Steel Re-bar TMT 25 mm Dia. FE-550D | TO | 30 | 54750 | 1642500 | 1938150 | 1598700 | 1886466 | 43800 | 1598700 | 1886466 | ZMAT
RE/0066-PRJ-T5-CIV-RS-SU | Reinforcement Supply | 2010 | GR01 | 2010 | SMARTWORLD THE EDITION | Ram Niwas & SonsDeepak gupta | 9110000887 | 50 |  |  | 2025-03-12 | Steel Re-bar TMT 10 mm Dia. FE-550D | TO | 14 | 52900 | 740600 | 873908 | 793500 | 936330 | 52900 | 793500 | 936330 | ZMAT
RE/0066-PRJ-T5-CIV-RS-SU | Reinforcement Supply | 2010 | GR01 | 2010 | SMARTWORLD THE EDITION | Carna Corporation Pvt LtdVISHWANATH | 9110000889 | 50 |  |  | 2025-03-12 | Steel Re-bar TMT 10 mm Dia. FE-550D | TO | 6 | 55500 | 333000 | 392940 | 333000 | 392940 | 0 | 333000 | 392940 | ZMAT
RE/0066-PRJ-T5-CIV-RS-SU | Reinforcement Supply | 2010 | GR01 | 2010 | SMARTWORLD THE EDITION | Rashtriya Ispat Nigam Ltd | 9110000961 | 50 |  |  | 2025-04-08 | Fe 550D TMT Steel Coil 10MM | TO | 9 | 58750 | 528750 | 623925 | 528750 | 623925 | 0 | 528750 | 623925 | ZMAT
RE/0066-PRJ-T5-CIV-RS-SU | Reinforcement Supply | 2010 | GR01 | 2010 | SMARTWORLD THE EDITION | Rashtriya Ispat Nigam Ltd | 9110000961 | 120 |  |  | 2025-04-08 | Fe 550D TMT Steel Coil 08MM | TO | 9 | 60000 | 540000 | 637200 | 540000 | 637200 | 0 | 540000 | 637200 | ZMAT
RE/0066-PRJ-T5-CIV-RS-SU | Reinforcement Supply | 2010 | GR01 | 2010 | SMARTWORLD THE EDITION | Vikrant Ispat Udyog | 9110000966 | 50 |  |  | 2025-04-09 | Fe 550D TMT Steel Coil 10MM | TO | 3 | 64250 | 192750 | 227445 | 192750 | 227445 | 0 | 192750 | 227445 | ZMAT
RE/0066-PRJ-T5-CIV-RS-SU | Reinforcement Supply | 2010 | GR01 | 2010 | SMARTWORLD THE EDITION | Vikrant Ispat Udyog | 9110000966 | 120 |  |  | 2025-04-09 | Fe 550D TMT Steel Coil 08MM | TO | 3 | 65750 | 197250 | 232755 | 197250 | 232755 | 0 | 197250 | 232755 | ZMAT
RE/0066-PRJ-T5-CIV-RS-SU | Reinforcement Supply | 2010 | GR01 | 2010 | SMARTWORLD THE EDITION | JINDAL STEEL LIMITEDMr Robin Taneja | 9110000991 | 190 |  |  | 2025-04-17 | Steel Re-bar TMT 25 mm Dia. FE-550D | TO | 8 | 57750 | 462000 | 545160 | 462000 | 545160 | 0 | 462000 | 545160 | ZMAT
RE/0066-PRJ-T5-CIV-RS-SU | Reinforcement Supply | 2010 | GR01 | 2010 | SMARTWORLD THE EDITION | Petropol India LimitedSANJAY GUPTA | 9110000993 | 30 |  |  | 2025-04-17 | Steel Re-bar TMT 10 mm Dia. FE-550D | TO | 40 | 56000 | 2240000 | 2643200 | 1942640 | 2292315.2 | 297360 | 1942640 | 2292315.2 | ZMAT | 2025-04-17 | 2025-04-30
RE/0066-PRJ-T5-CIV-RS-SU | Reinforcement Supply | 2010 | GR01 | 2010 | SMARTWORLD THE EDITION | Sapcon Steels Private Limited | 9110000999 | 70 |  |  | 2025-04-18 | Fe 550D TMT Steel Coil 10MM | TO | 40 | 58250 | 2330000 | 2749400 | 2330000 | 2749400 | 0 | 2330000 | 2749400 | ZMAT | 2025-04-11 | 2025-04-30
RE/0066-PRJ-T5-CIV-RS-SU | Reinforcement Supply | 2010 | GR01 | 2010 | SMARTWORLD THE EDITION | Sapcon Steels Private Limited | 9110001009 | 50 |  |  | 2025-04-28 | Steel Re-bar TMT 32 mm Dia. FE-550D | TO | 11 | 57000 | 627000 | 739860 | 399000 | 470820 | 228000 | 399000 | 470820 | ZMAT
RE/0066-PRJ-T5-CIV-RS-SU | Reinforcement Supply | 2010 | GR01 | 2010 | SMARTWORLD THE EDITION | Jindal Steel Limited | 9110001055 | 50 |  |  | 2025-05-17 | Steel Re-bar TMT 20 mm Dia. FE-550D | TO | 10 | 54850 | 548500 | 647230 | 548500 | 647230 | 0 | 548500 | 647230 | ZMAT | 2025-05-29 | 2025-06-29
RE/0066-PRJ-T5-CIV-RS-SU | Reinforcement Supply | 2010 | GR01 | 2010 | SMARTWORLD THE EDITION | Jindal Steel Limited | 9110001055 | 120 |  |  | 2025-05-17 | Steel Re-bar TMT 25 mm Dia. FE-550D | TO | 33 | 54850 | 1810050 | 2135859 | 1864900 | 2200582 | 54850 | 1864900 | 2200582 | ZMAT | 2025-05-29 | 2025-06-29
RE/0066-PRJ-T5-CIV-RS-SU | Reinforcement Supply | 2010 | GR01 | 2010 | SMARTWORLD THE EDITION | Jindal Steel Limited | 9110001073 | 60 |  |  | 2025-05-27 | Steel Re-bar TMT 12 mm Dia. FE-550D | TO | 10 | 57750 | 577500 | 681450 | 577500 | 681450 | 0 | 577500 | 681450 | ZMAT
RE/0066-PRJ-T5-CIV-RS-SU | Reinforcement Supply | 2010 | GR01 | 2010 | SMARTWORLD THE EDITION | Jindal Steel Limited | 9110001073 | 130 |  |  | 2025-05-27 | Steel Re-bar TMT 16 mm Dia. FE-550D | TO | 15 | 57750 | 866250 | 1022175 | 866250 | 1022175 | 0 | 866250 | 1022175 | ZMAT
RE/0066-PRJ-T5-CIV-RS-SU | Reinforcement Supply | 2010 | GR01 | 2010 | SMARTWORLD THE EDITION | Jindal Steel Limited | 9110001073 | 190 |  |  | 2025-05-27 | Steel Re-bar TMT 25 mm Dia. FE-550D | TO | 2 | 57750 | 115500 | 136290 | 115500 | 136290 | 0 | 115500 | 136290 | ZMAT
RE/0066-PRJ-T5-CIV-RS-SU | Reinforcement Supply | 2010 | GR01 | 2010 | SMARTWORLD THE EDITION | JINDAL STEEL LIMITEDMr Robin Taneja | 9110001079 | 50 |  |  | 2025-05-29 | Steel Re-bar TMT 25 mm Dia. FE-550D | TO | 12 | 54850 | 658200 | 776676 | 685625 | 809037.5 | 27425 | 685625 | 809037.5 | ZMAT | 2025-05-29 | 2025-06-29
RE/0066-PRJ-T5-CIV-RS-SU | Reinforcement Supply | 2010 | GR01 | 2010 | SMARTWORLD THE EDITION | Ram Niwas & SonsDeepak gupta | 9110001126 | 50 |  |  | 2025-06-20 | Steel Re-bar TMT 08 mm Dia. FE-550D | TO | 10 | 51000 | 510000 | 601800 | 530400 | 625872 | 20400 | 530400 | 625872 | ZMAT | 2025-06-20 | 2025-07-20
RE/0066-PRJ-T5-CIV-RS-SU | Reinforcement Supply | 2010 | GR01 | 2010 | SMARTWORLD THE EDITION | Jindal Steel Limited | 9110001127 | 50 |  |  | 2025-06-20 | Steel Re-bar TMT 12 mm Dia. FE-550D | TO | 30 | 50600 | 1518000 | 1791240 | 1518000 | 1791240 | 0 | 1518000 | 1791240 | ZMAT | 2025-06-20 | 2025-07-20
RE/0066-PRJ-T5-CIV-RS-SU | Reinforcement Supply | 2010 | GR01 | 2010 | SMARTWORLD THE EDITION | Jindal Steel Limited | 9110001127 | 130 |  |  | 2025-06-20 | Steel Re-bar TMT 16 mm Dia. FE-550D | TO | 25 | 50600 | 1265000 | 1492700 | 1224722.4 | 1445172.43 | 40277.6 | 1224722.4 | 1445172.43 | ZMAT | 2025-06-20 | 2025-07-20
RE/0066-PRJ-T5-CIV-RS-SU | Reinforcement Supply | 2010 | GR01 | 2010 | SMARTWORLD THE EDITION | Jindal Steel Limited | 9110001127 | 210 |  |  | 2025-06-20 | Steel Re-bar TMT 20 mm Dia. FE-550D | TO | 15 | 50600 | 759000 | 895620 | 759000 | 895620 | 0 | 759000 | 895620 | ZMAT | 2025-06-20 | 2025-07-20
RE/0066-PRJ-T5-CIV-RS-SU | Reinforcement Supply | 2010 | GR01 | 2010 | SMARTWORLD THE EDITION | Jindal Steel Limited | 9110001127 | 280 |  |  | 2025-06-20 | Steel Re-bar TMT 25 mm Dia. FE-550D | TO | 20 | 50600 | 1012000 | 1194160 | 1012000 | 1194160 | 0 | 1012000 | 1194160 | ZMAT | 2025-06-20 | 2025-07-20
RE/0066-PRJ-T5-CIV-RS-SU | Reinforcement Supply | 2010 | GR01 | 2010 | SMARTWORLD THE EDITION | Jindal Steel Limited | 9110001162 | 50 |  |  | 2025-07-17 | Steel Re-bar TMT 10 mm Dia. FE-550D | TO | 35 | 47500 | 1662500 | 1961750 | 0 | 0 | 1662500 | 0 | 0 | ZMAT | 2025-07-17 | 2025-08-17
RE/0066-PRJ-T5-CIV-RS-SU | Reinforcement Supply | 2010 | GR01 | 2010 | SMARTWORLD THE EDITION | Jindal Steel Limited | 9110001162 | 130 |  |  | 2025-07-17 | Steel Re-bar TMT 12 mm Dia. FE-550D | TO | 15 | 46500 | 697500 | 823050 | 0 | 0 | 697500 | 0 | 0 | ZMAT | 2025-07-17 | 2025-08-17
RE/0066-PRJ-T5-CIV-RS-SU | Reinforcement Supply | 2010 | GR01 | 2010 | SMARTWORLD THE EDITION | Jindal Steel Limited | 9110001162 | 210 |  |  | 2025-07-17 | Steel Re-bar TMT 16 mm Dia. FE-550D | TO | 5 | 46500 | 232500 | 274350 | 0 | 0 | 232500 | 0 | 0 | ZMAT | 2025-07-17 | 2025-08-17
RE/0066-PRJ-T5-CIV-RS-SU | Reinforcement Supply | 2010 | GR01 | 2010 | SMARTWORLD THE EDITION | Jindal Steel Limited | 9110001162 | 270 |  |  | 2025-07-17 | Steel Re-bar TMT 20 mm Dia. FE-550D | TO | 5 | 46500 | 232500 | 274350 | 0 | 0 | 232500 | 0 | 0 | ZMAT | 2025-07-17 | 2025-08-17
RE/0066-PRJ-T5-CIV-RS-SU | Reinforcement Supply | 2010 | GR01 | 2010 | SMARTWORLD THE EDITION | Jindal Steel Limited | 9110001162 | 340 |  |  | 2025-07-17 | Steel Re-bar TMT 25 mm Dia. FE-550D | TO | 5 | 46500 | 232500 | 274350 | 0 | 0 | 232500 | 0 | 0 | ZMAT | 2025-07-17 | 2025-08-17
RE/0066-PRJ-T5-CIV-RS-SU | Reinforcement Supply | 2010 | GR01 | 2010 | SMARTWORLD THE EDITION | Jindal Steel Limited | 9110001162 | 420 |  |  | 2025-07-17 | Steel Re-bar TMT 32 mm Dia. FE-550D | TO | 5 | 46500 | 232500 | 274350 | 0 | 0 | 232500 | 0 | 0 | ZMAT | 2025-07-17 | 2025-08-17
RE/0066-PRJ-T5-CIV-RS-SU | Reinforcement Supply | 2010 | GR01 | 2010 | SMARTWORLD THE EDITION | Rashtriya Ispat Nigam Ltd | 9110001212 | 50 |  |  | 2025-08-14 | Steel Re-bar TMT 08 mm Dia. FE-550D | TO | 5 | 49300 | 246500 | 290870 | 246500 | 290870 | 0 | 246500 | 290870 | ZMAT | 2025-08-14 | 2025-09-14
RE/0066-PRJ-T5-CIV-RS-SU | Reinforcement Supply | 2010 | GR01 | 2010 | SMARTWORLD THE EDITION | Rashtriya Ispat Nigam Ltd | 9110001212 | 110 |  |  | 2025-08-14 | Steel Re-bar TMT 10 mm Dia. FE-550D | TO | 50 | 47800 | 2390000 | 2820200 | 2390000 | 2820200 | 0 | 2390000 | 2820200 | ZMAT | 2025-08-14 | 2025-09-14
RE/0066-PRJ-T5-CIV-RS-SU | Reinforcement Supply | 2010 | GR01 | 2010 | SMARTWORLD THE EDITION | Jindal Steel Limited | 9110001213 | 50 |  |  | 2025-08-14 | Steel Re-bar TMT 12 mm Dia. FE-550D | TO | 30 | 47000 | 1410000 | 1663800 | 1410000 | 1663800 | 0 | 1410000 | 1663800 | ZMAT | 2025-08-14 | 2025-09-14
RE/0066-PRJ-T5-CIV-RS-SU | Reinforcement Supply | 2010 | GR01 | 2010 | SMARTWORLD THE EDITION | Jindal Steel Limited | 9110001213 | 110 |  |  | 2025-08-14 | Steel Re-bar TMT 16 mm Dia. FE-550D | TO | 10 | 47000 | 470000 | 554600 | 470000 | 554600 | 0 | 470000 | 554600 | ZMAT | 2025-08-14 | 2025-09-14
RE/0066-PRJ-T5-CIV-RS-SU | Reinforcement Supply | 2010 | GR01 | 2010 | SMARTWORLD THE EDITION | Jindal Steel Limited | 9110001213 | 170 |  |  | 2025-08-14 | Steel Re-bar TMT 20 mm Dia. FE-550D | TO | 10 | 47000 | 470000 | 554600 | 470000 | 554600 | 0 | 470000 | 554600 | ZMAT | 2025-08-14 | 2025-09-14
RE/0066-PRJ-T5-CIV-RS-SU | Reinforcement Supply | 2010 | GR01 | 2010 | SMARTWORLD THE EDITION | Jindal Steel Limited | 9110001213 | 230 |  |  | 2025-08-14 | Steel Re-bar TMT 25 mm Dia. FE-550D | TO | 10 | 47000 | 470000 | 554600 | 470000 | 554600 | 0 | 470000 | 554600 | ZMAT | 2025-08-14 | 2025-09-14
RE/0066-PRJ-T5-CIV-RS-SU | Reinforcement Supply | 2010 | GR01 | 2010 | SMARTWORLD THE EDITION | Jindal Steel Limited | 9110001213 | 290 |  |  | 2025-08-14 | Steel Re-bar TMT 32 mm Dia. FE-550D | TO | 10 | 47000 | 470000 | 554600 | 361759 | 426875.62 | 108241 | 361759 | 426875.62 | ZMAT | 2025-08-14 | 2025-09-14
RE/0066-PRJ-T5-CIV-RS-SU | Reinforcement Supply | 2010 | GR01 | 2010 | SMARTWORLD THE EDITION | Steel Authority Of India LTD | 9110001280 | 60 |  |  | 2025-09-18 | Steel Re-bar TMT 12 mm Dia. FE-550D | TO | 25.06 | 46260 | 1159275.6 | 1367945.21 | 1159275.6 | 1367945.21 | 0 | 1159275.6 | 1367945.22 | ZMAT | 2025-09-18 | 2025-10-18
RE/0066-PRJ-T5-CIV-RS-SU | Reinforcement Supply | 2010 | GR01 | 2010 | SMARTWORLD THE EDITION | Steel Authority Of India LTD | 9110001280 | 120 |  |  | 2025-09-18 | Steel Re-bar TMT 16 mm Dia. FE-550D | TO | 20 | 46260 | 925200 | 1091736 | 925200 | 1091736 | 0 | 925200 | 1091736 | ZMAT | 2025-09-18 | 2025-10-18
RE/0066-PRJ-T5-CIV-RS-SU | Reinforcement Supply | 2010 | GR01 | 2010 | SMARTWORLD THE EDITION | Steel Authority Of India LTD | 9110001280 | 180 |  |  | 2025-09-18 | Steel Re-bar TMT 20 mm Dia. FE-550D | TO | 23.75 | 46260 | 1098675 | 1296436.5 | 1098675 | 1296436.5 | 0 | 1098675 | 1296436.51 | ZMAT | 2025-09-18 | 2025-10-18
RE/0066-PRJ-T5-CIV-RS-SU | Reinforcement Supply | 2010 | GR01 | 2010 | SMARTWORLD THE EDITION | Steel Authority Of India LTD | 9110001280 | 240 |  |  | 2025-09-18 | Steel Re-bar TMT 25 mm Dia. FE-550D | TO | 14 | 46260 | 647640 | 764215.2 | 647640 | 764215.2 | 0 | 647640 | 764215.21 | ZMAT | 2025-09-18 | 2025-10-18
RE/0066-PRJ-T5-CIV-RS-SU | Reinforcement Supply | 2010 | GR01 | 2010 | SMARTWORLD THE EDITION | Steel Authority Of India LTD | 9110001280 | 330 |  |  | 2025-09-18 | Steel Re-bar TMT 10 mm Dia. FE-550D | TO | 16.9 | 47260 | 798694 | 942458.92 | 798694 | 942458.92 | 0 | 798694 | 942458.92 | ZMAT | 2025-09-18 | 2025-10-18
RE/0066-PRJ-T5-CIV-RS-SU | Reinforcement Supply | 2010 | GR01 | 2010 | SMARTWORLD THE EDITION | Steel Authority Of India LTD | 9110001280 | 350 |  |  | 2025-09-18 | Steel Re-bar TMT 32 mm Dia. FE-550D | TO | 14 | 46260 | 647640 | 764215.2 | 647640 | 764215.2 | 0 | 647640 | 764215.2 | ZMAT | 2025-09-18 | 2025-10-18
RE/0066-PRJ-T5-CIV-RS-SU | Reinforcement Supply | 2010 | GR01 | 2010 | SMARTWORLD THE EDITION | Ram Niwas & SonsDeepak gupta | 9110001305 | 50 |  |  | 2025-10-09 | Steel Re-bar TMT 08 mm Dia. FE-550D | TO | 6 | 47500 | 285000 | 336300 | 285000 | 336300 | 0 | 285000 | 336300 | ZMAT | 2025-10-09 | 2025-11-08
RE/0066-PRJ-T5-CIV-RS-SU | Reinforcement Supply | 2010 | GR01 | 2010 | SMARTWORLD THE EDITION | Ram Niwas & SonsDeepak gupta | 9110001305 | 110 |  |  | 2025-10-09 | Steel Re-bar TMT 10 mm Dia. FE-550D | TO | 28 | 46500 | 1302000 | 1536360 | 1302000 | 1536360 | 0 | 1302000 | 1536360 | ZMAT | 2025-10-09 | 2025-11-08
RE/0066-PRJ-T5-CIV-RS-SU | Reinforcement Supply | 2010 | GR01 | 2010 | SMARTWORLD THE EDITION | Jindal Steel Limited | 9110001307 | 50 |  |  | 2025-10-09 | Steel Re-bar TMT 12 mm Dia. FE-550D | TO | 5 | 46500 | 232500 | 274350 | 232500 | 274350 | 0 | 232500 | 274350 | ZMAT | 2025-10-09 | 2025-11-08
RE/0066-PRJ-T5-CIV-RS-SU | Reinforcement Supply | 2010 | GR01 | 2010 | SMARTWORLD THE EDITION | Jindal Steel Limited | 9110001307 | 110 |  |  | 2025-10-09 | Steel Re-bar TMT 16 mm Dia. FE-550D | TO | 20 | 46500 | 930000 | 1097400 | 930000 | 1097400 | 0 | 930000 | 1097400 | ZMAT | 2025-10-09 | 2025-11-08
RE/0066-PRJ-T5-CIV-RS-SU | Reinforcement Supply | 2010 | GR01 | 2010 | SMARTWORLD THE EDITION | Jindal Steel Limited | 9110001307 | 170 |  |  | 2025-10-09 | Steel Re-bar TMT 20 mm Dia. FE-550D | TO | 20 | 46500 | 930000 | 1097400 | 930000 | 1097400 | 0 | 930000 | 1097400 | ZMAT | 2025-10-09 | 2025-11-08
RE/0066-PRJ-T5-CIV-RS-SU | Reinforcement Supply | 2010 | GR01 | 2010 | SMARTWORLD THE EDITION | Jindal Steel Limited | 9110001307 | 230 |  |  | 2025-10-09 | Steel Re-bar TMT 25 mm Dia. FE-550D | TO | 17 | 46500 | 790500 | 932790 | 770412 | 909086.16 | 20088 | 770412 | 909086.16 | ZMAT | 2025-10-09 | 2025-11-08
RE/0066-PRJ-T5-CIV-RS-SU | Reinforcement Supply | 2010 | GR01 | 2010 | SMARTWORLD THE EDITION | Jindal Steel Limited | 9110001307 | 290 |  |  | 2025-10-09 | Steel Re-bar TMT 32 mm Dia. FE-550D | TO | 17 | 46500 | 790500 | 932790 | 790500 | 932790 | 0 | 790500 | 932790 | ZMAT | 2025-10-09 | 2025-11-08
RE/0066-PRJ-T5-CIV-RS-SU | Reinforcement Supply | 2010 | GR01 | 2010 | SMARTWORLD THE EDITION | Jindal Steel Limited | 9110001361 | 50 |  |  | 2025-11-07 | Steel Re-bar TMT 12 mm Dia. FE-550D | TO | 33 | 46100 | 1521300 | 1795134 | 1567400 | 1849532 | 46100 | 1567400 | 1849532 | ZMAT | 2025-11-07 | 2025-12-07
RE/0066-PRJ-T5-CIV-RS-SU | Reinforcement Supply | 2010 | GR01 | 2010 | SMARTWORLD THE EDITION | Jindal Steel Limited | 9110001361 | 110 |  |  | 2025-11-07 | Steel Re-bar TMT 16 mm Dia. FE-550D | TO | 25 | 46100 | 1152500 | 1359950 | 1175550 | 1387149 | 23050 | 1175550 | 1387149 | ZMAT | 2025-11-07 | 2025-12-07
RE/0066-PRJ-T5-CIV-RS-SU | Reinforcement Supply | 2010 | GR01 | 2010 | SMARTWORLD THE EDITION | Jindal Steel Limited | 9110001361 | 170 |  |  | 2025-11-07 | Steel Re-bar TMT 20 mm Dia. FE-550D | TO | 8 | 46100 | 368800 | 435184 | 368800 | 435184 | 0 | 368800 | 435184 | ZMAT | 2025-11-07 | 2025-12-07
RE/0066-PRJ-T5-CIV-RS-SU | Reinforcement Supply | 2010 | GR01 | 2010 | SMARTWORLD THE EDITION | Jindal Steel Limited | 9110001361 | 230 |  |  | 2025-11-07 | Steel Re-bar TMT 25 mm Dia. FE-550D | TO | 30 | 46100 | 1383000 | 1631940 | 1383000 | 1631940 | 0 | 1383000 | 1631940 | ZMAT | 2025-11-07 | 2025-12-07
RE/0066-PRJ-T5-CIV-RS-SU | Reinforcement Supply | 2010 | GR01 | 2010 | SMARTWORLD THE EDITION | Jindal Steel Limited | 9110001361 | 290 |  |  | 2025-11-07 | Steel Re-bar TMT 32 mm Dia. FE-550D | TO | 8 | 46100 | 368800 | 435184 | 368800 | 435184 | 0 | 368800 | 435184 | ZMAT | 2025-11-07 | 2025-12-07
RE/0066-PRJ-T5-CIV-RS-SU | Reinforcement Supply | 2010 | GR01 | 2010 | SMARTWORLD THE EDITION | Ram Niwas & SonsDeepak gupta | 9110001362 | 50 |  |  | 2025-11-07 | Steel Re-bar TMT 08 mm Dia. FE-550D | TO | 2.5 | 46900 | 117250 | 138355 | 117250 | 138355 | 0 | 117250 | 138355 | ZMAT | 2025-11-07 | 2025-12-07
RE/0066-PRJ-T5-CIV-RS-SU | Reinforcement Supply | 2010 | GR01 | 2010 | SMARTWORLD THE EDITION | Ram Niwas & SonsDeepak gupta | 9110001362 | 100 |  |  | 2025-11-07 | Steel Re-bar TMT 10 mm Dia. FE-550D | TO | 38 | 45900 | 1744200 | 2058156 | 1744200 | 2058156 | 0 | 1744200 | 2058156 | ZMAT | 2025-11-07 | 2025-12-07
RE/0066-PRJ-T5-CIV-RS-SU | Reinforcement Supply | 2010 | GR01 | 2010 | SMARTWORLD THE EDITION | Ram Niwas & SonsDeepak gupta | 9110001421 | 50 |  |  | 2025-12-10 | Steel Re-bar TMT 10 mm Dia. FE-550D | TO | 22 | 46500 | 1023000 | 1207140 | 930000 | 1097400 | 93000 | 930000 | 1097400 | ZMAT | 2025-12-10 | 2026-01-10
RE/0066-PRJ-T5-CIV-RS-SU | Reinforcement Supply | 2010 | GR01 | 2010 | SMARTWORLD THE EDITION | Ram Niwas & SonsDeepak gupta | 9110001421 | 110 |  |  | 2025-12-10 | Steel Re-bar TMT 08 mm Dia. FE-550D | TO | 12 | 47500 | 570000 | 672600 | 570000 | 672600 | 0 | 570000 | 672600 | ZMAT | 2025-12-10 | 2026-01-10
RE/0066-PRJ-T5-CIV-RS-SU | Reinforcement Supply | 2010 | GR01 | 2010 | SMARTWORLD THE EDITION | Jindal Steel Limited | 9110001422 | 50 |  |  | 2025-12-10 | Steel Re-bar TMT 12 mm Dia. FE-550D | TO | 20 | 46400 | 928000 | 1095040 | 928000 | 1095040 | 0 | 928000 | 1095040 | ZMAT | 2025-12-10 | 2026-01-10
RE/0066-PRJ-T5-CIV-RS-SU | Reinforcement Supply | 2010 | GR01 | 2010 | SMARTWORLD THE EDITION | Jindal Steel Limited | 9110001422 | 110 |  |  | 2025-12-10 | Steel Re-bar TMT 16 mm Dia. FE-550D | TO | 18 | 46400 | 835200 | 985536 | 835200 | 985536 | 0 | 835200 | 985536 | ZMAT | 2025-12-10 | 2026-01-10
RE/0066-PRJ-T5-CIV-RS-SU | Reinforcement Supply | 2010 | GR01 | 2010 | SMARTWORLD THE EDITION | Jindal Steel Limited | 9110001422 | 170 |  |  | 2025-12-10 | Steel Re-bar TMT 20 mm Dia. FE-550D | TO | 13 | 46400 | 603200 | 711776 | 603200 | 711776 | 0 | 603200 | 711776 | ZMAT | 2025-12-10 | 2026-01-10
RE/0066-PRJ-T5-CIV-RS-SU | Reinforcement Supply | 2010 | GR01 | 2010 | SMARTWORLD THE EDITION | Jindal Steel Limited | 9110001422 | 230 |  |  | 2025-12-10 | Steel Re-bar TMT 25 mm Dia. FE-550D | TO | 15 | 46400 | 696000 | 821280 | 696000 | 821280 | 0 | 696000 | 821280 | ZMAT | 2025-12-10 | 2026-01-10
RE/0066-PRJ-T5-CIV-RS-SU | Reinforcement Supply | 2010 | GR01 | 2010 | SMARTWORLD THE EDITION | Ram Niwas & SonsDeepak gupta | 9110001471 | 50 |  |  | 2026-01-12 | Steel Re-bar TMT 08 mm Dia. FE-550D | TO | 10 | 52000 | 520000 | 613600 | 520000 | 613600 | 0 | 520000 | 613600 | ZMAT | 2026-01-12 | 2026-02-12
RE/0066-PRJ-T5-CIV-RS-SU | Reinforcement Supply | 2010 | GR01 | 2010 | SMARTWORLD THE EDITION | ESL STEEL LIMITED | 9110001481 | 50 |  |  | 2026-01-12 | Steel Re-bar TMT 12 mm Dia. FE-550D | TO | 42 | 51800 | 2175600 | 2567208 | 2165240 | 2554983.2 | 10360 | 2165240 | 2554983.2 | ZMAT | 2026-01-12 | 2026-02-12
RE/0066-PRJ-T5-CIV-RS-SU | Reinforcement Supply | 2010 | GR01 | 2010 | SMARTWORLD THE EDITION | ESL STEEL LIMITED | 9110001481 | 110 |  |  | 2026-01-12 | Steel Re-bar TMT 16 mm Dia. FE-550D | TO | 2 | 51800 | 103600 | 122248 | 109246.2 | 128910.52 | 5646.2 | 109246.2 | 128910.52 | ZMAT | 2026-01-12 | 2026-02-12
RE/0066-PRJ-T5-CIV-RS-SU | Reinforcement Supply | 2010 | GR01 | 2010 | SMARTWORLD THE EDITION | ESL STEEL LIMITED | 9110001481 | 170 |  |  | 2026-01-12 | Steel Re-bar TMT 20 mm Dia. FE-550D | TO | 25 | 51800 | 1295000 | 1528100 | 1295000 | 1528100 | 0 | 1295000 | 1528100 | ZMAT | 2026-01-12 | 2026-02-12
RE/0066-PRJ-T5-CIV-RS-SU | Reinforcement Supply | 2010 | GR01 | 2010 | SMARTWORLD THE EDITION | ESL STEEL LIMITED | 9110001481 | 230 |  |  | 2026-01-12 | Steel Re-bar TMT 25 mm Dia. FE-550D | TO | 8 | 51800 | 414400 | 488992 | 414400 | 488992 | 0 | 414400 | 488992 | ZMAT | 2026-01-12 | 2026-02-12
RE/0066-PRJ-T5-CIV-RS-SU | Reinforcement Supply | 2010 | GR01 | 2010 | SMARTWORLD THE EDITION | Ram Niwas & SonsDeepak gupta | 9110001541 | 50 |  |  | 2026-02-07 | Steel Re-bar TMT 08 mm Dia. FE-550D | TO | 6 | 55300 | 331800 | 391524 | 331247 | 390871.46 | 553 | 331247 | 390871.46 | ZMAT | 2026-02-07 | 2026-03-31
RE/0066-PRJ-T5-CIV-RS-SU | Reinforcement Supply | 2010 | GR01 | 2010 | SMARTWORLD THE EDITION | Ram Niwas & SonsDeepak gupta | 9110001541 | 110 |  |  | 2026-02-07 | Steel Re-bar TMT 10 mm Dia. FE-550D | TO | 12 | 54300 | 651600 | 768888 | 651057 | 768247.26 | 543 | 651057 | 768247.26 | ZMAT | 2026-02-07 | 2026-03-31
RE/0066-PRJ-T5-CIV-RS-SU | Reinforcement Supply | 2010 | GR01 | 2010 | SMARTWORLD THE EDITION | Petropol India LimitedSANJAY GUPTA | 9110001546 | 50 |  |  | 2026-02-07 | Steel Re-bar TMT 08 mm Dia. FE-550D | TO | 7 | 55300 | 387100 | 456778 | 387100 | 456778 | 0 | 387100 | 456778 | ZMAT | 2026-02-07 | 2026-03-31
RE/0066-PRJ-T5-CIV-RS-SU | Reinforcement Supply | 2010 | GR01 | 2010 | SMARTWORLD THE EDITION | Petropol India LimitedSANJAY GUPTA | 9110001546 | 110 |  |  | 2026-02-07 | Steel Re-bar TMT 10 mm Dia. FE-550D | TO | 15 | 54300 | 814500 | 961110 | 811785 | 957906.3 | 2715 | 811785 | 957906.3 | ZMAT | 2026-02-07 | 2026-03-31
RE/0066-PRJ-T5-CIV-RS-SU | Reinforcement Supply | 2010 | GR01 | 2010 | SMARTWORLD THE EDITION | Jindal Steel Limited | 9110001551 | 50 |  |  | 2026-02-07 | Steel Re-bar TMT 12 mm Dia. FE-550D | TO | 26 | 58500 | 1521000 | 1794780 | 1521000 | 1794780 | 0 | 1521000 | 1794780 | ZMAT | 2026-02-07 | 2026-03-07
RE/0066-PRJ-T5-CIV-RS-SU | Reinforcement Supply | 2010 | GR01 | 2010 | SMARTWORLD THE EDITION | Jindal Steel Limited | 9110001551 | 110 |  |  | 2026-02-07 | Steel Re-bar TMT 16 mm Dia. FE-550D | TO | 30 | 58500 | 1755000 | 2070900 | 1755000 | 2070900 | 0 | 1755000 | 2070900 | ZMAT | 2026-02-07 | 2026-03-07
RE/0066-PRJ-T5-CIV-RS-SU | Reinforcement Supply | 2010 | GR01 | 2010 | SMARTWORLD THE EDITION | Jindal Steel Limited | 9110001551 | 170 |  |  | 2026-02-07 | Steel Re-bar TMT 20 mm Dia. FE-550D | TO | 3 | 58500 | 175500 | 207090 | 0 | 0 | 175500 | 0 | 0 | ZMAT | 2026-02-07 | 2026-03-07
RE/0066-PRJ-T5-CIV-RS-SU | Reinforcement Supply | 2010 | GR01 | 2010 | SMARTWORLD THE EDITION | Jindal Steel Limited | 9110001551 | 230 |  |  | 2026-02-07 | Steel Re-bar TMT 25 mm Dia. FE-550D | TO | 20 | 58500 | 1170000 | 1380600 | 1169415 | 1379909.7 | 585 | 1169415 | 1379909.7 | ZMAT | 2026-02-07 | 2026-03-07
RE/0066-PRJ-T5-CIV-RS-SU | Reinforcement Supply | 2010 | GR01 | 2010 | SMARTWORLD THE EDITION | Jindal Steel Limited | 9110001557 | 50 |  |  | 2026-02-10 | Steel Re-bar TMT 12 mm Dia. FE-550D | TO | 27 | 58500 | 1579500 | 1863810 | 1629459 | 1922761.62 | 49959 | 1629459 | 1922761.62 | ZMAT | 2026-02-10 | 2026-03-10
RE/0066-PRJ-T5-CIV-RS-SU | Reinforcement Supply | 2010 | GR01 | 2010 | SMARTWORLD THE EDITION | Jindal Steel Limited | 9110001557 | 110 |  |  | 2026-02-10 | Steel Re-bar TMT 25 mm Dia. FE-550D | TO | 48 | 58500 | 2808000 | 3313440 | 2237508 | 2640259.44 | 570492 | 2237508 | 2640259.44 | ZMAT | 2026-02-10 | 2026-03-10
RE/0066-PRJ-T5-CIV-RS-SU | Reinforcement Supply | 2010 | GR01 | 2010 | SMARTWORLD THE EDITION | Petropol India LimitedSANJAY GUPTA | 9110001558 | 50 |  |  | 2026-02-10 | Steel Re-bar TMT 08 mm Dia. FE-550D | TO | 18 | 55300 | 995400 | 1174572 | 994294 | 1173266.92 | 1106 | 994294 | 1173266.92 | ZMAT | 2026-02-10 | 2026-03-10
RE/0066-PRJ-T5-CIV-RS-SU | Reinforcement Supply | 2010 | GR01 | 2010 | SMARTWORLD THE EDITION | Ram Niwas & SonsDeepak gupta | 9110001607 | 50 |  |  | 2026-03-11 | Steel Re-bar TMT 10 mm Dia. FE-550D | TO | 37 | 55800 | 2064600 | 2436228 | 2064600 | 2436228 | 0 | 2064600 | 2436228 | ZMAT | 2026-03-11 | 2026-04-11
RE/0066-PRJ-T5-CIV-RS-SU | Reinforcement Supply | 2010 | GR01 | 2010 | SMARTWORLD THE EDITION | Ram Niwas & SonsDeepak gupta | 9110001607 | 110 |  |  | 2026-03-11 | Steel Re-bar TMT 08 mm Dia. FE-550D | TO | 30 | 56800 | 1704000 | 2010720 | 1677304 | 1979218.72 | 26696 | 1677304 | 1979218.72 | ZMAT | 2026-03-11 | 2026-04-11
RE/0066-PRJ-T5-CIV-RS-SU | Reinforcement Supply | 2010 | GR01 | 2010 | SMARTWORLD THE EDITION | ESL STEEL LIMITED | 9110001613 | 50 |  |  | 2026-03-11 | Steel Re-bar TMT 12 mm Dia. FE-550D | TO | 37 | 58250 | 2155250 | 2543195 | 2155250 | 2543195 | 0 | 2155250 | 2543195 | ZMAT | 2026-03-11 | 2026-04-11
RE/0066-PRJ-T5-CIV-RS-SU | Reinforcement Supply | 2010 | GR01 | 2010 | SMARTWORLD THE EDITION | ESL STEEL LIMITED | 9110001613 | 110 |  |  | 2026-03-11 | Steel Re-bar TMT 16 mm Dia. FE-550D | TO | 30 | 58250 | 1747500 | 2062050 | 1747500 | 2062050 | 0 | 1747500 | 2062050 | ZMAT | 2026-03-11 | 2026-04-11
RE/0066-PRJ-T5-CIV-RS-SU | Reinforcement Supply | 2010 | GR01 | 2010 | SMARTWORLD THE EDITION | ESL STEEL LIMITED | 9110001613 | 170 |  |  | 2026-03-11 | Steel Re-bar TMT 20 mm Dia. FE-550D | TO | 27 | 58250 | 1572750 | 1855845 | 1572750 | 1855845 | 0 | 1572750 | 1855845 | ZMAT | 2026-03-11 | 2026-04-11
RE/0066-PRJ-T5-CIV-RS-SU | Reinforcement Supply | 2010 | GR01 | 2010 | SMARTWORLD THE EDITION | ESL STEEL LIMITED | 9110001613 | 230 |  |  | 2026-03-11 | Steel Re-bar TMT 25 mm Dia. FE-550D | TO | 25 | 58250 | 1456250 | 1718375 | 1456250 | 1718375 | 0 | 1456250 | 1718375 | ZMAT | 2026-03-11 | 2026-04-11
RE/0066-PRJ-T5-CIV-RS-SU | Reinforcement Supply | 2010 | GR01 | 2010 | SMARTWORLD THE EDITION | Ram Niwas & SonsDeepak gupta | 9110001691 | 50 |  |  | 2026-04-10 | Steel Re-bar TMT 08 mm Dia. FE-550D | TO | 34 | 60800 | 2067200 | 2439296 | 2169344 | 2559825.92 | 102144 | 2169344 | 2559825.92 | ZMAT | 2026-04-10 | 2026-05-10
RE/0066-PRJ-T5-CIV-RS-SU | Reinforcement Supply | 2010 | GR01 | 2010 | SMARTWORLD THE EDITION | Ram Niwas & SonsDeepak gupta | 9110001691 | 110 |  |  | 2026-04-10 | Steel Re-bar TMT 10 mm Dia. FE-550D | TO | 9 | 59800 | 538200 | 635076 | 482586 | 569451.48 | 55614 | 482586 | 569451.48 | ZMAT | 2026-04-10 | 2026-05-10
RE/0066-PRJ-T5-CIV-RS-SU | Reinforcement Supply | 2010 | GR01 | 2010 | SMARTWORLD THE EDITION | ESL STEEL LIMITED | 9110001698 | 50 |  |  | 2026-04-10 | Steel Re-bar TMT 12 mm Dia. FE-550D | TO | 44 | 60500 | 2662000 | 3141160 | 2641611.5 | 3117101.57 | 20388.5 | 2641611.5 | 3117101.57 | ZMAT | 2026-04-10 | 2026-05-10
RE/0066-PRJ-T5-CIV-RS-SU | Reinforcement Supply | 2010 | GR01 | 2010 | SMARTWORLD THE EDITION | ESL STEEL LIMITED | 9110001698 | 110 |  |  | 2026-04-10 | Steel Re-bar TMT 16 mm Dia. FE-550D | TO | 9.5 | 60500 | 574750 | 678205 | 586850 | 692483 | 12100 | 586850 | 692483 | ZMAT | 2026-04-10 | 2026-05-10
RE/0066-PRJ-T5-CIV-RS-SU | Reinforcement Supply | 2010 | GR01 | 2010 | SMARTWORLD THE EDITION | ESL STEEL LIMITED | 9110001698 | 170 |  |  | 2026-04-10 | Steel Re-bar TMT 20 mm Dia. FE-550D | TO | 13 | 60500 | 786500 | 928070 | 786500 | 928070 | 0 | 786500 | 928070 | ZMAT | 2026-04-10 | 2026-05-10
RE/0066-PRJ-T5-CIV-RS-SU | Reinforcement Supply | 2010 | GR01 | 2010 | SMARTWORLD THE EDITION | ESL STEEL LIMITED | 9110001698 | 230 |  |  | 2026-04-10 | Steel Re-bar TMT 25 mm Dia. FE-550D | TO | 25 | 60500 | 1512500 | 1784750 | 1512500 | 1784750 | 0 | 1512500 | 1784750 | ZMAT | 2026-04-10 | 2026-05-10
RE/0066-PRJ-T5-CIV-RS-SU | Reinforcement Supply | 2010 | GR01 | 2010 | SMARTWORLD THE EDITION | ESL STEEL LIMITED | 9110001698 | 290 |  |  | 2026-04-10 | Steel Re-bar TMT 32 mm Dia. FE-550D | TO | 6 | 60500 | 363000 | 428340 | 363000 | 428340 | 0 | 363000 | 428340 | ZMAT | 2026-04-10 | 2026-05-10
RE/0066-PRJ-T5-CIV-RS-SU | Reinforcement Supply | 2010 | GR01 | 2010 | SMARTWORLD THE EDITION | Petropol India LimitedSANJAY GUPTA | 9110001791 | 50 |  |  | 2026-05-11 | Steel Re-bar TMT 08 mm Dia. FE-550D | TO | 53 | 55700 | 2952100 | 3483478 | 2952100 | 3483478 | 0 | 2952100 | 3483478 | ZMAT | 2026-05-11 | 2026-06-11
RE/0066-PRJ-T5-CIV-RS-SU | Reinforcement Supply | 2010 | GR01 | 2010 | SMARTWORLD THE EDITION | Petropol India LimitedSANJAY GUPTA | 9110001791 | 110 |  |  | 2026-05-11 | Steel Re-bar TMT 10 mm Dia. FE-550D | TO | 3 | 54700 | 164100 | 193638 | 164100 | 193638 | 0 | 164100 | 193638 | ZMAT | 2026-05-11 | 2026-06-11
RE/0066-PRJ-T5-CIV-RS-SU | Reinforcement Supply | 2010 | GR01 | 2010 | SMARTWORLD THE EDITION | Jindal Steel Limited | 9110001796 | 50 |  |  | 2026-05-11 | Steel Re-bar TMT 12 mm Dia. FE-550D | TO | 33 | 57200 | 1887600 | 2227368 | 1887600 | 2227368 | 0 | 0 | 0 | ZMAT | 2026-05-11 | 2026-06-11
RE/0066-PRJ-T5-CIV-RS-SU | Reinforcement Supply | 2010 | GR01 | 2010 | SMARTWORLD THE EDITION | Jindal Steel Limited | 9110001796 | 110 |  |  | 2026-05-11 | Steel Re-bar TMT 16 mm Dia. FE-550D | TO | 3 | 57200 | 171600 | 202488 | 85800 | 101244 | 85800 | 0 | 0 | ZMAT | 2026-05-11 | 2026-06-11
RE/0066-PRJ-T5-CIV-RS-SU | Reinforcement Supply | 2010 | GR01 | 2010 | SMARTWORLD THE EDITION | Jindal Steel Limited | 9110001796 | 170 |  |  | 2026-05-11 | Steel Re-bar TMT 20 mm Dia. FE-550D | TO | 29 | 57200 | 1658800 | 1957384 | 1658800 | 1957384 | 0 | 0 | 0 | ZMAT | 2026-05-11 | 2026-06-11
RE/0066-PRJ-T5-CIV-RS-SU | Reinforcement Supply | 2010 | GR01 | 2010 | SMARTWORLD THE EDITION | Jindal Steel Limited | 9110001796 | 230 |  |  | 2026-05-11 | Steel Re-bar TMT 25 mm Dia. FE-550D | TO | 13 | 57200 | 743600 | 877448 | 743600 | 877448 | 0 | 0 | 0 | ZMAT | 2026-05-11 | 2026-06-11
RE/0066-PRJ-T5-CIV-RS-SU | Reinforcement Supply | 2010 | GR01 | 2010 | SMARTWORLD THE EDITION | Jindal Steel Limited | 9110001796 | 290 |  |  | 2026-05-11 | Steel Re-bar TMT 32 mm Dia. FE-550D | TO | 4 | 57200 | 228800 | 269984 | 228800 | 269984 | 0 | 0 | 0 | ZMAT | 2026-05-11 | 2026-06-11
RE/0066-PRJ-T5-CIV-SW-AS | Aluminum Shuttering Supply | 2010 | GR01 | 2010 | SMARTWORLD THE EDITION | Ahluwalia Contracts India Limited | 9140000321 | 60 |  |  | 2024-07-20 | CENTERING & SHUTTERING Part B | AU | 1 | 0 | 168589130.13 | 198935173.55 | 53439037.51 | 63058064.26 | 115150092.62 | 43222781.46 | 51002882.12 | ZSER | 2024-07-15 | 2027-01-14
RE/0066-PRJ-T5-CIV-SW-CS | Conventional Shuttering | 2010 | GR01 | 2010 | SMARTWORLD THE EDITION | Ahluwalia Contracts India Limited | 9140000321 | 50 |  |  | 2024-07-20 | CENTERING & SHUTTERING Part A | AU | 1 | 0 | 18110979.38 | 21370955.67 | 15646566.4 | 18462948.35 | 2464412.98 | 15646566.46 | 18462948.42 | ZSER | 2024-07-15 | 2027-01-14
RE/0066-PRJ-T5-CIV-SW-SO | Shuttering Other | 2010 | GR01 | 2010 |  |  |  | 0 | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
RE/0066-PRJ-T5-CIV-WP | Waterproofing Works | 2010 | GR01 | 2010 | SMARTWORLD THE EDITION | Ahluwalia Contracts India Limited | 9140000321 | 110 |  |  | 2024-07-20 | FLOORING | AU | 1 | 0 | 1433 | 1690.94 | 0 | 0 | 1433 | 0 | 0 | ZSER | 2024-07-15 | 2027-01-14
RE/0066-PRJ-T5-CIV-WP | Waterproofing Works | 2010 | GR01 | 2010 | SMARTWORLD THE EDITION | Ahluwalia Contracts India Limited | 9140000321 | 120 |  |  | 2024-07-20 | WATER-PROOFING WORKS | AU | 1 | 0 | 19407993.86 | 22901432.75 | 440146.86 | 519373.3 | 18967847 | 440146.86 | 519373.3 | ZSER | 2024-07-15 | 2027-01-14
RE/0066-PRJ-T5-FAC-EF | Elevation Feature | 2010 | GR01 | 2010 | SMARTWORLD THE EDITION | Ahluwalia Contracts India Limited | 9140000321 | 100 |  |  | 2024-07-20 | STRUCTURAL STEEL WORKS | AU | 1 | 0 | 0.01 | 0.01 | 0 | 0 | 0.01 | 0 | 0 | ZSER | 2024-07-15 | 2027-01-14
RE/0066-PRJ-T5-FAC-EP | External Paint | 2010 | GR01 | 2010 | SMARTWORLD THE EDITION | Ahluwalia Contracts India Limited | 9140000321 | 160 |  |  | 2024-07-20 | Amed-Monthly rental payment to M/S ACIL | AU | 1 | 0 | 4866880 | 5742918.4 | 0 | 0 | 4866880 | 0 | 0 | ZSER | 2024-07-15 | 2027-01-14
RE/0066-PRJ-T5-FAC-GL | Glazing Works | 2010 | GR01 | 2010 |  |  |  | 0 | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
RE/0066-PRJ-T5-FAC-RA | Railing Works | 2010 | GR01 | 2010 |  |  |  | 0 | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
RE/0066-PRJ-T5-FIS-CF | Ceiling Finish Works | 2010 | GR01 | 2010 | SMARTWORLD THE EDITION | H. S. OBEROI BUILDTECH PVT. LTD.MANISH SINGH | 9140000561 | 20 |  |  | 2026-01-31 | Lead Apartment -Lift Lobby -Finishing | AU | 1 | 1077040.47 | 64655.85 | 76293.9 | 0 | 0 | 64655.85 | 0 | 0 | ZSER | 2026-01-16 | 2026-04-16
RE/0066-PRJ-T5-FIS-CF | Ceiling Finish Works | 2010 | GR01 | 2010 | SMARTWORLD THE EDITION | ANIMESH BUILDTECH INDIA PRIVATE LIMSunil kumar pandey | 9140000603 | 10 |  |  | 2026-03-10 | Finishing Work -T5 | AU | 1 | 0 | 76049264.22 | 89738131.78 | 0 | 0 | 76049264.22 | 0 | 0 | ZSER | 2026-04-14 | 2028-04-13
RE/0066-PRJ-T5-FIS-CF | Ceiling Finish Works | 2010 | GR01 | 2010 | SMARTWORLD THE EDITION | ANIMESH BUILDTECH INDIA PRIVATE LIMSunil kumar pandey | 9140000603 | 20 |  |  | 2026-03-10 | Finishing Work Lift Lobby -T5 | AU | 1 | 46230888.06 | 1167800 | 1378004 | 0 | 0 | 1167800 | 0 | 0 | ZSER | 2026-04-14 | 2028-04-13
RE/0066-PRJ-T5-FIS-DW | Door Works | 2010 | GR01 | 2010 |  |  |  | 0 | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
RE/0066-PRJ-T5-FIS-FF | Floor Finish Works | 2010 | GR01 | 2010 | SMARTWORLD THE EDITION | Ahluwalia Contracts India Limited | 9140000321 | 110 |  |  | 2024-07-20 | FLOORING | AU | 1 | 0 | 10574689.9 | 12478134.08 | 1111275.66 | 1311305.28 | 9463414.24 | 463031.53 | 546377.2 | ZSER | 2024-07-15 | 2027-01-14
RE/0066-PRJ-T5-FIS-FF | Floor Finish Works | 2010 | GR01 | 2010 | SMARTWORLD THE EDITION | H. S. OBEROI BUILDTECH PVT. LTD.MANISH SINGH | 9140000561 | 20 |  |  | 2026-01-31 | Lead Apartment -Lift Lobby -Finishing | AU | 1 | 0 | 394902.9 | 465985.42 | 2030717.8 | 2396247 | 1635814.9 | 0 | 0 | ZSER | 2026-01-16 | 2026-04-16
RE/0066-PRJ-T5-FIS-FF | Floor Finish Works | 2010 | GR01 | 2010 | SMARTWORLD THE EDITION | Spacewood Furnishers Pvt Ltd | 9140000598 | 10 |  |  | 2026-03-10 | SI of Kitchen & Vanit 4.5 BHK. | AU | 1 | 518812.2 | 137812.2 | 162618.4 | 0 | 0 | 137812.2 | 0 | 0 | ZSER | 2026-02-10 | 2026-03-10
RE/0066-PRJ-T5-FIS-FF | Floor Finish Works | 2010 | GR01 | 2010 | SMARTWORLD THE EDITION | ANIMESH BUILDTECH INDIA PRIVATE LIMSunil kumar pandey | 9140000603 | 10 |  |  | 2026-03-10 | Finishing Work -T5 | AU | 1 | 0 | 115430682 | 136208204.76 | 8650097.46 | 10207115 | 106780584.54 | 0 | 0 | ZSER | 2026-04-14 | 2028-04-13
RE/0066-PRJ-T5-FIS-FF | Floor Finish Works | 2010 | GR01 | 2010 | SMARTWORLD THE EDITION | ANIMESH BUILDTECH INDIA PRIVATE LIMSunil kumar pandey | 9140000603 | 20 |  |  | 2026-03-10 | Finishing Work Lift Lobby -T5 | AU | 1 | 0 | 26590118.4 | 31376339.71 | 0 | 0 | 26590118.4 | 0 | 0 | ZSER | 2026-04-14 | 2028-04-13
RE/0066-PRJ-T5-FIS-LF | Lobby Furniture | 2010 | GR01 | 2010 |  |  |  | 0 | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
RE/0066-PRJ-T5-FIS-MI | Misc Finish Works | 2010 | GR01 | 2010 | SMARTWORLD THE EDITION | ANIMESH BUILDTECH INDIA PRIVATE LIMSunil kumar pandey | 9140000603 | 10 |  |  | 2026-03-10 | Finishing Work -T5 | AU | 1 | 0 | 17369812 | 20496378.16 | 0 | 0 | 17369812 | 0 | 0 | ZSER | 2026-04-14 | 2028-04-13
RE/0066-PRJ-T5-FIS-MK | Modular Kitchen Works | 2010 | GR01 | 2010 | SMARTWORLD THE EDITION | Spacewood Furnishers Pvt Ltd | 9140000598 | 10 |  |  | 2026-03-10 | SI of Kitchen & Vanit 4.5 BHK. | AU | 1 | 0 | 381000 | 449580 | 0 | 0 | 381000 | 0 | 0 | ZSER | 2026-02-10 | 2026-03-10
RE/0066-PRJ-T5-FIS-MS | MS works | 2010 | GR01 | 2010 | SMARTWORLD THE EDITION | ANIMESH BUILDTECH INDIA PRIVATE LIMSunil kumar pandey | 9140000603 | 10 |  |  | 2026-03-10 | Finishing Work -T5 | AU | 1 | 0 | 3068000 | 3620240 | 0 | 0 | 3068000 | 0 | 0 | ZSER | 2026-04-14 | 2028-04-13
RE/0066-PRJ-T5-FIS-WF | Wall Finish Works | 2010 | GR01 | 2010 | SMARTWORLD THE EDITION | H. S. OBEROI BUILDTECH PVT. LTD.MANISH SINGH | 9140000561 | 20 |  |  | 2026-01-31 | Lead Apartment -Lift Lobby -Finishing | AU | 1 | 0 | 607987.41 | 717425.14 | 0 | 0 | 607987.41 | 0 | 0 | ZSER | 2026-01-16 | 2026-04-16
RE/0066-PRJ-T5-FIS-WF | Wall Finish Works | 2010 | GR01 | 2010 | SMARTWORLD THE EDITION | ANIMESH BUILDTECH INDIA PRIVATE LIMSunil kumar pandey | 9140000603 | 10 |  |  | 2026-03-10 | Finishing Work -T5 | AU | 1 | 0 | 85943260 | 101413046.8 | 0 | 0 | 85943260 | 0 | 0 | ZSER | 2026-04-14 | 2028-04-13
RE/0066-PRJ-T5-FIS-WF | Wall Finish Works | 2010 | GR01 | 2010 | SMARTWORLD THE EDITION | ANIMESH BUILDTECH INDIA PRIVATE LIMSunil kumar pandey | 9140000603 | 20 |  |  | 2026-03-10 | Finishing Work Lift Lobby -T5 | AU | 1 | 0 | 18472969.66 | 21798104.2 | 0 | 0 | 18472969.66 | 0 | 0 | ZSER | 2026-04-14 | 2028-04-13
RE/0066-PRJ-T5-FIS-WO | Wood Work | 2010 | GR01 | 2010 | SMARTWORLD THE EDITION | H. S. OBEROI BUILDTECH PVT. LTD.MANISH SINGH | 9140000561 | 20 |  |  | 2026-01-31 | Lead Apartment -Lift Lobby -Finishing | AU | 1 | 0 | 9494.31 | 11203.29 | 0 | 0 | 9494.31 | 0 | 0 | ZSER | 2026-01-16 | 2026-04-16
RE/0066-PRJ-T5-MEP-EW-HE | High Side Electrical Works | 2010 | GR01 | 2010 | SMARTWORLD THE EDITION | HKE Electric Contracts | 9140000365 | 10 |  |  | 2024-09-25 | Lightning Protection System for Basement | AU | 1 | 287000 | 143500 | 169330 | 143500 | 169330 | 0 | 143500.85 | 169331 | ZSER | 2024-09-25 | 2024-10-24
RE/0066-PRJ-T5-MEP-EW-HE | High Side Electrical Works | 2010 | GR01 | 2010 | SMARTWORLD THE EDITION | Dehn India Pvt Ltd | 9140000379 | 10 |  |  | 2024-10-24 | Lightning Protection System for Basement | AU | 1 | 0 | 979507 | 1155818.26 | 114034.79 | 134561.05 | 865472.21 | 114034.81 | 134561.08 | ZSER | 2024-10-24 | 2027-08-23
RE/0066-PRJ-T5-MEP-EW-HE | High Side Electrical Works | 2010 | GR01 | 2010 | SMARTWORLD THE EDITION | SATKARTAR ELECTRICALS AND ELECTRONIPRIVATE LIMITED | 9140000677 | 50 |  |  | 2026-06-02 | Electrical Works Tower T5 | AU | 1 | 63981894.21 | 22137268.33 | 26121976.63 | 0 | 0 | 22137268.33 | 0 | 0 | ZSER | 2026-06-01 | 2028-02-01
RE/0066-PRJ-T5-MEP-EW-LE | Low Side Electrical Works | 2010 | GR01 | 2010 | SMARTWORLD THE EDITION | Ahluwalia Contracts India Limited | 9140000321 | 140 |  |  | 2024-07-20 | CONDUITING | AU | 1 | 0 | 21508839.87 | 25380431.05 | 5697369.57 | 6722896.09 | 15811470.3 | 3998645.06 | 4718401.17 | ZSER | 2024-07-15 | 2027-01-14
RE/0066-PRJ-T5-MEP-EW-LE | Low Side Electrical Works | 2010 | GR01 | 2010 | SMARTWORLD THE EDITION | SATKARTAR ELECTRICALS AND ELECTRONIPRIVATE LIMITED | 9140000677 | 50 |  |  | 2026-06-02 | Electrical Works Tower T5 | AU | 1 | 0 | 41844625.88 | 49376658.54 | 0 | 0 | 41844625.88 | 0 | 0 | ZSER | 2026-06-01 | 2028-02-01
RE/0066-PRJ-T5-MEP-EW-LE | Low Side Electrical Works | 2010 | GR01 | 2010 | SMARTWORLD THE EDITION | TRIPLE A ENGINEERING PRIVATE LIMIT | 9160002689 | 10 |  |  | 2026-01-31 | Point Wiring (Flats) | AU | 1 | 133714 | 133714 | 133714 | 0 | 0 | 133714 | 0 | 0 | ZGEN | 2026-01-15 | 2026-04-15
RE/0066-PRJ-T5-MEP-EW-LE | Low Side Electrical Works | 2010 | GR01 | 2010 | SMARTWORLD THE EDITION | TRIPLE A ENGINEERING PRIVATE LIMIT | 9160002689 | 20 |  |  | 2026-01-31 | Point Wiring (Common area 1st . Floor ) | AU | 1 | 4865 | 4865 | 4865 | 0 | 0 | 4865 | 0 | 0 | ZGEN | 2026-01-15 | 2026-04-15
RE/0066-PRJ-T5-MEP-EW-LE | Low Side Electrical Works | 2010 | GR01 | 2010 | SMARTWORLD THE EDITION | TRIPLE A ENGINEERING PRIVATE LIMIT | 9160002689 | 30 |  |  | 2026-01-31 | Point Wiring (Staircase) | AU | 1 | 5376 | 5376 | 5376 | 0 | 0 | 5376 | 0 | 0 | ZGEN | 2026-01-15 | 2026-04-15
RE/0066-PRJ-T5-MEP-EW-LE | Low Side Electrical Works | 2010 | GR01 | 2010 | SMARTWORLD THE EDITION | TRIPLE A ENGINEERING PRIVATE LIMIT | 9160002689 | 40 |  |  | 2026-01-31 | Automation Work | AU | 1 | 313340 | 313340 | 313340 | 0 | 0 | 313340 | 0 | 0 | ZGEN | 2026-01-15 | 2026-04-15
RE/0066-PRJ-T5-MEP-EW-LE | Low Side Electrical Works | 2010 | GR01 | 2010 | SMARTWORLD THE EDITION | TRIPLE A ENGINEERING PRIVATE LIMIT | 9160002689 | 50 |  |  | 2026-01-31 | MODULAR SWITCHES & SOCKET | AU | 1 | 53533 | 53533 | 53533 | 0 | 0 | 53533 | 0 | 0 | ZGEN | 2026-01-15 | 2026-04-15
RE/0066-PRJ-T5-MEP-EW-LE | Low Side Electrical Works | 2010 | GR01 | 2010 | SMARTWORLD THE EDITION | TRIPLE A ENGINEERING PRIVATE LIMIT | 9160002689 | 60 |  |  | 2026-01-31 | SUB-MAINS WIRING | AU | 1 | 129450 | 129450 | 129450 | 0 | 0 | 129450 | 0 | 0 | ZGEN | 2026-01-15 | 2026-04-15
RE/0066-PRJ-T5-MEP-EW-LE | Low Side Electrical Works | 2010 | GR01 | 2010 | SMARTWORLD THE EDITION | TRIPLE A ENGINEERING PRIVATE LIMIT | 9160002689 | 70 |  |  | 2026-01-31 | CABLE TRAYS | AU | 1 | 39150 | 39150 | 39150 | 0 | 0 | 39150 | 0 | 0 | ZGEN | 2026-01-15 | 2026-04-15
RE/0066-PRJ-T5-MEP-EW-LE | Low Side Electrical Works | 2010 | GR01 | 2010 | SMARTWORLD THE EDITION | TRIPLE A ENGINEERING PRIVATE LIMIT | 9160002689 | 80 |  |  | 2026-01-31 | MV PANELS | AU | 1 | 93000 | 93000 | 93000 | 0 | 0 | 93000 | 0 | 0 | ZGEN | 2026-01-15 | 2026-04-15
RE/0066-PRJ-T5-MEP-EW-LE | Low Side Electrical Works | 2010 | GR01 | 2010 | SMARTWORLD THE EDITION | TRIPLE A ENGINEERING PRIVATE LIMIT | 9160002689 | 90 |  |  | 2026-01-31 | DISTRIBUTION SYSTEM AND ONT | AU | 1 | 36700 | 36700 | 36700 | 0 | 0 | 36700 | 0 | 0 | ZGEN | 2026-01-15 | 2026-04-15
RE/0066-PRJ-T5-MEP-EW-LE | Low Side Electrical Works | 2010 | GR01 | 2010 | SMARTWORLD THE EDITION | TRIPLE A ENGINEERING PRIVATE LIMIT | 9160002689 | 100 |  |  | 2026-01-31 | EARTHING INSTALLATION | AU | 1 | 69350 | 69350 | 69350 | 0 | 0 | 69350 | 0 | 0 | ZGEN | 2026-01-15 | 2026-04-15
RE/0066-PRJ-T5-MEP-EW-LE | Low Side Electrical Works | 2010 | GR01 | 2010 | SMARTWORLD THE EDITION | TRIPLE A ENGINEERING PRIVATE LIMIT | 9160002689 | 110 |  |  | 2026-01-31 | COMMON AREA LIGHT (FOR STAIRCASE, LIFT L | AU | 1 | 294000 | 294000 | 294000 | 0 | 0 | 294000 | 0 | 0 | ZGEN | 2026-01-15 | 2026-04-15
RE/0066-PRJ-T5-MEP-EW-LE | Low Side Electrical Works | 2010 | GR01 | 2010 | SMARTWORLD THE EDITION | TRIPLE A ENGINEERING PRIVATE LIMIT | 9160002689 | 120 |  |  | 2026-01-31 | FIRE ALARM SYSTEM & PUBLIC ADDRESS SYSTE | AU | 1 | 42438 | 42438 | 42438 | 0 | 0 | 42438 | 0 | 0 | ZGEN | 2026-01-15 | 2026-04-15
RE/0066-PRJ-T5-MEP-EW-LE | Low Side Electrical Works | 2010 | GR01 | 2010 | SMARTWORLD THE EDITION | TRIPLE A ENGINEERING PRIVATE LIMIT | 9160002689 | 130 |  |  | 2026-01-31 | VIDEO DOOR PHONE, | AU | 1 | 26000 | 26000 | 26000 | 0 | 0 | 26000 | 0 | 0 | ZGEN | 2026-01-15 | 2026-04-15
RE/0066-PRJ-T5-MEP-EW-LS | Light Fixtures Supply | 2010 | GR01 | 2010 |  |  |  | 0 | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
RE/0066-PRJ-T5-MEP-FF | Fire Fighting Work | 2010 | GR01 | 2010 | SMARTWORLD THE EDITION | Jagrati Civil Constructions Pvt Ltd | 9140000529 | 70 |  |  | 2025-11-26 | FIRE HYDRANT & EQUIPMENT | AU | 1 | 69523 | 69523 | 82037.14 | 0 | 0 | 69523 | 0 | 0 | ZSER | 2025-11-25 | 2026-03-15
RE/0066-PRJ-T5-MEP-FF | Fire Fighting Work | 2010 | GR01 | 2010 | SMARTWORLD THE EDITION | Jagrati Civil Constructions Pvt Ltd | 9140000529 | 80 |  |  | 2025-11-26 | AUTOMATIC SPRINKLER | AU | 1 | 224160 | 224160 | 264508.8 | 0 | 0 | 224160 | 0 | 0 | ZSER | 2025-11-25 | 2026-03-15
RE/0066-PRJ-T5-MEP-FF | Fire Fighting Work | 2010 | GR01 | 2010 | SMARTWORLD THE EDITION | Jagrati Civil Constructions Pvt Ltd | 9140000529 | 90 |  |  | 2025-11-26 | PORTABLE FIRE EXTINGUISHERS | AU | 1 | 8500 | 8500 | 10030 | 0 | 0 | 8500 | 0 | 0 | ZSER | 2025-11-25 | 2026-03-15
RE/0066-PRJ-T5-MEP-FF | Fire Fighting Work | 2010 | GR01 | 2010 | SMARTWORLD THE EDITION | Atom MEP Engineers Pvt. Ltd. | 9140000668 | 270 |  |  | 2026-05-19 | FF-FIRE HYDRANT & EQUIPMENT - T5 | AU | 1 | 3229898.36 | 3229898.36 | 3811280.06 | 0 | 0 | 3229898.36 | 0 | 0 | ZSER | 2026-04-04 | 2028-02-04
RE/0066-PRJ-T5-MEP-FF | Fire Fighting Work | 2010 | GR01 | 2010 | SMARTWORLD THE EDITION | Atom MEP Engineers Pvt. Ltd. | 9140000668 | 320 |  |  | 2026-05-19 | FF-AUTOMATIC SPRINKLER & WATER -T5 | AU | 1 | 18260627 | 18260627 | 21547539.86 | 0 | 0 | 18260627 | 0 | 0 | ZSER | 2026-04-04 | 2028-02-04
RE/0066-PRJ-T5-MEP-FF | Fire Fighting Work | 2010 | GR01 | 2010 | SMARTWORLD THE EDITION | Atom MEP Engineers Pvt. Ltd. | 9140000668 | 370 |  |  | 2026-05-19 | FF-PORTABLE FIRE EXTINGUISHERS -T5 | AU | 1 | 305085 | 305085 | 360000.3 | 0 | 0 | 305085 | 0 | 0 | ZSER | 2026-04-04 | 2028-02-04
RE/0066-PRJ-T5-MEP-HV-HS | High Side | 2010 | GR01 | 2010 |  |  |  | 0 | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
RE/0066-PRJ-T5-MEP-HV-LS | Low Side | 2010 | GR01 | 2010 | SMARTWORLD THE EDITION | Pahuja Aircon Pvt LtdVinay Malik | 9140000680 | 10 |  |  | 2026-06-02 | Common Area - HVAC Ducting & Grilles | AU | 1 | 196112 | 196112 | 231412.16 | 0 | 0 | 196112 | 0 | 0 | ZSER | 2026-04-15 | 2026-06-15
RE/0066-PRJ-T5-MEP-LT | Lifts | 2010 | GR01 | 2010 |  |  |  | 0 | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
RE/0066-PRJ-T5-MEP-PB-FS | Fixtures Supply | 2010 | GR01 | 2010 |  |  |  | 0 | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
RE/0066-PRJ-T5-MEP-PB-IP | Internal Plumbing | 2010 | GR01 | 2010 | SMARTWORLD THE EDITION | Jagrati Civil Constructions Pvt Ltd | 9140000529 | 30 |  |  | 2025-11-26 | SANITARY FIXTURES & FITTINGS 3 bhk | AU | 1 | 27875 | 27875 | 32892.5 | 0 | 0 | 27875 | 0 | 0 | ZSER | 2025-11-25 | 2026-03-15
RE/0066-PRJ-T5-MEP-PB-IP | Internal Plumbing | 2010 | GR01 | 2010 | SMARTWORLD THE EDITION | Jagrati Civil Constructions Pvt Ltd | 9140000529 | 40 |  |  | 2025-11-26 | SANITARY FIXTURES & FITTINGS 4 bhk | AU | 1 | 32975 | 32975 | 38910.5 | 0 | 0 | 32975 | 0 | 0 | ZSER | 2025-11-25 | 2026-03-15
RE/0066-PRJ-T5-MEP-PB-IP | Internal Plumbing | 2010 | GR01 | 2010 | SMARTWORLD THE EDITION | Jagrati Civil Constructions Pvt Ltd | 9140000529 | 50 |  |  | 2025-11-26 | INTERNAL DRAINAGE (SOIL, WASTE | AU | 1 | 130413.73 | 130413.73 | 153888.2 | 0 | 0 | 130413.73 | 0 | 0 | ZSER | 2025-11-25 | 2026-03-15
RE/0066-PRJ-T5-MEP-PB-IP | Internal Plumbing | 2010 | GR01 | 2010 | SMARTWORLD THE EDITION | Jagrati Civil Constructions Pvt Ltd | 9140000529 | 60 |  |  | 2025-11-26 | DOMESTIC AND FLUSHING WATER | AU | 1 | 86881.02 | 86881.02 | 102519.6 | 0 | 0 | 86881.02 | 0 | 0 | ZSER | 2025-11-25 | 2026-03-15
RE/0066-PRJ-T5-MEP-PB-IP | Internal Plumbing | 2010 | GR01 | 2010 | SMARTWORLD THE EDITION | Atom MEP Engineers Pvt. Ltd. | 9140000668 | 10 |  |  | 2026-05-19 | SANITARY FIXTURES & FITTINGS T-5 | AU | 1 | 3329060 | 3329060 | 3928290.8 | 0 | 0 | 3329060 | 0 | 0 | ZSER | 2026-04-04 | 2028-02-04
RE/0066-PRJ-T5-MEP-PB-IP | Internal Plumbing | 2010 | GR01 | 2010 | SMARTWORLD THE EDITION | Atom MEP Engineers Pvt. Ltd. | 9140000668 | 60 |  |  | 2026-05-19 | INTERNAL DRAINAGE T-5 | AU | 1 | 16873825.6 | 16873825.6 | 19911114.21 | 0 | 0 | 16873825.6 | 0 | 0 | ZSER | 2026-04-04 | 2028-02-04
RE/0066-PRJ-T5-MEP-PB-IP | Internal Plumbing | 2010 | GR01 | 2010 | SMARTWORLD THE EDITION | Atom MEP Engineers Pvt. Ltd. | 9140000668 | 110 |  |  | 2026-05-19 | DOMESTIC AND FLUSHING WATER T-5 | AU | 1 | 15363960.24 | 15363960.24 | 18129473.08 | 0 | 0 | 15363960.24 | 0 | 0 | ZSER | 2026-04-04 | 2028-02-04
RE/0066-PRJ-T5-MEP-PB-IP | Internal Plumbing | 2010 | GR01 | 2010 | SMARTWORLD THE EDITION | Atom MEP Engineers Pvt. Ltd. | 9140000668 | 180 |  |  | 2026-05-19 | MISCELLANEOUS ITEMS FOR TERRACE WATER-T5 | AU | 1 | 428820 | 428820 | 506007.6 | 0 | 0 | 428820 | 0 | 0 | ZSER | 2026-04-04 | 2028-02-04
RE/0066-PRJ-T5-MEP-PB-JC | JACUZZI | 2010 | GR01 | 2010 |  |  |  | 0 | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
RE/0066-PRJ-T5-MEP-PN | PNG Gas Pipe Line | 2010 | GR01 | 2010 |  |  |  | 0 | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
RE/0066-PRJ-T6-CIV-CC-LA | Concrete Labour | 2010 | GR01 | 2010 |  |  |  | 0 | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
RE/0066-PRJ-T6-CIV-CC-SL | Concrete Supply & Labour | 2010 | GR01 | 2010 | SMARTWORLD THE EDITION | Ahluwalia Contracts India Limited | 9140000321 | 20 |  |  | 2024-07-20 | REINFORCED CEMENT CONCRETE-I part A | AU | 1 | 0 | 115725888.24 | 136556548.12 | 63259495.33 | 74646204.49 | 52466392.91 | 63259495.42 | 74646204.59 | ZSER | 2024-07-15 | 2027-01-14
RE/0066-PRJ-T6-CIV-CC-SL | Concrete Supply & Labour | 2010 | GR01 | 2010 | SMARTWORLD THE EDITION | Ahluwalia Contracts India Limited | 9140000321 | 30 |  |  | 2024-07-20 | REINFORCED CEMENT CONCRETE-I Part B | AU | 1 | 0 | 87484504.36 | 103231715.14 | 48732038.36 | 57503805.26 | 38752466 | 42204594.27 | 49801421.24 | ZSER | 2024-07-15 | 2027-01-14
RE/0066-PRJ-T6-CIV-CC-SL | Concrete Supply & Labour | 2010 | GR01 | 2010 | SMARTWORLD THE EDITION | Ahluwalia Contracts India Limited | 9140000321 | 40 |  |  | 2024-07-20 | REINFORCED CEMENT CONCRETE-I Part C | AU | 1 | 0 | 117487570.12 | 138635332.74 | 42343954.05 | 49965865.78 | 75143616.07 | 36441301.01 | 43000735.19 | ZSER | 2024-07-15 | 2027-01-14
RE/0066-PRJ-T6-CIV-CC-SL | Concrete Supply & Labour | 2010 | GR01 | 2010 | SMARTWORLD THE EDITION | Ahluwalia Contracts India Limited | 9140000321 | 180 |  |  | 2024-07-20 | SUBSTITUTE ITEM | AU | 1 | 0 | 1266038.72 | 1493925.69 | 963719.56 | 1137189.08 | 302319.16 | 963719.56 | 1137189.08 | ZSER | 2024-07-15 | 2027-01-14
RE/0066-PRJ-T6-CIV-CC-SU | Concrete Supply | 2010 | GR01 | 2010 |  |  |  | 0 | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
RE/0066-PRJ-T6-CIV-EW | Earthwork | 2010 | GR01 | 2010 | SMARTWORLD THE EDITION | Ahluwalia Contracts India Limited | 9140000321 | 10 |  |  | 2024-07-20 | SITE DEVLOPMENT AND EARTH WORK | AU | 1 | 0 | 572481 | 675527.58 | 77934.13 | 91962.27 | 494546.87 | 77934.13 | 91962.27 | ZSER | 2024-07-15 | 2027-01-14
RE/0066-PRJ-T6-CIV-MS | Misc Structure Works | 2010 | GR01 | 2010 | SMARTWORLD THE EDITION | Ahluwalia Contracts India Limited | 9140000321 | 100 |  |  | 2024-07-20 | STRUCTURAL STEEL WORKS | AU | 1 | 0 | 38647408.26 | 45603941.75 | 4649766.03 | 5486723.91 | 33997642.23 | 3598929.58 | 4246736.91 | ZSER | 2024-07-15 | 2027-01-14
RE/0066-PRJ-T6-CIV-MS | Misc Structure Works | 2010 | GR01 | 2010 | SMARTWORLD THE EDITION | Ahluwalia Contracts India Limited | 9140000321 | 130 |  |  | 2024-07-20 | INTERNAL & EXTERNAL PLASTERING | AU | 1 | 0 | 607320 | 716637.6 | 0 | 0 | 607320 | 0 | 0 | ZSER | 2024-07-15 | 2027-01-14
RE/0066-PRJ-T6-CIV-MS | Misc Structure Works | 2010 | GR01 | 2010 | SMARTWORLD THE EDITION | Ahluwalia Contracts India Limited | 9140000321 | 160 |  |  | 2024-07-20 | Amed-Monthly rental payment to M/S ACIL | AU | 1 | 0 | 1230377.3 | 1451845.21 | 343391.41 | 405201.86 | 886985.89 | 0 | 0 | ZSER | 2024-07-15 | 2027-01-14
RE/0066-PRJ-T6-CIV-MW | Masonry Works | 2010 | GR01 | 2010 | SMARTWORLD THE EDITION | Ahluwalia Contracts India Limited | 9140000321 | 90 |  |  | 2024-07-20 | MASONARY WORKS | AU | 1 | 0 | 9627637.23 | 11360611.93 | 2039353.83 | 2406437.52 | 7588283.4 | 2039353.82 | 2406437.51 | ZSER | 2024-07-15 | 2027-01-14
RE/0066-PRJ-T6-CIV-PW-IP | Internal Plaster | 2010 | GR01 | 2010 | SMARTWORLD THE EDITION | Ahluwalia Contracts India Limited | 9140000321 | 130 |  |  | 2024-07-20 | INTERNAL & EXTERNAL PLASTERING | AU | 1 | 0 | 7118735.46 | 8400107.84 | 0 | 0 | 7118735.46 | 0 | 0 | ZSER | 2024-07-15 | 2027-01-14
RE/0066-PRJ-T6-CIV-PW-XP | External Plaster | 2010 | GR01 | 2010 | SMARTWORLD THE EDITION | Ahluwalia Contracts India Limited | 9140000321 | 130 |  |  | 2024-07-20 | INTERNAL & EXTERNAL PLASTERING | AU | 1 | 0 | 251000 | 296180 | 0 | 0 | 251000 | 0 | 0 | ZSER | 2024-07-15 | 2027-01-14
RE/0066-PRJ-T6-CIV-RS-LA | Reinforcement Labour | 2010 | GR01 | 2010 | SMARTWORLD THE EDITION | Ahluwalia Contracts India Limited | 9140000321 | 70 |  |  | 2024-07-20 | REINFORCEMENT STEEL Installation Part A | AU | 1 | 0 | 33633149 | 39687115.82 | 32657466.89 | 38535810.93 | 975682.11 | 32657479.17 | 38535825.42 | ZSER | 2024-07-15 | 2027-01-14
RE/0066-PRJ-T6-CIV-RS-LA | Reinforcement Labour | 2010 | GR01 | 2010 | SMARTWORLD THE EDITION | Ahluwalia Contracts India Limited | 9140000321 | 80 |  |  | 2024-07-20 | REINFORCEMENT STEEL Installation Part B | AU | 1 | 0 | 129654971.89 | 152992866.83 | 44275536.95 | 52245133.6 | 85379434.94 | 38398302.58 | 45309997.05 | ZSER | 2024-07-15 | 2027-01-14
RE/0066-PRJ-T6-CIV-RS-SU | Reinforcement Supply | 2010 | GR01 | 2010 | SMARTWORLD THE EDITION | Carna Corporation Pvt LtdVISHWANATH | 9110000657 | 80 |  |  | 2024-08-03 | Fe 550D TMT Steel 8 MM dia. | TO | 2.5 | 52500 | 131250 | 154875 | 71400 | 84252 | 59850 | 71400 | 84252.01 | ZMAT | 2024-08-03 | 2024-09-03
RE/0066-PRJ-T6-CIV-RS-SU | Reinforcement Supply | 2010 | GR01 | 2010 | SMARTWORLD THE EDITION | Carna Corporation Pvt LtdVISHWANATH | 9110000657 | 90 |  |  | 2024-08-03 | Fe 550D TMT Steel 10 MM dia. | TO | 4.5 | 51250 | 230625 | 272137.5 | 184756.25 | 218012.38 | 45868.75 | 184756.25 | 218012.27 | ZMAT | 2024-08-03 | 2024-09-03
RE/0066-PRJ-T6-CIV-RS-SU | Reinforcement Supply | 2010 | GR01 | 2010 | SMARTWORLD THE EDITION | Carna Corporation Pvt LtdVISHWANATH | 9110000657 | 100 |  |  | 2024-08-03 | Fe 550D TMT Steel 12 MM dia. | TO | 64.5 | 50500 | 3257250 | 3843555 | 3239575 | 3822698.5 | 17675 | 3239575 | 3822698.5 | ZMAT | 2024-08-03 | 2024-09-03
RE/0066-PRJ-T6-CIV-RS-SU | Reinforcement Supply | 2010 | GR01 | 2010 | SMARTWORLD THE EDITION | Carna Corporation Pvt LtdVISHWANATH | 9110000657 | 110 |  |  | 2024-08-03 | Fe 550D TMT Steel 16 MM dia. | TO | 22 | 50500 | 1111000 | 1310980 | 1104687.5 | 1303531.25 | 6312.5 | 1104687.5 | 1303531.54 | ZMAT | 2024-08-03 | 2024-09-03
RE/0066-PRJ-T6-CIV-RS-SU | Reinforcement Supply | 2010 | GR01 | 2010 | SMARTWORLD THE EDITION | Carna Corporation Pvt LtdVISHWANATH | 9110000657 | 120 |  |  | 2024-08-03 | Fe 550D TMT Steel 20 MM dia. | TO | 10 | 50500 | 505000 | 595900 | 306535 | 361711.3 | 198465 | 306535 | 361711.31 | ZMAT | 2024-08-03 | 2024-09-03
RE/0066-PRJ-T6-CIV-RS-SU | Reinforcement Supply | 2010 | GR01 | 2010 | SMARTWORLD THE EDITION | Carna Corporation Pvt LtdVISHWANATH | 9110000657 | 130 |  |  | 2024-08-03 | Fe 550D TMT Steel 25 MM dia. | TO | 117.5 | 50500 | 5933750 | 7001825 | 5816590 | 6863576.2 | 117160 | 5816590 | 6863576.23 | ZMAT | 2024-08-03 | 2024-09-03
RE/0066-PRJ-T6-CIV-RS-SU | Reinforcement Supply | 2010 | GR01 | 2010 | SMARTWORLD THE EDITION | Carna Corporation Pvt LtdVISHWANATH | 9110000657 | 140 |  |  | 2024-08-03 | Fe 550D TMT Steel 32 MM dia. | TO | 588.5 | 50500 | 29719250 | 35068715 | 29579163 | 34903412.34 | 140087 | 29579163 | 34903423.75 | ZMAT | 2024-08-03 | 2024-09-03
RE/0066-PRJ-T6-CIV-RS-SU | Reinforcement Supply | 2010 | GR01 | 2010 | SMARTWORLD THE EDITION | Carna Corporation Pvt LtdVISHWANATH | 9110000708 | 10 |  |  | 2024-09-23 | Fe 550D TMT Steel 8 MM dia. | TO | 7.5 | 50250 | 376875 | 444712.5 | 349991.26 | 412989.69 | 26883.74 | 349991.25 | 412989.68 | ZMAT | 2024-09-23 | 2024-10-22
RE/0066-PRJ-T6-CIV-RS-SU | Reinforcement Supply | 2010 | GR01 | 2010 | SMARTWORLD THE EDITION | Carna Corporation Pvt LtdVISHWANATH | 9110000708 | 30 |  |  | 2024-09-23 | Fe 550D TMT Steel 10 MM dia. | TO | 7.5 | 49000 | 367500 | 433650 | 390334 | 460594.12 | 22834 | 390334 | 460594.12 | ZMAT | 2024-09-23 | 2024-10-22
RE/0066-PRJ-T6-CIV-RS-SU | Reinforcement Supply | 2010 | GR01 | 2010 | SMARTWORLD THE EDITION | Carna Corporation Pvt LtdVISHWANATH | 9110000708 | 50 |  |  | 2024-09-23 | Fe 550D TMT Steel 12 MM dia. | TO | 15.5 | 48250 | 747875 | 882492.5 | 747875 | 882492.5 | 0 | 747875 | 882492.43 | ZMAT | 2024-09-23 | 2024-10-22
RE/0066-PRJ-T6-CIV-RS-SU | Reinforcement Supply | 2010 | GR01 | 2010 | SMARTWORLD THE EDITION | Carna Corporation Pvt LtdVISHWANATH | 9110000708 | 70 |  |  | 2024-09-23 | Fe 550D TMT Steel 16 MM dia. | TO | 15 | 48250 | 723750 | 854025 | 723750 | 854025 | 0 | 723750 | 854024.99 | ZMAT | 2024-09-23 | 2024-10-22
RE/0066-PRJ-T6-CIV-RS-SU | Reinforcement Supply | 2010 | GR01 | 2010 | SMARTWORLD THE EDITION | Carna Corporation Pvt LtdVISHWANATH | 9110000708 | 90 |  |  | 2024-09-23 | Fe 550D TMT Steel 20 MM dia. | TO | 29 | 48250 | 1399250 | 1651115 | 1456764 | 1718981.52 | 57514 | 1456764 | 1718982.16 | ZMAT | 2024-09-23 | 2024-10-22
RE/0066-PRJ-T6-CIV-RS-SU | Reinforcement Supply | 2010 | GR01 | 2010 | SMARTWORLD THE EDITION | Carna Corporation Pvt LtdVISHWANATH | 9110000708 | 110 |  |  | 2024-09-23 | Fe 550D TMT Steel 25 MM dia. | TO | 15 | 48250 | 723750 | 854025 | 723750 | 854025 | 0 | 723750 | 854025.13 | ZMAT | 2024-09-23 | 2024-10-22
RE/0066-PRJ-T6-CIV-RS-SU | Reinforcement Supply | 2010 | GR01 | 2010 | SMARTWORLD THE EDITION | Carna Corporation Pvt LtdVISHWANATH | 9110000708 | 130 |  |  | 2024-09-23 | Fe 550D TMT Steel 32 MM dia. | TO | 100 | 48250 | 4825000 | 5693500 | 4825000 | 5693500 | 0 | 4825000 | 5693500.23 | ZMAT | 2024-09-23 | 2024-10-22
RE/0066-PRJ-T6-CIV-RS-SU | Reinforcement Supply | 2010 | GR01 | 2010 | SMARTWORLD THE EDITION | Carna Corporation Pvt LtdVISHWANATH | 9110000709 | 10 |  |  | 2024-09-23 | Fe 550D TMT Steel 8 MM | TO | 17.5 | 50250 | 879375 | 1037662.5 | 879375 | 1037662.5 | 0 | 879375 | 1037662.49 | ZMAT | 2024-09-23 | 2024-10-22
RE/0066-PRJ-T6-CIV-RS-SU | Reinforcement Supply | 2010 | GR01 | 2010 | SMARTWORLD THE EDITION | Carna Corporation Pvt LtdVISHWANATH | 9110000709 | 20 |  |  | 2024-09-23 | Fe 550D TMT Steel 10 MM | TO | 70 | 49000 | 3430000 | 4047400 | 3430000 | 4047400 | 0 | 3430000 | 4047399.74 | ZMAT | 2024-09-23 | 2024-10-22
RE/0066-PRJ-T6-CIV-RS-SU | Reinforcement Supply | 2010 | GR01 | 2010 | SMARTWORLD THE EDITION | Carna Corporation Pvt LtdVISHWANATH | 9110000709 | 30 |  |  | 2024-09-23 | Fe 550D TMT Steel 16 MM | TO | 17.5 | 48250 | 844375 | 996362.5 | 844375 | 996362.5 | 0 | 844375 | 996362.72 | ZMAT | 2024-09-23 | 2024-10-22
RE/0066-PRJ-T6-CIV-RS-SU | Reinforcement Supply | 2010 | GR01 | 2010 | SMARTWORLD THE EDITION | Carna Corporation Pvt LtdVISHWANATH | 9110000709 | 40 |  |  | 2024-09-23 | Fe 550D TMT Steel 20 MM | TO | 20 | 48250 | 965000 | 1138700 | 965000 | 1138700 | 0 | 965000 | 1138699.98 | ZMAT | 2024-09-23 | 2024-10-22
RE/0066-PRJ-T6-CIV-RS-SU | Reinforcement Supply | 2010 | GR01 | 2010 | SMARTWORLD THE EDITION | Northern Steel and General MillsPrivate Limited | 9110000774 | 40 |  |  | 2024-11-15 | Steel Re-bar TMT 16 mm Dia. FE-550D | TO | 18 | 54500 | 981000 | 1157580 | 981000 | 1157580 | 0 | 981000 | 1157580 | ZMAT | 2025-01-20 | 2025-03-20
RE/0066-PRJ-T6-CIV-RS-SU | Reinforcement Supply | 2010 | GR01 | 2010 | SMARTWORLD THE EDITION | Northern Steel and General MillsPrivate Limited | 9110000774 | 110 |  |  | 2024-11-15 | Steel Re-bar TMT 20 mm Dia. FE-550D | TO | 3.5 | 54500 | 190750 | 225085 | 82295 | 97108.1 | 108455 | 82295 | 97108.1 | ZMAT | 2025-01-20 | 2025-03-20
RE/0066-PRJ-T6-CIV-RS-SU | Reinforcement Supply | 2010 | GR01 | 2010 | SMARTWORLD THE EDITION | Northern Steel and General MillsPrivate Limited | 9110000774 | 180 |  |  | 2024-11-15 | Steel Re-bar TMT 25 mm Dia. FE-550D | TO | 15.5 | 54500 | 844750 | 996805 | 844750 | 996805 | 0 | 844750 | 996805 | ZMAT | 2025-01-20 | 2025-03-20
RE/0066-PRJ-T6-CIV-RS-SU | Reinforcement Supply | 2010 | GR01 | 2010 | SMARTWORLD THE EDITION | Jindal Steel Limited | 9110000777 | 60 |  |  | 2024-11-15 | Steel Re-bar TMT 20 mm Dia. FE-550D | TO | 4 | 54500 | 218000 | 257240 | 111670.5 | 131771.19 | 106329.5 | 111670.5 | 131771.19 | ZMAT | 2025-01-20 | 2025-03-20
RE/0066-PRJ-T6-CIV-RS-SU | Reinforcement Supply | 2010 | GR01 | 2010 | SMARTWORLD THE EDITION | Jindal Steel Limited | 9110000777 | 130 |  |  | 2024-11-15 | Steel Re-bar TMT 25 mm Dia. FE-550D | TO | 11.5 | 54500 | 626750 | 739565 | 626750 | 739565 | 0 | 626750 | 739565 | ZMAT | 2025-01-20 | 2025-03-20
RE/0066-PRJ-T6-CIV-RS-SU | Reinforcement Supply | 2010 | GR01 | 2010 | SMARTWORLD THE EDITION | Jindal Steel Limited | 9110000777 | 200 |  |  | 2024-11-15 | Steel Re-bar TMT 32 mm Dia. FE-550D | TO | 8 | 54500 | 436000 | 514480 | 400738.5 | 472871.43 | 35261.5 | 400738.5 | 472871.43 | ZMAT | 2025-01-20 | 2025-03-20
RE/0066-PRJ-T6-CIV-RS-SU | Reinforcement Supply | 2010 | GR01 | 2010 | SMARTWORLD THE EDITION | Carna Corporation Pvt LtdVISHWANATH | 9110000779 | 60 |  |  | 2024-11-16 | Steel Re-bar TMT 20 mm Dia. FE-550D | TO | 5 | 54500 | 272500 | 321550 | 272500 | 321550 | 0 | 272500 | 321550 | ZMAT | 2025-01-20 | 2025-03-20
RE/0066-PRJ-T6-CIV-RS-SU | Reinforcement Supply | 2010 | GR01 | 2010 | SMARTWORLD THE EDITION | Carna Corporation Pvt LtdVISHWANATH | 9110000779 | 130 |  |  | 2024-11-16 | Steel Re-bar TMT 25 mm Dia. FE-550D | TO | 12 | 54500 | 654000 | 771720 | 708500 | 836030 | 54500 | 708500 | 836030 | ZMAT | 2025-01-20 | 2025-03-20
RE/0066-PRJ-T6-CIV-RS-SU | Reinforcement Supply | 2010 | GR01 | 2010 | SMARTWORLD THE EDITION | Ram Niwas & SonsDeepak gupta | 9110000782 | 30 |  |  | 2024-11-16 | Steel Re-bar TMT 08 mm Dia. FE-550D | TO | 9 | 52500 | 472500 | 557550 | 472500 | 557550 | 0 | 472500 | 557550.07 | ZMAT | 2024-11-16 | 2024-12-15
RE/0066-PRJ-T6-CIV-RS-SU | Reinforcement Supply | 2010 | GR01 | 2010 | SMARTWORLD THE EDITION | Rashtriya Ispat Nigam Ltd | 9110000790 | 70 |  |  | 2024-11-29 | Fe 550D TMT Steel Coil 10MM | TO | 37 | 54450 | 2014650 | 2377287 | 2014650 | 2377287 | 0 | 2014650 | 2377287 | ZMAT | 2024-11-29 | 2024-12-28
RE/0066-PRJ-T6-CIV-RS-SU | Reinforcement Supply | 2010 | GR01 | 2010 | SMARTWORLD THE EDITION | Rashtriya Ispat Nigam Ltd | 9110000790 | 140 |  |  | 2024-11-29 | Fe 550D TMT Steel Coil 12MM | TO | 16 | 53950 | 863200 | 1018576 | 781735.5 | 922447.89 | 81464.5 | 781735.5 | 922447.9 | ZMAT | 2024-11-29 | 2024-12-28
RE/0066-PRJ-T6-CIV-RS-SU | Reinforcement Supply | 2010 | GR01 | 2010 | SMARTWORLD THE EDITION | Carna Corporation Pvt LtdVISHWANATH | 9110000837 | 90 |  |  | 2025-01-09 | Steel Re-bar TMT 10 mm Dia. FE-550D | TO | 30 | 50150 | 1504500 | 1775310 | 1554650 | 1834487 | 50150 | 1554650 | 1834487 | ZMAT | 2025-01-20 | 2025-03-20
RE/0066-PRJ-T6-CIV-RS-SU | Reinforcement Supply | 2010 | GR01 | 2010 | SMARTWORLD THE EDITION | Ram Niwas & SonsDeepak gupta | 9110000862 | 80 |  |  | 2025-02-15 | Steel Re-bar TMT 10 mm Dia. FE-550D | TO | 27 | 50200 | 1355400 | 1599372 | 1355400 | 1599372 | 0 | 1355400 | 1599372 | ZMAT
RE/0066-PRJ-T6-CIV-RS-SU | Reinforcement Supply | 2010 | GR01 | 2010 | SMARTWORLD THE EDITION | Jindal Steel Limited | 9110000886 | 60 |  |  | 2025-03-12 | Steel Re-bar TMT 12 mm Dia. FE-550D | TO | 50 | 54750 | 2737500 | 3230250 | 2737500 | 3230250 | 0 | 2737500 | 3230250 | ZMAT
RE/0066-PRJ-T6-CIV-RS-SU | Reinforcement Supply | 2010 | GR01 | 2010 | SMARTWORLD THE EDITION | Jindal Steel Limited | 9110000886 | 120 |  |  | 2025-03-12 | Steel Re-bar TMT 16 mm Dia. FE-550D | TO | 30 | 54750 | 1642500 | 1938150 | 1631166.75 | 1924776.77 | 11333.25 | 1631166.75 | 1924776.77 | ZMAT
RE/0066-PRJ-T6-CIV-RS-SU | Reinforcement Supply | 2010 | GR01 | 2010 | SMARTWORLD THE EDITION | Jindal Steel Limited | 9110000886 | 180 |  |  | 2025-03-12 | Steel Re-bar TMT 20 mm Dia. FE-550D | TO | 40 | 54750 | 2190000 | 2584200 | 2158792.5 | 2547375.15 | 31207.5 | 2158792.5 | 2547375.15 | ZMAT
RE/0066-PRJ-T6-CIV-RS-SU | Reinforcement Supply | 2010 | GR01 | 2010 | SMARTWORLD THE EDITION | Jindal Steel Limited | 9110000886 | 200 |  |  | 2025-03-12 | Steel Re-bar TMT 25 mm Dia. FE-550D | TO | 30 | 54750 | 1642500 | 1938150 | 1623173.25 | 1915344.44 | 19326.75 | 1623173.25 | 1915344.44 | ZMAT
RE/0066-PRJ-T6-CIV-RS-SU | Reinforcement Supply | 2010 | GR01 | 2010 | SMARTWORLD THE EDITION | Ram Niwas & SonsDeepak gupta | 9110000887 | 60 |  |  | 2025-03-12 | Steel Re-bar TMT 10 mm Dia. FE-550D | TO | 14 | 52900 | 740600 | 873908 | 793500 | 936330 | 52900 | 793500 | 936330 | ZMAT
RE/0066-PRJ-T6-CIV-RS-SU | Reinforcement Supply | 2010 | GR01 | 2010 | SMARTWORLD THE EDITION | Carna Corporation Pvt LtdVISHWANATH | 9110000889 | 60 |  |  | 2025-03-12 | Steel Re-bar TMT 10 mm Dia. FE-550D | TO | 6 | 55500 | 333000 | 392940 | 276945 | 326795.1 | 56055 | 276945 | 326795.1 | ZMAT
RE/0066-PRJ-T6-CIV-RS-SU | Reinforcement Supply | 2010 | GR01 | 2010 | SMARTWORLD THE EDITION | Rashtriya Ispat Nigam Ltd | 9110000961 | 60 |  |  | 2025-04-08 | Fe 550D TMT Steel Coil 10MM | TO | 9 | 58750 | 528750 | 623925 | 528750 | 623925 | 0 | 528750 | 623925 | ZMAT
RE/0066-PRJ-T6-CIV-RS-SU | Reinforcement Supply | 2010 | GR01 | 2010 | SMARTWORLD THE EDITION | Rashtriya Ispat Nigam Ltd | 9110000961 | 130 |  |  | 2025-04-08 | Fe 550D TMT Steel Coil 08MM | TO | 9 | 60000 | 540000 | 637200 | 540000 | 637200 | 0 | 540000 | 637200 | ZMAT
RE/0066-PRJ-T6-CIV-RS-SU | Reinforcement Supply | 2010 | GR01 | 2010 | SMARTWORLD THE EDITION | Vikrant Ispat Udyog | 9110000966 | 60 |  |  | 2025-04-09 | Fe 550D TMT Steel Coil 10MM | TO | 3 | 64250 | 192750 | 227445 | 192750 | 227445 | 0 | 192750 | 227445 | ZMAT
RE/0066-PRJ-T6-CIV-RS-SU | Reinforcement Supply | 2010 | GR01 | 2010 | SMARTWORLD THE EDITION | Vikrant Ispat Udyog | 9110000966 | 130 |  |  | 2025-04-09 | Fe 550D TMT Steel Coil 08MM | TO | 3 | 65750 | 197250 | 232755 | 197250 | 232755 | 0 | 197250 | 232755 | ZMAT
RE/0066-PRJ-T6-CIV-RS-SU | Reinforcement Supply | 2010 | GR01 | 2010 | SMARTWORLD THE EDITION | JINDAL STEEL LIMITEDMr Robin Taneja | 9110000991 | 200 |  |  | 2025-04-17 | Steel Re-bar TMT 25 mm Dia. FE-550D | TO | 6.14 | 57750 | 354585 | 418410.3 | 354585 | 418410.3 | 0 | 354585 | 418410.3 | ZMAT
RE/0066-PRJ-T6-CIV-RS-SU | Reinforcement Supply | 2010 | GR01 | 2010 | SMARTWORLD THE EDITION | Petropol India LimitedSANJAY GUPTA | 9110000993 | 40 |  |  | 2025-04-17 | Steel Re-bar TMT 10 mm Dia. FE-550D | TO | 40 | 56000 | 2240000 | 2643200 | 2464000 | 2907520 | 224000 | 2464000 | 2907520 | ZMAT | 2025-04-17 | 2025-04-30
RE/0066-PRJ-T6-CIV-RS-SU | Reinforcement Supply | 2010 | GR01 | 2010 | SMARTWORLD THE EDITION | Sapcon Steels Private Limited | 9110000999 | 80 |  |  | 2025-04-18 | Fe 550D TMT Steel Coil 10MM | TO | 40 | 58250 | 2330000 | 2749400 | 2045740 | 2413973.2 | 284260 | 2045740 | 2413973.2 | ZMAT | 2025-04-11 | 2025-04-30
RE/0066-PRJ-T6-CIV-RS-SU | Reinforcement Supply | 2010 | GR01 | 2010 | SMARTWORLD THE EDITION | Sapcon Steels Private Limited | 9110001009 | 60 |  |  | 2025-04-28 | Steel Re-bar TMT 32 mm Dia. FE-550D | TO | 10 | 57000 | 570000 | 672600 | 310080 | 365894.4 | 259920 | 310080 | 365894.4 | ZMAT
RE/0066-PRJ-T6-CIV-RS-SU | Reinforcement Supply | 2010 | GR01 | 2010 | SMARTWORLD THE EDITION | Jindal Steel Limited | 9110001055 | 60 |  |  | 2025-05-17 | Steel Re-bar TMT 20 mm Dia. FE-550D | TO | 10 | 54850 | 548500 | 647230 | 589089 | 695125.02 | 40589 | 589089 | 695125.02 | ZMAT | 2025-05-29 | 2025-06-29
RE/0066-PRJ-T6-CIV-RS-SU | Reinforcement Supply | 2010 | GR01 | 2010 | SMARTWORLD THE EDITION | Jindal Steel Limited | 9110001055 | 130 |  |  | 2025-05-17 | Steel Re-bar TMT 25 mm Dia. FE-550D | TO | 33 | 54850 | 1810050 | 2135859 | 1864900 | 2200582 | 54850 | 1864900 | 2200582 | ZMAT | 2025-05-29 | 2025-06-29
RE/0066-PRJ-T6-CIV-RS-SU | Reinforcement Supply | 2010 | GR01 | 2010 | SMARTWORLD THE EDITION | Jindal Steel Limited | 9110001073 | 70 |  |  | 2025-05-27 | Steel Re-bar TMT 12 mm Dia. FE-550D | TO | 10 | 57750 | 577500 | 681450 | 552898.5 | 652420.23 | 24601.5 | 552898.5 | 652420.23 | ZMAT
RE/0066-PRJ-T6-CIV-RS-SU | Reinforcement Supply | 2010 | GR01 | 2010 | SMARTWORLD THE EDITION | Jindal Steel Limited | 9110001073 | 140 |  |  | 2025-05-27 | Steel Re-bar TMT 16 mm Dia. FE-550D | TO | 15 | 57750 | 866250 | 1022175 | 815314.51 | 962071.12 | 50935.49 | 815314.5 | 962071.12 | ZMAT
RE/0066-PRJ-T6-CIV-RS-SU | Reinforcement Supply | 2010 | GR01 | 2010 | SMARTWORLD THE EDITION | Jindal Steel Limited | 9110001073 | 200 |  |  | 2025-05-27 | Steel Re-bar TMT 25 mm Dia. FE-550D | TO | 4 | 57750 | 231000 | 272580 | 212808.75 | 251114.33 | 18191.25 | 212808.75 | 251114.33 | ZMAT
RE/0066-PRJ-T6-CIV-RS-SU | Reinforcement Supply | 2010 | GR01 | 2010 | SMARTWORLD THE EDITION | JINDAL STEEL LIMITEDMr Robin Taneja | 9110001079 | 60 |  |  | 2025-05-29 | Steel Re-bar TMT 25 mm Dia. FE-550D | TO | 12 | 54850 | 658200 | 776676 | 685625 | 809037.5 | 27425 | 685625 | 809037.5 | ZMAT | 2025-05-29 | 2025-06-29
RE/0066-PRJ-T6-CIV-RS-SU | Reinforcement Supply | 2010 | GR01 | 2010 | SMARTWORLD THE EDITION | Ram Niwas & SonsDeepak gupta | 9110001126 | 60 |  |  | 2025-06-20 | Steel Re-bar TMT 08 mm Dia. FE-550D | TO | 10 | 51000 | 510000 | 601800 | 510000 | 601800 | 0 | 510000 | 601800 | ZMAT | 2025-06-20 | 2025-07-20
RE/0066-PRJ-T6-CIV-RS-SU | Reinforcement Supply | 2010 | GR01 | 2010 | SMARTWORLD THE EDITION | Jindal Steel Limited | 9110001127 | 60 |  |  | 2025-06-20 | Steel Re-bar TMT 12 mm Dia. FE-550D | TO | 30 | 50600 | 1518000 | 1791240 | 1518000 | 1791240 | 0 | 1518000 | 1791240 | ZMAT | 2025-06-20 | 2025-07-20
RE/0066-PRJ-T6-CIV-RS-SU | Reinforcement Supply | 2010 | GR01 | 2010 | SMARTWORLD THE EDITION | Jindal Steel Limited | 9110001127 | 140 |  |  | 2025-06-20 | Steel Re-bar TMT 16 mm Dia. FE-550D | TO | 25 | 50600 | 1265000 | 1492700 | 1265000 | 1492700 | 0 | 1265000 | 1492700 | ZMAT | 2025-06-20 | 2025-07-20
RE/0066-PRJ-T6-CIV-RS-SU | Reinforcement Supply | 2010 | GR01 | 2010 | SMARTWORLD THE EDITION | Jindal Steel Limited | 9110001127 | 220 |  |  | 2025-06-20 | Steel Re-bar TMT 20 mm Dia. FE-550D | TO | 15 | 50600 | 759000 | 895620 | 759000 | 895620 | 0 | 759000 | 895620 | ZMAT | 2025-06-20 | 2025-07-20
RE/0066-PRJ-T6-CIV-RS-SU | Reinforcement Supply | 2010 | GR01 | 2010 | SMARTWORLD THE EDITION | Jindal Steel Limited | 9110001127 | 290 |  |  | 2025-06-20 | Steel Re-bar TMT 25 mm Dia. FE-550D | TO | 20 | 50600 | 1012000 | 1194160 | 1033403.8 | 1219416.48 | 21403.8 | 1033403.8 | 1219416.48 | ZMAT | 2025-06-20 | 2025-07-20
RE/0066-PRJ-T6-CIV-RS-SU | Reinforcement Supply | 2010 | GR01 | 2010 | SMARTWORLD THE EDITION | Jindal Steel Limited | 9110001162 | 60 |  |  | 2025-07-17 | Steel Re-bar TMT 10 mm Dia. FE-550D | TO | 35 | 47500 | 1662500 | 1961750 | 0 | 0 | 1662500 | 0 | 0 | ZMAT | 2025-07-17 | 2025-08-17
RE/0066-PRJ-T6-CIV-RS-SU | Reinforcement Supply | 2010 | GR01 | 2010 | SMARTWORLD THE EDITION | Jindal Steel Limited | 9110001162 | 140 |  |  | 2025-07-17 | Steel Re-bar TMT 12 mm Dia. FE-550D | TO | 15 | 46500 | 697500 | 823050 | 0 | 0 | 697500 | 0 | 0 | ZMAT | 2025-07-17 | 2025-08-17
RE/0066-PRJ-T6-CIV-RS-SU | Reinforcement Supply | 2010 | GR01 | 2010 | SMARTWORLD THE EDITION | Jindal Steel Limited | 9110001162 | 220 |  |  | 2025-07-17 | Steel Re-bar TMT 16 mm Dia. FE-550D | TO | 5 | 46500 | 232500 | 274350 | 0 | 0 | 232500 | 0 | 0 | ZMAT | 2025-07-17 | 2025-08-17
RE/0066-PRJ-T6-CIV-RS-SU | Reinforcement Supply | 2010 | GR01 | 2010 | SMARTWORLD THE EDITION | Jindal Steel Limited | 9110001162 | 280 |  |  | 2025-07-17 | Steel Re-bar TMT 20 mm Dia. FE-550D | TO | 5 | 46500 | 232500 | 274350 | 0 | 0 | 232500 | 0 | 0 | ZMAT | 2025-07-17 | 2025-08-17
RE/0066-PRJ-T6-CIV-RS-SU | Reinforcement Supply | 2010 | GR01 | 2010 | SMARTWORLD THE EDITION | Jindal Steel Limited | 9110001162 | 350 |  |  | 2025-07-17 | Steel Re-bar TMT 25 mm Dia. FE-550D | TO | 5 | 46500 | 232500 | 274350 | 0 | 0 | 232500 | 0 | 0 | ZMAT | 2025-07-17 | 2025-08-17
RE/0066-PRJ-T6-CIV-RS-SU | Reinforcement Supply | 2010 | GR01 | 2010 | SMARTWORLD THE EDITION | Jindal Steel Limited | 9110001162 | 430 |  |  | 2025-07-17 | Steel Re-bar TMT 32 mm Dia. FE-550D | TO | 5 | 46500 | 232500 | 274350 | 0 | 0 | 232500 | 0 | 0 | ZMAT | 2025-07-17 | 2025-08-17
RE/0066-PRJ-T6-CIV-RS-SU | Reinforcement Supply | 2010 | GR01 | 2010 | SMARTWORLD THE EDITION | Rashtriya Ispat Nigam Ltd | 9110001212 | 60 |  |  | 2025-08-14 | Steel Re-bar TMT 08 mm Dia. FE-550D | TO | 5 | 49300 | 246500 | 290870 | 169592 | 200118.56 | 76908 | 169592 | 200118.56 | ZMAT | 2025-08-14 | 2025-09-14
RE/0066-PRJ-T6-CIV-RS-SU | Reinforcement Supply | 2010 | GR01 | 2010 | SMARTWORLD THE EDITION | Rashtriya Ispat Nigam Ltd | 9110001212 | 120 |  |  | 2025-08-14 | Steel Re-bar TMT 10 mm Dia. FE-550D | TO | 50 | 47800 | 2390000 | 2820200 | 2375182 | 2802714.76 | 14818 | 2375182 | 2802714.76 | ZMAT | 2025-08-14 | 2025-09-14
RE/0066-PRJ-T6-CIV-RS-SU | Reinforcement Supply | 2010 | GR01 | 2010 | SMARTWORLD THE EDITION | Jindal Steel Limited | 9110001213 | 60 |  |  | 2025-08-14 | Steel Re-bar TMT 12 mm Dia. FE-550D | TO | 30 | 47000 | 1410000 | 1663800 | 1410000 | 1663800 | 0 | 1410000 | 1663800 | ZMAT | 2025-08-14 | 2025-09-14
RE/0066-PRJ-T6-CIV-RS-SU | Reinforcement Supply | 2010 | GR01 | 2010 | SMARTWORLD THE EDITION | Jindal Steel Limited | 9110001213 | 120 |  |  | 2025-08-14 | Steel Re-bar TMT 16 mm Dia. FE-550D | TO | 10 | 47000 | 470000 | 554600 | 413741 | 488214.38 | 56259 | 413741 | 488214.38 | ZMAT | 2025-08-14 | 2025-09-14
RE/0066-PRJ-T6-CIV-RS-SU | Reinforcement Supply | 2010 | GR01 | 2010 | SMARTWORLD THE EDITION | Jindal Steel Limited | 9110001213 | 180 |  |  | 2025-08-14 | Steel Re-bar TMT 20 mm Dia. FE-550D | TO | 10 | 47000 | 470000 | 554600 | 454161 | 535909.98 | 15839 | 454161 | 535909.98 | ZMAT | 2025-08-14 | 2025-09-14
RE/0066-PRJ-T6-CIV-RS-SU | Reinforcement Supply | 2010 | GR01 | 2010 | SMARTWORLD THE EDITION | Jindal Steel Limited | 9110001213 | 240 |  |  | 2025-08-14 | Steel Re-bar TMT 25 mm Dia. FE-550D | TO | 10 | 47000 | 470000 | 554600 | 470000 | 554600 | 0 | 470000 | 554600 | ZMAT | 2025-08-14 | 2025-09-14
RE/0066-PRJ-T6-CIV-RS-SU | Reinforcement Supply | 2010 | GR01 | 2010 | SMARTWORLD THE EDITION | Jindal Steel Limited | 9110001213 | 300 |  |  | 2025-08-14 | Steel Re-bar TMT 32 mm Dia. FE-550D | TO | 10 | 47000 | 470000 | 554600 | 0 | 0 | 470000 | 0 | 0 | ZMAT | 2025-08-14 | 2025-09-14
RE/0066-PRJ-T6-CIV-RS-SU | Reinforcement Supply | 2010 | GR01 | 2010 | SMARTWORLD THE EDITION | Steel Authority Of India LTD | 9110001280 | 70 |  |  | 2025-09-18 | Steel Re-bar TMT 12 mm Dia. FE-550D | TO | 27 | 46260 | 1249020 | 1473843.6 | 1249020 | 1473843.6 | 0 | 1249020 | 1473843.6 | ZMAT | 2025-09-18 | 2025-10-18
RE/0066-PRJ-T6-CIV-RS-SU | Reinforcement Supply | 2010 | GR01 | 2010 | SMARTWORLD THE EDITION | Steel Authority Of India LTD | 9110001280 | 130 |  |  | 2025-09-18 | Steel Re-bar TMT 16 mm Dia. FE-550D | TO | 19.6 | 46260 | 906696 | 1069901.28 | 906696 | 1069901.28 | 0 | 906696 | 1069901.28 | ZMAT | 2025-09-18 | 2025-10-18
RE/0066-PRJ-T6-CIV-RS-SU | Reinforcement Supply | 2010 | GR01 | 2010 | SMARTWORLD THE EDITION | Steel Authority Of India LTD | 9110001280 | 190 |  |  | 2025-09-18 | Steel Re-bar TMT 20 mm Dia. FE-550D | TO | 25 | 46260 | 1156500 | 1364670 | 1156500 | 1364670 | 0 | 1156500 | 1364670 | ZMAT | 2025-09-18 | 2025-10-18
RE/0066-PRJ-T6-CIV-RS-SU | Reinforcement Supply | 2010 | GR01 | 2010 | SMARTWORLD THE EDITION | Steel Authority Of India LTD | 9110001280 | 250 |  |  | 2025-09-18 | Steel Re-bar TMT 25 mm Dia. FE-550D | TO | 14 | 46260 | 647640 | 764215.2 | 647640 | 764215.2 | 0 | 647640 | 764215.21 | ZMAT | 2025-09-18 | 2025-10-18
RE/0066-PRJ-T6-CIV-RS-SU | Reinforcement Supply | 2010 | GR01 | 2010 | SMARTWORLD THE EDITION | Steel Authority Of India LTD | 9110001280 | 340 |  |  | 2025-09-18 | Steel Re-bar TMT 10 mm Dia. FE-550D | TO | 2.5 | 47260 | 118150 | 139417 | 118150 | 139417 | 0 | 118150 | 139417 | ZMAT | 2025-09-18 | 2025-10-18
RE/0066-PRJ-T6-CIV-RS-SU | Reinforcement Supply | 2010 | GR01 | 2010 | SMARTWORLD THE EDITION | Steel Authority Of India LTD | 9110001280 | 360 |  |  | 2025-09-18 | Steel Re-bar TMT 32 mm Dia. FE-550D | TO | 14 | 46260 | 647640 | 764215.2 | 647640 | 764215.2 | 0 | 647640 | 764215.2 | ZMAT | 2025-09-18 | 2025-10-18
RE/0066-PRJ-T6-CIV-RS-SU | Reinforcement Supply | 2010 | GR01 | 2010 | SMARTWORLD THE EDITION | Ram Niwas & SonsDeepak gupta | 9110001305 | 60 |  |  | 2025-10-09 | Steel Re-bar TMT 08 mm Dia. FE-550D | TO | 6 | 47500 | 285000 | 336300 | 280250 | 330695 | 4750 | 280250 | 330695 | ZMAT | 2025-10-09 | 2025-11-08
RE/0066-PRJ-T6-CIV-RS-SU | Reinforcement Supply | 2010 | GR01 | 2010 | SMARTWORLD THE EDITION | Ram Niwas & SonsDeepak gupta | 9110001305 | 120 |  |  | 2025-10-09 | Steel Re-bar TMT 10 mm Dia. FE-550D | TO | 28 | 46500 | 1302000 | 1536360 | 0 | 0 | 1302000 | 0 | 0 | ZMAT | 2025-10-09 | 2025-11-08
RE/0066-PRJ-T6-CIV-RS-SU | Reinforcement Supply | 2010 | GR01 | 2010 | SMARTWORLD THE EDITION | Jindal Steel Limited | 9110001307 | 60 |  |  | 2025-10-09 | Steel Re-bar TMT 12 mm Dia. FE-550D | TO | 5 | 46500 | 232500 | 274350 | 176607 | 208396.26 | 55893 | 176607 | 208396.26 | ZMAT | 2025-10-09 | 2025-11-08
RE/0066-PRJ-T6-CIV-RS-SU | Reinforcement Supply | 2010 | GR01 | 2010 | SMARTWORLD THE EDITION | Jindal Steel Limited | 9110001307 | 120 |  |  | 2025-10-09 | Steel Re-bar TMT 16 mm Dia. FE-550D | TO | 20 | 46500 | 930000 | 1097400 | 837325.5 | 988044.09 | 92674.5 | 837325.5 | 988044.09 | ZMAT | 2025-10-09 | 2025-11-08
RE/0066-PRJ-T6-CIV-RS-SU | Reinforcement Supply | 2010 | GR01 | 2010 | SMARTWORLD THE EDITION | Jindal Steel Limited | 9110001307 | 180 |  |  | 2025-10-09 | Steel Re-bar TMT 20 mm Dia. FE-550D | TO | 20 | 46500 | 930000 | 1097400 | 930000 | 1097400 | 0 | 930000 | 1097400 | ZMAT | 2025-10-09 | 2025-11-08
RE/0066-PRJ-T6-CIV-RS-SU | Reinforcement Supply | 2010 | GR01 | 2010 | SMARTWORLD THE EDITION | Jindal Steel Limited | 9110001307 | 240 |  |  | 2025-10-09 | Steel Re-bar TMT 25 mm Dia. FE-550D | TO | 17 | 46500 | 790500 | 932790 | 790500 | 932790 | 0 | 790500 | 932790 | ZMAT | 2025-10-09 | 2025-11-08
RE/0066-PRJ-T6-CIV-RS-SU | Reinforcement Supply | 2010 | GR01 | 2010 | SMARTWORLD THE EDITION | Jindal Steel Limited | 9110001307 | 300 |  |  | 2025-10-09 | Steel Re-bar TMT 32 mm Dia. FE-550D | TO | 17 | 46500 | 790500 | 932790 | 790500 | 932790 | 0 | 790500 | 932790 | ZMAT | 2025-10-09 | 2025-11-08
RE/0066-PRJ-T6-CIV-RS-SU | Reinforcement Supply | 2010 | GR01 | 2010 | SMARTWORLD THE EDITION | Jindal Steel Limited | 9110001361 | 60 |  |  | 2025-11-07 | Steel Re-bar TMT 12 mm Dia. FE-550D | TO | 33 | 46100 | 1521300 | 1795134 | 1556013.3 | 1836095.69 | 34713.3 | 1556013.3 | 1836095.69 | ZMAT | 2025-11-07 | 2025-12-07
RE/0066-PRJ-T6-CIV-RS-SU | Reinforcement Supply | 2010 | GR01 | 2010 | SMARTWORLD THE EDITION | Jindal Steel Limited | 9110001361 | 120 |  |  | 2025-11-07 | Steel Re-bar TMT 16 mm Dia. FE-550D | TO | 25 | 46100 | 1152500 | 1359950 | 1175550 | 1387149 | 23050 | 1175550 | 1387149 | ZMAT | 2025-11-07 | 2025-12-07
RE/0066-PRJ-T6-CIV-RS-SU | Reinforcement Supply | 2010 | GR01 | 2010 | SMARTWORLD THE EDITION | Jindal Steel Limited | 9110001361 | 180 |  |  | 2025-11-07 | Steel Re-bar TMT 20 mm Dia. FE-550D | TO | 10 | 46100 | 461000 | 543980 | 472571.1 | 557633.9 | 11571.1 | 472571.1 | 557633.9 | ZMAT | 2025-11-07 | 2025-12-07
RE/0066-PRJ-T6-CIV-RS-SU | Reinforcement Supply | 2010 | GR01 | 2010 | SMARTWORLD THE EDITION | Jindal Steel Limited | 9110001361 | 240 |  |  | 2025-11-07 | Steel Re-bar TMT 25 mm Dia. FE-550D | TO | 30 | 46100 | 1383000 | 1631940 | 60391 | 71261.38 | 1322609 | 60391 | 71261.38 | ZMAT | 2025-11-07 | 2025-12-07
RE/0066-PRJ-T6-CIV-RS-SU | Reinforcement Supply | 2010 | GR01 | 2010 | SMARTWORLD THE EDITION | Jindal Steel Limited | 9110001361 | 300 |  |  | 2025-11-07 | Steel Re-bar TMT 32 mm Dia. FE-550D | TO | 8 | 46100 | 368800 | 435184 | 360963 | 425936.34 | 7837 | 360963 | 425936.34 | ZMAT | 2025-11-07 | 2025-12-07
RE/0066-PRJ-T6-CIV-RS-SU | Reinforcement Supply | 2010 | GR01 | 2010 | SMARTWORLD THE EDITION | Ram Niwas & SonsDeepak gupta | 9110001362 | 60 |  |  | 2025-11-07 | Steel Re-bar TMT 08 mm Dia. FE-550D | TO | 2.5 | 46900 | 117250 | 138355 | 117250 | 138355 | 0 | 117250 | 138355 | ZMAT | 2025-11-07 | 2025-12-07
RE/0066-PRJ-T6-CIV-RS-SU | Reinforcement Supply | 2010 | GR01 | 2010 | SMARTWORLD THE EDITION | Ram Niwas & SonsDeepak gupta | 9110001362 | 110 |  |  | 2025-11-07 | Steel Re-bar TMT 10 mm Dia. FE-550D | TO | 38 | 45900 | 1744200 | 2058156 | 1744200 | 2058156 | 0 | 1744200 | 2058156 | ZMAT | 2025-11-07 | 2025-12-07
RE/0066-PRJ-T6-CIV-RS-SU | Reinforcement Supply | 2010 | GR01 | 2010 | SMARTWORLD THE EDITION | Ram Niwas & SonsDeepak gupta | 9110001421 | 60 |  |  | 2025-12-10 | Steel Re-bar TMT 10 mm Dia. FE-550D | TO | 21 | 46500 | 976500 | 1152270 | 101835 | 120165.3 | 874665 | 101835 | 120165.3 | ZMAT | 2025-12-10 | 2026-01-10
RE/0066-PRJ-T6-CIV-RS-SU | Reinforcement Supply | 2010 | GR01 | 2010 | SMARTWORLD THE EDITION | Ram Niwas & SonsDeepak gupta | 9110001421 | 120 |  |  | 2025-12-10 | Steel Re-bar TMT 08 mm Dia. FE-550D | TO | 10 | 47500 | 475000 | 560500 | 475000 | 560500 | 0 | 475000 | 560500 | ZMAT | 2025-12-10 | 2026-01-10
RE/0066-PRJ-T6-CIV-RS-SU | Reinforcement Supply | 2010 | GR01 | 2010 | SMARTWORLD THE EDITION | Jindal Steel Limited | 9110001422 | 60 |  |  | 2025-12-10 | Steel Re-bar TMT 12 mm Dia. FE-550D | TO | 20 | 46400 | 928000 | 1095040 | 345123.2 | 407245.38 | 582876.8 | 345123.2 | 407245.38 | ZMAT | 2025-12-10 | 2026-01-10
RE/0066-PRJ-T6-CIV-RS-SU | Reinforcement Supply | 2010 | GR01 | 2010 | SMARTWORLD THE EDITION | Jindal Steel Limited | 9110001422 | 120 |  |  | 2025-12-10 | Steel Re-bar TMT 16 mm Dia. FE-550D | TO | 20 | 46400 | 928000 | 1095040 | 928000 | 1095040 | 0 | 928000 | 1095040 | ZMAT | 2025-12-10 | 2026-01-10
RE/0066-PRJ-T6-CIV-RS-SU | Reinforcement Supply | 2010 | GR01 | 2010 | SMARTWORLD THE EDITION | Jindal Steel Limited | 9110001422 | 180 |  |  | 2025-12-10 | Steel Re-bar TMT 20 mm Dia. FE-550D | TO | 15 | 46400 | 696000 | 821280 | 696000 | 821280 | 0 | 696000 | 821280 | ZMAT | 2025-12-10 | 2026-01-10
RE/0066-PRJ-T6-CIV-RS-SU | Reinforcement Supply | 2010 | GR01 | 2010 | SMARTWORLD THE EDITION | Jindal Steel Limited | 9110001422 | 240 |  |  | 2025-12-10 | Steel Re-bar TMT 25 mm Dia. FE-550D | TO | 15 | 46400 | 696000 | 821280 | 734558.4 | 866778.91 | 38558.4 | 734558.4 | 866778.91 | ZMAT | 2025-12-10 | 2026-01-10
RE/0066-PRJ-T6-CIV-RS-SU | Reinforcement Supply | 2010 | GR01 | 2010 | SMARTWORLD THE EDITION | Ram Niwas & SonsDeepak gupta | 9110001471 | 60 |  |  | 2026-01-12 | Steel Re-bar TMT 08 mm Dia. FE-550D | TO | 10 | 52000 | 520000 | 613600 | 520000 | 613600 | 0 | 520000 | 613600 | ZMAT | 2026-01-12 | 2026-02-12
RE/0066-PRJ-T6-CIV-RS-SU | Reinforcement Supply | 2010 | GR01 | 2010 | SMARTWORLD THE EDITION | ESL STEEL LIMITED | 9110001481 | 60 |  |  | 2026-01-12 | Steel Re-bar TMT 12 mm Dia. FE-550D | TO | 40 | 51800 | 2072000 | 2444960 | 2072000 | 2444960 | 0 | 2072000 | 2444960 | ZMAT | 2026-01-12 | 2026-02-12
RE/0066-PRJ-T6-CIV-RS-SU | Reinforcement Supply | 2010 | GR01 | 2010 | SMARTWORLD THE EDITION | ESL STEEL LIMITED | 9110001481 | 120 |  |  | 2026-01-12 | Steel Re-bar TMT 16 mm Dia. FE-550D | TO | 1 | 51800 | 51800 | 61124 | 51800 | 61124 | 0 | 51800 | 61124 | ZMAT | 2026-01-12 | 2026-02-12
RE/0066-PRJ-T6-CIV-RS-SU | Reinforcement Supply | 2010 | GR01 | 2010 | SMARTWORLD THE EDITION | ESL STEEL LIMITED | 9110001481 | 180 |  |  | 2026-01-12 | Steel Re-bar TMT 20 mm Dia. FE-550D | TO | 25 | 51800 | 1295000 | 1528100 | 1295000 | 1528100 | 0 | 1295000 | 1528100 | ZMAT | 2026-01-12 | 2026-02-12
RE/0066-PRJ-T6-CIV-RS-SU | Reinforcement Supply | 2010 | GR01 | 2010 | SMARTWORLD THE EDITION | ESL STEEL LIMITED | 9110001481 | 240 |  |  | 2026-01-12 | Steel Re-bar TMT 25 mm Dia. FE-550D | TO | 8 | 51800 | 414400 | 488992 | 0 | 0 | 414400 | 0 | 0 | ZMAT | 2026-01-12 | 2026-02-12
RE/0066-PRJ-T6-CIV-RS-SU | Reinforcement Supply | 2010 | GR01 | 2010 | SMARTWORLD THE EDITION | Ram Niwas & SonsDeepak gupta | 9110001541 | 60 |  |  | 2026-02-07 | Steel Re-bar TMT 08 mm Dia. FE-550D | TO | 6 | 55300 | 331800 | 391524 | 325164 | 383693.52 | 6636 | 325164 | 383693.52 | ZMAT | 2026-02-07 | 2026-03-31
RE/0066-PRJ-T6-CIV-RS-SU | Reinforcement Supply | 2010 | GR01 | 2010 | SMARTWORLD THE EDITION | Ram Niwas & SonsDeepak gupta | 9110001541 | 120 |  |  | 2026-02-07 | Steel Re-bar TMT 10 mm Dia. FE-550D | TO | 12 | 54300 | 651600 | 768888 | 622821 | 734928.78 | 28779 | 622821 | 734928.78 | ZMAT | 2026-02-07 | 2026-03-31
RE/0066-PRJ-T6-CIV-RS-SU | Reinforcement Supply | 2010 | GR01 | 2010 | SMARTWORLD THE EDITION | Petropol India LimitedSANJAY GUPTA | 9110001546 | 60 |  |  | 2026-02-07 | Steel Re-bar TMT 08 mm Dia. FE-550D | TO | 7 | 55300 | 387100 | 456778 | 384888 | 454167.84 | 2212 | 384888 | 454167.84 | ZMAT | 2026-02-07 | 2026-03-31
RE/0066-PRJ-T6-CIV-RS-SU | Reinforcement Supply | 2010 | GR01 | 2010 | SMARTWORLD THE EDITION | Petropol India LimitedSANJAY GUPTA | 9110001546 | 120 |  |  | 2026-02-07 | Steel Re-bar TMT 10 mm Dia. FE-550D | TO | 15 | 54300 | 814500 | 961110 | 305166 | 360095.88 | 509334 | 305166 | 360095.88 | ZMAT | 2026-02-07 | 2026-03-31
RE/0066-PRJ-T6-CIV-RS-SU | Reinforcement Supply | 2010 | GR01 | 2010 | SMARTWORLD THE EDITION | Jindal Steel Limited | 9110001551 | 60 |  |  | 2026-02-07 | Steel Re-bar TMT 12 mm Dia. FE-550D | TO | 26 | 58500 | 1521000 | 1794780 | 1423597.5 | 1679845.05 | 97402.5 | 1423597.5 | 1679845.05 | ZMAT | 2026-02-07 | 2026-03-07
RE/0066-PRJ-T6-CIV-RS-SU | Reinforcement Supply | 2010 | GR01 | 2010 | SMARTWORLD THE EDITION | Jindal Steel Limited | 9110001551 | 120 |  |  | 2026-02-07 | Steel Re-bar TMT 16 mm Dia. FE-550D | TO | 30 | 58500 | 1755000 | 2070900 | 1845967.5 | 2178241.65 | 90967.5 | 1845967.5 | 2178241.65 | ZMAT | 2026-02-07 | 2026-03-07
RE/0066-PRJ-T6-CIV-RS-SU | Reinforcement Supply | 2010 | GR01 | 2010 | SMARTWORLD THE EDITION | Jindal Steel Limited | 9110001551 | 180 |  |  | 2026-02-07 | Steel Re-bar TMT 20 mm Dia. FE-550D | TO | 3 | 58500 | 175500 | 207090 | 0 | 0 | 175500 | 0 | 0 | ZMAT | 2026-02-07 | 2026-03-07
RE/0066-PRJ-T6-CIV-RS-SU | Reinforcement Supply | 2010 | GR01 | 2010 | SMARTWORLD THE EDITION | Jindal Steel Limited | 9110001551 | 240 |  |  | 2026-02-07 | Steel Re-bar TMT 25 mm Dia. FE-550D | TO | 20 | 58500 | 1170000 | 1380600 | 1092780 | 1289480.4 | 77220 | 1092780 | 1289480.4 | ZMAT | 2026-02-07 | 2026-03-07
RE/0066-PRJ-T6-CIV-RS-SU | Reinforcement Supply | 2010 | GR01 | 2010 | SMARTWORLD THE EDITION | Jindal Steel Limited | 9110001557 | 60 |  |  | 2026-02-10 | Steel Re-bar TMT 12 mm Dia. FE-550D | TO | 27 | 58500 | 1579500 | 1863810 | 1518660 | 1792018.8 | 60840 | 1518660 | 1792018.8 | ZMAT | 2026-02-10 | 2026-03-10
RE/0066-PRJ-T6-CIV-RS-SU | Reinforcement Supply | 2010 | GR01 | 2010 | SMARTWORLD THE EDITION | Jindal Steel Limited | 9110001557 | 120 |  |  | 2026-02-10 | Steel Re-bar TMT 25 mm Dia. FE-550D | TO | 48 | 58500 | 2808000 | 3313440 | 2497482 | 2947028.76 | 310518 | 2497482 | 2947028.76 | ZMAT | 2026-02-10 | 2026-03-10
RE/0066-PRJ-T6-CIV-RS-SU | Reinforcement Supply | 2010 | GR01 | 2010 | SMARTWORLD THE EDITION | Petropol India LimitedSANJAY GUPTA | 9110001558 | 60 |  |  | 2026-02-10 | Steel Re-bar TMT 08 mm Dia. FE-550D | TO | 18 | 55300 | 995400 | 1174572 | 897519 | 1059072.42 | 97881 | 897519 | 1059072.42 | ZMAT | 2026-02-10 | 2026-03-10
RE/0066-PRJ-T6-CIV-RS-SU | Reinforcement Supply | 2010 | GR01 | 2010 | SMARTWORLD THE EDITION | Ram Niwas & SonsDeepak gupta | 9110001607 | 60 |  |  | 2026-03-11 | Steel Re-bar TMT 10 mm Dia. FE-550D | TO | 37 | 55800 | 2064600 | 2436228 | 2062926 | 2434252.68 | 1674 | 2062926 | 2434252.68 | ZMAT | 2026-03-11 | 2026-04-11
RE/0066-PRJ-T6-CIV-RS-SU | Reinforcement Supply | 2010 | GR01 | 2010 | SMARTWORLD THE EDITION | Ram Niwas & SonsDeepak gupta | 9110001607 | 120 |  |  | 2026-03-11 | Steel Re-bar TMT 08 mm Dia. FE-550D | TO | 30 | 56800 | 1704000 | 2010720 | 1704000 | 2010720 | 0 | 1704000 | 2010720 | ZMAT | 2026-03-11 | 2026-04-11
RE/0066-PRJ-T6-CIV-RS-SU | Reinforcement Supply | 2010 | GR01 | 2010 | SMARTWORLD THE EDITION | ESL STEEL LIMITED | 9110001613 | 60 |  |  | 2026-03-11 | Steel Re-bar TMT 12 mm Dia. FE-550D | TO | 37 | 58250 | 2155250 | 2543195 | 2155250 | 2543195 | 0 | 2155250 | 2543195 | ZMAT | 2026-03-11 | 2026-04-11
RE/0066-PRJ-T6-CIV-RS-SU | Reinforcement Supply | 2010 | GR01 | 2010 | SMARTWORLD THE EDITION | ESL STEEL LIMITED | 9110001613 | 120 |  |  | 2026-03-11 | Steel Re-bar TMT 16 mm Dia. FE-550D | TO | 30 | 58250 | 1747500 | 2062050 | 1728219.25 | 2039298.72 | 19280.75 | 1728219.25 | 2039298.72 | ZMAT | 2026-03-11 | 2026-04-11
RE/0066-PRJ-T6-CIV-RS-SU | Reinforcement Supply | 2010 | GR01 | 2010 | SMARTWORLD THE EDITION | ESL STEEL LIMITED | 9110001613 | 180 |  |  | 2026-03-11 | Steel Re-bar TMT 20 mm Dia. FE-550D | TO | 27 | 58250 | 1572750 | 1855845 | 1391010 | 1641391.8 | 181740 | 1391010 | 1641391.8 | ZMAT | 2026-03-11 | 2026-04-11
RE/0066-PRJ-T6-CIV-RS-SU | Reinforcement Supply | 2010 | GR01 | 2010 | SMARTWORLD THE EDITION | ESL STEEL LIMITED | 9110001613 | 240 |  |  | 2026-03-11 | Steel Re-bar TMT 25 mm Dia. FE-550D | TO | 25 | 58250 | 1456250 | 1718375 | 1462715.75 | 1726004.59 | 6465.75 | 1462715.75 | 1726004.59 | ZMAT | 2026-03-11 | 2026-04-11
RE/0066-PRJ-T6-CIV-RS-SU | Reinforcement Supply | 2010 | GR01 | 2010 | SMARTWORLD THE EDITION | Ram Niwas & SonsDeepak gupta | 9110001691 | 60 |  |  | 2026-04-10 | Steel Re-bar TMT 08 mm Dia. FE-550D | TO | 34 | 60800 | 2067200 | 2439296 | 2188800 | 2582784 | 121600 | 2188800 | 2582784 | ZMAT | 2026-04-10 | 2026-05-10
RE/0066-PRJ-T6-CIV-RS-SU | Reinforcement Supply | 2010 | GR01 | 2010 | SMARTWORLD THE EDITION | Ram Niwas & SonsDeepak gupta | 9110001691 | 120 |  |  | 2026-04-10 | Steel Re-bar TMT 10 mm Dia. FE-550D | TO | 9 | 59800 | 538200 | 635076 | 538200 | 635076 | 0 | 538200 | 635076 | ZMAT | 2026-04-10 | 2026-05-10
RE/0066-PRJ-T6-CIV-RS-SU | Reinforcement Supply | 2010 | GR01 | 2010 | SMARTWORLD THE EDITION | ESL STEEL LIMITED | 9110001698 | 60 |  |  | 2026-04-10 | Steel Re-bar TMT 12 mm Dia. FE-550D | TO | 44 | 60500 | 2662000 | 3141160 | 2548260 | 3006946.8 | 113740 | 2548260 | 3006946.8 | ZMAT | 2026-04-10 | 2026-05-10
RE/0066-PRJ-T6-CIV-RS-SU | Reinforcement Supply | 2010 | GR01 | 2010 | SMARTWORLD THE EDITION | ESL STEEL LIMITED | 9110001698 | 120 |  |  | 2026-04-10 | Steel Re-bar TMT 16 mm Dia. FE-550D | TO | 6.5 | 60500 | 393250 | 464035 | 410553 | 484452.54 | 17303 | 410553 | 484452.54 | ZMAT | 2026-04-10 | 2026-05-10
RE/0066-PRJ-T6-CIV-RS-SU | Reinforcement Supply | 2010 | GR01 | 2010 | SMARTWORLD THE EDITION | ESL STEEL LIMITED | 9110001698 | 180 |  |  | 2026-04-10 | Steel Re-bar TMT 20 mm Dia. FE-550D | TO | 13 | 60500 | 786500 | 928070 | 787831 | 929640.58 | 1331 | 787831 | 929640.58 | ZMAT | 2026-04-10 | 2026-05-10
RE/0066-PRJ-T6-CIV-RS-SU | Reinforcement Supply | 2010 | GR01 | 2010 | SMARTWORLD THE EDITION | ESL STEEL LIMITED | 9110001698 | 240 |  |  | 2026-04-10 | Steel Re-bar TMT 25 mm Dia. FE-550D | TO | 25 | 60500 | 1512500 | 1784750 | 1587157 | 1872845.26 | 74657 | 1587157 | 1872845.26 | ZMAT | 2026-04-10 | 2026-05-10
RE/0066-PRJ-T6-CIV-RS-SU | Reinforcement Supply | 2010 | GR01 | 2010 | SMARTWORLD THE EDITION | ESL STEEL LIMITED | 9110001698 | 300 |  |  | 2026-04-10 | Steel Re-bar TMT 32 mm Dia. FE-550D | TO | 6 | 60500 | 363000 | 428340 | 356768.5 | 420986.83 | 6231.5 | 356768.5 | 420986.83 | ZMAT | 2026-04-10 | 2026-05-10
RE/0066-PRJ-T6-CIV-RS-SU | Reinforcement Supply | 2010 | GR01 | 2010 | SMARTWORLD THE EDITION | Petropol India LimitedSANJAY GUPTA | 9110001791 | 60 |  |  | 2026-05-11 | Steel Re-bar TMT 08 mm Dia. FE-550D | TO | 53 | 55700 | 2952100 | 3483478 | 2952100 | 3483478 | 0 | 2952100 | 3483478 | ZMAT | 2026-05-11 | 2026-06-11
RE/0066-PRJ-T6-CIV-RS-SU | Reinforcement Supply | 2010 | GR01 | 2010 | SMARTWORLD THE EDITION | Petropol India LimitedSANJAY GUPTA | 9110001791 | 120 |  |  | 2026-05-11 | Steel Re-bar TMT 10 mm Dia. FE-550D | TO | 3 | 54700 | 164100 | 193638 | 130186 | 153619.48 | 33914 | 130186 | 153619.48 | ZMAT | 2026-05-11 | 2026-06-11
RE/0066-PRJ-T6-CIV-RS-SU | Reinforcement Supply | 2010 | GR01 | 2010 | SMARTWORLD THE EDITION | Jindal Steel Limited | 9110001796 | 60 |  |  | 2026-05-11 | Steel Re-bar TMT 12 mm Dia. FE-550D | TO | 33 | 57200 | 1887600 | 2227368 | 1480793.6 | 1747336.45 | 406806.4 | 0 | 0 | ZMAT | 2026-05-11 | 2026-06-11
RE/0066-PRJ-T6-CIV-RS-SU | Reinforcement Supply | 2010 | GR01 | 2010 | SMARTWORLD THE EDITION | Jindal Steel Limited | 9110001796 | 120 |  |  | 2026-05-11 | Steel Re-bar TMT 16 mm Dia. FE-550D | TO | 3 | 57200 | 171600 | 202488 | 128928.8 | 152135.98 | 42671.2 | 0 | 0 | ZMAT | 2026-05-11 | 2026-06-11
RE/0066-PRJ-T6-CIV-RS-SU | Reinforcement Supply | 2010 | GR01 | 2010 | SMARTWORLD THE EDITION | Jindal Steel Limited | 9110001796 | 180 |  |  | 2026-05-11 | Steel Re-bar TMT 20 mm Dia. FE-550D | TO | 29 | 57200 | 1658800 | 1957384 | 1383210.4 | 1632188.27 | 275589.6 | 0 | 0 | ZMAT | 2026-05-11 | 2026-06-11
RE/0066-PRJ-T6-CIV-RS-SU | Reinforcement Supply | 2010 | GR01 | 2010 | SMARTWORLD THE EDITION | Jindal Steel Limited | 9110001796 | 240 |  |  | 2026-05-11 | Steel Re-bar TMT 25 mm Dia. FE-550D | TO | 13 | 57200 | 743600 | 877448 | 743600 | 877448 | 0 | 0 | 0 | ZMAT | 2026-05-11 | 2026-06-11
RE/0066-PRJ-T6-CIV-RS-SU | Reinforcement Supply | 2010 | GR01 | 2010 | SMARTWORLD THE EDITION | Jindal Steel Limited | 9110001796 | 300 |  |  | 2026-05-11 | Steel Re-bar TMT 32 mm Dia. FE-550D | TO | 4 | 57200 | 228800 | 269984 | 228800 | 269984 | 0 | 0 | 0 | ZMAT | 2026-05-11 | 2026-06-11
RE/0066-PRJ-T6-CIV-SW-AS | Aluminum Shuttering Supply | 2010 | GR01 | 2010 | SMARTWORLD THE EDITION | Ahluwalia Contracts India Limited | 9140000321 | 60 |  |  | 2024-07-20 | CENTERING & SHUTTERING Part B | AU | 1 | 0 | 168589130.13 | 198935173.55 | 47157445.42 | 55645785.59 | 121431684.71 | 38118050.53 | 44979299.63 | ZSER | 2024-07-15 | 2027-01-14
RE/0066-PRJ-T6-CIV-SW-CS | Conventional Shuttering | 2010 | GR01 | 2010 | SMARTWORLD THE EDITION | Ahluwalia Contracts India Limited | 9140000321 | 50 |  |  | 2024-07-20 | CENTERING & SHUTTERING Part A | AU | 1 | 0 | 18132637.36 | 21396512.08 | 15531214.88 | 18326833.56 | 2601422.48 | 15531203.53 | 18326820.17 | ZSER | 2024-07-15 | 2027-01-14
RE/0066-PRJ-T6-CIV-SW-SO | Shuttering Other | 2010 | GR01 | 2010 |  |  |  | 0 | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
RE/0066-PRJ-T6-CIV-WP | Waterproofing Works | 2010 | GR01 | 2010 | SMARTWORLD THE EDITION | Ahluwalia Contracts India Limited | 9140000321 | 110 |  |  | 2024-07-20 | FLOORING | AU | 1 | 0 | 1433 | 1690.94 | 0 | 0 | 1433 | 0 | 0 | ZSER | 2024-07-15 | 2027-01-14
RE/0066-PRJ-T6-CIV-WP | Waterproofing Works | 2010 | GR01 | 2010 | SMARTWORLD THE EDITION | Ahluwalia Contracts India Limited | 9140000321 | 120 |  |  | 2024-07-20 | WATER-PROOFING WORKS | AU | 1 | 0 | 19414333.86 | 22908913.95 | 440146.86 | 519373.3 | 18974187 | 440146.86 | 519373.3 | ZSER | 2024-07-15 | 2027-01-14
RE/0066-PRJ-T6-FAC-EF | Elevation Feature | 2010 | GR01 | 2010 | SMARTWORLD THE EDITION | Ahluwalia Contracts India Limited | 9140000321 | 100 |  |  | 2024-07-20 | STRUCTURAL STEEL WORKS | AU | 1 | 0 | 0.01 | 0.01 | 0 | 0 | 0.01 | 0 | 0 | ZSER | 2024-07-15 | 2027-01-14
RE/0066-PRJ-T6-FAC-EP | External Paint | 2010 | GR01 | 2010 | SMARTWORLD THE EDITION | Ahluwalia Contracts India Limited | 9140000321 | 160 |  |  | 2024-07-20 | Amed-Monthly rental payment to M/S ACIL | AU | 1 | 0 | 4866880 | 5742918.4 | 0 | 0 | 4866880 | 0 | 0 | ZSER | 2024-07-15 | 2027-01-14
RE/0066-PRJ-T6-FAC-GL | Glazing Works | 2010 | GR01 | 2010 |  |  |  | 0 | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
RE/0066-PRJ-T6-FAC-RA | Railing Works | 2010 | GR01 | 2010 |  |  |  | 0 | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
RE/0066-PRJ-T6-FIS-CF | Ceiling Finish Works | 2010 | GR01 | 2010 |  |  |  | 0 | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
RE/0066-PRJ-T6-FIS-CN | Stone Work (Kitchen & Toilet Counter) | 2010 | GR01 | 2010 |  |  |  | 0 | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
RE/0066-PRJ-T6-FIS-DW | Door Works | 2010 | GR01 | 2010 |  |  |  | 0 | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
RE/0066-PRJ-T6-FIS-FF | Floor Finish Works | 2010 | GR01 | 2010 | SMARTWORLD THE EDITION | Ahluwalia Contracts India Limited | 9140000321 | 110 |  |  | 2024-07-20 | FLOORING | AU | 1 | 0 | 10574689.9 | 12478134.08 | 0 | 0 | 10574689.9 | 0 | 0 | ZSER | 2024-07-15 | 2027-01-14
RE/0066-PRJ-T6-FIS-GL | Glazing Works | 2010 | GR01 | 2010 |  |  |  | 0 | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
RE/0066-PRJ-T6-FIS-LF | Lobby Furniture | 2010 | GR01 | 2010 |  |  |  | 0 | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
RE/0066-PRJ-T6-FIS-MD | Modular Kitchen Works | 2010 | GR01 | 2010 |  |  |  | 0 | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
RE/0066-PRJ-T6-FIS-MF | Misc Finish Works | 2010 | GR01 | 2010 |  |  |  | 0 | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
RE/0066-PRJ-T6-FIS-MI | Misc Works (Canopy MS/Toilet Cubicals/Ro | 2010 | GR01 | 2010 |  |  |  | 0 | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
RE/0066-PRJ-T6-FIS-MK | Modular Kitchen | 2010 | GR01 | 2010 |  |  |  | 0 | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
RE/0066-PRJ-T6-FIS-MR | Mirror | 2010 | GR01 | 2010 |  |  |  | 0 | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
RE/0066-PRJ-T6-FIS-MS | MS Railing | 2010 | GR01 | 2010 |  |  |  | 0 | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
RE/0066-PRJ-T6-FIS-MW | MS works | 2010 | GR01 | 2010 |  |  |  | 0 | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
RE/0066-PRJ-T6-FIS-SG | Signage Works | 2010 | GR01 | 2010 |  |  |  | 0 | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
RE/0066-PRJ-T6-FIS-ST | Glass Partition (Study & Toilet) | 2010 | GR01 | 2010 |  |  |  | 0 | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
RE/0066-PRJ-T6-FIS-VT | Vanity Cabinet (Wood) | 2010 | GR01 | 2010 |  |  |  | 0 | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
RE/0066-PRJ-T6-FIS-WF | Wall Finish Works | 2010 | GR01 | 2010 |  |  |  | 0 | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
RE/0066-PRJ-T6-FIS-WO | Wood Work | 2010 | GR01 | 2010 |  |  |  | 0 | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
RE/0066-PRJ-T6-MEP-EW-HE | High Side Electrical Works | 2010 | GR01 | 2010 | SMARTWORLD THE EDITION | HKE Electric Contracts | 9140000365 | 10 |  |  | 2024-09-25 | Lightning Protection System for Basement | AU | 1 | 0 | 143500 | 169330 | 143500 | 169330 | 0 | 143500.85 | 169331 | ZSER | 2024-09-25 | 2024-10-24
RE/0066-PRJ-T6-MEP-EW-HE | High Side Electrical Works | 2010 | GR01 | 2010 | SMARTWORLD THE EDITION | Dehn India Pvt Ltd | 9140000379 | 10 |  |  | 2024-10-24 | Lightning Protection System for Basement | AU | 1 | 0 | 979507 | 1155818.26 | 111744.51 | 131858.52 | 867762.49 | 111744.53 | 131858.55 | ZSER | 2024-10-24 | 2027-08-23
RE/0066-PRJ-T6-MEP-EW-HE | High Side Electrical Works | 2010 | GR01 | 2010 | SMARTWORLD THE EDITION | SATKARTAR ELECTRICALS AND ELECTRONIPRIVATE LIMITED | 9140000677 | 60 |  |  | 2026-06-02 | Electrical Works Tower T6 | AU | 1 | 93345352.39 | 51427154.11 | 60684041.85 | 0 | 0 | 51427154.11 | 0 | 0 | ZSER | 2026-06-01 | 2028-02-01
RE/0066-PRJ-T6-MEP-EW-LE | Low Side Electrical Works | 2010 | GR01 | 2010 | SMARTWORLD THE EDITION | Ahluwalia Contracts India Limited | 9140000321 | 140 |  |  | 2024-07-20 | CONDUITING | AU | 1 | 0 | 21508839.87 | 25380431.05 | 5268340.98 | 6216642.36 | 16240498.89 | 3730301.46 | 4401755.72 | ZSER | 2024-07-15 | 2027-01-14
RE/0066-PRJ-T6-MEP-EW-LE | Low Side Electrical Works | 2010 | GR01 | 2010 | SMARTWORLD THE EDITION | SATKARTAR ELECTRICALS AND ELECTRONIPRIVATE LIMITED | 9140000677 | 60 |  |  | 2026-06-02 | Electrical Works Tower T6 | AU | 1 | 0 | 41918198.28 | 49463473.97 | 0 | 0 | 41918198.28 | 0 | 0 | ZSER | 2026-06-01 | 2028-02-01
RE/0066-PRJ-T6-MEP-EW-LS | Light Fixtures Supply | 2010 | GR01 | 2010 |  |  |  | 0 | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
RE/0066-PRJ-T6-MEP-FF | Fire Fighting Work | 2010 | GR01 | 2010 | SMARTWORLD THE EDITION | Atom MEP Engineers Pvt. Ltd. | 9140000668 | 280 |  |  | 2026-05-19 | FF-FIRE HYDRANT & EQUIPMENT - T6 | AU | 1 | 2769700 | 2769700 | 3268246 | 0 | 0 | 2769700 | 0 | 0 | ZSER | 2026-04-04 | 2028-02-04
RE/0066-PRJ-T6-MEP-FF | Fire Fighting Work | 2010 | GR01 | 2010 | SMARTWORLD THE EDITION | Atom MEP Engineers Pvt. Ltd. | 9140000668 | 330 |  |  | 2026-05-19 | FF-AUTOMATIC SPRINKLER & WATER -T6 | AU | 1 | 17432576 | 17432576 | 20570439.68 | 0 | 0 | 17432576 | 0 | 0 | ZSER | 2026-04-04 | 2028-02-04
RE/0066-PRJ-T6-MEP-FF | Fire Fighting Work | 2010 | GR01 | 2010 | SMARTWORLD THE EDITION | Atom MEP Engineers Pvt. Ltd. | 9140000668 | 380 |  |  | 2026-05-19 | FF-PORTABLE FIRE EXTINGUISHERS-T6 | AU | 1 | 305085 | 305085 | 360000.3 | 0 | 0 | 305085 | 0 | 0 | ZSER | 2026-04-04 | 2028-02-04
RE/0066-PRJ-T6-MEP-HV-HS | High Side | 2010 | GR01 | 2010 |  |  |  | 0 | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
RE/0066-PRJ-T6-MEP-HV-LS | Low Side | 2010 | GR01 | 2010 |  |  |  | 0 | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
RE/0066-PRJ-T6-MEP-LT | Lifts | 2010 | GR01 | 2010 |  |  |  | 0 | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
RE/0066-PRJ-T6-MEP-PB-FS | Fixtures Supply | 2010 | GR01 | 2010 |  |  |  | 0 | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
RE/0066-PRJ-T6-MEP-PB-IP | Internal Plumbing | 2010 | GR01 | 2010 | SMARTWORLD THE EDITION | Atom MEP Engineers Pvt. Ltd. | 9140000668 | 20 |  |  | 2026-05-19 | SANITARY FIXTURES & FITTINGS T-6 | AU | 1 | 3329060 | 3329060 | 3928290.8 | 0 | 0 | 3329060 | 0 | 0 | ZSER | 2026-04-04 | 2028-02-04
RE/0066-PRJ-T6-MEP-PB-IP | Internal Plumbing | 2010 | GR01 | 2010 | SMARTWORLD THE EDITION | Atom MEP Engineers Pvt. Ltd. | 9140000668 | 70 |  |  | 2026-05-19 | INTERNAL DRAINAGE T-6 | AU | 1 | 16873825.6 | 16873825.6 | 19911114.21 | 0 | 0 | 16873825.6 | 0 | 0 | ZSER | 2026-04-04 | 2028-02-04
RE/0066-PRJ-T6-MEP-PB-IP | Internal Plumbing | 2010 | GR01 | 2010 | SMARTWORLD THE EDITION | Atom MEP Engineers Pvt. Ltd. | 9140000668 | 120 |  |  | 2026-05-19 | DOMESTIC AND FLUSHING WATER T-6 | AU | 1 | 15363960.24 | 15363960.24 | 18129473.08 | 0 | 0 | 15363960.24 | 0 | 0 | ZSER | 2026-04-04 | 2028-02-04
RE/0066-PRJ-T6-MEP-PB-IP | Internal Plumbing | 2010 | GR01 | 2010 | SMARTWORLD THE EDITION | Atom MEP Engineers Pvt. Ltd. | 9140000668 | 190 |  |  | 2026-05-19 | MISCELLANEOUS ITEMS FOR TERRACE WATER-T6 | AU | 1 | 428820 | 428820 | 506007.6 | 0 | 0 | 428820 | 0 | 0 | ZSER | 2026-04-04 | 2028-02-04
RE/0066-PRJ-T6-MEP-PB-JC | JACUZZI | 2010 | GR01 | 2010 |  |  |  | 0 | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
RE/0066-PRJ-T6-MEP-PN | PNG Gas Pipe Line | 2010 | GR01 | 2010 |  |  |  | 0 | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
RE/0066-RES-MK-OM | Other Marketing Expenses | 2010 |  | 2010 | SMARTWORLD THE EDITION | Khushi Enterprises | 9140000201 | 10 |  |  | 2023-08-25 | Barricade Branding & Company Logo | AU | 1 | 216026.72 | 216026.72 | 254911.53 | 216026.71 | 254911.52 | 0.01 | 216026.71 | 254911.52 | ZSER | 2023-03-05 | 2023-03-15
RE/0066-RES-MK-OM | Other Marketing Expenses | 2010 |  | 2010 | SMARTWORLD THE EDITION | Sudershan Global Events & ServicesLtd. | 9160000024 | 10 |  |  | 2023-03-10 | CP event at The Oberoi - 5th March | AU | 1 | 926426 | 0 | 0 | 926426 | 1093182.68 | 926426 | 926426 | 1093182.68 | ZGEN | 2023-03-05 | 2023-03-05
RE/0066-RES-MK-OM | Other Marketing Expenses | 2010 |  | 2010 | SMARTWORLD THE EDITION | Native Super Ventures Pvt Ltd | 9160000052 | 10 |  |  | 2023-04-28 | Locallity Drone Shoot | AU | 1 | 20000 | 0 | 0 | 20000 | 23600 | 20000 | 20000 | 23600 | ZGEN | 2023-04-28 | 2023-04-28
RE/0066-RES-MK-OM | Other Marketing Expenses | 2010 |  | 2010 | SMARTWORLD THE EDITION | Grapevine Entertainment | 9160000097 | 10 |  |  | 2023-05-22 | CP Meet At 62 Sales Gallery on 4th May23 | AU | 1 | 300000 | 0 | 0 | 300000 | 354000 | 300000 | 300000 | 354000 | ZGEN | 2023-05-04 | 2023-05-04
RE/0066-RES-MK-OM | Other Marketing Expenses | 2010 |  | 2010 | SMARTWORLD THE EDITION | New Sign Grafix | 9160000110 | 10 |  |  | 2023-05-30 | Runner Board | AU | 1 | 248000 | 248000 | 292640 | 248000 | 292640 | 0 | 248000 | 292640 | ZGEN | 2022-04-18 | 2022-04-23
RE/0066-RES-MK-OM | Other Marketing Expenses | 2010 |  | 2010 | SMARTWORLD THE EDITION | Grapevine Entertainment | 9160000166 | 10 |  |  | 2023-06-19 | Stall Fabrication for promoted New Proj. | AU | 1 | 42000 | 42000 | 49560 | 42000 | 49560 | 0 | 42000 | 49560 | ZGEN | 2023-05-28 | 2023-05-28
RE/0066-SCO-75-AD -01 | House Keeping Expenses | 2010 |  | 2010 | SMARTWORLD THE EDITION | Prime Solutions | 9110000101 | 20 |  |  | 2023-05-16 | M-FOLD | NO | 2505 | 31.78 | 79608.9 | 93938.5 | 56822.89 | 67051.01 | 22786.01 | 56821.42 | 67049.14 | ZMAT | 2025-01-20 | 2025-03-20
RE/0066-SCO-75-AD -01 | House Keeping Expenses | 2010 |  | 2010 | SMARTWORLD THE EDITION | Prime Solutions | 9110000101 | 30 |  |  | 2023-05-16 | TOILET ROLL ELEGANT | NO | 2500 | 12.75 | 31875 | 37612.5 | 14407.69 | 17001.08 | 17467.31 | 14407.5 | 17001.75 | ZMAT | 2025-01-20 | 2025-03-20
RE/0066-SCO-75-AD -01 | House Keeping Expenses | 2010 |  | 2010 | SMARTWORLD THE EDITION | Prime Solutions | 9110000101 | 40 |  |  | 2023-05-16 | MIST TISSUE | NO | 2500 | 30 | 75000 | 88500 | 36000 | 42480 | 39000 | 35999.96 | 42479.74 | ZMAT | 2025-01-20 | 2025-03-20
RE/0066-SCO-75-AD -01 | House Keeping Expenses | 2010 |  | 2010 | SMARTWORLD THE EDITION | Prime Solutions | 9110000101 | 50 |  |  | 2023-05-16 | TOWEL NAPKIN | NO | 3700 | 14.5 | 53650 | 63307 | 21750.35 | 25665.41 | 31899.65 | 21750 | 25665.37 | ZMAT | 2025-01-20 | 2025-03-20
RE/0066-SCO-75-AD -01 | House Keeping Expenses | 2010 |  | 2010 | SMARTWORLD THE EDITION | Updater Services limited | 9110000355 | 10 |  |  | 2024-01-12 | FEATHER BRUSH 766 | NO | 2 | 73.5 | 147 | 173.46 | 146.99 | 173.45 | 0.01 | 147 | 173.4 | ZMAT | 2025-01-20 | 2025-03-20
RE/0066-SCO-75-AD -01 | House Keeping Expenses | 2010 |  | 2010 | SMARTWORLD THE EDITION | Updater Services limited | 9110000355 | 20 |  |  | 2024-01-12 | YELLOW DUSTER LARGE | NO | 12 | 21 | 252 | 264.6 | 252.02 | 264.62 | 0.02 | 252 | 264.6 | ZMAT | 2025-01-20 | 2025-03-20
RE/0066-SCO-75-AD -01 | House Keeping Expenses | 2010 |  | 2010 | SMARTWORLD THE EDITION | Updater Services limited | 9110000355 | 30 |  |  | 2024-01-12 | ODONIL 75 GMS 766 | NO | 5 | 71.4 | 357 | 421.26 | 356.99 | 421.25 | 0.01 | 357 | 421.2 | ZMAT | 2025-01-20 | 2025-03-20
RE/0066-SCO-75-AD -01 | House Keeping Expenses | 2010 |  | 2010 | SMARTWORLD THE EDITION | Updater Services limited | 9110000355 | 40 |  |  | 2024-01-12 | PLASTIC MUG BIG 766 | NO | 2 | 24.15 | 48.3 | 56.99 | 48.31 | 57 | 0.01 | 48.16 | 56.76 | ZMAT | 2025-01-20 | 2025-03-20
RE/0066-SCO-75-AD -01 | House Keeping Expenses | 2010 |  | 2010 | SMARTWORLD THE EDITION | Updater Services limited | 9110000355 | 50 |  |  | 2024-01-12 | GLASS WIPER (GOOD QUALITY) 766 | NO | 4 | 784.88 | 3139.52 | 3704.63 | 3139.53 | 3704.64 | 0.01 | 3139.52 | 3704.74 | ZMAT | 2025-01-20 | 2025-03-20
RE/0066-SCO-75-AD -01 | House Keeping Expenses | 2010 |  | 2010 | SMARTWORLD THE EDITION | Updater Services limited | 9110000355 | 60 |  |  | 2024-01-12 | Nepthelene Ball ( M ) (Superior ) White | NO | 1 | 144.9 | 144.9 | 170.98 | 144.9 | 170.98 | 0 | 144.9 | 171 | ZMAT | 2025-01-20 | 2025-03-20
RE/0066-SCO-75-AD -01 | House Keeping Expenses | 2010 |  | 2010 | SMARTWORLD THE EDITION | Updater Services limited | 9110000355 | 70 |  |  | 2024-01-12 | ROOM FRESHNER-PREMIUM VENNILA 766 | NO | 5 | 132.83 | 664.15 | 783.7 | 664.15 | 783.7 | 0 | 664.15 | 783.75 | ZMAT | 2025-01-20 | 2025-03-20
RE/0066-SCO-75-AD -01 | House Keeping Expenses | 2010 |  | 2010 | SMARTWORLD THE EDITION | Updater Services limited | 9110000355 | 80 |  |  | 2024-01-12 | DISPOSABLE BAG SMALL BLACK 766 | NO | 20 | 114.71 | 2294.2 | 2707.16 | 2294.18 | 2707.13 | 0.02 | 2294.2 | 2707.22 | ZMAT | 2025-01-20 | 2025-03-20
RE/0066-SCO-75-AD -01 | House Keeping Expenses | 2010 |  | 2010 | SMARTWORLD THE EDITION | Updater Services limited | 9110000355 | 90 |  |  | 2024-01-12 | DISPOSABLE BAG BIG BLACK (45-50) 766 | NO | 30 | 114.71 | 3441.3 | 4060.73 | 3441.32 | 4060.76 | 0.02 | 3441.3 | 4060.72 | ZMAT | 2025-01-20 | 2025-03-20
RE/0066-SCO-75-AD -01 | House Keeping Expenses | 2010 |  | 2010 | SMARTWORLD THE EDITION | Updater Services limited | 9110000355 | 100 |  |  | 2024-01-12 | HIT SPRAY BLACK 766 | NO | 3 | 181.13 | 543.39 | 641.2 | 543.38 | 641.19 | 0.01 | 543.39 | 641.19 | ZMAT | 2025-01-20 | 2025-03-20
RE/0066-SCO-75-AD -01 | House Keeping Expenses | 2010 |  | 2010 | SMARTWORLD THE EDITION | Updater Services limited | 9110000355 | 110 |  |  | 2024-01-12 | TASKI - R7 766 | NO | 5 | 131.25 | 656.25 | 774.38 | 656.23 | 774.35 | 0.02 | 656.25 | 774.46 | ZMAT | 2025-01-20 | 2025-03-20
RE/0066-SCO-75-AD -01 | House Keeping Expenses | 2010 |  | 2010 | SMARTWORLD THE EDITION | Updater Services limited | 9110000355 | 120 |  |  | 2024-01-12 | Taski TR 101 - Carpet Shampoo 766 | NO | 5 | 288.75 | 1443.75 | 1703.63 | 1443.77 | 1703.65 | 0.02 | 1443.75 | 1703.56 | ZMAT | 2025-01-20 | 2025-03-20
RE/0066-SCO-75-AD -01 | House Keeping Expenses | 2010 |  | 2010 | SMARTWORLD THE EDITION | Updater Services limited | 9110000355 | 130 |  |  | 2024-01-12 | MICRO FIBER CLOTH Blue | NO | 10 | 126 | 1260 | 1323 | 1260 | 1323 | 0 | 1260 | 1323 | ZMAT | 2025-01-20 | 2025-03-20
RE/0066-SCO-75-AD -01 | House Keeping Expenses | 2010 |  | 2010 | SMARTWORLD THE EDITION | Updater Services limited | 9110000355 | 140 |  |  | 2024-01-12 | YELLOW DUSTER LARGE | NO | 8 | 21 | 168 | 176.4 | 167.98 | 176.38 | 0.02 | 168 | 176.4 | ZMAT | 2025-01-20 | 2025-03-20
RE/0066-SCO-75-AD -01 | House Keeping Expenses | 2010 |  | 2010 | SMARTWORLD THE EDITION | Updater Services limited | 9110000355 | 150 |  |  | 2024-01-12 | DUST PAN IPS | NO | 3 | 21 | 63 | 74.34 | 62.99 | 74.33 | 0.01 | 63 | 74.4 | ZMAT | 2025-01-20 | 2025-03-20
RE/0066-SCO-75-AD -01 | House Keeping Expenses | 2010 |  | 2010 | SMARTWORLD THE EDITION | Updater Services limited | 9110000355 | 160 |  |  | 2024-01-12 | PLASTIC MUG BIG | NO | 3 | 21 | 63 | 74.34 | 62.99 | 74.33 | 0.01 | 63 | 74.4 | ZMAT | 2025-01-20 | 2025-03-20
RE/0066-SCO-75-AD -01 | House Keeping Expenses | 2010 |  | 2010 | SMARTWORLD THE EDITION | Updater Services limited | 9110000355 | 170 |  |  | 2024-01-12 | BLUE DUST CONTROLLER SET | NO | 3 | 330.75 | 992.25 | 1170.86 | 992.23 | 1170.83 | 0.02 | 992 | 1170.6 | ZMAT | 2025-01-20 | 2025-03-20
RE/0066-SCO-75-AD -01 | House Keeping Expenses | 2010 |  | 2010 | SMARTWORLD THE EDITION | Updater Services limited | 9110000355 | 180 |  |  | 2024-01-12 | RUBBER GLOVES RED | NO | 5 | 47.25 | 236.25 | 278.78 | 236.23 | 278.75 | 0.02 | 236.1 | 278.7 | ZMAT | 2025-01-20 | 2025-03-20
RE/0066-SCO-75-AD -01 | House Keeping Expenses | 2010 |  | 2010 | SMARTWORLD THE EDITION | Updater Services limited | 9110000355 | 190 |  |  | 2024-01-12 | SCOTCH BRIGHT 3M | NO | 10 | 24.15 | 241.5 | 284.97 | 241.48 | 284.95 | 0.02 | 241.5 | 284.9 | ZMAT | 2025-01-20 | 2025-03-20
RE/0066-SCO-75-AD -01 | House Keeping Expenses | 2010 |  | 2010 | SMARTWORLD THE EDITION | Updater Services limited | 9110000355 | 200 |  |  | 2024-01-12 | HARD BROOM (BIG) | NO | 15 | 47.25 | 708.75 | 708.75 | 708.75 | 708.75 | 0 | 708.75 | 708.75 | ZMAT | 2025-01-20 | 2025-03-20
RE/0066-SCO-75-AD -01 | House Keeping Expenses | 2010 |  | 2010 | SMARTWORLD THE EDITION | Updater Services limited | 9110000355 | 210 |  |  | 2024-01-12 | GLASS WIPER (GOOD QUALITY) | NO | 1 | 682.5 | 682.5 | 805.35 | 682.52 | 805.37 | 0.02 | 682.5 | 805.3 | ZMAT | 2025-01-20 | 2025-03-20
RE/0066-SCO-75-AD -01 | House Keeping Expenses | 2010 |  | 2010 | SMARTWORLD THE EDITION | Updater Services limited | 9110000355 | 220 |  |  | 2024-01-12 | Blue Check Duster | NO | 12 | 10.5 | 126 | 132.3 | 125.98 | 132.28 | 0.02 | 126 | 132.4 | ZMAT | 2025-01-20 | 2025-03-20
RE/0066-SCO-75-AD -01 | House Keeping Expenses | 2010 |  | 2010 | SMARTWORLD THE EDITION | Updater Services limited | 9110000355 | 230 |  |  | 2024-01-12 | WIPER MEDIUM | NO | 3 | 126 | 378 | 446.04 | 377.99 | 446.03 | 0.01 | 378 | 446 | ZMAT | 2025-01-20 | 2025-03-20
RE/0066-SCO-75-AD -01 | House Keeping Expenses | 2010 |  | 2010 | SMARTWORLD THE EDITION | Updater Services limited | 9110000355 | 240 |  |  | 2024-01-12 | SPRAY BOTTEL | NO | 5 | 52.5 | 262.5 | 309.75 | 262.52 | 309.77 | 0.02 | 262.5 | 309.7 | ZMAT | 2025-01-20 | 2025-03-20
RE/0066-SCO-75-AD -01 | House Keeping Expenses | 2010 |  | 2010 | SMARTWORLD THE EDITION | Updater Services limited | 9110000355 | 250 |  |  | 2024-01-12 | ROOM FRESHNER-PREMIUM | NO | 3 | 115.5 | 346.5 | 408.87 | 346.53 | 408.9 | 0.03 | 346.5 | 408.9 | ZMAT | 2025-01-20 | 2025-03-20
RE/0066-SCO-75-AD -01 | House Keeping Expenses | 2010 |  | 2010 | SMARTWORLD THE EDITION | Updater Services limited | 9110000355 | 260 |  |  | 2024-01-12 | DISPOSABLE BAG SMALL BLACK | NO | 25 | 99.75 | 2493.75 | 2942.63 | 2493.74 | 2942.61 | 0.01 | 2493.75 | 2942.54 | ZMAT | 2025-01-20 | 2025-03-20
RE/0066-SCO-75-AD -01 | House Keeping Expenses | 2010 |  | 2010 | SMARTWORLD THE EDITION | Updater Services limited | 9110000355 | 270 |  |  | 2024-01-12 | DISPOSABLE BAG BIG BLACK (45-50) | NO | 30 | 99.75 | 2992.5 | 3531.15 | 2992.5 | 3531.15 | 0 | 2992.5 | 3531.09 | ZMAT | 2025-01-20 | 2025-03-20
RE/0066-SCO-75-AD -01 | House Keeping Expenses | 2010 |  | 2010 | SMARTWORLD THE EDITION | Updater Services limited | 9110000355 | 280 |  |  | 2024-01-12 | PRILL 425 ML | NO | 14 | 86.1 | 1205.4 | 1422.37 | 1193.37 | 1408.18 | 12.03 | 1193.3 | 1408.1 | ZMAT | 2025-01-20 | 2025-03-20
RE/0066-SCO-75-AD -01 | House Keeping Expenses | 2010 |  | 2010 | SMARTWORLD THE EDITION | Updater Services limited | 9110000355 | 290 |  |  | 2024-01-12 | TASKI - D7 | NO | 5 | 309.26 | 1546.3 | 1824.63 | 1546.32 | 1824.66 | 0.02 | 1546.3 | 1824.69 | ZMAT | 2025-01-20 | 2025-03-20
RE/0066-SCO-75-AD -01 | House Keeping Expenses | 2010 |  | 2010 | SMARTWORLD THE EDITION | Updater Services limited | 9110000355 | 300 |  |  | 2024-01-12 | TASKI - R5 | NO | 10 | 204.06 | 2040.6 | 2407.91 | 2040.6 | 2407.91 | 0 | 2040.6 | 2407.99 | ZMAT | 2025-01-20 | 2025-03-20
RE/0066-SCO-75-AD -01 | House Keeping Expenses | 2010 |  | 2010 | SMARTWORLD THE EDITION | Updater Services limited | 9110000355 | 310 |  |  | 2024-01-12 | TASKI - R6 | NO | 5 | 145.31 | 726.55 | 857.33 | 726.56 | 857.34 | 0.01 | 726.55 | 857.35 | ZMAT | 2025-01-20 | 2025-03-20
RE/0066-SCO-75-AD -01 | House Keeping Expenses | 2010 |  | 2010 | SMARTWORLD THE EDITION | Updater Services limited | 9110000355 | 320 |  |  | 2024-01-12 | TASKI - 103 | NO | 5 | 325.5 | 1627.5 | 1920.45 | 1627.48 | 1920.43 | 0.02 | 1627.5 | 1920.49 | ZMAT | 2025-01-20 | 2025-03-20
RE/0066-SCO-75-AD -01 | House Keeping Expenses | 2010 |  | 2010 | SMARTWORLD THE EDITION | Updater Services limited | 9110000355 | 330 |  |  | 2024-01-12 | HIT SPRAY (M) BLACK/ 200ML | NO | 10 | 87.15 | 871.5 | 1028.37 | 871.49 | 1028.36 | 0.01 | 870.75 | 1027.55 | ZMAT | 2025-01-20 | 2025-03-20
RE/0066-SCO-75-AD -01 | House Keeping Expenses | 2010 |  | 2010 | SMARTWORLD THE EDITION | Updater Services limited | 9110000355 | 340 |  |  | 2024-01-12 | HIT SPRAY (M) RED 200ML | NO | 3 | 87.15 | 261.45 | 308.51 | 261.46 | 308.52 | 0.01 | 261.45 | 308.45 | ZMAT | 2025-01-20 | 2025-03-20
RE/0066-SCO-75-AD -01 | House Keeping Expenses | 2010 |  | 2010 | SMARTWORLD THE EDITION | Updater Services limited | 9110000355 | 350 |  |  | 2024-01-12 | Urinal Cubes 765 | NO | 3 | 72.45 | 217.35 | 256.47 | 217.36 | 256.48 | 0.01 | 217.35 | 256.55 | ZMAT | 2025-01-20 | 2025-03-20
RE/0066-SCO-75-AD -01 | House Keeping Expenses | 2010 |  | 2010 | SMARTWORLD THE EDITION | Updater Services limited | 9110000355 | 360 |  |  | 2024-01-12 | Urinal Screen Crew ( H) 765 | NO | 8 | 144.9 | 1159.2 | 1367.86 | 1159.21 | 1367.87 | 0.01 | 1159.16 | 1367.74 | ZMAT | 2025-01-20 | 2025-03-20
RE/0066-SCO-75-AD -01 | House Keeping Expenses | 2010 |  | 2010 | SMARTWORLD THE EDITION | Updater Services limited | 9110000355 | 370 |  |  | 2024-01-12 | TOILET BRUSH 765 | NO | 5 | 73.5 | 367.5 | 433.65 | 367.48 | 433.63 | 0.02 | 367.5 | 433.69 | ZMAT | 2025-01-20 | 2025-03-20
RE/0066-SCO-75-AD -01 | House Keeping Expenses | 2010 |  | 2010 | SMARTWORLD THE EDITION | Updater Services limited | 9110000355 | 380 |  |  | 2024-01-12 | ALLOUT REFILL 765 | NO | 5 | 72.45 | 362.25 | 427.46 | 362.25 | 427.45 | 0 | 362.25 | 427.44 | ZMAT | 2025-01-20 | 2025-03-20
RE/0066-SCO-75-AD -01 | House Keeping Expenses | 2010 |  | 2010 | SMARTWORLD THE EDITION | Updater Services limited | 9110000355 | 390 |  |  | 2024-01-12 | SPONGE 765 | NO | 5 | 21 | 105 | 123.9 | 105.03 | 123.93 | 0.03 | 105 | 124 | ZMAT | 2025-01-20 | 2025-03-20
RE/0066-SCO-75-AD -01 | House Keeping Expenses | 2010 |  | 2010 | SMARTWORLD THE EDITION | Updater Services limited | 9110000355 | 400 |  |  | 2024-01-12 | KITCHEN WIPER 765 | NO | 3 | 36.23 | 108.69 | 128.25 | 108.72 | 128.29 | 0.03 | 108.69 | 128.29 | ZMAT | 2025-01-20 | 2025-03-20
RE/0066-SCO-75-AD -01 | House Keeping Expenses | 2010 |  | 2010 | SMARTWORLD THE EDITION | Updater Services limited | 9110000355 | 410 |  |  | 2024-01-12 | Toilet Pump 765 | NO | 3 | 54.34 | 163.02 | 192.36 | 163.01 | 192.35 | 0.01 | 163.02 | 192.42 | ZMAT | 2025-01-20 | 2025-03-20
RE/0066-SCO-75-AD -01 | House Keeping Expenses | 2010 |  | 2010 | SMARTWORLD THE EDITION | Updater Services limited | 9110000355 | 420 |  |  | 2024-01-12 | ROOM FRESHNER TIN 765 | NO | 10 | 108.68 | 1086.8 | 1282.42 | 1086.78 | 1282.4 | 0.02 | 1086.8 | 1282.38 | ZMAT | 2025-01-20 | 2025-03-20
RE/0066-SCO-75-AD -01 | House Keeping Expenses | 2010 |  | 2010 | SMARTWORLD THE EDITION | Updater Services limited | 9110000355 | 430 |  |  | 2024-01-12 | DISPOSABLE BAG SMALL BLACK 765 | NO | 20 | 114.71 | 2294.2 | 2707.16 | 2294.2 | 2707.16 | 0 | 2294.2 | 2707.17 | ZMAT | 2025-01-20 | 2025-03-20
RE/0066-SCO-75-AD -01 | House Keeping Expenses | 2010 |  | 2010 | SMARTWORLD THE EDITION | Updater Services limited | 9110000355 | 440 |  |  | 2024-01-12 | DISPOSABLE BAG BIG BLACK (45-50) 765 | NO | 20 | 114.71 | 2294.2 | 2707.16 | 2294.2 | 2707.16 | 0 | 2294.2 | 2707.17 | ZMAT | 2025-01-20 | 2025-03-20
RE/0066-SCO-75-AD -01 | House Keeping Expenses | 2010 |  | 2010 | SMARTWORLD THE EDITION | Updater Services limited | 9110000355 | 450 |  |  | 2024-01-12 | PRILL 425 ML 765 | NO | 10 | 99.02 | 990.2 | 1168.44 | 990.23 | 1168.47 | 0.03 | 990.2 | 1168.39 | ZMAT | 2025-01-20 | 2025-03-20
RE/0066-SCO-75-AD -01 | House Keeping Expenses | 2010 |  | 2010 | SMARTWORLD THE EDITION | Updater Services limited | 9110000355 | 460 |  |  | 2024-01-12 | TASKI - R2 765 | NO | 5 | 236.25 | 1181.25 | 1393.88 | 1181.23 | 1393.85 | 0.02 | 1181.25 | 1393.83 | ZMAT | 2025-01-20 | 2025-03-20
RE/0066-SCO-75-AD -01 | House Keeping Expenses | 2010 |  | 2010 | SMARTWORLD THE EDITION | Updater Services limited | 9110000355 | 470 |  |  | 2024-01-12 | TASKI - R5 765 | NO | 5 | 236.25 | 1181.25 | 1393.88 | 1181.23 | 1393.85 | 0.02 | 1181.25 | 1393.83 | ZMAT | 2025-01-20 | 2025-03-20
RE/0066-SCO-75-AD -01 | House Keeping Expenses | 2010 |  | 2010 | SMARTWORLD THE EDITION | Updater Services limited | 9110000355 | 480 |  |  | 2024-01-12 | Taski TR 101 - Carpet Shampoo 765 | NO | 5 | 288.75 | 1443.75 | 1703.63 | 1443.75 | 1703.62 | 0 | 1443.75 | 1703.53 | ZMAT | 2025-01-20 | 2025-03-20
RE/0066-SCO-75-AD -01 | House Keeping Expenses | 2010 |  | 2010 | SMARTWORLD THE EDITION | Updater Services limited | 9110000355 | 490 |  |  | 2024-01-12 | HIT SPRAY (M) BLACK/ 200ML 765 | NO | 5 | 100.22 | 501.1 | 591.3 | 501.1 | 591.3 | 0 | 501.1 | 591.29 | ZMAT | 2025-01-20 | 2025-03-20
RE/0066-SCO-75-AD -01 | House Keeping Expenses | 2010 |  | 2010 | SMARTWORLD THE EDITION | Updater Services limited | 9110000355 | 500 |  |  | 2024-01-12 | TASKI - CLEAN URINAL SCREEN | NO | 4 | 406.35 | 1625.4 | 1917.97 | 1625.42 | 1918 | 0.02 | 1625.4 | 1918 | ZMAT | 2025-01-20 | 2025-03-20
RE/0066-SCO-75-AD -01 | House Keeping Expenses | 2010 |  | 2010 | SMARTWORLD THE EDITION | Updater Services limited | 9110000355 | 510 |  |  | 2024-01-12 | MICRO FIBER CLOTH Blue | NO | 10 | 126 | 1260 | 1323 | 1260 | 1323 | 0 | 1260 | 1323 | ZMAT | 2025-01-20 | 2025-03-20
RE/0066-SCO-75-AD -01 | House Keeping Expenses | 2010 |  | 2010 | SMARTWORLD THE EDITION | Updater Services limited | 9110000355 | 520 |  |  | 2024-01-12 | YELLOW DUSTER LARGE | NO | 12 | 21 | 252 | 264.6 | 252 | 264.6 | 0 | 252 | 264.6 | ZMAT | 2025-01-20 | 2025-03-20
RE/0066-SCO-75-AD -01 | House Keeping Expenses | 2010 |  | 2010 | SMARTWORLD THE EDITION | Updater Services limited | 9110000355 | 530 |  |  | 2024-01-12 | Urinal Cube A-1( Best Qlty) | NO | 5 | 84 | 420 | 495.6 | 420.01 | 495.61 | 0.01 | 362.01 | 427.21 | ZMAT | 2025-01-20 | 2025-03-20
RE/0066-SCO-75-AD -01 | House Keeping Expenses | 2010 |  | 2010 | SMARTWORLD THE EDITION | Updater Services limited | 9110000355 | 540 |  |  | 2024-01-12 | FEATHER BRUSH | NO | 4 | 57.75 | 231 | 272.58 | 231.02 | 272.6 | 0.02 | 231 | 272.6 | ZMAT | 2025-01-20 | 2025-03-20
RE/0066-SCO-75-AD -01 | House Keeping Expenses | 2010 |  | 2010 | SMARTWORLD THE EDITION | Updater Services limited | 9110000355 | 550 |  |  | 2024-01-12 | DUST PAN IPS | NO | 3 | 21 | 63 | 74.34 | 63.05 | 74.4 | 0.05 | 63 | 74.4 | ZMAT | 2025-01-20 | 2025-03-20
RE/0066-SCO-75-AD -01 | House Keeping Expenses | 2010 |  | 2010 | SMARTWORLD THE EDITION | Updater Services limited | 9110000355 | 560 |  |  | 2024-01-12 | BLUE DUST CONTROLLER SET | NO | 2 | 330.75 | 661.5 | 780.57 | 661.44 | 780.5 | 0.06 | 661.5 | 780.5 | ZMAT | 2025-01-20 | 2025-03-20
RE/0066-SCO-75-AD -01 | House Keeping Expenses | 2010 |  | 2010 | SMARTWORLD THE EDITION | Updater Services limited | 9110000355 | 570 |  |  | 2024-01-12 | RUBBER GLOVES RED | NO | 2 | 47.25 | 94.5 | 111.51 | 94.49 | 111.5 | 0.01 | 94.5 | 111.5 | ZMAT | 2025-01-20 | 2025-03-20
RE/0066-SCO-75-AD -01 | House Keeping Expenses | 2010 |  | 2010 | SMARTWORLD THE EDITION | Updater Services limited | 9110000355 | 580 |  |  | 2024-01-12 | SPONGE | NO | 5 | 15.75 | 78.75 | 92.93 | 78.77 | 92.95 | 0.02 | 78.75 | 92.95 | ZMAT | 2025-01-20 | 2025-03-20
RE/0066-SCO-75-AD -01 | House Keeping Expenses | 2010 |  | 2010 | SMARTWORLD THE EDITION | Updater Services limited | 9110000355 | 590 |  |  | 2024-01-12 | KITCHEN WIPER | NO | 2 | 31.5 | 63 | 74.34 | 63.05 | 74.4 | 0.05 | 63 | 74.4 | ZMAT | 2025-01-20 | 2025-03-20
RE/0066-SCO-75-AD -01 | House Keeping Expenses | 2010 |  | 2010 | SMARTWORLD THE EDITION | Updater Services limited | 9110000355 | 600 |  |  | 2024-01-12 | ODONIL 50 GMS | NO | 8 | 36.75 | 294 | 346.92 | 294.07 | 347 | 0.07 | 294 | 347 | ZMAT | 2025-01-20 | 2025-03-20
RE/0066-SCO-75-AD -01 | House Keeping Expenses | 2010 |  | 2010 | SMARTWORLD THE EDITION | Updater Services limited | 9110000355 | 610 |  |  | 2024-01-12 | GLASS CLEANING SCRAPPER | NO | 2 | 341.25 | 682.5 | 805.35 | 682.46 | 805.3 | 0.04 | 682.5 | 805.3 | ZMAT | 2025-01-20 | 2025-03-20
RE/0066-SCO-75-AD -01 | House Keeping Expenses | 2010 |  | 2010 | SMARTWORLD THE EDITION | Updater Services limited | 9110000355 | 620 |  |  | 2024-01-12 | SCOTCH BRIGHT 3M | NO | 8 | 24.15 | 193.2 | 227.98 | 193.22 | 228 | 0.02 | 193.2 | 228 | ZMAT | 2025-01-20 | 2025-03-20
RE/0066-SCO-75-AD -01 | House Keeping Expenses | 2010 |  | 2010 | SMARTWORLD THE EDITION | Updater Services limited | 9110000355 | 630 |  |  | 2024-01-12 | GLASS SCRAPER BLADE | NO | 1 | 682.5 | 682.5 | 805.35 | 682.46 | 805.3 | 0.04 | 682.5 | 805.3 | ZMAT | 2025-01-20 | 2025-03-20
RE/0066-SCO-75-AD -01 | House Keeping Expenses | 2010 |  | 2010 | SMARTWORLD THE EDITION | Updater Services limited | 9110000355 | 640 |  |  | 2024-01-12 | HARD BROOM (BIG) | NO | 8 | 47.25 | 378 | 378 | 378 | 378 | 0 | 378 | 378 | ZMAT | 2025-01-20 | 2025-03-20
RE/0066-SCO-75-AD -01 | House Keeping Expenses | 2010 |  | 2010 | SMARTWORLD THE EDITION | Updater Services limited | 9110000355 | 650 |  |  | 2024-01-12 | CARPET BRUSH | NO | 3 | 52.5 | 157.5 | 185.85 | 157.54 | 185.9 | 0.04 | 157.5 | 185.9 | ZMAT | 2025-01-20 | 2025-03-20
RE/0066-SCO-75-AD -01 | House Keeping Expenses | 2010 |  | 2010 | SMARTWORLD THE EDITION | Updater Services limited | 9110000355 | 660 |  |  | 2024-01-12 | FEM HAND WASH 5 LITS | NO | 2 | 661.5 | 1323 | 1561.14 | 1323.05 | 1561.2 | 0.05 | 1323 | 1561.2 | ZMAT | 2025-01-20 | 2025-03-20
RE/0066-SCO-75-AD -01 | House Keeping Expenses | 2010 |  | 2010 | SMARTWORLD THE EDITION | Updater Services limited | 9110000355 | 670 |  |  | 2024-01-12 | Paper Napkin ( Super) | NO | 30 | 21 | 630 | 743.4 | 630 | 743.4 | 0 | 630 | 743.4 | ZMAT | 2025-01-20 | 2025-03-20
RE/0066-SCO-75-AD -01 | House Keeping Expenses | 2010 |  | 2010 | SMARTWORLD THE EDITION | Updater Services limited | 9110000355 | 680 |  |  | 2024-01-12 | Blue Check Duster | NO | 15 | 10.5 | 157.5 | 165.38 | 157.43 | 165.3 | 0.07 | 157.5 | 165.3 | ZMAT | 2025-01-20 | 2025-03-20
RE/0066-SCO-75-AD -01 | House Keeping Expenses | 2010 |  | 2010 | SMARTWORLD THE EDITION | Updater Services limited | 9110000355 | 690 |  |  | 2024-01-12 | Red Check Duster | NO | 12 | 10.5 | 126 | 132.3 | 126.1 | 132.4 | 0.1 | 126 | 132.4 | ZMAT | 2025-01-20 | 2025-03-20
RE/0066-SCO-75-AD -01 | House Keeping Expenses | 2010 |  | 2010 | SMARTWORLD THE EDITION | Updater Services limited | 9110000355 | 700 |  |  | 2024-01-12 | WIPER LARGE | NO | 2 | 147 | 294 | 346.92 | 294.07 | 347 | 0.07 | 294 | 347 | ZMAT | 2025-01-20 | 2025-03-20
RE/0066-SCO-75-AD -01 | House Keeping Expenses | 2010 |  | 2010 | SMARTWORLD THE EDITION | Updater Services limited | 9110000355 | 710 |  |  | 2024-01-12 | SPRAY BOTTEL | NO | 6 | 52.5 | 315 | 371.7 | 315.08 | 371.8 | 0.08 | 315 | 371.8 | ZMAT | 2025-01-20 | 2025-03-20
RE/0066-SCO-75-AD -01 | House Keeping Expenses | 2010 |  | 2010 | SMARTWORLD THE EDITION | Updater Services limited | 9110000355 | 720 |  |  | 2024-01-12 | ROOM FRESHNER-PREMIUM | NO | 7 | 115.5 | 808.5 | 954.03 | 808.56 | 954.1 | 0.06 | 808.5 | 954.1 | ZMAT | 2025-01-20 | 2025-03-20
RE/0066-SCO-75-AD -01 | House Keeping Expenses | 2010 |  | 2010 | SMARTWORLD THE EDITION | Updater Services limited | 9110000355 | 730 |  |  | 2024-01-12 | FLOOR CLEANING CLOTH MEDIUM | NO | 18 | 21 | 378 | 396.9 | 378.1 | 397 | 0.1 | 378 | 397 | ZMAT | 2025-01-20 | 2025-03-20
RE/0066-SCO-75-AD -01 | House Keeping Expenses | 2010 |  | 2010 | SMARTWORLD THE EDITION | Updater Services limited | 9110000355 | 740 |  |  | 2024-01-12 | PRILL 425 ML | NO | 10 | 86.1 | 861 | 1015.98 | 861.02 | 1016 | 0.02 | 861 | 1016 | ZMAT | 2025-01-20 | 2025-03-20
RE/0066-SCO-75-AD -01 | House Keeping Expenses | 2010 |  | 2010 | SMARTWORLD THE EDITION | Updater Services limited | 9110000355 | 750 |  |  | 2024-01-12 | TASKI - R1 | NO | 10 | 233.53 | 2335.3 | 2755.65 | 2335.34 | 2755.7 | 0.04 | 2334.85 | 2755.25 | ZMAT | 2025-01-20 | 2025-03-20
RE/0066-SCO-75-AD -01 | House Keeping Expenses | 2010 |  | 2010 | SMARTWORLD THE EDITION | Updater Services limited | 9110000355 | 760 |  |  | 2024-01-12 | TASKI - R2 | NO | 10 | 202.62 | 2026.2 | 2390.92 | 2026.27 | 2391 | 0.07 | 2026.2 | 2391 | ZMAT | 2025-01-20 | 2025-03-20
RE/0066-SCO-75-AD -01 | House Keeping Expenses | 2010 |  | 2010 | SMARTWORLD THE EDITION | Updater Services limited | 9110000355 | 770 |  |  | 2024-01-12 | TASKI - R3 | NO | 5 | 269.18 | 1345.9 | 1588.16 | 1345.85 | 1588.1 | 0.05 | 1345.9 | 1588.1 | ZMAT | 2025-01-20 | 2025-03-20
RE/0066-SCO-75-AD -01 | House Keeping Expenses | 2010 |  | 2010 | SMARTWORLD THE EDITION | Updater Services limited | 9110000355 | 780 |  |  | 2024-01-12 | TASKI - R5 | NO | 5 | 204.06 | 1020.3 | 1203.95 | 1020.25 | 1203.9 | 0.05 | 1020.3 | 1203.9 | ZMAT | 2025-01-20 | 2025-03-20
RE/0066-SCO-75-AD -01 | House Keeping Expenses | 2010 |  | 2010 | SMARTWORLD THE EDITION | Updater Services limited | 9110000355 | 790 |  |  | 2024-01-12 | TASKI - R6 | NO | 10 | 145.31 | 1453.1 | 1714.66 | 1453.14 | 1714.7 | 0.04 | 1453.1 | 1714.7 | ZMAT | 2025-01-20 | 2025-03-20
RE/0066-SCO-75-AD -01 | House Keeping Expenses | 2010 |  | 2010 | SMARTWORLD THE EDITION | Updater Services limited | 9110000355 | 800 |  |  | 2024-01-12 | Taski TR 101 - Carpet Shampoo | NO | 5 | 250.51 | 1252.55 | 1478.01 | 1252.5 | 1477.95 | 0.05 | 1252.55 | 1477.95 | ZMAT | 2025-01-20 | 2025-03-20
RE/0066-SCO-75-AD -01 | House Keeping Expenses | 2010 |  | 2010 | SMARTWORLD THE EDITION | Updater Services limited | 9110000355 | 810 |  |  | 2024-01-12 | HIT SPRAY (M) block 200ML | NO | 5 | 87.15 | 435.75 | 514.19 | 435.72 | 514.15 | 0.03 | 435.75 | 514.15 | ZMAT | 2025-01-20 | 2025-03-20
RE/0066-SCO-75-AD -01 | House Keeping Expenses | 2010 |  | 2010 | SMARTWORLD THE EDITION | Updater Services limited | 9110000355 | 820 |  |  | 2024-01-12 | Urinal Cubes | NO | 1 | 23.1 | 23.1 | 27.26 | 0 | 0 | 23.1 | 0 | 0 | ZMAT | 2025-01-20 | 2025-03-20
RE/0066-SCO-75-AD -01 | House Keeping Expenses | 2010 |  | 2010 | SMARTWORLD THE EDITION | Updater Services limited | 9110000355 | 830 |  |  | 2024-01-12 | Urinal Screen Crew ( H) | NO | 8 | 144.9 | 1159.2 | 1367.86 | 1159.21 | 1367.87 | 0.01 | 1159.2 | 1367.79 | ZMAT | 2025-01-20 | 2025-03-20
RE/0066-SCO-75-AD -01 | House Keeping Expenses | 2010 |  | 2010 | SMARTWORLD THE EDITION | Updater Services limited | 9110000355 | 840 |  |  | 2024-01-12 | TOILET BRUSH | NO | 5 | 73.5 | 367.5 | 433.65 | 367.48 | 433.63 | 0.02 | 367.5 | 433.7 | ZMAT | 2025-01-20 | 2025-03-20
RE/0066-SCO-75-AD -01 | House Keeping Expenses | 2010 |  | 2010 | SMARTWORLD THE EDITION | Updater Services limited | 9110000355 | 850 |  |  | 2024-01-12 | ODONIL 75 GMS | NO | 10 | 71.4 | 714 | 842.52 | 714.01 | 842.53 | 0.01 | 714 | 842.59 | ZMAT | 2025-01-20 | 2025-03-20
RE/0066-SCO-75-AD -01 | House Keeping Expenses | 2010 |  | 2010 | SMARTWORLD THE EDITION | Updater Services limited | 9110000355 | 860 |  |  | 2024-01-12 | RUBBER GLOVES RED | NO | 5 | 54.34 | 271.7 | 320.61 | 271.72 | 320.63 | 0.02 | 271.7 | 320.7 | ZMAT | 2025-01-20 | 2025-03-20
RE/0066-SCO-75-AD -01 | House Keeping Expenses | 2010 |  | 2010 | SMARTWORLD THE EDITION | Updater Services limited | 9110000355 | 870 |  |  | 2024-01-12 | SPRAYGUN 1/2 LTR | NO | 5 | 78.75 | 393.75 | 464.63 | 393.75 | 464.62 | 0 | 393.75 | 464.55 | ZMAT | 2025-01-20 | 2025-03-20
RE/0066-SCO-75-AD -01 | House Keeping Expenses | 2010 |  | 2010 | SMARTWORLD THE EDITION | Updater Services limited | 9110000355 | 880 |  |  | 2024-01-12 | Air Freshner 300ml - Premium | NO | 5 | 144.9 | 724.5 | 854.91 | 724.49 | 854.9 | 0.01 | 724.5 | 854.89 | ZMAT | 2025-01-20 | 2025-03-20
RE/0066-SCO-75-AD -01 | House Keeping Expenses | 2010 |  | 2010 | SMARTWORLD THE EDITION | Updater Services limited | 9110000355 | 890 |  |  | 2024-01-12 | HARD BROOM (BIG) | NO | 10 | 54.34 | 543.4 | 543.4 | 543.4 | 543.4 | 0 | 543.4 | 543.4 | ZMAT | 2025-01-20 | 2025-03-20
RE/0066-SCO-75-AD -01 | House Keeping Expenses | 2010 |  | 2010 | SMARTWORLD THE EDITION | Updater Services limited | 9110000355 | 900 |  |  | 2024-01-12 | Blue Check Duster | NO | 12 | 23.1 | 277.2 | 291.06 | 277.21 | 291.07 | 0.01 | 277.2 | 291.06 | ZMAT | 2025-01-20 | 2025-03-20
RE/0066-SCO-75-AD -01 | House Keeping Expenses | 2010 |  | 2010 | SMARTWORLD THE EDITION | Updater Services limited | 9110000355 | 910 |  |  | 2024-01-12 | PLASTIC BUCKET 20 LTR | NO | 2 | 181.13 | 362.26 | 427.47 | 362.25 | 427.46 | 0.01 | 362.26 | 427.46 | ZMAT | 2025-01-20 | 2025-03-20
RE/0066-SCO-75-AD -01 | House Keeping Expenses | 2010 |  | 2010 | SMARTWORLD THE EDITION | Updater Services limited | 9110000355 | 920 |  |  | 2024-01-12 | DISPOSABLE BAG SMALL BLACK | NO | 5 | 114.71 | 573.55 | 676.79 | 573.58 | 676.82 | 0.03 | 573.55 | 676.74 | ZMAT | 2025-01-20 | 2025-03-20
RE/0066-SCO-75-AD -01 | House Keeping Expenses | 2010 |  | 2010 | SMARTWORLD THE EDITION | Updater Services limited | 9110000355 | 930 |  |  | 2024-01-12 | DISPOSABLE BAG BIG BLACK (45-50) | NO | 15 | 114.71 | 1720.65 | 2030.37 | 1720.66 | 2030.38 | 0.01 | 1720.65 | 2030.43 | ZMAT | 2025-01-20 | 2025-03-20
RE/0066-SCO-75-AD -01 | House Keeping Expenses | 2010 |  | 2010 | SMARTWORLD THE EDITION | Updater Services limited | 9110000355 | 940 |  |  | 2024-01-12 | BRASSO (500 ML) | NO | 2 | 241.5 | 483 | 569.94 | 482.99 | 569.93 | 0.01 | 483 | 569.99 | ZMAT | 2025-01-20 | 2025-03-20
RE/0066-SCO-75-AD -01 | House Keeping Expenses | 2010 |  | 2010 | SMARTWORLD THE EDITION | Updater Services limited | 9110000355 | 950 |  |  | 2024-01-12 | HIT SPRAY BLACK | NO | 5 | 181.13 | 905.65 | 1068.67 | 905.64 | 1068.65 | 0.01 | 905.65 | 1068.64 | ZMAT | 2025-01-20 | 2025-03-20
RE/0066-SCO-75-AD -01 | House Keeping Expenses | 2010 |  | 2010 | SMARTWORLD THE EDITION | Updater Services limited | 9110000355 | 960 |  |  | 2024-01-12 | SOFTBROOM BIG PIPE | NO | 3 | 108.68 | 326.04 | 326.04 | 326.04 | 326.04 | 0 | 326.04 | 326.04 | ZMAT | 2025-01-20 | 2025-03-20
RE/0066-SCO-75-AD -01 | House Keeping Expenses | 2010 |  | 2010 | SMARTWORLD THE EDITION | Updater Services limited | 9110000355 | 970 |  |  | 2024-01-12 | TASKI - R5 | NO | 5 | 236.25 | 1181.25 | 1393.88 | 1181.23 | 1393.85 | 0.02 | 1181.25 | 1393.84 | ZMAT | 2025-01-20 | 2025-03-20
RE/0066-SCO-75-AD -01 | House Keeping Expenses | 2010 |  | 2010 | SMARTWORLD THE EDITION | Updater Services limited | 9110000355 | 980 |  |  | 2024-01-12 | TASKI - R7 | NO | 5 | 131.25 | 656.25 | 774.38 | 656.25 | 774.38 | 0 | 656.25 | 774.44 | ZMAT | 2025-01-20 | 2025-03-20
RE/0066-SCO-75-AD -01 | House Keeping Expenses | 2010 |  | 2010 | SMARTWORLD THE EDITION | Updater Services limited | 9110000355 | 990 |  |  | 2024-01-12 | Taski TR 101 - Carpet Shampoo | NO | 5 | 288.75 | 1443.75 | 1703.63 | 1443.75 | 1703.62 | 0 | 1443.75 | 1703.53 | ZMAT | 2025-01-20 | 2025-03-20
RE/0066-SCO-75-AD -01 | House Keeping Expenses | 2010 |  | 2010 | SMARTWORLD THE EDITION | Updater Services limited | 9110000355 | 1000 |  |  | 2024-01-12 | HIT SPRAY (M) RED 200ML 765 | NO | 2 | 102.64 | 205.28 | 242.23 | 205.26 | 242.21 | 0.02 | 205.28 | 242.28 | ZMAT | 2025-01-20 | 2025-03-20
RE/0066-SCO-75-AD -01 | House Keeping Expenses | 2010 |  | 2010 | SMARTWORLD THE EDITION | Updater Services limited | 9110000355 | 1010 |  |  | 2024-01-12 | ALLOUT REFILL | NO | 6 | 63 | 378 | 446.04 | 378.03 | 446.07 | 0.03 | 378 | 446 | ZMAT | 2025-01-20 | 2025-03-20
RE/0066-SCO-75-AD -01 | House Keeping Expenses | 2010 |  | 2010 | SMARTWORLD THE EDITION | Updater Services limited | 9110000355 | 1020 |  |  | 2024-01-12 | TOILET ROUND BRUSH NYLON | NO | 3 | 47.25 | 141.75 | 167.27 | 141.76 | 167.28 | 0.01 | 141.75 | 167.35 | ZMAT | 2025-01-20 | 2025-03-20
RE/0066-SCO-75-AD -01 | House Keeping Expenses | 2010 |  | 2010 | SMARTWORLD THE EDITION | Updater Services limited | 9110000355 | 1030 |  |  | 2024-01-12 | HARD BROOM (BIG) | NO | 20 | 47.25 | 945 | 945 | 945 | 945 | 0 | 945 | 945 | ZMAT | 2025-01-20 | 2025-03-20
RE/0066-SCO-75-AD -01 | House Keeping Expenses | 2010 |  | 2010 | SMARTWORLD THE EDITION | Updater Services limited | 9110000355 | 1040 |  |  | 2024-01-12 | GLASS WIPER (GOOD QUALITY) | NO | 1 | 682.5 | 682.5 | 805.35 | 682.52 | 805.37 | 0.02 | 682.5 | 805.3 | ZMAT | 2025-01-20 | 2025-03-20
RE/0066-SCO-75-AD -01 | House Keeping Expenses | 2010 |  | 2010 | SMARTWORLD THE EDITION | Updater Services limited | 9110000355 | 1050 |  |  | 2024-01-12 | Toilet Pump | NO | 3 | 47.25 | 141.75 | 167.27 | 141.76 | 167.28 | 0.01 | 141.75 | 167.35 | ZMAT | 2025-01-20 | 2025-03-20
RE/0066-SCO-75-AD -01 | House Keeping Expenses | 2010 |  | 2010 | SMARTWORLD THE EDITION | Updater Services limited | 9110000355 | 1060 |  |  | 2024-01-12 | Blue Check Duster | NO | 12 | 10.5 | 126 | 132.3 | 126.03 | 132.33 | 0.03 | 126 | 132.4 | ZMAT | 2025-01-20 | 2025-03-20
RE/0066-SCO-75-AD -01 | House Keeping Expenses | 2010 |  | 2010 | SMARTWORLD THE EDITION | Updater Services limited | 9110000355 | 1070 |  |  | 2024-01-12 | ROOM FRESHNER-PREMIUM | NO | 5 | 115.5 | 577.5 | 681.45 | 577.48 | 681.43 | 0.02 | 577.5 | 681.5 | ZMAT | 2025-01-20 | 2025-03-20
RE/0066-SCO-75-AD -01 | House Keeping Expenses | 2010 |  | 2010 | SMARTWORLD THE EDITION | Updater Services limited | 9110000355 | 1080 |  |  | 2024-01-12 | AIR POCKET | NO | 4 | 47.25 | 189 | 223.02 | 188.98 | 223 | 0.02 | 189 | 223 | ZMAT | 2025-01-20 | 2025-03-20
RE/0066-SCO-75-AD -01 | House Keeping Expenses | 2010 |  | 2010 | SMARTWORLD THE EDITION | Updater Services limited | 9110000355 | 1090 |  |  | 2024-01-12 | PRILL 425 ML | NO | 5 | 86.1 | 430.5 | 507.99 | 430.48 | 507.97 | 0.02 | 430.5 | 508.1 | ZMAT | 2025-01-20 | 2025-03-20
RE/0066-SCO-75-AD -01 | House Keeping Expenses | 2010 |  | 2010 | SMARTWORLD THE EDITION | Updater Services limited | 9110000355 | 1100 |  |  | 2024-01-12 | TASKI - R3 | NO | 5 | 269.18 | 1345.9 | 1588.16 | 1345.91 | 1588.17 | 0.01 | 1345.9 | 1588.1 | ZMAT | 2025-01-20 | 2025-03-20
RE/0066-SCO-75-AD -01 | House Keeping Expenses | 2010 |  | 2010 | SMARTWORLD THE EDITION | Updater Services limited | 9110000355 | 1110 |  |  | 2024-01-12 | TASKI - R4 | NO | 5 | 422.23 | 2111.15 | 2491.16 | 2111.14 | 2491.15 | 0.01 | 2111.15 | 2491.15 | ZMAT | 2025-01-20 | 2025-03-20
RE/0066-SCO-75-AD -01 | House Keeping Expenses | 2010 |  | 2010 | SMARTWORLD THE EDITION | Updater Services limited | 9110000355 | 1120 |  |  | 2024-01-12 | TASKI - R5 | NO | 5 | 204.06 | 1020.3 | 1203.95 | 1020.34 | 1204 | 0.04 | 1020.3 | 1203.9 | ZMAT | 2025-01-20 | 2025-03-20
RE/0066-SCO-75-AD -01 | House Keeping Expenses | 2010 |  | 2010 | SMARTWORLD THE EDITION | Updater Services limited | 9110000355 | 1130 |  |  | 2024-01-12 | TASKI - R6 | NO | 5 | 145.31 | 726.55 | 857.33 | 726.57 | 857.35 | 0.02 | 726.55 | 857.35 | ZMAT | 2025-01-20 | 2025-03-20
RE/0066-SCO-75-AD -01 | House Keeping Expenses | 2010 |  | 2010 | SMARTWORLD THE EDITION | Updater Services limited | 9110000355 | 1140 |  |  | 2024-01-12 | FLOOR SCRUBBING PAD WHITE 17" INCH | NO | 1 | 383.25 | 383.25 | 452.24 | 383.26 | 452.25 | 0.01 | 383.25 | 452.25 | ZMAT | 2025-01-20 | 2025-03-20
RE/0066-SCO-75-AD -01 | House Keeping Expenses | 2010 |  | 2010 | SMARTWORLD THE EDITION | Updater Services limited | 9110000355 | 1150 |  |  | 2024-01-12 | FLOOR SCRUBBING PAD RED 17" INCH | NO | 1 | 383.25 | 383.25 | 452.24 | 383.26 | 452.25 | 0.01 | 383.25 | 452.25 | ZMAT | 2025-01-20 | 2025-03-20
RE/0066-SCO-75-AD -01 | House Keeping Expenses | 2010 |  | 2010 | SMARTWORLD THE EDITION | Updater Services limited | 9110000355 | 1160 |  |  | 2024-01-12 | YELLOW DUSTER LARGE 786 | NO | 12 | 30.19 | 362.28 | 380.39 | 362.29 | 380.4 | 0.01 | 362.3 | 380.5 | ZMAT | 2025-01-20 | 2025-03-20
RE/0066-SCO-75-AD -01 | House Keeping Expenses | 2010 |  | 2010 | SMARTWORLD THE EDITION | Updater Services limited | 9110000355 | 1170 |  |  | 2024-01-12 | Urinal Cubes ( A-1) 786 | NO | 3 | 96.6 | 289.8 | 341.96 | 289.83 | 342 | 0.03 | 290.17 | 342.37 | ZMAT | 2025-01-20 | 2025-03-20
RE/0066-SCO-75-AD -01 | House Keeping Expenses | 2010 |  | 2010 | SMARTWORLD THE EDITION | Updater Services limited | 9110000355 | 1180 |  |  | 2024-01-12 | ODONIL 50 GMS 786 | NO | 5 | 42.26 | 211.3 | 249.33 | 211.33 | 249.37 | 0.03 | 211.3 | 249.3 | ZMAT | 2025-01-20 | 2025-03-20
RE/0066-SCO-75-AD -01 | House Keeping Expenses | 2010 |  | 2010 | SMARTWORLD THE EDITION | Updater Services limited | 9110000355 | 1190 |  |  | 2024-01-12 | FEM HAND WASH 5 LITS 786 | NO | 2 | 760.73 | 1521.46 | 1795.32 | 1521.47 | 1795.34 | 0.01 | 1521.46 | 1795.26 | ZMAT | 2025-01-20 | 2025-03-20
RE/0066-SCO-75-AD -01 | House Keeping Expenses | 2010 |  | 2010 | SMARTWORLD THE EDITION | Updater Services limited | 9110000355 | 1200 |  |  | 2024-01-12 | Blue Check Duster 786 | NO | 12 | 23.1 | 277.2 | 291.06 | 277.2 | 291.06 | 0 | 277.2 | 291 | ZMAT | 2025-01-20 | 2025-03-20
RE/0066-SCO-75-AD -01 | House Keeping Expenses | 2010 |  | 2010 | SMARTWORLD THE EDITION | Updater Services limited | 9110000355 | 1210 |  |  | 2024-01-12 | Red Check Duster 786 | NO | 12 | 23.1 | 277.2 | 291.06 | 277.18 | 291.04 | 0.02 | 277.2 | 291 | ZMAT | 2025-01-20 | 2025-03-20
RE/0066-SCO-75-AD -01 | House Keeping Expenses | 2010 |  | 2010 | SMARTWORLD THE EDITION | Updater Services limited | 9110000355 | 1220 |  |  | 2024-01-12 | ROOM FRESHNER-PREMIUM VENNILA 786 | NO | 10 | 132.83 | 1328.3 | 1567.39 | 1328.31 | 1567.4 | 0.01 | 1328.3 | 1567.5 | ZMAT | 2025-01-20 | 2025-03-20
RE/0066-SCO-75-AD -01 | House Keeping Expenses | 2010 |  | 2010 | SMARTWORLD THE EDITION | Updater Services limited | 9110000355 | 1230 |  |  | 2024-01-12 | DISPOSABLE BAG BIG BLACK (45-50) 786 | NO | 20 | 114.71 | 2294.2 | 2707.16 | 2294.2 | 2707.16 | 0 | 2294.2 | 2707.2 | ZMAT | 2025-01-20 | 2025-03-20
RE/0066-SCO-75-AD -01 | House Keeping Expenses | 2010 |  | 2010 | SMARTWORLD THE EDITION | Updater Services limited | 9110000355 | 1240 |  |  | 2024-01-12 | DETTOL HAND WASH 900ml 786 | NO | 2 | 152.15 | 304.3 | 359.07 | 304.3 | 359.07 | 0 | 304.3 | 359.1 | ZMAT | 2025-01-20 | 2025-03-20
RE/0066-SCO-75-AD -01 | House Keeping Expenses | 2010 |  | 2010 | SMARTWORLD THE EDITION | Updater Services limited | 9110000355 | 1250 |  |  | 2024-01-12 | PRILL 425 ML 786 | NO | 10 | 99.02 | 990.2 | 1168.44 | 990.21 | 1168.45 | 0.01 | 990.2 | 1168.4 | ZMAT | 2025-01-20 | 2025-03-20
RE/0066-SCO-75-AD -01 | House Keeping Expenses | 2010 |  | 2010 | SMARTWORLD THE EDITION | Updater Services limited | 9110000355 | 1260 |  |  | 2024-01-12 | TASKI - R1 786 | NO | 5 | 270.9 | 1354.5 | 1598.31 | 1354.49 | 1598.3 | 0.01 | 1354.5 | 1598.3 | ZMAT | 2025-01-20 | 2025-03-20
RE/0066-SCO-75-AD -01 | House Keeping Expenses | 2010 |  | 2010 | SMARTWORLD THE EDITION | Updater Services limited | 9110000355 | 1270 |  |  | 2024-01-12 | TASKI - R5 786 | NO | 5 | 236.25 | 1181.25 | 1393.88 | 1181.26 | 1393.89 | 0.01 | 1181.25 | 1393.85 | ZMAT | 2025-01-20 | 2025-03-20
RE/0066-SCO-75-AD -01 | House Keeping Expenses | 2010 |  | 2010 | SMARTWORLD THE EDITION | Updater Services limited | 9110000355 | 1280 |  |  | 2024-01-12 | TASKI - R6 786 | NO | 5 | 168 | 840 | 991.2 | 840 | 991.2 | 0 | 840 | 991.2 | ZMAT | 2025-01-20 | 2025-03-20
RE/0066-SCO-75-AD -01 | House Keeping Expenses | 2010 |  | 2010 | SMARTWORLD THE EDITION | Updater Services limited | 9110000355 | 1290 |  |  | 2024-01-12 | AIRWICK AUTOMATIC REFILL 786 | NO | 4 | 317.57 | 1270.28 | 1498.93 | 1270.27 | 1498.92 | 0.01 | 1270.28 | 1498.88 | ZMAT | 2025-01-20 | 2025-03-20
RE/0066-SCO-75-AD -01 | House Keeping Expenses | 2010 |  | 2010 | SMARTWORLD THE EDITION | Updater Services limited | 9110000355 | 1300 |  |  | 2024-01-12 | FLOOR SCRUBBING PAD RED 17" INCH 786 | NO | 1 | 440.74 | 440.74 | 520.07 | 440.74 | 520.07 | 0 | 440.74 | 520.14 | ZMAT | 2025-01-20 | 2025-03-20
RE/0066-SCO-75-AD -01 | House Keeping Expenses | 2010 |  | 2010 | SMARTWORLD THE EDITION | Updater Services limited | 9110000355 | 1310 |  |  | 2024-01-12 | BIO URINAL SCREEN | NO | 10 | 144.9 | 1449 | 1709.82 | 0 | 0 | 1449 | 0 | 0 | ZMAT | 2025-01-20 | 2025-03-20
RE/0066-SCO-75-AD -01 | House Keeping Expenses | 2010 |  | 2010 | SMARTWORLD THE EDITION | Updater Services limited | 9110000355 | 1320 |  |  | 2024-01-12 | ALLOUT REFILL | NO | 5 | 72.45 | 362.25 | 427.46 | 0 | 0 | 362.25 | 0 | 0 | ZMAT | 2025-01-20 | 2025-03-20
RE/0066-SCO-75-AD -01 | House Keeping Expenses | 2010 |  | 2010 | SMARTWORLD THE EDITION | Updater Services limited | 9110000355 | 1330 |  |  | 2024-01-12 | BUCKET 15 LTR | NO | 2 | 181.13 | 362.26 | 427.47 | 0 | 0 | 362.26 | 0 | 0 | ZMAT | 2025-01-20 | 2025-03-20
RE/0066-SCO-75-AD -01 | House Keeping Expenses | 2010 |  | 2010 | SMARTWORLD THE EDITION | Updater Services limited | 9110000355 | 1340 |  |  | 2024-01-12 | BUCKET 5 LTR | NO | 1 | 96.6 | 96.6 | 113.99 | 0 | 0 | 96.6 | 0 | 0 | ZMAT | 2025-01-20 | 2025-03-20
RE/0066-SCO-75-AD -01 | House Keeping Expenses | 2010 |  | 2010 | SMARTWORLD THE EDITION | Updater Services limited | 9110000355 | 1350 |  |  | 2024-01-12 | DRAINEX | NO | 5 | 26.57 | 132.85 | 156.76 | 0 | 0 | 132.85 | 0 | 0 | ZMAT | 2025-01-20 | 2025-03-20
RE/0066-SCO-75-AD -01 | House Keeping Expenses | 2010 |  | 2010 | SMARTWORLD THE EDITION | Updater Services limited | 9110000355 | 1360 |  |  | 2024-01-12 | ODONIL 50 GMS | NO | 10 | 42.26 | 422.6 | 498.67 | 0 | 0 | 422.6 | 0 | 0 | ZMAT | 2025-01-20 | 2025-03-20
RE/0066-SCO-75-AD -01 | House Keeping Expenses | 2010 |  | 2010 | SMARTWORLD THE EDITION | Updater Services limited | 9110000355 | 1370 |  |  | 2024-01-12 | SCOTCH BRIGHT 3M | NO | 7 | 27.77 | 194.39 | 229.38 | 0 | 0 | 194.39 | 0 | 0 | ZMAT | 2025-01-20 | 2025-03-20
RE/0066-SCO-75-AD -01 | House Keeping Expenses | 2010 |  | 2010 | SMARTWORLD THE EDITION | Updater Services limited | 9110000355 | 1390 |  |  | 2024-01-12 | NAPTHOLIN BALLS (1 KG) | NO | 1 | 217.35 | 217.35 | 256.47 | 0 | 0 | 217.35 | 0 | 0 | ZMAT | 2025-01-20 | 2025-03-20
RE/0066-SCO-75-AD -01 | House Keeping Expenses | 2010 |  | 2010 | SMARTWORLD THE EDITION | Updater Services limited | 9110000355 | 1400 |  |  | 2024-01-12 | ROOM FRESHNER-PREMIUM VENNILA | NO | 5 | 132.83 | 664.15 | 783.7 | 0 | 0 | 664.15 | 0 | 0 | ZMAT | 2025-01-20 | 2025-03-20
RE/0066-SCO-75-AD -01 | House Keeping Expenses | 2010 |  | 2010 | SMARTWORLD THE EDITION | Updater Services limited | 9110000355 | 1410 |  |  | 2024-01-12 | AIR POCKET | NO | 5 | 60.38 | 301.9 | 356.24 | 0 | 0 | 301.9 | 0 | 0 | ZMAT | 2025-01-20 | 2025-03-20
RE/0066-SCO-75-AD -01 | House Keeping Expenses | 2010 |  | 2010 | SMARTWORLD THE EDITION | Updater Services limited | 9110000355 | 1420 |  |  | 2024-01-12 | FLOOR CLEANING CLOTH MEDIUM | NO | 10 | 35.02 | 350.2 | 367.71 | 0 | 0 | 350.2 | 0 | 0 | ZMAT | 2025-01-20 | 2025-03-20
RE/0066-SCO-75-AD -01 | House Keeping Expenses | 2010 |  | 2010 | SMARTWORLD THE EDITION | Updater Services limited | 9110000355 | 1430 |  |  | 2024-01-12 | PRILL 425 ML | NO | 10 | 99.02 | 990.2 | 1168.44 | 0 | 0 | 990.2 | 0 | 0 | ZMAT | 2025-01-20 | 2025-03-20
RE/0066-SCO-75-AD -01 | House Keeping Expenses | 2010 |  | 2010 | SMARTWORLD THE EDITION | Updater Services limited | 9110000355 | 1440 |  |  | 2024-01-12 | TASKI - R2 | NO | 10 | 236.25 | 2362.5 | 2787.75 | 0 | 0 | 2362.5 | 0 | 0 | ZMAT | 2025-01-20 | 2025-03-20
RE/0066-SCO-75-AD -01 | House Keeping Expenses | 2010 |  | 2010 | SMARTWORLD THE EDITION | Updater Services limited | 9110000355 | 1450 |  |  | 2024-01-12 | TASKI - R5 | NO | 5 | 236.25 | 1181.25 | 1393.88 | 0 | 0 | 1181.25 | 0 | 0 | ZMAT | 2025-01-20 | 2025-03-20
RE/0066-SCO-75-AD -01 | House Keeping Expenses | 2010 |  | 2010 | SMARTWORLD THE EDITION | Updater Services limited | 9110000355 | 1460 |  |  | 2024-01-12 | TASKI - R6 | NO | 5 | 168 | 840 | 991.2 | 0 | 0 | 840 | 0 | 0 | ZMAT | 2025-01-20 | 2025-03-20
RE/0066-SCO-75-AD -01 | House Keeping Expenses | 2010 |  | 2010 | SMARTWORLD THE EDITION | Updater Services limited | 9110000355 | 1470 |  |  | 2024-01-12 | TASKI - R7 | NO | 5 | 131.25 | 656.25 | 774.38 | 0 | 0 | 656.25 | 0 | 0 | ZMAT | 2025-01-20 | 2025-03-20
RE/0066-SCO-75-AD -01 | House Keeping Expenses | 2010 |  | 2010 | SMARTWORLD THE EDITION | Updater Services limited | 9110000355 | 1480 |  |  | 2024-01-12 | AIRWICK AUTOMATIC REFILL | NO | 5 | 317.57 | 1587.85 | 1873.66 | 0 | 0 | 1587.85 | 0 | 0 | ZMAT | 2025-01-20 | 2025-03-20
RE/0066-SCO-75-AD -01 | House Keeping Expenses | 2010 |  | 2010 | SMARTWORLD THE EDITION | Updater Services limited | 9110000355 | 1490 |  |  | 2024-01-12 | FLOOR SCRUBBING PAD RED 17" INCH | NO | 1 | 440.74 | 440.74 | 520.07 | 0 | 0 | 440.74 | 0 | 0 | ZMAT | 2025-01-20 | 2025-03-20
RE/0066-SCO-75-AD -01 | House Keeping Expenses | 2010 |  | 2010 | SMARTWORLD THE EDITION | Updater Services limited | 9110000355 | 1500 |  |  | 2024-01-12 | HIT SPRAY (M) RED 200ML | NO | 5 | 102.64 | 513.2 | 605.58 | 0 | 0 | 513.2 | 0 | 0 | ZMAT | 2025-01-20 | 2025-03-20
RE/0066-SCO-75-AD -01 | House Keeping Expenses | 2010 |  | 2010 | SMARTWORLD THE EDITION | Updater Services limited | 9110000355 | 1510 |  |  | 2024-01-12 | HIT SPRAY (M) BLOCK 200ML | NO | 5 | 102.64 | 513.2 | 605.58 | 0 | 0 | 513.2 | 0 | 0 | ZMAT | 2025-01-20 | 2025-03-20
RE/0066-SCO-75-AD -01 | House Keeping Expenses | 2010 |  | 2010 | SMARTWORLD THE EDITION | Updater Services limited | 9110000355 | 1520 |  |  | 2024-01-12 | BIO URINAL SCREEN | NO | 5 | 144.9 | 724.5 | 854.91 | 0 | 0 | 724.5 | 0 | 0 | ZMAT | 2025-01-20 | 2025-03-20
RE/0066-SCO-75-AD -01 | House Keeping Expenses | 2010 |  | 2010 | SMARTWORLD THE EDITION | Updater Services limited | 9110000355 | 1530 |  |  | 2024-01-12 | Urinal Cubes | NO | 3 | 84 | 252 | 297.36 | 0 | 0 | 252 | 0 | 0 | ZMAT | 2025-01-20 | 2025-03-20
RE/0066-SCO-75-AD -01 | House Keeping Expenses | 2010 |  | 2010 | SMARTWORLD THE EDITION | Updater Services limited | 9110000355 | 1540 |  |  | 2024-01-12 | FEATHER BRUSH | NO | 3 | 73.5 | 220.5 | 260.19 | 0 | 0 | 220.5 | 0 | 0 | ZMAT | 2025-01-20 | 2025-03-20
RE/0066-SCO-75-AD -01 | House Keeping Expenses | 2010 |  | 2010 | SMARTWORLD THE EDITION | Updater Services limited | 9110000355 | 1550 |  |  | 2024-01-12 | SCOTCH BRIGHT 3M | NO | 5 | 27.77 | 138.85 | 163.84 | 0 | 0 | 138.85 | 0 | 0 | ZMAT | 2025-01-20 | 2025-03-20
RE/0066-SCO-75-AD -01 | House Keeping Expenses | 2010 |  | 2010 | SMARTWORLD THE EDITION | Updater Services limited | 9110000355 | 1560 |  |  | 2024-01-12 | ROOM FRESHNER-PREMIUM VENNILA | NO | 3 | 132.83 | 398.49 | 470.22 | 0 | 0 | 398.49 | 0 | 0 | ZMAT | 2025-01-20 | 2025-03-20
RE/0066-SCO-75-AD -01 | House Keeping Expenses | 2010 |  | 2010 | SMARTWORLD THE EDITION | Updater Services limited | 9110000355 | 1580 |  |  | 2024-01-12 | TASKI - R2 | NO | 5 | 236.25 | 1181.25 | 1393.88 | 0 | 0 | 1181.25 | 0 | 0 | ZMAT | 2025-01-20 | 2025-03-20
RE/0066-SCO-75-AD -01 | House Keeping Expenses | 2010 |  | 2010 | SMARTWORLD THE EDITION | Updater Services limited | 9110000355 | 1590 |  |  | 2024-01-12 | TASKI - R5 | NO | 5 | 236.25 | 1181.25 | 1393.88 | 0 | 0 | 1181.25 | 0 | 0 | ZMAT | 2025-01-20 | 2025-03-20
RE/0066-SCO-75-AD -01 | House Keeping Expenses | 2010 |  | 2010 | SMARTWORLD THE EDITION | Updater Services limited | 9110000355 | 1600 |  |  | 2024-01-12 | TASKI - R7 | NO | 5 | 131.25 | 656.25 | 774.38 | 0 | 0 | 656.25 | 0 | 0 | ZMAT | 2025-01-20 | 2025-03-20
RE/0066-SCO-75-AD -01 | House Keeping Expenses | 2010 |  | 2010 | SMARTWORLD THE EDITION | Updater Services limited | 9110000355 | 1610 |  |  | 2024-01-12 | HIT SPRAY (M) BLACK/ 200ML | NO | 5 | 100.22 | 501.1 | 591.3 | 0 | 0 | 501.1 | 0 | 0 | ZMAT | 2025-01-20 | 2025-03-20
RE/0066-SCO-75-AD -01 | House Keeping Expenses | 2010 |  | 2010 | SMARTWORLD THE EDITION | Updater Services limited | 9110000355 | 1620 |  |  | 2024-01-12 | YELLOW DUSTER LARGE | NO | 12 | 30.19 | 362.28 | 380.39 | 362.36 | 380.48 | 0.08 | 362.74 | 380.93 | ZMAT | 2025-01-20 | 2025-03-20
RE/0066-SCO-75-AD -01 | House Keeping Expenses | 2010 |  | 2010 | SMARTWORLD THE EDITION | Updater Services limited | 9110000355 | 1630 |  |  | 2024-01-12 | SPONGE | NO | 5 | 21 | 105 | 123.9 | 105.08 | 124 | 0.08 | 105 | 123.99 | ZMAT | 2025-01-20 | 2025-03-20
RE/0066-SCO-75-AD -01 | House Keeping Expenses | 2010 |  | 2010 | SMARTWORLD THE EDITION | Updater Services limited | 9110000355 | 1640 |  |  | 2024-01-12 | Toilet Pump | NO | 3 | 54.34 | 163.02 | 192.36 | 163.07 | 192.42 | 0.05 | 163.02 | 192.41 | ZMAT | 2025-01-20 | 2025-03-20
RE/0066-SCO-75-AD -01 | House Keeping Expenses | 2010 |  | 2010 | SMARTWORLD THE EDITION | Updater Services limited | 9110000355 | 1650 |  |  | 2024-01-12 | Blue Check Duster | NO | 12 | 23.1 | 277.2 | 291.06 | 277.14 | 291 | 0.06 | 277.2 | 290.99 | ZMAT | 2025-01-20 | 2025-03-20
RE/0066-SCO-75-AD -01 | House Keeping Expenses | 2010 |  | 2010 | SMARTWORLD THE EDITION | Updater Services limited | 9110000355 | 1660 |  |  | 2024-01-12 | ROOM FRESHNER-PREMIUM VENNILA | NO | 5 | 132.83 | 664.15 | 783.7 | 664.19 | 783.75 | 0.04 | 664.15 | 783.72 | ZMAT | 2025-01-20 | 2025-03-20
RE/0066-SCO-75-AD -01 | House Keeping Expenses | 2010 |  | 2010 | SMARTWORLD THE EDITION | Updater Services limited | 9110000355 | 1670 |  |  | 2024-01-12 | PRILL 425 ML | NO | 5 | 99.02 | 495.1 | 584.22 | 495.17 | 584.3 | 0.07 | 495.1 | 584.28 | ZMAT | 2025-01-20 | 2025-03-20
RE/0066-SCO-75-AD -01 | House Keeping Expenses | 2010 |  | 2010 | SMARTWORLD THE EDITION | Updater Services limited | 9110000355 | 1680 |  |  | 2024-01-12 | TASKI - R1 | NO | 5 | 270.9 | 1354.5 | 1598.31 | 1354.49 | 1598.3 | 0.01 | 1354.5 | 1598.23 | ZMAT | 2025-01-20 | 2025-03-20
RE/0066-SCO-75-AD -01 | House Keeping Expenses | 2010 |  | 2010 | SMARTWORLD THE EDITION | Updater Services limited | 9110000355 | 1690 |  |  | 2024-01-12 | TASKI - R3 | NO | 5 | 315 | 1575 | 1858.5 | 1575.08 | 1858.6 | 0.08 | 1575 | 1858.52 | ZMAT | 2025-01-20 | 2025-03-20
RE/0066-SCO-75-AD -01 | House Keeping Expenses | 2010 |  | 2010 | SMARTWORLD THE EDITION | Updater Services limited | 9110000355 | 1700 |  |  | 2024-01-12 | TASKI - R4 | NO | 5 | 488.25 | 2441.25 | 2880.68 | 2441.23 | 2880.65 | 0.02 | 2441.25 | 2880.53 | ZMAT | 2025-01-20 | 2025-03-20
RE/0066-SCO-75-AD -01 | House Keeping Expenses | 2010 |  | 2010 | SMARTWORLD THE EDITION | Updater Services limited | 9110000355 | 1710 |  |  | 2024-01-12 | TASKI - R6 | NO | 5 | 168 | 840 | 991.2 | 840 | 991.2 | 0 | 840 | 991.16 | ZMAT | 2025-01-20 | 2025-03-20
RE/0066-SCO-75-AD -01 | House Keeping Expenses | 2010 |  | 2010 | SMARTWORLD THE EDITION | Updater Services limited | 9110000355 | 1720 |  |  | 2024-01-12 | TASKI - R7 | NO | 5 | 131.25 | 656.25 | 774.38 | 656.31 | 774.45 | 0.06 | 656.25 | 774.42 | ZMAT | 2025-01-20 | 2025-03-20
RE/0066-SCO-75-AD -01 | House Keeping Expenses | 2010 |  | 2010 | SMARTWORLD THE EDITION | Updater Services limited | 9110000355 | 1730 |  |  | 2024-01-12 | HIT SPRAY (M) RED 200ML | NO | 2 | 100.22 | 200.44 | 236.52 | 200.37 | 236.44 | 0.07 | 200.44 | 236.43 | ZMAT | 2025-01-20 | 2025-03-20
RE/0066-SCO-75-AD -01 | House Keeping Expenses | 2010 |  | 2010 | SMARTWORLD THE EDITION | Updater Services limited | 9110000355 | 1740 |  |  | 2024-01-12 | HIT SPRAY (M) BLOCK 200ML | NO | 3 | 100.22 | 300.66 | 354.78 | 300.73 | 354.86 | 0.07 | 300.66 | 354.84 | ZMAT | 2025-01-20 | 2025-03-20
RE/0066-SCO-75-AD -01 | House Keeping Expenses | 2010 |  | 2010 | SMARTWORLD THE EDITION | Updater Services limited | 9110000355 | 1750 |  |  | 2024-01-12 | HARD BROOM (BIG) | NO | 1077.099 | 100.22 | 107946.86 | 107946.86 | 0 | 0 | 107946.86 | 0 | 0 | ZMAT | 2025-01-20 | 2025-03-20
RE/0066-SCO-75-AD -01 | House Keeping Expenses | 2010 |  | 2010 | SWD Central office-75 | K MART BUSINESS SOLUTIONSSunny | 9110001012 | 390 |  |  | 2025-04-28 | (2163)Bucket (comes in 5Ltr) | NO | 2 | 55 | 110 | 129.8 | 0 | 0 | 110 | 0 | 0 | ZMAT | 2025-04-01 | 2026-03-31
RE/0066-SCO-75-AD -01 | House Keeping Expenses | 2010 |  | 2010 | SMARTWORLD THE EDITION | Ansh Carrier | 9160000583 | 10 |  |  | 2024-01-30 | Safty tank cleanin | AU | 1 | 55000 | 55000 | 64900 | 55000 | 64900 | 0 | 55000 | 64900 | ZGEN | 2025-01-20 | 2025-03-20
RE/0066-SCO-75-AD -01 | House Keeping Expenses | 2010 |  | 2010 | SMARTWORLD THE EDITION | Landscaperz IndiaVikram | 9160000623 | 10 |  |  | 2024-02-10 | Deployment of 02 No of Gardeners | AU | 1 | 32643.78 | 32643.78 | 38519.66 | 32644.92 | 38521 | 1.14 | 32643.8 | 38519.68 | ZGEN | 2024-02-15 | 2024-03-31
RE/0066-SCO-75-AD -01 | House Keeping Expenses | 2010 |  | 2010 | SWD Central office-75 | Believe Solution Services | 9160000946 | 10 |  |  | 2024-06-18 | STP(operator) 2 | AU | 1 | 73374.9 | 73374.9 | 86582.38 | 73377.86 | 86585.88 | 2.96 | 73374.99 | 86582.49 | ZGEN | 2024-02-15 | 2024-03-31
RE/0066-SCO-75-AD -01 | House Keeping Expenses | 2010 |  | 2010 | SWD Central office-75 | Believe Solution Services | 9160000946 | 10 |  |  | 2024-06-18 | STP(operator) 2 | AU | 1 | 0 | 73374.9 | 86582.38 | 73377.86 | 86585.88 | 2.96 | 73374.99 | 86582.49 | ZGEN | 2024-02-15 | 2024-03-31
RE/0066-SCO-75-AD -02 | Pantry Expenses | 2010 |  | 2010 | SMARTWORLD THE EDITION | PalbisRahul | 9110000087 | 12 |  |  | 2023-05-03 | Zeera Cookies | NO | 402 | 150 | 60300 | 71154 | 0 | 0 | 60300 | 0 | 0 | ZMAT | 2025-01-20 | 2025-03-20
RE/0066-SCO-75-AD -02 | Pantry Expenses | 2010 |  | 2010 | SMARTWORLD THE EDITION | PalbisRahul | 9110000087 | 22 |  |  | 2023-05-03 | Coconut Cookies | NO | 413 | 205 | 84665 | 99904.7 | 33825 | 39913.5 | 50840 | 33825 | 39913.5 | ZMAT | 2025-01-20 | 2025-03-20
RE/0066-SCO-75-AD -02 | Pantry Expenses | 2010 |  | 2010 | SMARTWORLD THE EDITION | PalbisRahul | 9110000087 | 32 |  |  | 2023-05-03 | Chocolate Cookies | NO | 442 | 215 | 95030 | 112135.4 | 12900 | 15222 | 82130 | 12900 | 15222 | ZMAT | 2025-01-20 | 2025-03-20
RE/0066-SCO-75-AD -02 | Pantry Expenses | 2010 |  | 2010 | SMARTWORLD THE EDITION | PalbisRahul | 9110000087 | 42 |  |  | 2023-05-03 | Butter Cookies | NO | 173.9 | 500 | 86950 | 102601 | 45000 | 53100 | 41950 | 45000 | 53100 | ZMAT | 2025-01-20 | 2025-03-20
RE/0066-SCO-75-AD -02 | Pantry Expenses | 2010 |  | 2010 | SMARTWORLD THE EDITION | PalbisRahul | 9110000087 | 52 |  |  | 2023-05-03 | Almond Cookies | NO | 217.414 | 290 | 63050.06 | 74399.07 | 47850 | 56463 | 15200.06 | 47850 | 56463 | ZMAT | 2025-01-20 | 2025-03-20
RE/0066-SCO-75-AD -02 | Pantry Expenses | 2010 |  | 2010 | SMARTWORLD THE EDITION | SMS CommercialRakesh | 9110000108 | 10 |  |  | 2023-05-17 | 750ML PET PEPSI COLA 24*40MRP | NO | 2666 | 22.86 | 60944.76 | 85322.66 | 5016.14 | 7022.6 | 55928.62 | 5485.2 | 7679.2 | ZMAT | 2025-01-20 | 2025-03-20
RE/0066-SCO-75-AD -02 | Pantry Expenses | 2010 |  | 2010 | SMARTWORLD THE EDITION | SMS CommercialRakesh | 9110000108 | 20 |  |  | 2023-05-17 | 750ML PET MIRINDA 24*40MRP | NO | 2700 | 22.86 | 61722 | 86410.8 | 2508.07 | 3511.3 | 59213.93 | 2743 | 3840.2 | ZMAT | 2025-01-20 | 2025-03-20
RE/0066-SCO-75-AD -02 | Pantry Expenses | 2010 |  | 2010 | SMARTWORLD THE EDITION | SMS CommercialRakesh | 9110000108 | 30 |  |  | 2023-05-17 | 750ML PET MOUNTAIN DEW 24*40MR | NO | 2600 | 22.86 | 59436 | 83210.4 | 2508.06 | 3511.29 | 56927.94 | 2743.2 | 3840.6 | ZMAT | 2025-01-20 | 2025-03-20
RE/0066-SCO-75-AD -02 | Pantry Expenses | 2010 |  | 2010 | SMARTWORLD THE EDITION | Luck Aqua | 9110000122 | 20 |  |  | 2023-05-23 | Drinking Water | NO | 3719 | 15 | 55785 | 62479.2 | 18134.96 | 20311.15 | 37650.04 | 18135.4 | 20312 | ZMAT | 2025-01-20 | 2025-03-20
RE/0066-SCO-75-AD -03 | Electricity Expenses | 2010 |  | 2010 |  |  |  | 0 | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
RE/0066-SCO-75-AD -04 | Office Expenses | 2010 |  | 2010 | SMARTWORLD THE EDITION | HansrajHansraj | 9110000264 | 30 |  |  | 2023-09-06 | Horticulture Water Tanker | L | 90 | 325 | 29250 | 29250 | 0 | 0 | 29250 | 0 | 0 | ZMAT | 2025-01-20 | 2025-03-20
RE/0066-SCO-75-AD -04 | Office Expenses | 2010 |  | 2010 | SMARTWORLD THE EDITION | HansrajHansraj | 9110000264 | 40 |  |  | 2023-09-06 | Washroom Water Tanker | L | 102 | 650 | 66300 | 66300 | 0 | 0 | 66300 | 0 | 0 | ZMAT | 2025-01-20 | 2025-03-20
RE/0066-SCO-75-AD -04 | Office Expenses | 2010 |  | 2010 | SMARTWORLD THE EDITION | HansrajHansraj | 9110000341 | 10 |  |  | 2024-01-03 | Horticulture Water Tanker | L | 234 | 325 | 76050 | 76050 | 21125 | 21125 | 54925 | 21125 | 21125 | ZMAT | 2025-01-20 | 2025-03-20
RE/0066-SCO-75-AD -04 | Office Expenses | 2010 |  | 2010 | SMARTWORLD THE EDITION | HansrajHansraj | 9110000341 | 20 |  |  | 2024-01-03 | Washroom Water Tanker | L | 420 | 650 | 273000 | 273000 | 239200 | 239200 | 33800 | 239200 | 239200 | ZMAT | 2025-01-20 | 2025-03-20
RE/0066-SCO-75-AD -04 | Office Expenses | 2010 |  | 2010 | SMARTWORLD THE EDITION | Max ComMayank | 9160000366 | 10 |  |  | 2023-09-08 | Walky Talky on Rent (Sep'23 to Mar'24) | AU | 1 | 5220 | 5220 | 6159.6 | 5220.34 | 6160 | 0.34 | 5219.66 | 6159.2 | ZGEN | 2023-09-01 | 2024-03-31
RE/0066-SCO-75-AD -04 | Office Expenses | 2010 |  | 2010 | SMARTWORLD THE EDITION | Dagar Power Projects Pvt. ltd. | 9160000427 | 10 |  |  | 2023-11-02 | 100 KVA DG Services | AU | 1 | 9862.06 | 9808.51 | 11574.04 | 9855.93 | 11630 | 47.42 | 9856.07 | 11630.16 | ZGEN | 2023-09-01 | 2023-09-30
RE/0066-SCO-75-AD -04 | Office Expenses | 2010 |  | 2010 | SMARTWORLD THE EDITION | Dagar Power Projects Pvt. ltd. | 9160000427 | 10 |  |  | 2023-11-02 | 100 KVA DG Services | AU | 1 | 0 | 53.55 | 56.23 | 11076.19 | 11630 | 11022.64 | 11076.34 | 11630.16 | ZGEN | 2023-09-01 | 2023-09-30
RE/0066-SCO-75-AD -04 | Office Expenses | 2010 |  | 2010 | SMARTWORLD THE EDITION | Dagar Power Projects Pvt. ltd. | 9160000427 | 20 |  |  | 2023-11-02 | 25 KVA DG Services | AU | 1 | 3761.21 | 3707.66 | 4375.04 | 3755.08 | 4431 | 47.42 | 3755.35 | 4431.31 | ZGEN | 2023-09-01 | 2023-09-30
RE/0066-SCO-75-AD -04 | Office Expenses | 2010 |  | 2010 | SMARTWORLD THE EDITION | Dagar Power Projects Pvt. ltd. | 9160000427 | 20 |  |  | 2023-11-02 | 25 KVA DG Services | AU | 1 | 0 | 53.55 | 56.23 | 4220 | 4431 | 4166.45 | 4220.3 | 4431.31 | ZGEN | 2023-09-01 | 2023-09-30
RE/0066-SCO-75-AD -04 | Office Expenses | 2010 |  | 2010 | SMARTWORLD THE EDITION | Dagar Power Projects Pvt. ltd. | 9160000427 | 30 |  |  | 2023-11-02 | 40 KVA DG Services | AU | 1 | 9024.78 | 8971.23 | 10586.05 | 9018.64 | 10642 | 47.41 | 9018.71 | 10642.08 | ZGEN | 2023-09-01 | 2023-09-30
RE/0066-SCO-75-AD -04 | Office Expenses | 2010 |  | 2010 | SMARTWORLD THE EDITION | Dagar Power Projects Pvt. ltd. | 9160000427 | 30 |  |  | 2023-11-02 | 40 KVA DG Services | AU | 1 | 0 | 53.55 | 56.23 | 10135.24 | 10642 | 10081.69 | 10135.31 | 10642.08 | ZGEN | 2023-09-01 | 2023-09-30
RE/0066-SCO-75-AD -04 | Office Expenses | 2010 |  | 2010 | SMARTWORLD THE EDITION | Dagar Power Projects Pvt. ltd. | 9160000684 | 10 |  |  | 2024-03-12 | Preventive maintenance of 100 KVA DG set | AU | 1 | 11299.36 | 53.55 | 56.23 | 12691.43 | 13326 | 12637.88 | 12691.49 | 13326.06 | ZGEN | 2024-03-02 | 2024-03-17
RE/0066-SCO-75-AD -04 | Office Expenses | 2010 |  | 2010 | SMARTWORLD THE EDITION | Dagar Power Projects Pvt. ltd. | 9160000684 | 10 |  |  | 2024-03-12 | Preventive maintenance of 100 KVA DG set | AU | 1 | 0 | 11245.81 | 13270.06 | 11293.22 | 13326 | 47.41 | 11293.27 | 13326.06 | ZGEN | 2024-03-02 | 2024-03-17
RE/0066-SCO-75-AD -04 | Office Expenses | 2010 |  | 2010 | SMARTWORLD THE EDITION | Dagar Power Projects Pvt. ltd. | 9160000685 | 10 |  |  | 2024-03-12 | Preventive maintenance of 100 KVA DG set | AU | 1 | 11299.36 | 53.55 | 56.23 | 12691.43 | 13326 | 12637.88 | 12691.49 | 13326.06 | ZGEN | 2024-03-02 | 2024-03-17
RE/0066-SCO-75-AD -04 | Office Expenses | 2010 |  | 2010 | SMARTWORLD THE EDITION | Dagar Power Projects Pvt. ltd. | 9160000685 | 10 |  |  | 2024-03-12 | Preventive maintenance of 100 KVA DG set | AU | 1 | 0 | 11245.81 | 13270.06 | 11293.22 | 13326 | 47.41 | 11293.27 | 13326.06 | ZGEN | 2024-03-02 | 2024-03-17
RE/0066-SCO-75-AD -04 | Office Expenses | 2010 |  | 2010 | SMARTWORLD THE EDITION | Dagar Power Projects Pvt. ltd. | 9160000686 | 10 |  |  | 2024-03-12 | Preventive maintenance of 25 KVA DG set | AU | 1 | 5261.21 | 53.55 | 56.23 | 5905.71 | 6201 | 5852.16 | 5906.01 | 6201.31 | ZGEN | 2024-03-03 | 2024-03-18
RE/0066-SCO-75-AD -04 | Office Expenses | 2010 |  | 2010 | SMARTWORLD THE EDITION | Dagar Power Projects Pvt. ltd. | 9160000686 | 10 |  |  | 2024-03-12 | Preventive maintenance of 25 KVA DG set | AU | 1 | 0 | 5207.66 | 6145.04 | 5255.08 | 6201 | 47.42 | 5255.35 | 6201.31 | ZGEN | 2024-03-03 | 2024-03-18
RE/0066-SCO-75-AD -05 | Power & Fuel Expenses | 2010 | GR01 | 2010 |  |  |  | 0 | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
RE/0066-SCO-75-AD -06 | Asset | 2010 | GR01 | 2010 |  |  |  | 0 | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
RE/0066-SCO-75-AD -07 | Vehicle repair & Maintenance | 2010 | GR01 | 2010 |  |  |  | 0 | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
RE/0066-SCO-75-AD -08 | Printing & Stationery Expenses | 2010 |  | 2010 | SMARTWORLD THE EDITION | Book Mark Office AutomationPreeti Shivhare | 9110000175 | 40 |  |  | 2023-06-26 | Stationery Items | NO | 5 | 505 | 2525 | 2828 | 2525.89 | 2829 | 0.89 | 2521 | 2823 | ZMAT | 2025-01-20 | 2025-03-20
RE/0066-SCO-75-AD -08 | Printing & Stationery Expenses | 2010 |  | 2010 | SMARTWORLD THE EDITION | Book Mark Office AutomationPreeti Shivhare | 9110000175 | 50 |  |  | 2023-06-26 | Plotter Paper Roll- A/1 Size (oddy) | NO | 5 | 652 | 3260 | 3651.2 | 3260.71 | 3652 | 0.71 | 3260 | 3652 | ZMAT | 2025-01-20 | 2025-03-20
RE/0066-SCO-75-AD -08 | Printing & Stationery Expenses | 2010 |  | 2010 | SMARTWORLD THE EDITION | Book Mark Office AutomationPreeti Shivhare | 9110000175 | 60 |  |  | 2023-06-26 | Index File | NO | 4 | 75 | 300 | 354 | 300 | 354 | 0 | 300 | 354 | ZMAT | 2025-01-20 | 2025-03-20
RE/0066-SCO-75-AD -08 | Printing & Stationery Expenses | 2010 |  | 2010 | SMARTWORLD THE EDITION | Book Mark Office AutomationPreeti Shivhare | 9110000175 | 70 |  |  | 2023-06-26 | Box File | NO | 2 | 110 | 220 | 259.6 | 220.34 | 260 | 0.34 | 220 | 260 | ZMAT | 2025-01-20 | 2025-03-20
RE/0066-SCO-75-AD -08 | Printing & Stationery Expenses | 2010 |  | 2010 | SMARTWORLD THE EDITION | Book Mark Office AutomationPreeti Shivhare | 9110000175 | 80 |  |  | 2023-06-26 | Note Pad | NO | 10 | 23.9 | 239 | 282.02 | 239.83 | 283 | 0.83 | 239 | 283 | ZMAT | 2025-01-20 | 2025-03-20
RE/0066-SCO-75-AD -08 | Printing & Stationery Expenses | 2010 |  | 2010 | SMARTWORLD THE EDITION | Book Mark Office AutomationPreeti Shivhare | 9110000175 | 90 |  |  | 2023-06-26 | Punching Machine | NO | 1 | 108 | 108 | 127.44 | 108.47 | 128 | 0.47 | 108 | 128 | ZMAT | 2025-01-20 | 2025-03-20
RE/0066-SCO-75-AD -08 | Printing & Stationery Expenses | 2010 |  | 2010 | SMARTWORLD THE EDITION | Book Mark Office AutomationPreeti Shivhare | 9110000175 | 100 |  |  | 2023-06-26 | Permanent Marker | NO | 2 | 13 | 26 | 30.68 | 25.42 | 30 | 0.58 | 26 | 30 | ZMAT | 2025-01-20 | 2025-03-20
RE/0066-SCO-75-AD -08 | Printing & Stationery Expenses | 2010 |  | 2010 | SMARTWORLD THE EDITION | Book Mark Office AutomationPreeti Shivhare | 9110000175 | 110 |  |  | 2023-06-26 | Highlighter | NO | 2 | 12.5 | 25 | 29.5 | 24.58 | 29 | 0.42 | 25 | 29 | ZMAT | 2025-01-20 | 2025-03-20
RE/0066-SCO-75-AD -08 | Printing & Stationery Expenses | 2010 |  | 2010 | SMARTWORLD THE EDITION | Book Mark Office AutomationPreeti Shivhare | 9110000175 | 120 |  |  | 2023-06-26 | Pencil | NO | 50 | 5 | 250 | 295 | 250.85 | 296 | 0.85 | 250 | 296 | ZMAT | 2025-01-20 | 2025-03-20
RE/0066-SCO-75-AD -08 | Printing & Stationery Expenses | 2010 |  | 2010 | SMARTWORLD THE EDITION | Book Mark Office AutomationPreeti Shivhare | 9110000175 | 130 |  |  | 2023-06-26 | Ball Pen Blue 0.45 Reynolds | NO | 20 | 6 | 120 | 141.6 | 120.34 | 142 | 0.34 | 120 | 142 | ZMAT | 2025-01-20 | 2025-03-20
RE/0066-SCO-75-AD -08 | Printing & Stationery Expenses | 2010 |  | 2010 | SMARTWORLD THE EDITION | Book Mark Office AutomationPreeti Shivhare | 9110000175 | 140 |  |  | 2023-06-26 | Ball Pen Blue 0.45 Reynolds | NO | 100 | 6 | 600 | 708 | 600 | 708 | 0 | 600 | 708 | ZMAT | 2025-01-20 | 2025-03-20
RE/0066-SCO-75-AD -08 | Printing & Stationery Expenses | 2010 |  | 2010 | SMARTWORLD THE EDITION | Book Mark Office AutomationPreeti Shivhare | 9110000175 | 150 |  |  | 2023-06-26 | Copier Paper A/3 | NO | 5 | 546 | 2730 | 3057.6 | 2730.36 | 3058 | 0.36 | 2730 | 3058 | ZMAT | 2025-01-20 | 2025-03-20
RE/0066-SCO-75-AD -08 | Printing & Stationery Expenses | 2010 |  | 2010 | SMARTWORLD THE EDITION | Book Mark Office AutomationPreeti Shivhare | 9110000175 | 160 |  |  | 2023-06-26 | Box File | NO | 100 | 110 | 11000 | 12980 | 11000 | 12980 | 0 | 11000 | 12980 | ZMAT | 2025-01-20 | 2025-03-20
RE/0066-SCO-75-AD -08 | Printing & Stationery Expenses | 2010 |  | 2010 | SMARTWORLD THE EDITION | Book Mark Office AutomationPreeti Shivhare | 9110000175 | 170 |  |  | 2023-06-26 | Dura Cell AA | NO | 50 | 33.5 | 1675 | 1976.5 | 1675.42 | 1977 | 0.42 | 1675 | 1977 | ZMAT | 2025-01-20 | 2025-03-20
RE/0066-SCO-75-AD -08 | Printing & Stationery Expenses | 2010 |  | 2010 | SMARTWORLD THE EDITION | Book Mark Office AutomationPreeti Shivhare | 9110000175 | 180 |  |  | 2023-06-26 | Permanent Marker Black | NO | 24 | 13 | 312 | 368.16 | 311.86 | 368 | 0.14 | 312 | 368 | ZMAT | 2025-01-20 | 2025-03-20
RE/0066-SCO-75-AD -08 | Printing & Stationery Expenses | 2010 |  | 2010 | SMARTWORLD THE EDITION | Book Mark Office AutomationPreeti Shivhare | 9110000175 | 190 |  |  | 2023-06-26 | CD Marker | NO | 20 | 7.5 | 150 | 177 | 150.85 | 178 | 0.85 | 150 | 178 | ZMAT | 2025-01-20 | 2025-03-20
RE/0066-SCO-75-AD -08 | Printing & Stationery Expenses | 2010 |  | 2010 | SMARTWORLD THE EDITION | Book Mark Office AutomationPreeti Shivhare | 9110000175 | 200 |  |  | 2023-06-26 | Cobra File | NO | 50 | 11 | 550 | 649 | 550.85 | 650 | 0.85 | 550 | 650 | ZMAT | 2025-01-20 | 2025-03-20
RE/0066-SCO-75-AD -08 | Printing & Stationery Expenses | 2010 |  | 2010 | SMARTWORLD THE EDITION | Book Mark Office AutomationPreeti Shivhare | 9110000175 | 210 |  |  | 2023-06-26 | Binder Clip 25 MM | NO | 10 | 32 | 320 | 377.6 | 320.34 | 378 | 0.34 | 320 | 378 | ZMAT | 2025-01-20 | 2025-03-20
RE/0066-SCO-75-AD -08 | Printing & Stationery Expenses | 2010 |  | 2010 | SMARTWORLD THE EDITION | Book Mark Office AutomationPreeti Shivhare | 9110000175 | 220 |  |  | 2023-06-26 | Inward Register | NO | 5 | 274 | 1370 | 1616.6 | 1369.49 | 1616 | 0.51 | 1370 | 1616 | ZMAT | 2025-01-20 | 2025-03-20
RE/0066-SCO-75-AD -08 | Printing & Stationery Expenses | 2010 |  | 2010 | SMARTWORLD THE EDITION | Book Mark Office AutomationPreeti Shivhare | 9110000175 | 230 |  |  | 2023-06-26 | Out Ward Register | NO | 5 | 274 | 1370 | 1616.6 | 1369.49 | 1616 | 0.51 | 1370 | 1616 | ZMAT | 2025-01-20 | 2025-03-20
RE/0066-SCO-75-AD -08 | Printing & Stationery Expenses | 2010 |  | 2010 | SMARTWORLD THE EDITION | Book Mark Office AutomationPreeti Shivhare | 9110000175 | 240 |  |  | 2023-06-26 | Button Folder | NO | 50 | 23 | 1150 | 1357 | 1150.85 | 1358 | 0.85 | 1150 | 1358 | ZMAT | 2025-01-20 | 2025-03-20
RE/0066-SCO-75-AD -08 | Printing & Stationery Expenses | 2010 |  | 2010 | SMARTWORLD THE EDITION | Book Mark Office AutomationPreeti Shivhare | 9110000175 | 250 |  |  | 2023-06-26 | L Folder | NO | 30 | 9 | 270 | 318.6 | 269.49 | 318 | 0.51 | 270 | 318 | ZMAT | 2025-01-20 | 2025-03-20
RE/0066-SCO-75-AD -08 | Printing & Stationery Expenses | 2010 |  | 2010 | SMARTWORLD THE EDITION | Book Mark Office AutomationPreeti Shivhare | 9110000175 | 260 |  |  | 2023-06-26 | Box File | NO | 48 | 110 | 5280 | 6230.4 | 5279.66 | 6230 | 0.34 | 5280 | 6230 | ZMAT | 2025-01-20 | 2025-03-20
RE/0066-SCO-75-AD -08 | Printing & Stationery Expenses | 2010 |  | 2010 | SMARTWORLD THE EDITION | Book Mark Office AutomationPreeti Shivhare | 9110000175 | 270 |  |  | 2023-06-26 | Sketch Pen | NO | 12 | 15.5 | 186 | 219.48 | 186.44 | 220 | 0.44 | 186 | 220 | ZMAT | 2025-01-20 | 2025-03-20
RE/0066-SCO-75-AD -08 | Printing & Stationery Expenses | 2010 |  | 2010 | SMARTWORLD THE EDITION | Book Mark Office AutomationPreeti Shivhare | 9110000175 | 280 |  |  | 2023-06-26 | Writing Pad A/5 | NO | 20 | 23.9 | 478 | 564.04 | 477.97 | 564 | 0.03 | 478 | 564 | ZMAT | 2025-01-20 | 2025-03-20
RE/0066-SCO-75-AD -08 | Printing & Stationery Expenses | 2010 |  | 2010 | SMARTWORLD THE EDITION | Book Mark Office AutomationPreeti Shivhare | 9110000175 | 290 |  |  | 2023-06-26 | Copier Paper A/4 | NO | 100 | 238 | 23800 | 26656 | 23800 | 26656 | 0 | 23800 | 26655.49 | ZMAT | 2025-01-20 | 2025-03-20
RE/0066-SCO-75-AD -08 | Printing & Stationery Expenses | 2010 |  | 2010 | SMARTWORLD THE EDITION | Book Mark Office AutomationPreeti Shivhare | 9110000175 | 300 |  |  | 2023-06-26 | Copier Paper A/3 | NO | 25 | 546 | 13650 | 15288 | 13650 | 15288 | 0 | 13650 | 15287.71 | ZMAT | 2025-01-20 | 2025-03-20
RE/0066-SCO-75-AD -08 | Printing & Stationery Expenses | 2010 |  | 2010 | SMARTWORLD THE EDITION | Book Mark Office AutomationPreeti Shivhare | 9110000175 | 310 |  |  | 2023-06-26 | Stationery Items | NO | 5 | 505 | 2525 | 2828 | 2525.89 | 2829 | 0.89 | 2525 | 2828.94 | ZMAT | 2025-01-20 | 2025-03-20
RE/0066-SCO-75-AD -08 | Printing & Stationery Expenses | 2010 |  | 2010 | SMARTWORLD THE EDITION | Book Mark Office AutomationPreeti Shivhare | 9110000175 | 320 |  |  | 2023-06-26 | Plotter Paper Roll- A/1 Size (oddy) | NO | 10 | 652 | 6520 | 7302.4 | 6519.64 | 7302 | 0.36 | 6520 | 7301.86 | ZMAT | 2025-01-20 | 2025-03-20
RE/0066-SCO-75-AD -08 | Printing & Stationery Expenses | 2010 |  | 2010 | SMARTWORLD THE EDITION | Book Mark Office AutomationPreeti Shivhare | 9110000175 | 330 |  |  | 2023-06-26 | Box File | NO | 100 | 110 | 11000 | 12980 | 11000 | 12980 | 0 | 11000 | 12979.32 | ZMAT | 2025-01-20 | 2025-03-20
RE/0066-SCO-75-AD -08 | Printing & Stationery Expenses | 2010 |  | 2010 | SMARTWORLD THE EDITION | Book Mark Office AutomationPreeti Shivhare | 9110000175 | 340 |  |  | 2023-06-26 | Cobra File | NO | 36 | 11 | 396 | 467.28 | 385.59 | 455 | 10.41 | 385 | 454.98 | ZMAT | 2025-01-20 | 2025-03-20
RE/0066-SCO-75-AD -08 | Printing & Stationery Expenses | 2010 |  | 2010 | SMARTWORLD THE EDITION | Book Mark Office AutomationPreeti Shivhare | 9110000175 | 350 |  |  | 2023-06-26 | L Folder | NO | 100 | 9 | 900 | 1062 | 900 | 1062 | 0 | 900 | 1061.94 | ZMAT | 2025-01-20 | 2025-03-20
RE/0066-SCO-75-AD -08 | Printing & Stationery Expenses | 2010 |  | 2010 | SMARTWORLD THE EDITION | Book Mark Office AutomationPreeti Shivhare | 9110000175 | 360 |  |  | 2023-06-26 | Button Folder | NO | 61 | 23 | 1403 | 1655.54 | 1149.63 | 1356.56 | 253.37 | 1150 | 1357.93 | ZMAT | 2025-01-20 | 2025-03-20
RE/0066-SCO-75-AD -08 | Printing & Stationery Expenses | 2010 |  | 2010 | SMARTWORLD THE EDITION | Book Mark Office AutomationPreeti Shivhare | 9110000175 | 370 |  |  | 2023-06-26 | Measurement Tape 30M | NO | 1 | 289 | 289 | 341.02 | 288.98 | 341 | 0.02 | 289 | 340.98 | ZMAT | 2025-01-20 | 2025-03-20
RE/0066-SCO-75-AD -08 | Printing & Stationery Expenses | 2010 |  | 2010 | SMARTWORLD THE EDITION | Book Mark Office AutomationPreeti Shivhare | 9110000175 | 380 |  |  | 2023-06-26 | Steel Scale 12 Inch | NO | 6 | 19 | 114 | 134.52 | 113.56 | 134 | 0.44 | 114 | 133.99 | ZMAT | 2025-01-20 | 2025-03-20
RE/0066-SCO-75-AD -08 | Printing & Stationery Expenses | 2010 |  | 2010 | SMARTWORLD THE EDITION | Book Mark Office AutomationPreeti Shivhare | 9110000175 | 390 |  |  | 2023-06-26 | Calculator | NO | 575.949 | 382 | 220012.52 | 259614.77 | 2292 | 2704.56 | 217720.52 | 2292 | 2703.86 | ZMAT | 2025-01-20 | 2025-03-20
RE/0066-SCO-75-AD -08 | Printing & Stationery Expenses | 2010 |  | 2010 | SMARTWORLD THE EDITION | Book Mark Office AutomationPreeti Shivhare | 9110000175 | 400 |  |  | 2023-06-26 | Register 192pgs | NO | 40 | 96 | 3840 | 4300.8 | 3840 | 4300.8 | 0 | 3840 | 4300.8 | ZMAT | 2025-01-20 | 2025-03-20
RE/0066-SCO-75-AD -08 | Printing & Stationery Expenses | 2010 |  | 2010 | SMARTWORLD THE EDITION | Book Mark Office AutomationPreeti Shivhare | 9110000175 | 410 |  |  | 2023-06-26 | Cello Tape 2 Inch | NO | 10 | 32 | 320 | 377.6 | 320 | 377.6 | 0 | 320 | 377.6 | ZMAT | 2025-01-20 | 2025-03-20
RE/0066-SCO-75-AD -08 | Printing & Stationery Expenses | 2010 |  | 2010 | SMARTWORLD THE EDITION | Book Mark Office AutomationPreeti Shivhare | 9110000175 | 420 |  |  | 2023-06-26 | Cello Tape 1 Inch | NO | 10 | 14 | 140 | 165.2 | 140 | 165.2 | 0 | 140 | 165.2 | ZMAT | 2025-01-20 | 2025-03-20
RE/0066-SCO-75-AD -08 | Printing & Stationery Expenses | 2010 |  | 2010 | SMARTWORLD THE EDITION | Book Mark Office AutomationPreeti Shivhare | 9110000175 | 430 |  |  | 2023-06-26 | Steel Scale 12 Inch | NO | 10 | 19 | 190 | 224.2 | 190 | 224.2 | 0 | 190 | 224.2 | ZMAT | 2025-01-20 | 2025-03-20
RE/0066-SCO-75-AD -08 | Printing & Stationery Expenses | 2010 |  | 2010 | SMARTWORLD THE EDITION | Book Mark Office AutomationPreeti Shivhare | 9110000175 | 440 |  |  | 2023-06-26 | Box File | NO | 100 | 110 | 11000 | 12980 | 11000 | 12980 | 0 | 11000 | 12980 | ZMAT | 2025-01-20 | 2025-03-20
RE/0066-SCO-75-AD -08 | Printing & Stationery Expenses | 2010 |  | 2010 | SMARTWORLD THE EDITION | Book Mark Office AutomationPreeti Shivhare | 9110000175 | 450 |  |  | 2023-06-26 | Post It Flags | NO | 10 | 30 | 300 | 354 | 300 | 354 | 0 | 300 | 354 | ZMAT | 2025-01-20 | 2025-03-20
RE/0066-SCO-75-AD -08 | Printing & Stationery Expenses | 2010 |  | 2010 | SMARTWORLD THE EDITION | Book Mark Office AutomationPreeti Shivhare | 9110000175 | 460 |  |  | 2023-06-26 | Dura Cell 9V | NO | 10 | 231.2 | 2312 | 2728.16 | 2312.03 | 2728.2 | 0.03 | 2312 | 2728.2 | ZMAT | 2025-01-20 | 2025-03-20
RE/0066-SCO-75-AD -08 | Printing & Stationery Expenses | 2010 |  | 2010 | SMARTWORLD THE EDITION | Book Mark Office AutomationPreeti Shivhare | 9110000175 | 470 |  |  | 2023-06-26 | Stapler Pin 23/17 | NO | 50 | 44 | 2200 | 2596 | 2200 | 2596 | 0 | 2200 | 2596 | ZMAT | 2025-01-20 | 2025-03-20
RE/0066-SCO-75-AD -08 | Printing & Stationery Expenses | 2010 |  | 2010 | SMARTWORLD THE EDITION | Book Mark Office AutomationPreeti Shivhare | 9110000175 | 480 |  |  | 2023-06-26 | Cello Tape 1 Inch | NO | 12 | 14 | 168 | 176.4 | 0 | 0 | 168 | 0 | 0 | ZMAT | 2025-01-20 | 2025-03-20
RE/0066-SCO-75-AD -08 | Printing & Stationery Expenses | 2010 |  | 2010 | SMARTWORLD THE EDITION | Book Mark Office AutomationPreeti Shivhare | 9110000175 | 490 |  |  | 2023-06-26 | Inward Register | NO | 2 | 274 | 548 | 575.4 | 0 | 0 | 548 | 0 | 0 | ZMAT | 2025-01-20 | 2025-03-20
RE/0066-SCO-75-AD -08 | Printing & Stationery Expenses | 2010 |  | 2010 | SMARTWORLD THE EDITION | Book Mark Office AutomationPreeti Shivhare | 9110000175 | 500 |  |  | 2023-06-26 | Brown Tape | NO | 12 | 32 | 384 | 403.2 | 0 | 0 | 384 | 0 | 0 | ZMAT | 2025-01-20 | 2025-03-20
RE/0066-SCO-75-AD -08 | Printing & Stationery Expenses | 2010 |  | 2010 | SMARTWORLD THE EDITION | Book Mark Office AutomationPreeti Shivhare | 9110000175 | 510 |  |  | 2023-06-26 | Dura Cell AA | NO | 20 | 33.5 | 670 | 703.5 | 0 | 0 | 670 | 0 | 0 | ZMAT | 2025-01-20 | 2025-03-20
RE/0066-SCO-75-AD -08 | Printing & Stationery Expenses | 2010 |  | 2010 | SMARTWORLD THE EDITION | Book Mark Office AutomationPreeti Shivhare | 9110000175 | 520 |  |  | 2023-06-26 | Dura Cell AAA | NO | 10 | 33.5 | 335 | 351.75 | 0 | 0 | 335 | 0 | 0 | ZMAT | 2025-01-20 | 2025-03-20
RE/0066-SCO-75-AD -08 | Printing & Stationery Expenses | 2010 |  | 2010 | SMARTWORLD THE EDITION | Book Mark Office AutomationPreeti Shivhare | 9110000175 | 530 |  |  | 2023-06-26 | Note Pad | NO | 200 | 23.9 | 4780 | 5019 | 0 | 0 | 4780 | 0 | 0 | ZMAT | 2025-01-20 | 2025-03-20
RE/0066-SCO-75-AD -08 | Printing & Stationery Expenses | 2010 |  | 2010 | SMARTWORLD THE EDITION | Book Mark Office AutomationPreeti Shivhare | 9110000175 | 540 |  |  | 2023-06-26 | Whitener | NO | 10 | 17.6 | 176 | 184.8 | 0 | 0 | 176 | 0 | 0 | ZMAT | 2025-01-20 | 2025-03-20
RE/0066-SCO-75-AD -08 | Printing & Stationery Expenses | 2010 |  | 2010 | SMARTWORLD THE EDITION | Book Mark Office AutomationPreeti Shivhare | 9110000175 | 550 |  |  | 2023-06-26 | White Board Duster | NO | 10 | 42 | 420 | 441 | 0 | 0 | 420 | 0 | 0 | ZMAT | 2025-01-20 | 2025-03-20
RE/0066-SCO-75-AD -08 | Printing & Stationery Expenses | 2010 |  | 2010 | SMARTWORLD THE EDITION | Book Mark Office AutomationPreeti Shivhare | 9110000175 | 560 |  |  | 2023-06-26 | CD Marker | NO | 20 | 7.5 | 150 | 157.5 | 0 | 0 | 150 | 0 | 0 | ZMAT | 2025-01-20 | 2025-03-20
RE/0066-SCO-75-AD -08 | Printing & Stationery Expenses | 2010 |  | 2010 | SMARTWORLD THE EDITION | Book Mark Office AutomationPreeti Shivhare | 9110000175 | 570 |  |  | 2023-06-26 | White Board Marker Black | NO | 20 | 18.5 | 370 | 388.5 | 0 | 0 | 370 | 0 | 0 | ZMAT | 2025-01-20 | 2025-03-20
RE/0066-SCO-75-AD -08 | Printing & Stationery Expenses | 2010 |  | 2010 | SMARTWORLD THE EDITION | Book Mark Office AutomationPreeti Shivhare | 9110000175 | 580 |  |  | 2023-06-26 | Post It Flags | NO | 12 | 30 | 360 | 424.8 | 359.32 | 424 | 0.68 | 360 | 424.8 | ZMAT | 2025-01-20 | 2025-03-20
RE/0066-SCO-75-AD -08 | Printing & Stationery Expenses | 2010 |  | 2010 | SMARTWORLD THE EDITION | Book Mark Office AutomationPreeti Shivhare | 9110000175 | 590 |  |  | 2023-06-26 | Cello Tape 2 Inch | NO | 12 | 32 | 384 | 453.12 | 384.75 | 454 | 0.75 | 384 | 453.2 | ZMAT | 2025-01-20 | 2025-03-20
RE/0066-SCO-75-AD -08 | Printing & Stationery Expenses | 2010 |  | 2010 | SMARTWORLD THE EDITION | Book Mark Office AutomationPreeti Shivhare | 9110000175 | 600 |  |  | 2023-06-26 | Envelope A3 Yellow | NO | 100 | 4.88 | 488 | 575.84 | 488.14 | 576 | 0.14 | 488 | 575.8 | ZMAT | 2025-01-20 | 2025-03-20
RE/0066-SCO-75-AD -08 | Printing & Stationery Expenses | 2010 |  | 2010 | SMARTWORLD THE EDITION | Book Mark Office AutomationPreeti Shivhare | 9110000175 | 610 |  |  | 2023-06-26 | Correction Pen | NO | 12 | 17.6 | 211.2 | 249.22 | 211.19 | 249.2 | 0.01 | 211.2 | 249.2 | ZMAT | 2025-01-20 | 2025-03-20
RE/0066-SCO-75-AD -08 | Printing & Stationery Expenses | 2010 |  | 2010 | SMARTWORLD THE EDITION | Book Mark Office AutomationPreeti Shivhare | 9110000175 | 620 |  |  | 2023-06-26 | Stationery Items | NO | 6 | 382 | 2292 | 2704.56 | 2038.98 | 2406 | 253.02 | 2292 | 2704.6 | ZMAT | 2025-01-20 | 2025-03-20
RE/0066-SCO-75-AD -08 | Printing & Stationery Expenses | 2010 |  | 2010 | SMARTWORLD THE EDITION | Book Mark Office AutomationPreeti Shivhare | 9110000175 | 630 |  |  | 2023-06-26 | Stapler Pin Big | NO | 6 | 13.9 | 83.4 | 98.41 | 84.24 | 99.4 | 0.84 | 83.4 | 98.4 | ZMAT | 2025-01-20 | 2025-03-20
RE/0066-SCO-75-AD -08 | Printing & Stationery Expenses | 2010 |  | 2010 | SMARTWORLD THE EDITION | Book Mark Office AutomationPreeti Shivhare | 9110000175 | 640 |  |  | 2023-06-26 | Enevelope 10.5 Inch X4.5 Inch | NO | 1000 | 1.1 | 1100 | 1298 | 0 | 0 | 1100 | 0 | 0 | ZMAT | 2025-01-20 | 2025-03-20
RE/0066-SCO-75-AD -08 | Printing & Stationery Expenses | 2010 |  | 2010 | SMARTWORLD THE EDITION | Book Mark Office AutomationPreeti Shivhare | 9110000175 | 650 |  |  | 2023-06-26 | Use & Through Pen | NO | 400 | 2.45 | 980 | 1156.4 | 0 | 0 | 980 | 0 | 0 | ZMAT | 2025-01-20 | 2025-03-20
RE/0066-SCO-75-AD -08 | Printing & Stationery Expenses | 2010 |  | 2010 | SMARTWORLD THE EDITION | Book Mark Office AutomationPreeti Shivhare | 9110000175 | 660 |  |  | 2023-06-26 | Envelope A4 Yellow | NO | 400 | 3.25 | 1300 | 1534 | 0 | 0 | 1300 | 0 | 0 | ZMAT | 2025-01-20 | 2025-03-20
RE/0066-SCO-75-AD -08 | Printing & Stationery Expenses | 2010 |  | 2010 | SMARTWORLD THE EDITION | Book Mark Office AutomationPreeti Shivhare | 9110000175 | 670 |  |  | 2023-06-26 | Pencil | NO | 400 | 3.3 | 1320 | 1557.6 | 0 | 0 | 1320 | 0 | 0 | ZMAT | 2025-01-20 | 2025-03-20
RE/0066-SCO-75-AD -08 | Printing & Stationery Expenses | 2010 |  | 2010 | SMARTWORLD THE EDITION | Book Mark Office AutomationPreeti Shivhare | 9110000175 | 680 |  |  | 2023-06-26 | Envelope A3 Yellow | NO | 200 | 4.88 | 976 | 1151.68 | 0 | 0 | 976 | 0 | 0 | ZMAT | 2025-01-20 | 2025-03-20
RE/0066-SCO-75-AD -08 | Printing & Stationery Expenses | 2010 |  | 2010 | SMARTWORLD THE EDITION | Book Mark Office AutomationPreeti Shivhare | 9110000175 | 690 |  |  | 2023-06-26 | Ball Pen Black | NO | 13 | 7 | 91 | 107.38 | 0 | 0 | 91 | 0 | 0 | ZMAT | 2025-01-20 | 2025-03-20
RE/0066-SCO-75-AD -08 | Printing & Stationery Expenses | 2010 |  | 2010 | SMARTWORLD THE EDITION | Book Mark Office AutomationPreeti Shivhare | 9110000175 | 700 |  |  | 2023-06-26 | CD Marker | NO | 20 | 7.5 | 150 | 177 | 0 | 0 | 150 | 0 | 0 | ZMAT | 2025-01-20 | 2025-03-20
RE/0066-SCO-75-AD -08 | Printing & Stationery Expenses | 2010 |  | 2010 | SMARTWORLD THE EDITION | Book Mark Office AutomationPreeti Shivhare | 9110000175 | 710 |  |  | 2023-06-26 | Cello Tape 1 Inch | NO | 12 | 14 | 168 | 198.24 | 0 | 0 | 168 | 0 | 0 | ZMAT | 2025-01-20 | 2025-03-20
RE/0066-SCO-75-AD -08 | Printing & Stationery Expenses | 2010 |  | 2010 | SMARTWORLD THE EDITION | Book Mark Office AutomationPreeti Shivhare | 9110000175 | 720 |  |  | 2023-06-26 | Whitener | NO | 10 | 17.6 | 176 | 207.68 | 0 | 0 | 176 | 0 | 0 | ZMAT | 2025-01-20 | 2025-03-20
RE/0066-SCO-75-AD -08 | Printing & Stationery Expenses | 2010 |  | 2010 | SMARTWORLD THE EDITION | Book Mark Office AutomationPreeti Shivhare | 9110000175 | 730 |  |  | 2023-06-26 | White Board Marker Black | NO | 20 | 18.5 | 370 | 436.6 | 0 | 0 | 370 | 0 | 0 | ZMAT | 2025-01-20 | 2025-03-20
RE/0066-SCO-75-AD -08 | Printing & Stationery Expenses | 2010 |  | 2010 | SMARTWORLD THE EDITION | Book Mark Office AutomationPreeti Shivhare | 9110000175 | 740 |  |  | 2023-06-26 | Paper Cutter | NO | 10 | 20.2 | 202 | 238.36 | 0 | 0 | 202 | 0 | 0 | ZMAT | 2025-01-20 | 2025-03-20
RE/0066-SCO-75-AD -08 | Printing & Stationery Expenses | 2010 |  | 2010 | SMARTWORLD THE EDITION | Book Mark Office AutomationPreeti Shivhare | 9110000175 | 750 |  |  | 2023-06-26 | Note Pad | NO | 200 | 23.9 | 4780 | 5640.4 | 0 | 0 | 4780 | 0 | 0 | ZMAT | 2025-01-20 | 2025-03-20
RE/0066-SCO-75-AD -08 | Printing & Stationery Expenses | 2010 |  | 2010 | SMARTWORLD THE EDITION | Book Mark Office AutomationPreeti Shivhare | 9110000175 | 760 |  |  | 2023-06-26 | Brown Tape | NO | 12 | 32 | 384 | 453.12 | 0 | 0 | 384 | 0 | 0 | ZMAT | 2025-01-20 | 2025-03-20
RE/0066-SCO-75-AD -08 | Printing & Stationery Expenses | 2010 |  | 2010 | SMARTWORLD THE EDITION | Book Mark Office AutomationPreeti Shivhare | 9110000175 | 770 |  |  | 2023-06-26 | Dura Cell AA | NO | 20 | 33.5 | 670 | 790.6 | 0 | 0 | 670 | 0 | 0 | ZMAT | 2025-01-20 | 2025-03-20
RE/0066-SCO-75-AD -08 | Printing & Stationery Expenses | 2010 |  | 2010 | SMARTWORLD THE EDITION | Book Mark Office AutomationPreeti Shivhare | 9110000175 | 780 |  |  | 2023-06-26 | Dura Cell AAA | NO | 10 | 33.5 | 335 | 395.3 | 0 | 0 | 335 | 0 | 0 | ZMAT | 2025-01-20 | 2025-03-20
RE/0066-SCO-75-AD -08 | Printing & Stationery Expenses | 2010 |  | 2010 | SMARTWORLD THE EDITION | Book Mark Office AutomationPreeti Shivhare | 9110000175 | 790 |  |  | 2023-06-26 | White Board Duster | NO | 10 | 42 | 420 | 495.6 | 0 | 0 | 420 | 0 | 0 | ZMAT | 2025-01-20 | 2025-03-20
RE/0066-SCO-75-AD -08 | Printing & Stationery Expenses | 2010 |  | 2010 | SMARTWORLD THE EDITION | Book Mark Office AutomationPreeti Shivhare | 9110000175 | 800 |  |  | 2023-06-26 | Register | NO | 20 | 274 | 5480 | 6466.4 | 0 | 0 | 5480 | 0 | 0 | ZMAT | 2025-01-20 | 2025-03-20
RE/0066-SCO-75-AD -08 | Printing & Stationery Expenses | 2010 |  | 2010 | SMARTWORLD THE EDITION | Book Mark Office AutomationPreeti Shivhare | 9110000175 | 810 |  |  | 2023-06-26 | Inward Register | NO | 2 | 274 | 548 | 646.64 | 0 | 0 | 548 | 0 | 0 | ZMAT | 2025-01-20 | 2025-03-20
RE/0066-SCO-75-AD -08 | Printing & Stationery Expenses | 2010 |  | 2010 | SMARTWORLD THE EDITION | Book Mark Office AutomationPreeti Shivhare | 9110000175 | 820 |  |  | 2023-06-26 | Plotter Paper Roll- A/1 Size (oddy) | NO | 20 | 652 | 13040 | 14604.8 | 13040 | 14604.8 | 0 | 13040.4 | 14605.2 | ZMAT | 2025-01-20 | 2025-03-20
RE/0066-SCO-75-AD -08 | Printing & Stationery Expenses | 2010 |  | 2010 | SMARTWORLD THE EDITION | Book Mark Office AutomationPreeti Shivhare | 9110000175 | 830 |  |  | 2023-06-26 | Box File | NO | 50 | 110 | 5500 | 6490 | 5500 | 6490 | 0 | 5500 | 6490.06 | ZMAT | 2025-01-20 | 2025-03-20
RE/0066-SCO-75-AD -08 | Printing & Stationery Expenses | 2010 |  | 2010 | SMARTWORLD THE EDITION | Book Mark Office AutomationPreeti Shivhare | 9110000175 | 840 |  |  | 2023-06-26 | Stapler Big | NO | 20 | 181 | 3620 | 4271.6 | 3620 | 4271.6 | 0 | 3620 | 4271.64 | ZMAT | 2025-01-20 | 2025-03-20
RE/0066-SCO-75-AD -08 | Printing & Stationery Expenses | 2010 |  | 2010 | SMARTWORLD THE EDITION | Book Mark Office AutomationPreeti Shivhare | 9110000175 | 850 |  |  | 2023-06-26 | Envelope A/3 White | NO | 200 | 4.88 | 976 | 1151.68 | 975.93 | 1151.6 | 0.07 | 976 | 1151.61 | ZMAT | 2025-01-20 | 2025-03-20
RE/0066-SCO-75-AD -08 | Printing & Stationery Expenses | 2010 |  | 2010 | SMARTWORLD THE EDITION | Book Mark Office AutomationPreeti Shivhare | 9110000175 | 860 |  |  | 2023-06-26 | Post It 3 Color | NO | 20 | 39.35 | 787 | 928.66 | 786.95 | 928.6 | 0.05 | 787 | 928.61 | ZMAT | 2025-01-20 | 2025-03-20
RE/0066-SCO-75-AD -08 | Printing & Stationery Expenses | 2010 |  | 2010 | SMARTWORLD THE EDITION | Book Mark Office AutomationPreeti Shivhare | 9110000175 | 870 |  |  | 2023-06-26 | Copier Paper A/3 | NO | 25 | 546 | 13650 | 15288 | 13650 | 15288 | 0 | 13650 | 15288 | ZMAT | 2025-01-20 | 2025-03-20
RE/0066-SCO-75-AD -08 | Printing & Stationery Expenses | 2010 |  | 2010 | SMARTWORLD THE EDITION | Book Mark Office AutomationPreeti Shivhare | 9110000175 | 880 |  |  | 2023-06-26 | Copier Paper A/4 75GSM | NO | 50 | 238 | 11900 | 13328 | 11900 | 13328 | 0 | 11900 | 13328 | ZMAT | 2025-01-20 | 2025-03-20
RE/0066-SCO-75-AD -08 | Printing & Stationery Expenses | 2010 |  | 2010 | SMARTWORLD THE EDITION | Book Mark Office AutomationPreeti Shivhare | 9110000175 | 890 |  |  | 2023-06-26 | Cello Tape 2 Inch | NO | 20 | 32 | 640 | 755.2 | 640 | 755.2 | 0 | 640 | 755.21 | ZMAT | 2025-01-20 | 2025-03-20
RE/0066-SCO-75-AD -08 | Printing & Stationery Expenses | 2010 |  | 2010 | SMARTWORLD THE EDITION | Book Mark Office AutomationPreeti Shivhare | 9110000175 | 900 |  |  | 2023-06-26 | Cello Tape 1 Inch | NO | 20 | 14 | 280 | 330.4 | 280 | 330.4 | 0 | 280 | 330.4 | ZMAT | 2025-01-20 | 2025-03-20
RE/0066-SCO-75-AD -08 | Printing & Stationery Expenses | 2010 |  | 2010 | SMARTWORLD THE EDITION | Book Mark Office AutomationPreeti Shivhare | 9110000175 | 910 |  |  | 2023-06-26 | Scissors | NO | 5 | 72.6 | 363 | 428.34 | 363.05 | 428.4 | 0.05 | 363 | 428.4 | ZMAT | 2025-01-20 | 2025-03-20
RE/0066-SCO-75-AD -08 | Printing & Stationery Expenses | 2010 |  | 2010 | SMARTWORLD THE EDITION | Book Mark Office AutomationPreeti Shivhare | 9110000175 | 920 |  |  | 2023-06-26 | Scissors Big | NO | 5 | 116 | 580 | 684.4 | 580 | 684.4 | 0 | 580 | 684.41 | ZMAT | 2025-01-20 | 2025-03-20
RE/0066-SCO-75-AD -08 | Printing & Stationery Expenses | 2010 |  | 2010 | SMARTWORLD THE EDITION | Book Mark Office AutomationPreeti Shivhare | 9110000175 | 930 |  |  | 2023-06-26 | Correction Pen | NO | 10 | 17.6 | 176 | 207.68 | 175.93 | 207.6 | 0.07 | 176 | 207.6 | ZMAT | 2025-01-20 | 2025-03-20
RE/0066-SCO-75-AD -08 | Printing & Stationery Expenses | 2010 |  | 2010 | SMARTWORLD THE EDITION | Book Mark Office AutomationPreeti Shivhare | 9110000175 | 940 |  |  | 2023-06-26 | Uniball Pen | NO | 96 | 49.1 | 4713.6 | 5562.05 | 4713.56 | 5562 | 0.04 | 4713.6 | 5562.04 | ZMAT | 2025-01-20 | 2025-03-20
RE/0066-SCO-75-AD -08 | Printing & Stationery Expenses | 2010 |  | 2010 | SMARTWORLD THE EDITION | Book Mark Office AutomationPreeti Shivhare | 9110000175 | 950 |  |  | 2023-06-26 | Dura Cell AA | NO | 40 | 33.5 | 1340 | 1581.2 | 1340 | 1581.2 | 0 | 1340 | 1581.21 | ZMAT | 2025-01-20 | 2025-03-20
RE/0066-SCO-75-AD -08 | Printing & Stationery Expenses | 2010 |  | 2010 | SMARTWORLD THE EDITION | Book Mark Office AutomationPreeti Shivhare | 9110000175 | 960 |  |  | 2023-06-26 | Dura Cell AAA | NO | 20 | 33.5 | 670 | 790.6 | 670 | 790.6 | 0 | 670 | 790.61 | ZMAT | 2025-01-20 | 2025-03-20
RE/0066-SCO-75-AD -08 | Printing & Stationery Expenses | 2010 |  | 2010 | SMARTWORLD THE EDITION | Book Mark Office AutomationPreeti Shivhare | 9110000175 | 970 |  |  | 2023-06-26 | Register 192pgs | NO | 10 | 96 | 960 | 1075.2 | 960 | 1075.2 | 0 | 960 | 1075.2 | ZMAT | 2025-01-20 | 2025-03-20
RE/0066-SCO-75-AD -08 | Printing & Stationery Expenses | 2010 |  | 2010 | SMARTWORLD THE EDITION | Book Mark Office AutomationPreeti Shivhare | 9110000175 | 980 |  |  | 2023-06-26 | Register Big | NO | 5 | 110 | 550 | 649 | 550 | 649 | 0 | 550 | 649 | ZMAT | 2025-01-20 | 2025-03-20
RE/0066-SCO-75-AD -08 | Printing & Stationery Expenses | 2010 |  | 2010 | SMARTWORLD THE EDITION | Book Mark Office AutomationPreeti Shivhare | 9110000175 | 990 |  |  | 2023-06-26 | Cello Tape 1 Inch | NO | 10 | 14 | 140 | 165.2 | 140 | 165.2 | 0 | 140 | 165.2 | ZMAT | 2025-01-20 | 2025-03-20
RE/0066-SCO-75-AD -08 | Printing & Stationery Expenses | 2010 |  | 2010 | SMARTWORLD THE EDITION | Book Mark Office AutomationPreeti Shivhare | 9110000175 | 1000 |  |  | 2023-06-26 | Permanent Marker Red | NO | 10 | 13 | 130 | 153.4 | 130 | 153.4 | 0 | 130 | 153.4 | ZMAT | 2025-01-20 | 2025-03-20
RE/0066-SCO-75-AD -08 | Printing & Stationery Expenses | 2010 |  | 2010 | SMARTWORLD THE EDITION | Book Mark Office AutomationPreeti Shivhare | 9110000175 | 1010 |  |  | 2023-06-26 | Punching Machine | NO | 10 | 108 | 1080 | 1274.4 | 1080 | 1274.4 | 0 | 1080 | 1274.4 | ZMAT | 2025-01-20 | 2025-03-20
RE/0066-SCO-75-AD -08 | Printing & Stationery Expenses | 2010 |  | 2010 | SMARTWORLD THE EDITION | Book Mark Office AutomationPreeti Shivhare | 9110000175 | 1020 |  |  | 2023-06-26 | Punching Machine Big | NO | 10 | 962 | 9620 | 11351.6 | 9620 | 11351.6 | 0 | 9620 | 11351.6 | ZMAT | 2025-01-20 | 2025-03-20
RE/0066-SCO-75-AD -08 | Printing & Stationery Expenses | 2010 |  | 2010 | SMARTWORLD THE EDITION | Book Mark Office AutomationPreeti Shivhare | 9110000175 | 1030 |  |  | 2023-06-26 | Highlighter | NO | 25 | 12.5 | 312.5 | 368.75 | 312.46 | 368.7 | 0.04 | 312.2 | 368.4 | ZMAT | 2025-01-20 | 2025-03-20
RE/0066-SCO-75-AD -08 | Printing & Stationery Expenses | 2010 |  | 2010 | SMARTWORLD THE EDITION | Book Mark Office AutomationPreeti Shivhare | 9110000175 | 1040 |  |  | 2023-06-26 | Gel Pen | NO | 20 | 9 | 180 | 212.4 | 180 | 212.4 | 0 | 180 | 212.4 | ZMAT | 2025-01-20 | 2025-03-20
RE/0066-SCO-75-AD -08 | Printing & Stationery Expenses | 2010 |  | 2010 | SMARTWORLD THE EDITION | Book Mark Office AutomationPreeti Shivhare | 9110000175 | 1050 |  |  | 2023-06-26 | Ball Pen Blue 0.45 Reynolds | NO | 20 | 6 | 120 | 141.6 | 120 | 141.6 | 0 | 120 | 141.6 | ZMAT | 2025-01-20 | 2025-03-20
RE/0066-SCO-75-AD -08 | Printing & Stationery Expenses | 2010 |  | 2010 | SMARTWORLD THE EDITION | Book Mark Office AutomationPreeti Shivhare | 9110000175 | 1060 |  |  | 2023-06-26 | Calculator | NO | 10 | 382 | 3820 | 4507.6 | 3820 | 4507.6 | 0 | 3820 | 4507.6 | ZMAT | 2025-01-20 | 2025-03-20
RE/0066-SCO-75-AD -08 | Printing & Stationery Expenses | 2010 |  | 2010 | SMARTWORLD THE EDITION | Book Mark Office AutomationPreeti Shivhare | 9110000175 | 1070 |  |  | 2023-06-26 | Yellow Envelope A/4 | NO | 50 | 3.2 | 160 | 188.8 | 160 | 188.8 | 0 | 160 | 188.8 | ZMAT | 2025-01-20 | 2025-03-20
RE/0066-SCO-75-AD -08 | Printing & Stationery Expenses | 2010 |  | 2010 | SMARTWORLD THE EDITION | Book Mark Office AutomationPreeti Shivhare | 9110000175 | 1080 |  |  | 2023-06-26 | Plotter Paper Roll- A/1 Size (oddy) | NO | 7 | 652 | 4564 | 5111.68 | 4563.93 | 5111.6 | 0.07 | 4564 | 5111.6 | ZMAT | 2025-01-20 | 2025-03-20
RE/0066-SCO-75-AD -08 | Printing & Stationery Expenses | 2010 |  | 2010 | SMARTWORLD THE EDITION | Book Mark Office AutomationPreeti Shivhare | 9110000175 | 1090 |  |  | 2023-06-26 | Plotter Paper Roll -A/0 Size | NO | 12 | 505 | 6060 | 6787.2 | 6060 | 6787.2 | 0 | 6060 | 6787.2 | ZMAT | 2025-01-20 | 2025-03-20
RE/0066-SCO-75-AD -08 | Printing & Stationery Expenses | 2010 |  | 2010 | SMARTWORLD THE EDITION | Book Mark Office AutomationPreeti Shivhare | 9110000175 | 1100 |  |  | 2023-06-26 | Box File | NO | 50 | 110 | 5500 | 6490 | 5500 | 6490 | 0 | 5500 | 6490 | ZMAT | 2025-01-20 | 2025-03-20
RE/0066-SCO-75-AD -08 | Printing & Stationery Expenses | 2010 |  | 2010 | SMARTWORLD THE EDITION | Book Mark Office AutomationPreeti Shivhare | 9110000175 | 1110 |  |  | 2023-06-26 | Visiting Card Holder Big | NO | 5 | 335 | 1675 | 1976.5 | 1675.08 | 1976.6 | 0.08 | 1675 | 1976.6 | ZMAT | 2025-01-20 | 2025-03-20
RE/0066-SCO-75-AD -08 | Printing & Stationery Expenses | 2010 |  | 2010 | SMARTWORLD THE EDITION | Book Mark Office AutomationPreeti Shivhare | 9110000175 | 1120 |  |  | 2023-06-26 | Notice Board 4*3 Inch | NO | 2 | 685 | 1370 | 1616.6 | 1370 | 1616.6 | 0 | 1370 | 1616.6 | ZMAT | 2025-01-20 | 2025-03-20
RE/0066-SCO-75-AD -08 | Printing & Stationery Expenses | 2010 |  | 2010 | SMARTWORLD THE EDITION | Book Mark Office AutomationPreeti Shivhare | 9110000175 | 1130 |  |  | 2023-06-26 | Stationery Items | NO | 100 | 110 | 11000 | 12980 | 11000 | 12980 | 0 | 11000 | 12980 | ZMAT | 2025-01-20 | 2025-03-20
RE/0066-SCO-75-AD -08 | Printing & Stationery Expenses | 2010 |  | 2010 | SMARTWORLD THE EDITION | Book Mark Office AutomationPreeti Shivhare | 9110000175 | 1140 |  |  | 2023-06-26 | Sketch Pen | NO | 6 | 15.5 | 93 | 109.74 | 93.05 | 109.8 | 0.05 | 93 | 109.8 | ZMAT | 2025-01-20 | 2025-03-20
RE/0066-SCO-75-AD -08 | Printing & Stationery Expenses | 2010 |  | 2010 | SMARTWORLD THE EDITION | Book Mark Office AutomationPreeti Shivhare | 9110000175 | 1150 |  |  | 2023-06-26 | Note Pad | NO | 50 | 39.25 | 1962.5 | 2315.75 | 1962.46 | 2315.7 | 0.04 | 1962.4 | 2315.6 | ZMAT | 2025-01-20 | 2025-03-20
RE/0066-SCO-75-AD -08 | Printing & Stationery Expenses | 2010 |  | 2010 | SMARTWORLD THE EDITION | Book Mark Office AutomationPreeti Shivhare | 9110000175 | 1160 |  |  | 2023-06-26 | Register 144pgs | NO | 20 | 79 | 1580 | 1769.6 | 1580 | 1769.6 | 0 | 1580 | 1769.59 | ZMAT | 2025-01-20 | 2025-03-20
RE/0066-SCO-75-AD -08 | Printing & Stationery Expenses | 2010 |  | 2010 | SMARTWORLD THE EDITION | Book Mark Office AutomationPreeti Shivhare | 9110000175 | 1170 |  |  | 2023-06-26 | Spiral Pad | NO | 40 | 33 | 1320 | 1557.6 | 1320 | 1557.6 | 0 | 1320 | 1557.59 | ZMAT | 2025-01-20 | 2025-03-20
RE/0066-SCO-75-AD -08 | Printing & Stationery Expenses | 2010 |  | 2010 | SMARTWORLD THE EDITION | Book Mark Office AutomationPreeti Shivhare | 9110000175 | 1180 |  |  | 2023-06-26 | Double Side Tape | NO | 20 | 21 | 420 | 495.6 | 420 | 495.6 | 0 | 420 | 495.6 | ZMAT | 2025-01-20 | 2025-03-20
RE/0066-SCO-75-AD -08 | Printing & Stationery Expenses | 2010 |  | 2010 | SMARTWORLD THE EDITION | Book Mark Office AutomationPreeti Shivhare | 9110000175 | 1190 |  |  | 2023-06-26 | Cello Tape 1 Inch | NO | 30 | 14 | 420 | 495.6 | 420 | 495.6 | 0 | 420 | 495.6 | ZMAT | 2025-01-20 | 2025-03-20
RE/0066-SCO-75-AD -08 | Printing & Stationery Expenses | 2010 |  | 2010 | SMARTWORLD THE EDITION | Book Mark Office AutomationPreeti Shivhare | 9110000175 | 1200 |  |  | 2023-06-26 | Cello Tape 2 Inch | NO | 30 | 32 | 960 | 1132.8 | 960 | 1132.8 | 0 | 960 | 1132.8 | ZMAT | 2025-01-20 | 2025-03-20
RE/0066-SCO-75-AD -08 | Printing & Stationery Expenses | 2010 |  | 2010 | SMARTWORLD THE EDITION | Book Mark Office AutomationPreeti Shivhare | 9110000175 | 1210 |  |  | 2023-06-26 | Punching Machine | NO | 5 | 108 | 540 | 637.2 | 540 | 637.2 | 0 | 540 | 637.2 | ZMAT | 2025-01-20 | 2025-03-20
RE/0066-SCO-75-AD -08 | Printing & Stationery Expenses | 2010 |  | 2010 | SMARTWORLD THE EDITION | Book Mark Office AutomationPreeti Shivhare | 9110000175 | 1220 |  |  | 2023-06-26 | Fevi Quick | NO | 10 | 8 | 80 | 94.4 | 80 | 94.4 | 0 | 80 | 94.4 | ZMAT | 2025-01-20 | 2025-03-20
RE/0066-SCO-75-AD -08 | Printing & Stationery Expenses | 2010 |  | 2010 | SMARTWORLD THE EDITION | Book Mark Office AutomationPreeti Shivhare | 9110000175 | 1230 |  |  | 2023-06-26 | Dura Cell AAA | NO | 20 | 33.5 | 670 | 790.6 | 670 | 790.6 | 0 | 670 | 790.6 | ZMAT | 2025-01-20 | 2025-03-20
RE/0066-SCO-75-AD -08 | Printing & Stationery Expenses | 2010 |  | 2010 | SMARTWORLD THE EDITION | Book Mark Office AutomationPreeti Shivhare | 9110000175 | 1240 |  |  | 2023-06-26 | Dura Cell AA | NO | 20 | 33.5 | 670 | 790.6 | 670 | 790.6 | 0 | 670 | 790.6 | ZMAT | 2025-01-20 | 2025-03-20
RE/0066-SCO-75-AD -08 | Printing & Stationery Expenses | 2010 |  | 2010 | SMARTWORLD THE EDITION | Book Mark Office AutomationPreeti Shivhare | 9110000175 | 1250 |  |  | 2023-06-26 | White Board Duster | NO | 10 | 42 | 420 | 495.6 | 420 | 495.6 | 0 | 420 | 495.6 | ZMAT | 2025-01-20 | 2025-03-20
RE/0066-SCO-75-AD -08 | Printing & Stationery Expenses | 2010 |  | 2010 | SMARTWORLD THE EDITION | Book Mark Office AutomationPreeti Shivhare | 9110000175 | 1260 |  |  | 2023-06-26 | Permanent Marker Black | NO | 30 | 13 | 390 | 460.2 | 390 | 460.2 | 0 | 390 | 460.2 | ZMAT | 2025-01-20 | 2025-03-20
RE/0066-SCO-75-AD -08 | Printing & Stationery Expenses | 2010 |  | 2010 | SMARTWORLD THE EDITION | Book Mark Office AutomationPreeti Shivhare | 9110000175 | 1270 |  |  | 2023-06-26 | Permanent Marker Red | NO | 30 | 13 | 390 | 460.2 | 390 | 460.2 | 0 | 390 | 460.2 | ZMAT | 2025-01-20 | 2025-03-20
RE/0066-SCO-75-AD -08 | Printing & Stationery Expenses | 2010 |  | 2010 | SMARTWORLD THE EDITION | Book Mark Office AutomationPreeti Shivhare | 9110000175 | 1280 |  |  | 2023-06-26 | OHP Parmanent Marker | NO | 30 | 13 | 390 | 460.2 | 390 | 460.2 | 0 | 390 | 460.2 | ZMAT | 2025-01-20 | 2025-03-20
RE/0066-SCO-75-AD -08 | Printing & Stationery Expenses | 2010 |  | 2010 | SMARTWORLD THE EDITION | Book Mark Office AutomationPreeti Shivhare | 9110000175 | 1290 |  |  | 2023-06-26 | Binder Clip 25 MM | NO | 20 | 32 | 640 | 755.2 | 640 | 755.2 | 0 | 640 | 755.2 | ZMAT | 2025-01-20 | 2025-03-20
RE/0066-SCO-75-AD -08 | Printing & Stationery Expenses | 2010 |  | 2010 | SMARTWORLD THE EDITION | Book Mark Office AutomationPreeti Shivhare | 9110000175 | 1300 |  |  | 2023-06-26 | Binder Clip 15 MM | NO | 24 | 20 | 480 | 566.4 | 480 | 566.4 | 0 | 480 | 566.4 | ZMAT | 2025-01-20 | 2025-03-20
RE/0066-SCO-75-AD -08 | Printing & Stationery Expenses | 2010 |  | 2010 | SMARTWORLD THE EDITION | Book Mark Office AutomationPreeti Shivhare | 9110000175 | 1310 |  |  | 2023-06-26 | Binder Clip 19 MM | NO | 20 | 23 | 460 | 542.8 | 460 | 542.8 | 0 | 460 | 542.8 | ZMAT | 2025-01-20 | 2025-03-20
RE/0066-SCO-75-AD -08 | Printing & Stationery Expenses | 2010 |  | 2010 | SMARTWORLD THE EDITION | Book Mark Office AutomationPreeti Shivhare | 9110000175 | 1320 |  |  | 2023-06-26 | Punching Machine | NO | 30 | 73 | 2190 | 2584.2 | 2190 | 2584.2 | 0 | 2190 | 2584.19 | ZMAT | 2025-01-20 | 2025-03-20
RE/0066-SCO-75-AD -08 | Printing & Stationery Expenses | 2010 |  | 2010 | SMARTWORLD THE EDITION | Book Mark Office AutomationPreeti Shivhare | 9110000175 | 1330 |  |  | 2023-06-26 | Punching Machine Big 1975 | NO | 30 | 108 | 3240 | 3823.2 | 3240 | 3823.2 | 0 | 3240 | 3823.18 | ZMAT | 2025-01-20 | 2025-03-20
RE/0066-SCO-75-AD -08 | Printing & Stationery Expenses | 2010 |  | 2010 | SMARTWORLD THE EDITION | Book Mark Office AutomationPreeti Shivhare | 9110000175 | 1340 |  |  | 2023-06-26 | Stapler | NO | 30 | 66 | 1980 | 2336.4 | 1980 | 2336.4 | 0 | 1980 | 2336.39 | ZMAT | 2025-01-20 | 2025-03-20
RE/0066-SCO-75-AD -08 | Printing & Stationery Expenses | 2010 |  | 2010 | SMARTWORLD THE EDITION | Book Mark Office AutomationPreeti Shivhare | 9110000175 | 1350 |  |  | 2023-06-26 | Stapler Big | NO | 30 | 181 | 5430 | 6407.4 | 5430 | 6407.4 | 0 | 5430 | 6407.37 | ZMAT | 2025-01-20 | 2025-03-20
RE/0066-SCO-75-AD -08 | Printing & Stationery Expenses | 2010 |  | 2010 | SMARTWORLD THE EDITION | Book Mark Office AutomationPreeti Shivhare | 9110000175 | 1360 |  |  | 2023-06-26 | Stapler Pin 24/6 | NO | 279 | 13.9 | 3878.1 | 4576.16 | 3878.05 | 4576.1 | 0.05 | 3878.1 | 4576.08 | ZMAT | 2025-01-20 | 2025-03-20
RE/0066-SCO-75-AD -08 | Printing & Stationery Expenses | 2010 |  | 2010 | SMARTWORLD THE EDITION | Book Mark Office AutomationPreeti Shivhare | 9110000175 | 1370 |  |  | 2023-06-26 | Pencil | NO | 20 | 33 | 660 | 778.8 | 660 | 778.8 | 0 | 660 | 778.8 | ZMAT | 2025-01-20 | 2025-03-20
RE/0066-SCO-75-AD -08 | Printing & Stationery Expenses | 2010 |  | 2010 | SMARTWORLD THE EDITION | Book Mark Office AutomationPreeti Shivhare | 9110000175 | 1380 |  |  | 2023-06-26 | Stapler Pin 23/17 | NO | 7 | 44 | 308 | 363.44 | 307.97 | 363.4 | 0.03 | 308 | 363.4 | ZMAT | 2025-01-20 | 2025-03-20
RE/0066-SCO-75-AD -08 | Printing & Stationery Expenses | 2010 |  | 2010 | SMARTWORLD THE EDITION | Book Mark Office AutomationPreeti Shivhare | 9110000175 | 1390 |  |  | 2023-06-26 | Correction Pen | NO | 30 | 17.6 | 528 | 623.04 | 527.97 | 623 | 0.03 | 528 | 623 | ZMAT | 2025-01-20 | 2025-03-20
RE/0066-SCO-75-AD -08 | Printing & Stationery Expenses | 2010 |  | 2010 | SMARTWORLD THE EDITION | Book Mark Office AutomationPreeti Shivhare | 9110000175 | 1400 |  |  | 2023-06-26 | Scissors | NO | 24 | 72.6 | 1742.4 | 2056.03 | 1742.37 | 2056 | 0.03 | 1742.4 | 2055.99 | ZMAT | 2025-01-20 | 2025-03-20
RE/0066-SCO-75-AD -08 | Printing & Stationery Expenses | 2010 |  | 2010 | SMARTWORLD THE EDITION | Book Mark Office AutomationPreeti Shivhare | 9110000175 | 1410 |  |  | 2023-06-26 | Paper Cutter | NO | 20 | 20.2 | 404 | 476.72 | 404.07 | 476.8 | 0.07 | 404 | 476.8 | ZMAT | 2025-01-20 | 2025-03-20
RE/0066-SCO-75-AD -08 | Printing & Stationery Expenses | 2010 |  | 2010 | SMARTWORLD THE EDITION | Book Mark Office AutomationPreeti Shivhare | 9110000175 | 1420 |  |  | 2023-06-26 | Highlighter | NO | 150 | 12.5 | 1875 | 2212.5 | 1875.08 | 2212.6 | 0.08 | 1875 | 2212.59 | ZMAT | 2025-01-20 | 2025-03-20
RE/0066-SCO-75-AD -08 | Printing & Stationery Expenses | 2010 |  | 2010 | SMARTWORLD THE EDITION | Book Mark Office AutomationPreeti Shivhare | 9110000175 | 1430 |  |  | 2023-06-26 | Sketch Pen | NO | 30 | 15.5 | 465 | 548.7 | 465.08 | 548.8 | 0.08 | 465 | 548.8 | ZMAT | 2025-01-20 | 2025-03-20
RE/0066-SCO-75-AD -08 | Printing & Stationery Expenses | 2010 |  | 2010 | SMARTWORLD THE EDITION | Book Mark Office AutomationPreeti Shivhare | 9110000175 | 1440 |  |  | 2023-06-26 | Sticky Notes3M | NO | 30 | 22.5 | 675 | 796.5 | 675.08 | 796.6 | 0.08 | 675 | 796.6 | ZMAT | 2025-01-20 | 2025-03-20
RE/0066-SCO-75-AD -08 | Printing & Stationery Expenses | 2010 |  | 2010 | SMARTWORLD THE EDITION | Book Mark Office AutomationPreeti Shivhare | 9110000175 | 1450 |  |  | 2023-06-26 | Steel Scale | NO | 25 | 19 | 475 | 560.5 | 475.08 | 560.6 | 0.08 | 475 | 560.6 | ZMAT | 2025-01-20 | 2025-03-20
RE/0066-SCO-75-AD -08 | Printing & Stationery Expenses | 2010 |  | 2010 | SMARTWORLD THE EDITION | Book Mark Office AutomationPreeti Shivhare | 9110000175 | 1460 |  |  | 2023-06-26 | Ball Pen Blue 0.45 Reynolds | NO | 30 | 6 | 180 | 212.4 | 180 | 212.4 | 0 | 180 | 212.4 | ZMAT | 2025-01-20 | 2025-03-20
RE/0066-SCO-75-AD -08 | Printing & Stationery Expenses | 2010 |  | 2010 | SMARTWORLD THE EDITION | Book Mark Office AutomationPreeti Shivhare | 9110000175 | 1470 |  |  | 2023-06-26 | Gel Pen Blue | NO | 50 | 9 | 450 | 531 | 450 | 531 | 0 | 450 | 531 | ZMAT | 2025-01-20 | 2025-03-20
RE/0066-SCO-75-AD -08 | Printing & Stationery Expenses | 2010 |  | 2010 | SMARTWORLD THE EDITION | Book Mark Office AutomationPreeti Shivhare | 9110000175 | 1480 |  |  | 2023-06-26 | CELLO FINEGRIP BALLPEN BLACK | NO | 30 | 7 | 210 | 247.8 | 210 | 247.8 | 0 | 210 | 247.8 | ZMAT | 2025-01-20 | 2025-03-20
RE/0066-SCO-75-AD -08 | Printing & Stationery Expenses | 2010 |  | 2010 | SMARTWORLD THE EDITION | Book Mark Office AutomationPreeti Shivhare | 9110000175 | 1490 |  |  | 2023-06-26 | Calculator | NO | 20 | 382 | 7640 | 9015.2 | 7640 | 9015.2 | 0 | 7640 | 9015.16 | ZMAT | 2025-01-20 | 2025-03-20
RE/0066-SCO-75-AD -08 | Printing & Stationery Expenses | 2010 |  | 2010 | SMARTWORLD THE EDITION | Book Mark Office AutomationPreeti Shivhare | 9110000175 | 1500 |  |  | 2023-06-26 | Envelope A4 Yellow | NO | 150 | 3.25 | 487.5 | 575.25 | 487.54 | 575.3 | 0.04 | 487.5 | 575.3 | ZMAT | 2025-01-20 | 2025-03-20
RE/0066-SCO-75-AD -08 | Printing & Stationery Expenses | 2010 |  | 2010 | SMARTWORLD THE EDITION | Book Mark Office AutomationPreeti Shivhare | 9110000175 | 1510 |  |  | 2023-06-26 | Envelope A3 Yellow | NO | 150 | 4.88 | 732 | 863.76 | 732.03 | 863.8 | 0.03 | 732 | 863.8 | ZMAT | 2025-01-20 | 2025-03-20
RE/0066-SCO-75-AD -08 | Printing & Stationery Expenses | 2010 |  | 2010 | SMARTWORLD THE EDITION | Book Mark Office AutomationPreeti Shivhare | 9110000175 | 1520 |  |  | 2023-06-26 | L Folder | NO | 100 | 9 | 900 | 1062 | 900 | 1062 | 0 | 900 | 1061.99 | ZMAT | 2025-01-20 | 2025-03-20
RE/0066-SCO-75-AD -08 | Printing & Stationery Expenses | 2010 |  | 2010 | SMARTWORLD THE EDITION | Book Mark Office AutomationPreeti Shivhare | 9110000175 | 1530 |  |  | 2023-06-26 | Button Folder | NO | 90 | 23 | 2070 | 2442.6 | 2070 | 2442.6 | 0 | 2070 | 2442.59 | ZMAT | 2025-01-20 | 2025-03-20
RE/0066-SCO-75-AD -08 | Printing & Stationery Expenses | 2010 |  | 2010 | SMARTWORLD THE EDITION | Book Mark Office AutomationPreeti Shivhare | 9110000175 | 1540 |  |  | 2023-06-26 | Cobra File | NO | 100 | 11 | 1100 | 1298 | 1100 | 1298 | 0 | 1100 | 1297.99 | ZMAT | 2025-01-20 | 2025-03-20
RE/0066-SCO-75-AD -08 | Printing & Stationery Expenses | 2010 |  | 2010 | SMARTWORLD THE EDITION | Book Mark Office AutomationPreeti Shivhare | 9110000175 | 1550 |  |  | 2023-06-26 | Copier Paper A/4 75GSM | NO | 60 | 238 | 14280 | 15993.6 | 14280 | 15993.6 | 0 | 14280 | 15993.53 | ZMAT | 2025-01-20 | 2025-03-20
RE/0066-SCO-75-AD -08 | Printing & Stationery Expenses | 2010 |  | 2010 | SMARTWORLD THE EDITION | Book Mark Office AutomationPreeti Shivhare | 9110000175 | 1560 |  |  | 2023-06-26 | Copier Paper A/3 | NO | 5 | 546 | 2730 | 3057.6 | 2730 | 3057.6 | 0 | 2730 | 3057.59 | ZMAT | 2025-01-20 | 2025-03-20
RE/0066-SCO-75-AD -08 | Printing & Stationery Expenses | 2010 |  | 2010 | SMARTWORLD THE EDITION | Book Mark Office AutomationPreeti Shivhare | 9110000175 | 1570 |  |  | 2023-06-26 | Plotter Paper Roll- A/1 Size (oddy) | NO | 40 | 652 | 26080 | 29209.6 | 26080 | 29209.6 | 0 | 26080 | 29209.46 | ZMAT | 2025-01-20 | 2025-03-20
RE/0066-SCO-75-AD -08 | Printing & Stationery Expenses | 2010 |  | 2010 | SMARTWORLD THE EDITION | Book Mark Office AutomationPreeti Shivhare | 9110000175 | 1580 |  |  | 2023-06-26 | Plotter Paper Roll -A/0 Size | NO | 30 | 505 | 15150 | 16968 | 15150 | 16968 | 0 | 15150 | 16967.92 | ZMAT | 2025-01-20 | 2025-03-20
RE/0066-SCO-75-AD -08 | Printing & Stationery Expenses | 2010 |  | 2010 | SMARTWORLD THE EDITION | Book Mark Office AutomationPreeti Shivhare | 9110000175 | 1590 |  |  | 2023-06-26 | Box File | NO | 100 | 110 | 11000 | 12980 | 11000 | 12980 | 0 | 11000 | 12979.94 | ZMAT | 2025-01-20 | 2025-03-20
RE/0066-SCO-75-AD -08 | Printing & Stationery Expenses | 2010 |  | 2010 | SMARTWORLD THE EDITION | Book Mark Office AutomationPreeti Shivhare | 9110000175 | 1600 |  |  | 2023-06-26 | Uniball Pen | NO | 50 | 49.1 | 2455 | 2896.9 | 2455.08 | 2897 | 0.08 | 2455 | 2896.99 | ZMAT | 2025-01-20 | 2025-03-20
RE/0066-SCO-75-AD -08 | Printing & Stationery Expenses | 2010 |  | 2010 | SMARTWORLD THE EDITION | Book Mark Office AutomationPreeti Shivhare | 9110000175 | 1610 |  |  | 2023-06-26 | Visiting Card Holder Big | NO | 5 | 335 | 1675 | 1976.5 | 1675.08 | 1976.6 | 0.08 | 1675 | 1976.59 | ZMAT | 2025-01-20 | 2025-03-20
RE/0066-SCO-75-AD -08 | Printing & Stationery Expenses | 2010 |  | 2010 | SMARTWORLD THE EDITION | Book Mark Office AutomationPreeti Shivhare | 9110000175 | 1620 |  |  | 2023-06-26 | Register Big | NO | 15 | 110 | 1650 | 1947 | 1650 | 1947 | 0 | 1650 | 1946.99 | ZMAT | 2025-01-20 | 2025-03-20
RE/0066-SCO-75-AD -08 | Printing & Stationery Expenses | 2010 |  | 2010 | SMARTWORLD THE EDITION | Book Mark Office AutomationPreeti Shivhare | 9110000175 | 1630 |  |  | 2023-06-26 | Dura Cell 9V | NO | 20 | 231.2 | 4624 | 5456.32 | 4624.07 | 5456.4 | 0.07 | 4624 | 5456.37 | ZMAT | 2025-01-20 | 2025-03-20
RE/0066-SCO-75-AD -08 | Printing & Stationery Expenses | 2010 |  | 2010 | SMARTWORLD THE EDITION | Book Mark Office AutomationPreeti Shivhare | 9110000175 | 1640 |  |  | 2023-06-26 | Register 192pgs | NO | 25 | 96 | 2400 | 2688 | 2400 | 2688 | 0 | 2400 | 2687.99 | ZMAT | 2025-01-20 | 2025-03-20
RE/0066-SCO-75-AD -08 | Printing & Stationery Expenses | 2010 |  | 2010 | SMARTWORLD THE EDITION | Book Mark Office AutomationPreeti Shivhare | 9110000175 | 1650 |  |  | 2023-06-26 | Pencil | NO | 100 | 5 | 500 | 590 | 500 | 590 | 0 | 500 | 590 | ZMAT | 2025-01-20 | 2025-03-20
RE/0066-SCO-75-AD -08 | Printing & Stationery Expenses | 2010 |  | 2010 | SMARTWORLD THE EDITION | Book Mark Office AutomationPreeti Shivhare | 9110000175 | 1660 |  |  | 2023-06-26 | GEL PEN BLACK | NO | 50 | 9 | 450 | 531 | 450 | 531 | 0 | 450 | 531 | ZMAT | 2025-01-20 | 2025-03-20
RE/0066-SCO-75-AD -08 | Printing & Stationery Expenses | 2010 |  | 2010 | SMARTWORLD THE EDITION | Book Mark Office AutomationPreeti Shivhare | 9110000175 | 1670 |  |  | 2023-06-26 | GEL PEN RED | NO | 50 | 9 | 450 | 531 | 450 | 531 | 0 | 450 | 531 | ZMAT | 2025-01-20 | 2025-03-20
RE/0066-SCO-75-AD -08 | Printing & Stationery Expenses | 2010 |  | 2010 | SMARTWORLD THE EDITION | Book Mark Office AutomationPreeti Shivhare | 9110000175 | 1680 |  |  | 2023-06-26 | Racer Gel Pen Reynold | NO | 60 | 9 | 540 | 637.2 | 540 | 637.2 | 0 | 540 | 637.2 | ZMAT | 2025-01-20 | 2025-03-20
RE/0066-SCO-75-AD -08 | Printing & Stationery Expenses | 2010 |  | 2010 | SMARTWORLD THE EDITION | Book Mark Office AutomationPreeti Shivhare | 9110000175 | 1690 |  |  | 2023-06-26 | Uniball Pen | NO | 180 | 49.1 | 8838 | 10428.84 | 8837.97 | 10428.8 | 0.03 | 8838 | 10428.74 | ZMAT | 2025-01-20 | 2025-03-20
RE/0066-SCO-75-AD -08 | Printing & Stationery Expenses | 2010 |  | 2010 | SMARTWORLD THE EDITION | Book Mark Office AutomationPreeti Shivhare | 9110000175 | 1700 |  |  | 2023-06-26 | Visiting Card Holder Big | NO | 10 | 335 | 3350 | 3953 | 3350 | 3953 | 0 | 3350 | 3952.98 | ZMAT | 2025-01-20 | 2025-03-20
RE/0066-SCO-75-AD -08 | Printing & Stationery Expenses | 2010 |  | 2010 | SMARTWORLD THE EDITION | Book Mark Office AutomationPreeti Shivhare | 9110000175 | 1710 |  |  | 2023-06-26 | Brown Tape 2 Inch | NO | 30 | 32 | 960 | 1132.8 | 960 | 1132.8 | 0 | 960 | 1132.79 | ZMAT | 2025-01-20 | 2025-03-20
RE/0066-SCO-75-AD -08 | Printing & Stationery Expenses | 2010 |  | 2010 | SMARTWORLD THE EDITION | Book Mark Office AutomationPreeti Shivhare | 9110000175 | 1720 |  |  | 2023-06-26 | Stapler Pin 23/17 | NO | 13 | 44 | 572 | 674.96 | 572.03 | 675 | 0.03 | 572 | 675 | ZMAT | 2025-01-20 | 2025-03-20
RE/0066-SCO-75-AD -08 | Printing & Stationery Expenses | 2010 |  | 2010 | SMARTWORLD THE EDITION | Book Mark Office AutomationPreeti Shivhare | 9110000175 | 1730 |  |  | 2023-06-26 | Button Folder | NO | 10 | 23 | 230 | 271.4 | 230 | 271.4 | 0 | 230 | 271.4 | ZMAT | 2025-01-20 | 2025-03-20
RE/0066-SCO-75-AD -08 | Printing & Stationery Expenses | 2010 |  | 2010 | SMARTWORLD THE EDITION | Book Mark Office AutomationPreeti Shivhare | 9110000175 | 1740 |  |  | 2023-06-26 | Copier Paper A/3 | NO | 25 | 546 | 13650 | 15288 | 13650 | 15288 | 0 | 13650 | 15287.92 | ZMAT | 2025-01-20 | 2025-03-20
RE/0066-SCO-75-AD -08 | Printing & Stationery Expenses | 2010 |  | 2010 | SMARTWORLD THE EDITION | Book Mark Office AutomationPreeti Shivhare | 9110000175 | 1750 |  |  | 2023-06-26 | L Folder | NO | 10 | 9 | 90 | 106.2 | 90 | 106.2 | 0 | 90 | 106.2 | ZMAT | 2025-01-20 | 2025-03-20
RE/0066-SCO-75-AD -09 | Repair & Maintenance Expenses | 2010 | GR01 | 2010 | SWD Central office-75 | Haarish Electric vehicles | 9140000372 | 10 |  |  | 2024-10-24 | Cleaning of Joints and application of Mu | AU | 1 | 72110 | 72110 | 85089.8 | 0 | 0 | 72110 | 0 | 0 | ZSER | 2024-10-24 | 2024-11-08
RE/0066-SCO-75-AD -10 | Travel Expenses | 2010 |  | 2010 | SMARTWORLD THE EDITION | Tecknomen Facility Services Pvt. LtDwarka | 9160000471 | 10 |  |  | 2023-11-30 | Support Manpower and Rider conveyance | AU | 1 | 9095.12 | 9095.12 | 10732.24 | 9095.1 | 10732.22 | 0.02 | 9095.1 | 10732.22 | ZGEN | 2023-03-01 | 2023-03-31
RE/0066-SCO-75-AD -11 | Security Manpower Expenses | 2010 |  | 2010 | SMARTWORLD THE EDITION | G4S SECURE SOLUTIONS (INDIA) PVT LT | 9160000273 | 10 |  |  | 2023-07-29 | Hiring of Manpower for Security | AU | 1 | 1752571.06 | 1752571.06 | 2068033.85 | 1752427.75 | 2067864.75 | 143.31 | 1752569.58 | 2068032.11 | ZGEN | 2023-06-29 | 2024-06-28
RE/0066-SCO-75-AD -11 | Security Manpower Expenses | 2010 |  | 2010 | SMARTWORLD THE EDITION | Max ComMayank | 9160000366 | 20 |  |  | 2023-09-08 | Walky Talky on Rent (Sep'23 to Mar'24) | AU | 1 | 5220 | 5220 | 6159.6 | 5222.03 | 6162 | 2.03 | 5220 | 6159.6 | ZGEN | 2023-09-01 | 2024-03-31
RE/0066-SCO-75-AD -11 | Security Manpower Expenses | 2010 |  | 2010 | SMARTWORLD THE EDITION | Peregrine Guarding Private LimitedSiddharth Dahiya | 9160000390 | 10 |  |  | 2023-09-26 | Security Manpower | AU | 1 | 62417.99 | 62417.99 | 73653.23 | 62418.64 | 73653.99 | 0.65 | 62418.64 | 73653.99 | ZGEN | 2023-07-01 | 2023-07-16
RE/0066-SCO-75-IT -02 | Lease Line Expenses | 2010 |  | 2010 | SMARTWORLD THE EDITION | Bharti Airtel LimitedMr. Sourabh | 9160000518 | 10 |  |  | 2023-12-20 | ILL 200 Mbps_at Sec-75 | AU | 1 | 625000 | 625000 | 737500 | 625001.02 | 737501.2 | 1.02 | 625000.17 | 737500.2 | ZGEN | 2023-02-07 | 2024-10-06
RE/0066-SCO-75-IT -02 | Lease Line Expenses | 2010 |  | 2010 | SMARTWORLD THE EDITION | Fusionnet Web Services LimitedMs. Palak | 9160000584 | 10 |  |  | 2024-01-30 | Renewal For ILL Recurring Charges | AU | 1 | 430000 | 430000 | 507400 | 360407.97 | 425281.4 | 69592.03 | 430000 | 507400 | ZGEN | 2024-02-07 | 2025-02-28
RE/0066-SCO-75-IT -04 | Rental Charges IT | 2010 |  | 2010 | SMARTWORLD THE EDITION | Nuways Creation Pvt. Ltd.Ravinder | 9160000521 | 10 |  |  | 2023-12-26 | Rental Charges of Canon TX-5400 Plotter | AU | 1 | 576000 | 576000 | 679680 | 176000.17 | 207680.2 | 399999.83 | 176000 | 207680 | ZGEN | 2021-07-30 | 2024-07-30
RE/0066-SCO-75-IT -04 | Rental Charges IT | 2010 |  | 2010 | SMARTWORLD THE EDITION | Nuways Creation Pvt. Ltd.Ravinder | 9160000521 | 20 |  |  | 2023-12-26 | Amendment_Plotter_Extra Pages_Office 75 | AU | 1 | 5010 | 5010 | 5911.8 | 5010 | 5911.8 | 0 | 5010 | 5911.8 | ZGEN | 2021-07-30 | 2024-07-30
RE/0066-SCO-75-IT -04 | Rental Charges IT | 2010 |  | 2010 | SMARTWORLD THE EDITION | Nuways Creation Pvt. Ltd.Ravinder | 9160000732 | 10 |  |  | 2024-03-29 | Printer Rental at Sec-75 ETSY | AU | 1 | 60000 | 60000 | 70800 | 60000 | 70800 | 0 | 60000 | 70800 | ZGEN | 2024-04-01 | 2025-03-31
RE/0066-SCO-75-IT -05 | AMC Charges | 2010 |  | 2010 |  |  |  | 0 | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
RE/0066-SFE-1 | Sample Flat Expenses | 2010 |  | 2010 | SMARTWORLD THE EDITION | Steel Bhandar | 9110000055 | 11 |  |  | 2023-03-28 | Steel Re-bar TMT 10 mm Dia. FE-500D | TO | 11.5 | 56000 | 644000 | 759920 | 629440 | 742739.2 | 14560 | 629440 | 742739.2 | ZMAT | 2023-03-23 | 2023-03-31
RE/0066-SFE-1 | Sample Flat Expenses | 2010 |  | 2010 | SMARTWORLD THE EDITION | DDC Interiors Pvt. Ltd. | 9110000099 | 10 |  |  | 2023-05-16 | SOFA 4 SEATER | NO | 11 | 78000 | 858000 | 1012440 | 858000 | 1012440 | 0 | 858000 | 1012440 | ZMAT | 2025-01-20 | 2025-03-20
RE/0066-SFE-1 | Sample Flat Expenses | 2010 |  | 2010 | SMARTWORLD THE EDITION | DDC Interiors Pvt. Ltd. | 9110000099 | 20 |  |  | 2023-05-16 | SOFA 3.5 SEATER | NO | 10 | 67000 | 670000 | 790600 | 670000 | 790600 | 0 | 670000 | 790600 | ZMAT | 2025-01-20 | 2025-03-20
RE/0066-SFE-1 | Sample Flat Expenses | 2010 |  | 2010 | SMARTWORLD THE EDITION | DDC Interiors Pvt. Ltd. | 9110000099 | 30 |  |  | 2023-05-16 | SOFA 2 SEATER | NO | 5 | 48000 | 240000 | 283200 | 240000 | 283200 | 0 | 240000 | 283200 | ZMAT | 2025-01-20 | 2025-03-20
RE/0066-SFE-1 | Sample Flat Expenses | 2010 |  | 2010 | SMARTWORLD THE EDITION | DDC Interiors Pvt. Ltd. | 9110000099 | 40 |  |  | 2023-05-16 | LOUNGE CHAIR TYPE01 | NO | 6 | 30000 | 180000 | 212400 | 180000 | 212400 | 0 | 180000 | 212400 | ZMAT | 2025-01-20 | 2025-03-20
RE/0066-SFE-1 | Sample Flat Expenses | 2010 |  | 2010 | SMARTWORLD THE EDITION | DDC Interiors Pvt. Ltd. | 9110000099 | 50 |  |  | 2023-05-16 | LOUNGE CHAIR TYPE02 | NO | 16 | 28000 | 448000 | 528640 | 448000 | 528640 | 0 | 448000 | 528640 | ZMAT | 2025-01-20 | 2025-03-20
RE/0066-SFE-1 | Sample Flat Expenses | 2010 |  | 2010 | SMARTWORLD THE EDITION | DDC Interiors Pvt. Ltd. | 9110000099 | 60 |  |  | 2023-05-16 | LOUNGE CHAIR TYPE03 | NO | 16 | 25000 | 400000 | 472000 | 400000 | 472000 | 0 | 400000 | 472000 | ZMAT | 2025-01-20 | 2025-03-20
RE/0066-SFE-1 | Sample Flat Expenses | 2010 |  | 2010 | SMARTWORLD THE EDITION | DDC Interiors Pvt. Ltd. | 9110000099 | 70 |  |  | 2023-05-16 | CAFE CHAIR | NO | 22 | 16000 | 352000 | 415360 | 352000 | 415360 | 0 | 352000 | 415360 | ZMAT | 2025-01-20 | 2025-03-20
RE/0066-SFE-1 | Sample Flat Expenses | 2010 |  | 2010 | SMARTWORLD THE EDITION | DDC Interiors Pvt. Ltd. | 9110000099 | 80 |  |  | 2023-05-16 | CAFE BAR STOOL | NO | 3 | 15000 | 45000 | 53100 | 45000 | 53100 | 0 | 44990 | 53088 | ZMAT | 2025-01-20 | 2025-03-20
RE/0066-SFE-1 | Sample Flat Expenses | 2010 |  | 2010 | SMARTWORLD THE EDITION | DDC Interiors Pvt. Ltd. | 9110000099 | 90 |  |  | 2023-05-16 | ROUND CENTER TABLE SIZE-750mm dia | NO | 3 | 29500 | 88500 | 104430 | 88500 | 104430 | 0 | 88500 | 104430 | ZMAT | 2025-01-20 | 2025-03-20
RE/0066-SFE-1 | Sample Flat Expenses | 2010 |  | 2010 | SMARTWORLD THE EDITION | DDC Interiors Pvt. Ltd. | 9110000099 | 100 |  |  | 2023-05-16 | ROUND CENTER TABLE SIZE-900mm dia | NO | 5 | 40000 | 200000 | 236000 | 200000 | 236000 | 0 | 200000 | 236000 | ZMAT | 2025-01-20 | 2025-03-20
RE/0066-SFE-1 | Sample Flat Expenses | 2010 |  | 2010 | SMARTWORLD THE EDITION | DDC Interiors Pvt. Ltd. | 9110000099 | 110 |  |  | 2023-05-16 | RECTANGULAR CENTRE TABLE | NO | 5 | 40000 | 200000 | 236000 | 200000 | 236000 | 0 | 200000 | 236000 | ZMAT | 2025-01-20 | 2025-03-20
RE/0066-SFE-1 | Sample Flat Expenses | 2010 |  | 2010 | SMARTWORLD THE EDITION | DDC Interiors Pvt. Ltd. | 9110000099 | 120 |  |  | 2023-05-16 | ROUND CENTER TABLE 750-600mm dia | NO | 5 | 29500 | 147500 | 174050 | 147500 | 174050 | 0 | 147500 | 174050 | ZMAT | 2025-01-20 | 2025-03-20
RE/0066-SFE-1 | Sample Flat Expenses | 2010 |  | 2010 | SMARTWORLD THE EDITION | DDC Interiors Pvt. Ltd. | 9110000099 | 140 |  |  | 2023-05-16 | DESINER CANSOLE TABLE | NO | 1 | 46300 | 46300 | 54634 | 46300 | 54634 | 0 | 46310 | 54646 | ZMAT | 2025-01-20 | 2025-03-20
RE/0066-SFE-1 | Sample Flat Expenses | 2010 |  | 2010 | SMARTWORLD THE EDITION | DDC Interiors Pvt. Ltd. | 9110000099 | 150 |  |  | 2023-05-16 | ROUND SIDE TABLE | NO | 36 | 17500 | 630000 | 743400 | 630000 | 743400 | 0 | 630000 | 743400 | ZMAT | 2025-01-20 | 2025-03-20
RE/0066-SFE-1 | Sample Flat Expenses | 2010 |  | 2010 | SMARTWORLD THE EDITION | DDC Interiors Pvt. Ltd. | 9110000099 | 160 |  |  | 2023-05-16 | DESINER CANSOLE TABLE | NO | 11 | 40000 | 440000 | 519200 | 440000 | 519200 | 0 | 440000 | 519200 | ZMAT | 2025-01-20 | 2025-03-20
RE/0066-SFE-1 | Sample Flat Expenses | 2010 |  | 2010 | SMARTWORLD THE EDITION | DDC Interiors Pvt. Ltd. | 9110000099 | 170 |  |  | 2023-05-16 | ROUND CENTER TABLE 750-600mm dia | NO | 5 | 29500 | 147500 | 174050 | 147500 | 174050 | 0 | 147500 | 174050 | ZMAT | 2025-01-20 | 2025-03-20
RE/0066-SFE-1 | Sample Flat Expenses | 2010 |  | 2010 | SMARTWORLD THE EDITION | DDC Interiors Pvt. Ltd. | 9110000181 | 10 |  |  | 2023-06-28 | GROUND FLOOR LOBBY- CENTRE TABLE | NO | 26 | 4000 | 104000 | 122720 | 104000 | 122720 | 0 | 104000 | 122720 | ZMAT | 2025-01-20 | 2025-03-20
RE/0066-SFE-1 | Sample Flat Expenses | 2010 |  | 2010 | SMARTWORLD THE EDITION | DDC Interiors Pvt. Ltd. | 9110000181 | 20 |  |  | 2023-06-28 | GROUND FLOOR LOBBY- CONSOLES | NO | 12 | 9500 | 114000 | 134520 | 114000 | 134520 | 0 | 114000 | 134520 | ZMAT | 2025-01-20 | 2025-03-20
RE/0066-SFE-1 | Sample Flat Expenses | 2010 |  | 2010 | SMARTWORLD THE EDITION | DDC Interiors Pvt. Ltd. | 9110000181 | 30 |  |  | 2023-06-28 | FOR VASES | NO | 350 | 700 | 245000 | 289100 | 245000 | 289100 | 0 | 245000 | 289100 | ZMAT | 2025-01-20 | 2025-03-20
RE/0066-SFE-1 | Sample Flat Expenses | 2010 |  | 2010 | SMARTWORLD THE EDITION | DDC Interiors Pvt. Ltd. | 9110000181 | 40 |  |  | 2023-06-28 | FOR SOFA'S /LOUNGE CHAIRS | NO | 50 | 3001 | 150050 | 177059 | 150050 | 177059 | 0 | 150050 | 177059 | ZMAT | 2025-01-20 | 2025-03-20
RE/0066-SFE-1 | Sample Flat Expenses | 2010 |  | 2010 | SMARTWORLD THE EDITION | DDC Interiors Pvt. Ltd. | 9110000181 | 50 |  |  | 2023-06-28 | GROUND FLOOR LOBBY- CENTRE TABLE/side | NO | 48 | 4000 | 192000 | 226560 | 192000 | 226560 | 0 | 192000 | 226560 | ZMAT | 2025-01-20 | 2025-03-20
RE/0066-SFE-1 | Sample Flat Expenses | 2010 |  | 2010 | SMARTWORLD THE EDITION | DDC Interiors Pvt. Ltd. | 9110000181 | 60 |  |  | 2023-06-28 | GROUND FLOOR LOBBY- CONSOLES | NO | 24 | 9400 | 225600 | 266208 | 225600 | 266208 | 0 | 225600 | 266208 | ZMAT | 2025-01-20 | 2025-03-20
RE/0066-SFE-1 | Sample Flat Expenses | 2010 |  | 2010 | SMARTWORLD THE EDITION | DDC Interiors Pvt. Ltd. | 9110000181 | 70 |  |  | 2023-06-28 | 3000 x 2400 mm Hand Tufted, Wool and Ten | NO | 8 | 71000 | 568000 | 670240 | 568000 | 670240 | 0 | 568000 | 670240 | ZMAT | 2025-01-20 | 2025-03-20
RE/0066-SFE-1 | Sample Flat Expenses | 2010 |  | 2010 | SMARTWORLD THE EDITION | DDC Interiors Pvt. Ltd. | 9110000181 | 80 |  |  | 2023-06-28 | 1500 x 2400 mm Hand Tufted, Wool and Ten | NO | 8 | 35000 | 280000 | 330400 | 280000 | 330400 | 0 | 280000 | 330400 | ZMAT | 2025-01-20 | 2025-03-20
RE/0066-SFE-1 | Sample Flat Expenses | 2010 |  | 2010 | SMARTWORLD THE EDITION | DDC Interiors Pvt. Ltd. | 9110000181 | 90 |  |  | 2023-06-28 | 3000 mm dia Hand Tufted, Wool and Tencel | NO | 2 | 90000 | 180000 | 212400 | 180000 | 212400 | 0 | 180000 | 212400 | ZMAT | 2025-01-20 | 2025-03-20
RE/0066-SFE-1 | Sample Flat Expenses | 2010 |  | 2010 | SMARTWORLD THE EDITION | DDC Interiors Pvt. Ltd. | 9110000181 | 100 |  |  | 2023-06-28 | 1600 mm dia Hand Tufted, Wool and Tencel | NO | 2 | 30000 | 60000 | 70800 | 60000 | 70800 | 0 | 60000 | 70800 | ZMAT | 2025-01-20 | 2025-03-20
RE/0066-SFE-1 | Sample Flat Expenses | 2010 |  | 2010 | SMARTWORLD THE EDITION | N S Concrete Pvt Ltd | 9110000300 | 10 |  |  | 2023-11-18 | M25 grade | M3 | 100 | 4205 | 420500 | 496190 | 178712.5 | 210880.75 | 241787.5 | 178713 | 210881 | ZMAT | 2025-01-20 | 2025-03-20
RE/0066-SFE-1 | Sample Flat Expenses | 2010 |  | 2010 | SMARTWORLD THE EDITION | N S Concrete Pvt Ltd | 9110000300 | 20 |  |  | 2023-11-18 | Amendment 1 - M 7.5 grade | M3 | 50 | 3572.5 | 178625 | 210777.5 | 0 | 0 | 178625 | 0 | 0 | ZMAT | 2025-01-20 | 2025-03-20
RE/0066-SFE-1 | Sample Flat Expenses | 2010 |  | 2010 | SMARTWORLD THE EDITION | DDC Interiors Pvt. Ltd. | 9140000123 | 10 |  |  | 2023-05-12 | Interior Work - 10 Nos. GF Meeting Room | AU | 1 | 2720700 | 2720700 | 3210426 | 2584665.58 | 3049905.38 | 136034.42 | 2584665.42 | 3049905.2 | ZSER | 2023-05-03 | 2023-06-02
RE/0066-SFE-1 | Sample Flat Expenses | 2010 |  | 2010 | SMARTWORLD THE EDITION | DDC Interiors Pvt. Ltd. | 9140000123 | 20 |  |  | 2023-05-12 | Interior Work - 2Nos Lounge Meeting Room | AU | 1 | 981780 | 981780 | 1158500.4 | 932690.03 | 1100574.23 | 49089.97 | 932690.92 | 1100575.28 | ZSER | 2023-05-03 | 2023-06-02
RE/0066-SFE-1 | Sample Flat Expenses | 2010 |  | 2010 | SMARTWORLD THE EDITION | DDC Interiors Pvt. Ltd. | 9140000123 | 30 |  |  | 2023-05-12 | Interior Work - Board room-2 No.s | AU | 1 | 845440 | 845440 | 997619.2 | 803168.86 | 947739.25 | 42271.14 | 803169.02 | 947739.44 | ZSER | 2023-05-03 | 2023-06-02
RE/0066-SFE-1 | Sample Flat Expenses | 2010 |  | 2010 | SMARTWORLD THE EDITION | DDC Interiors Pvt. Ltd. | 9140000123 | 40 |  |  | 2023-05-12 | Interior Work - Cabin-2 No.s | AU | 1 | 366400 | 366400 | 432352 | 348080.34 | 410734.8 | 18319.66 | 348080 | 410734.4 | ZSER | 2023-05-03 | 2023-06-02
RE/0066-SFE-1 | Sample Flat Expenses | 2010 |  | 2010 | SMARTWORLD THE EDITION | DDC Interiors Pvt. Ltd. | 9140000123 | 50 |  |  | 2023-05-12 | Interior Work - Lobby Area | AU | 1 | 4859000 | 4859000 | 5733620 | 4616050.1 | 5446939.12 | 242949.9 | 4616050 | 5446939 | ZSER | 2023-05-03 | 2023-06-02
RE/0066-SFE-1 | Sample Flat Expenses | 2010 |  | 2010 | SMARTWORLD THE EDITION | DDC Interiors Pvt. Ltd. | 9140000123 | 60 |  |  | 2023-05-12 | Housekeeping Labour for Furn. Mov& Hand. | AU | 1 | 384000 | 384000 | 453120 | 364800.02 | 430464.02 | 19199.98 | 364800 | 430464 | ZSER | 2023-05-03 | 2023-06-02
RE/0066-SFE-1 | Sample Flat Expenses | 2010 |  | 2010 | SMARTWORLD THE EDITION | M/s Hi-Tech InfraMr. Ajay Bhati | 9140000139 | 10 |  |  | 2023-05-24 | Sheet Barricading Works - Sec-66 | AU | 1 | 489740 | 489740 | 577893.2 | 95265.98 | 112413.86 | 394474.02 | 95265.98 | 112413.86 | ZSER | 2023-05-08 | 2023-06-07
RE/0066-SFE-1 | Sample Flat Expenses | 2010 |  | 2010 | SMARTWORLD THE EDITION | Frontline Construction | 9140000143 | 10 |  |  | 2023-05-26 | Block Work and Plaster Work in Show Flat | AU | 1 | 653350 | 653350 | 770953 | 368567.74 | 434909.93 | 284782.26 | 368567.74 | 434909.93 | ZSER | 2023-05-23 | 2023-07-22
RE/0066-SFE-1 | Sample Flat Expenses | 2010 |  | 2010 | SMARTWORLD THE EDITION | Orange Sky | 9140000148 | 10 |  |  | 2023-05-31 | SWD_66@62_SAMPLE FLAT INTERIOR VIEWS | AU | 1 | 100000 | 100000 | 118000 | 100000 | 118000 | 0 | 100000 | 118000 | ZSER | 2023-05-24 | 2023-06-23
RE/0066-SFE-1 | Sample Flat Expenses | 2010 |  | 2010 | SMARTWORLD THE EDITION | Rudraa Creators Pvt Ltd. | 9140000204 | 40 |  |  | 2023-08-31 | Interior Works For Show Flat Sec-66 | AU | 1 | 25682745 | 25682745 | 30305639.1 | 25682744.88 | 30305638.96 | 0.12 | 25682745.69 | 30305639.91 | ZSER | 2023-08-18 | 2023-11-18
RE/0066-SFE-1 | Sample Flat Expenses | 2010 |  | 2010 | SMARTWORLD THE EDITION | Rudraa Creators Pvt Ltd. | 9140000204 | 50 |  |  | 2023-08-31 | Amend -Interior Works For Show Flat | AU | 1 | 4168820 | 4168820 | 4919207.6 | 3264185.98 | 3851739.46 | 904634.02 | 3264185.98 | 3851739.46 | ZSER | 2023-08-18 | 2023-11-18
RE/0066-SFE-1 | Sample Flat Expenses | 2010 |  | 2010 | SMARTWORLD THE EDITION | Orange Sky | 9140000212 | 10 |  |  | 2023-09-16 | 3D-Virtual reality experience consultanc | AU | 1 | 750000 | 750000 | 885000 | 750000 | 885000 | 0 | 750000 | 885000 | ZSER | 2023-09-14 | 2023-10-30
RE/0066-SFE-1 | Sample Flat Expenses | 2010 |  | 2010 | SMARTWORLD THE EDITION | SJR Facade & Interiors Private Limi | 9140000216 | 30 |  |  | 2023-09-27 | Facade Repair works | AU | 1 | 7100 | 7100 | 8378 | 0 | 0 | 7100 | 0 | 0 | ZSER | 2023-09-21 | 2023-10-11
RE/0066-SFE-1 | Sample Flat Expenses | 2010 |  | 2010 | SMARTWORLD THE EDITION | DCM Shriram LimitedShailendra | 9140000223 | 10 |  |  | 2023-10-09 | Door Window of Sample Flat 66 | AU | 1 | 150040.67 | 150040.67 | 177047.99 | 150039.55 | 177046.67 | 1.12 | 150039.55 | 177046.67 | ZSER | 2023-09-29 | 2023-10-29
RE/0066-SFE-1 | Sample Flat Expenses | 2010 |  | 2010 | SMARTWORLD THE EDITION | Aqua Graphics | 9140000230 | 10 |  |  | 2023-11-09 | Fountain Sculpture | AU | 1 | 1850000 | 1850000 | 2183000 | 1850000 | 2183000 | 0 | 1850000 | 2183000 | ZSER | 2023-11-03 | 2024-12-18
RE/0066-SFE-1 | Sample Flat Expenses | 2010 |  | 2010 | SMARTWORLD THE EDITION | Aqua Graphics | 9140000230 | 20 |  |  | 2023-11-09 | PVD columns/pillars as per Amendmnet 1 | AU | 1 | 292824 | 292824 | 345532.32 | 292804.97 | 345509.86 | 19.03 | 292823.98 | 345532.3 | ZSER | 2023-11-03 | 2024-12-18
RE/0066-SFE-1 | Sample Flat Expenses | 2010 |  | 2010 | SMARTWORLD THE EDITION | K K Anand Infrastructure Pvt LTD | 9140000238 | 10 |  |  | 2023-12-26 | Landscape works | AU | 1 | 1018000 | 1018000 | 1201240 | 708294.15 | 835787.1 | 309705.85 | 708294.15 | 835787.1 | ZSER | 2023-12-13 | 2024-01-13
RE/0066-SFE-1 | Sample Flat Expenses | 2010 |  | 2010 | SMARTWORLD THE EDITION | K K Anand Infrastructure Pvt LTD | 9140000240 | 10 |  |  | 2023-12-30 | Landscape finishing & Horticulture work | AU | 1 | 2868282 | 2868282 | 3384572.76 | 2582702.03 | 3047588.4 | 285579.97 | 2582702.03 | 3047588.4 | ZSER | 2023-12-29 | 2024-03-29
RE/0066-SFE-1 | Sample Flat Expenses | 2010 |  | 2010 | SMARTWORLD THE EDITION | Neerway Projects Private limited | 9140000241 | 10 |  |  | 2023-12-30 | Repair of Water Body as per amend-1 | AU | 1 | 70000 | 70000 | 82600 | 70000 | 82600 | 0 | 70000 | 82600 | ZSER | 2023-12-21 | 2024-01-21
RE/0066-SFE-1 | Sample Flat Expenses | 2010 |  | 2010 | SMARTWORLD THE EDITION | INNERSPACE.INC | 9140000253 | 10 |  |  | 2023-12-27 | Supply and installation workstation, | AU | 1 | 171600 | 171600 | 202488 | 171600 | 202488 | 0 | 171600 | 202488 | ZSER | 2024-01-09 | 2024-01-24
RE/0066-SFE-1 | Sample Flat Expenses | 2010 |  | 2010 | SMARTWORLD THE EDITION | Shree Krishna Secauto Private Limit | 9140000258 | 10 |  |  | 2024-02-21 | Home Automation System | AU | 1 | 108946 | 108946 | 128556.28 | 108945.76 | 128556 | 0.24 | 108946.02 | 128556.3 | ZSER | 2023-12-29 | 2024-01-29
RE/0066-SFE-1 | Sample Flat Expenses | 2010 |  | 2010 | SMARTWORLD THE EDITION | Rudraa Creators Pvt Ltd. | 9140000287 | 10 |  |  | 2024-05-06 | Interior Finishing Works at Showflat | AU | 1 | 2428229.1 | 2428229.1 | 2865310.34 | 2363435.34 | 2788853.7 | 64793.76 | 2363435.34 | 2788853.7 | ZSER | 2024-05-08 | 2024-06-08
RE/0066-SFE-1 | Sample Flat Expenses | 2010 |  | 2010 | SMARTWORLD THE EDITION | That Is ITH Interior Company Limite | 9160000058 | 10 |  |  | 2023-05-02 | Sample Flat Interior Design Consultant | AU | 1 | 18500 | 0 | 0 | 18500 | 18500 | 18500 | 1507916.5 | 1507916.5 | ZGEN | 2023-03-17 | 2023-04-24
RE/0066-SFE-1 | Sample Flat Expenses | 2010 |  | 2010 | SMARTWORLD THE EDITION | Euronics Industries Private Limited | 9160000492 | 10 |  |  | 2023-12-11 | AIR CURTAIN | AU | 1 | 42432 | 42432 | 50069.76 | 42432.19 | 50069.99 | 0.19 | 42432.03 | 50069.8 | ZGEN | 2023-12-01 | 2023-12-12
RE/0066-SFE-1 | Sample Flat Expenses | 2010 |  | 2010 | SMARTWORLD THE EDITION | Euronics Industries Private Limited | 9160000492 | 20 |  |  | 2023-12-11 | Fright | AU | 1 | 1800 | 1800 | 2124 | 1800.01 | 2124.01 | 0.01 | 1800 | 2124 | ZGEN | 2023-12-01 | 2023-12-12
RE/0066-SFE-1 | Sample Flat Expenses | 2010 |  | 2010 | SMARTWORLD THE EDITION | First Impression Sign Systems | 9160000587 | 10 |  |  | 2024-02-01 | Supply & Installation of Signage | AU | 1 | 340000 | 340000 | 401200 | 340000 | 401200 | 0 | 340000 | 401200 | ZGEN | 2024-01-05 | 2024-02-05
RE/0066-SFE-1 | Sample Flat Expenses | 2010 |  | 2010 | SMARTWORLD THE EDITION | First Impression Sign Systems | 9160000587 | 20 |  |  | 2024-02-01 | Crane, Scaffolding Charges | AU | 1 | 35000 | 35000 | 41300 | 35000 | 41300 | 0 | 35000 | 41300 | ZGEN | 2024-01-05 | 2024-02-05
RE/0066-SGE-SF-01 | Sales Gallery & Show Flat Expenses | 2010 |  | 2010 | SMARTWORLD THE EDITION | DDC Interiors Pvt. Ltd. | 9140000123 | 70 |  |  | 2023-05-12 | Amenedment 1 Interior works extra items | AU | 1 | 1826800 | 1826800 | 2155624 | 790872.03 | 933229 | 1035927.97 | 790870.93 | 933227.7 | ZSER | 2023-05-03 | 2023-06-02
RE/0066-SGE-SF-01 | Sales Gallery & Show Flat Expenses | 2010 |  | 2010 | SMARTWORLD THE EDITION | True Wall Specialities Private Limi | 9140000202 | 10 |  |  | 2023-08-28 | Facade Work in Show Flat | AU | 1 | 9109770.72 | 9109770.72 | 10749529.45 | 4895287.29 | 5776439 | 4214483.43 | 4895402.42 | 5776574.85 | ZSER | 2023-06-13 | 2023-09-11
RE/0066-SGE-SF-01 | Sales Gallery & Show Flat Expenses | 2010 |  | 2010 | SMARTWORLD THE EDITION | Tech Nova Water Proofing Pvt. Ltd. | 9140000203 | 10 |  |  | 2023-08-31 | Terrace Waterproofing Work at Sec-62 SG | AU | 1 | 422625 | 422625 | 498697.5 | 311207.97 | 367225.4 | 111417.03 | 311207.37 | 367224.7 | ZSER | 2023-06-15 | 2023-07-16
RE/0066-SGE-SF-01 | Sales Gallery & Show Flat Expenses | 2010 |  | 2010 | SMARTWORLD THE EDITION | SJR Facade & Interiors Private Limi | 9140000216 | 20 |  |  | 2023-09-27 | FAÇADE WORKS As per Amed-1 | AU | 1 | 433061.16 | 433061.16 | 511012.17 | 290009.72 | 342211.47 | 143051.44 | 290009.6 | 342211.33 | ZSER | 2023-09-21 | 2023-10-11
RE/0066-SGE-SF-01 | Sales Gallery & Show Flat Expenses | 2010 |  | 2010 | SMARTWORLD THE EDITION | Shri baba Construction | 9140000217 | 10 |  |  | 2023-09-27 | CIVIL WORKS FOR SHOW FLAT SEC-66 RCCBUND | AU | 1 | 92000.38 | 92000.38 | 108560.45 | 72508.42 | 85559.94 | 19491.96 | 72510.12 | 85561.94 | ZSER | 2023-09-21 | 2023-10-12
RE/0066-SGE-SF-01 | Sales Gallery & Show Flat Expenses | 2010 |  | 2010 | SMARTWORLD THE EDITION | Shri baba Construction | 9140000217 | 20 |  |  | 2023-09-27 | Amendment 1 Civil & Structure works | AU | 1 | 1145278.2 | 1145278.2 | 1351428.28 | 547387.39 | 645917.12 | 597890.81 | 547387.67 | 645917.45 | ZSER | 2023-09-21 | 2023-10-12
RE/0066-SGE-SF-01 | Sales Gallery & Show Flat Expenses | 2010 |  | 2010 | SMARTWORLD THE EDITION | DCM Shriram LimitedShailendra | 9140000223 | 20 |  |  | 2023-10-09 | Aluminium Window Amendment 1 | AU | 1 | 7995.14 | 7995.14 | 9434.27 | 0 | 0 | 7995.14 | 0 | 0 | ZSER | 2023-09-29 | 2023-10-29
RE/0066-SGE-SF-01 | Sales Gallery & Show Flat Expenses | 2010 |  | 2010 | SMARTWORLD THE EDITION | DCM Shriram LimitedShailendra | 9140000223 | 30 |  |  | 2023-10-09 | P/F Aluminium Louver Door Amend -2 | AU | 1 | 39638.07 | 39638.07 | 46772.92 | 0 | 0 | 39638.07 | 0 | 0 | ZSER | 2023-09-29 | 2023-10-29
RE/0066-SGE-SF-01 | Sales Gallery & Show Flat Expenses | 2010 |  | 2010 | SMARTWORLD THE EDITION | C. Jena & CompanyC. Jena & Company | 9140000228 | 10 |  |  | 2023-11-04 | UPVC Rain Water Pipe Work for ShowFlat66 | AU | 1 | 36000 | 36000 | 42480 | 23520.34 | 27754 | 12479.66 | 23520 | 27753.6 | ZSER | 2023-10-23 | 2023-11-23
RE/0066-SGE-SF-01 | Sales Gallery & Show Flat Expenses | 2010 |  | 2010 | SMARTWORLD THE EDITION | P.C. CUSTOMER SERVICE CENTRE | 9140000500 | 10 |  |  | 2025-09-19 | Panel Modification at 62 Gallery | AU | 1 | 60410 | 60410 | 71283.8 | 0 | 0 | 60410 | 0 | 0 | ZSER | 2025-09-16 | 2025-10-16
RE/0066-SGE-SF-01 | Sales Gallery & Show Flat Expenses | 2010 |  | 2010 | SMARTWORLD THE EDITION | P.C. CUSTOMER SERVICE CENTRE | 9140000500 | 20 |  |  | 2025-09-19 | Panel Modification at 62 Gallery Amend-1 | AU | 1 | 52725 | 52725 | 62215.5 | 0 | 0 | 52725 | 0 | 0 | ZSER | 2025-09-16 | 2025-10-16
RE/0066-SGE-SF-01 | Sales Gallery & Show Flat Expenses | 2010 |  | 2010 | SMARTWORLD THE EDITION | P.C. CUSTOMER SERVICE CENTRE | 9140000500 | 20 |  |  | 2025-09-19 | Panel Modification at 62 Gallery Amend-1 | AU | 1 | 0 | 52725 | 62215.5 | 0 | 0 | 52725 | 0 | 0 | ZSER | 2025-09-16 | 2025-10-16
RE/0066-SGE-SF-01 | Sales Gallery & Show Flat Expenses | 2010 |  | 2010 | SMARTWORLD THE EDITION | Peregrine Guarding Private LimitedSiddharth Dahiya | 9160000168 | 10 |  |  | 2023-06-20 | Transition Security Services | AU | 1 | 66000 | 66000 | 77880 | 66000 | 77880 | 0 | 66000 | 77880 | ZGEN | 2023-04-01 | 2024-03-31
RE/0066-SGE-SF-01 | Sales Gallery & Show Flat Expenses | 2010 |  | 2010 | SMARTWORLD THE EDITION | Milan Flower ShopChander | 9160000187 | 10 |  |  | 2023-06-28 | Flower | AU | 1 | 140448 | 140448 | 140448 | 140452 | 140452 | 4 | 140448 | 140448 | ZGEN | 2023-04-01 | 2024-03-31
RE/0066-SGE-SF-01 | Sales Gallery & Show Flat Expenses | 2010 |  | 2010 | SMARTWORLD THE EDITION | Metro Electronics WorldMr.Roopesh Verma | 9160000203 | 10 |  |  | 2023-07-04 | AC AMC Charges - 62 Sales Gallery | AU | 1 | 259424 | 259424 | 306120.32 | 259426.85 | 306123.68 | 2.85 | 259427.25 | 306124.16 | ZGEN | 2023-05-01 | 2024-03-31
RE/0066-SGE-SF-01 | Sales Gallery & Show Flat Expenses | 2010 |  | 2010 | SMARTWORLD THE EDITION | Tecknomen Facility Services Pvt. LtDwarka | 9160000370 | 10 |  |  | 2023-09-14 | Transition Security Services | AU | 1 | 110000 | 110000 | 129800 | 110000 | 129800 | 0 | 110000 | 129800 | ZGEN | 2023-07-01 | 2023-12-31
RE/0066-SGE-SF-AD -01 | House Keeping Expenses | 2010 |  | 2010 | SMARTWORLD THE EDITION | Prime Solutions | 9110000190 | 10 |  |  | 2023-07-10 | JANITORIAL ITEMS | NO | 73216.53 | 1 | 73216.53 | 86395.51 | 62048.5 | 73217.23 | 11168.03 | 62048.4 | 73217.03 | ZMAT | 2025-01-20 | 2025-03-20
RE/0066-SGE-SF-AD -01 | House Keeping Expenses | 2010 |  | 2010 | SMARTWORLD THE EDITION | Prime Solutions | 9110000190 | 20 |  |  | 2023-07-10 | M-FOLD | NO | 5220 | 31.78 | 165891.6 | 195752.09 | 165892.03 | 195752.59 | 0.43 | 165889.3 | 195746.59 | ZMAT | 2025-01-20 | 2025-03-20
RE/0066-SGE-SF-AD -01 | House Keeping Expenses | 2010 |  | 2010 | SMARTWORLD THE EDITION | Prime Solutions | 9110000190 | 30 |  |  | 2023-07-10 | TOILET ROLL ELEGANT | NO | 1980 | 12.75 | 25245 | 29789.1 | 25244.89 | 29788.97 | 0.11 | 25245 | 29791.37 | ZMAT | 2025-01-20 | 2025-03-20
RE/0066-SGE-SF-AD -01 | House Keeping Expenses | 2010 |  | 2010 | SMARTWORLD THE EDITION | Prime Solutions | 9110000190 | 40 |  |  | 2023-07-10 | MIST TISSUE | NO | 2703.855 | 30 | 81115.65 | 95716.47 | 48599.99 | 57347.99 | 32515.66 | 48600 | 57347.2 | ZMAT | 2025-01-20 | 2025-03-20
RE/0066-SGE-SF-AD -01 | House Keeping Expenses | 2010 |  | 2010 | SMARTWORLD THE EDITION | Prime Solutions | 9110000190 | 50 |  |  | 2023-07-10 | TOWEL NAPKIN | NO | 2125 | 14.5 | 30812.5 | 36358.75 | 30812.56 | 36358.82 | 0.06 | 30814.5 | 36362.32 | ZMAT | 2025-01-20 | 2025-03-20
RE/0066-SGE-SF-AD -01 | House Keeping Expenses | 2010 |  | 2010 | SMARTWORLD THE EDITION | Updater Services limited | 9110000199 | 10 |  |  | 2023-07-18 | Cleaning Equipment | NO | 12 | 5694 | 68328 | 80627.04 | 68328.54 | 80627.68 | 0.54 | 68328.16 | 80622.04 | ZMAT | 2025-01-20 | 2025-03-20
RE/0066-SGE-SF-AD -01 | House Keeping Expenses | 2010 |  | 2010 | SMARTWORLD THE EDITION | Updater Services limited | 9110000199 | 20 |  |  | 2023-07-18 | MST TOOLS | NO | 12 | 2400 | 28800 | 33984 | 28800 | 33984 | 0 | 28800 | 33983.96 | ZMAT | 2025-01-20 | 2025-03-20
RE/0066-SGE-SF-AD -01 | House Keeping Expenses | 2010 |  | 2010 | SMARTWORLD THE EDITION | Updater Services limited | 9110000199 | 30 |  |  | 2023-07-18 | WHITE PHENYLE CANE 5 LTR CLEANO | NO | 1 | 138.86 | 138.86 | 163.85 | 0 | 0 | 138.86 | 0 | 0 | ZMAT | 2025-01-20 | 2025-03-20
RE/0066-SGE-SF-AD -01 | House Keeping Expenses | 2010 |  | 2010 | SMARTWORLD THE EDITION | Updater Services limited | 9110000199 | 40 |  |  | 2023-07-18 | WHITE PHENYLE CANE 5 LTR CLEANO 1770 | NO | 2 | 138.86 | 277.72 | 327.71 | 277.73 | 327.72 | 0.01 | 277.72 | 327.72 | ZMAT | 2025-01-20 | 2025-03-20
RE/0066-SGE-SF-AD -01 | House Keeping Expenses | 2010 |  | 2010 | SMARTWORLD THE EDITION | Updater Services limited | 9110000199 | 50 |  |  | 2023-07-18 | MICRO FIBER CLOTH Blue 1770 | NO | 2 | 144.9 | 289.8 | 304.29 | 289.9 | 304.4 | 0.1 | 289.8 | 304.4 | ZMAT | 2025-01-20 | 2025-03-20
RE/0066-SGE-SF-AD -01 | House Keeping Expenses | 2010 |  | 2010 | SMARTWORLD THE EDITION | Updater Services limited | 9110000199 | 60 |  |  | 2023-07-18 | TOILET PUMP G.Q 1770 | NO | 2 | 66.41 | 132.82 | 156.73 | 132.9 | 156.82 | 0.08 | 132.82 | 156.82 | ZMAT | 2025-01-20 | 2025-03-20
RE/0066-SGE-SF-AD -01 | House Keeping Expenses | 2010 |  | 2010 | SMARTWORLD THE EDITION | Updater Services limited | 9110000199 | 70 |  |  | 2023-07-18 | CHECK DUSTER MEDIUM 20X20 1770 | NO | 6 | 23.1 | 138.6 | 145.53 | 138.67 | 145.6 | 0.07 | 138.42 | 145.42 | ZMAT | 2025-01-20 | 2025-03-20
RE/0066-SGE-SF-AD -01 | House Keeping Expenses | 2010 |  | 2010 | SMARTWORLD THE EDITION | Updater Services limited | 9110000199 | 80 |  |  | 2023-07-18 | SCOTCH BRIGHT 3M 1770 | NO | 4 | 27.77 | 111.08 | 131.07 | 111.08 | 131.08 | 0 | 111.08 | 131.08 | ZMAT | 2025-01-20 | 2025-03-20
RE/0066-SGE-SF-AD -01 | House Keeping Expenses | 2010 |  | 2010 | SMARTWORLD THE EDITION | Updater Services limited | 9110000199 | 90 |  |  | 2023-07-18 | Urinal Cube A-1( Best Qlty) 1770 | NO | 5 | 96.6 | 483 | 569.94 | 483.05 | 570 | 0.05 | 483 | 570 | ZMAT | 2025-01-20 | 2025-03-20
RE/0066-SGE-SF-AD -01 | House Keeping Expenses | 2010 |  | 2010 | SMARTWORLD THE EDITION | Updater Services limited | 9110000199 | 100 |  |  | 2023-07-18 | ALLOUT REFILL WITH MACHINE 1770 | NO | 6 | 90.56 | 543.36 | 641.16 | 543.36 | 641.16 | 0 | 543.36 | 641.16 | ZMAT | 2025-01-20 | 2025-03-20
RE/0066-SGE-SF-AD -01 | House Keeping Expenses | 2010 |  | 2010 | SMARTWORLD THE EDITION | Updater Services limited | 9110000199 | 110 |  |  | 2023-07-18 | COLIN 500 ML 1770 | NO | 5 | 100.8 | 504 | 594.72 | 504.07 | 594.8 | 0.07 | 504 | 594.8 | ZMAT | 2025-01-20 | 2025-03-20
RE/0066-SGE-SF-AD -01 | House Keeping Expenses | 2010 |  | 2010 | SMARTWORLD THE EDITION | Updater Services limited | 9110000199 | 120 |  |  | 2023-07-18 | DUST PAN IPS 1770 | NO | 1 | 30.19 | 30.19 | 35.62 | 30.16 | 35.59 | 0.03 | 30.19 | 35.59 | ZMAT | 2025-01-20 | 2025-03-20
RE/0066-SGE-SF-AD -01 | House Keeping Expenses | 2010 |  | 2010 | SMARTWORLD THE EDITION | Updater Services limited | 9110000199 | 130 |  |  | 2023-07-18 | RUBBER GLOVES RED 1770 | NO | 5 | 54.34 | 271.7 | 320.61 | 271.78 | 320.7 | 0.08 | 271.7 | 320.7 | ZMAT | 2025-01-20 | 2025-03-20
RE/0066-SGE-SF-AD -01 | House Keeping Expenses | 2010 |  | 2010 | SMARTWORLD THE EDITION | Updater Services limited | 9110000199 | 140 |  |  | 2023-07-18 | TOILET ROUND BRUSH NYLON 1770 | NO | 2 | 54.34 | 108.68 | 128.24 | 108.71 | 128.28 | 0.03 | 108.68 | 128.28 | ZMAT | 2025-01-20 | 2025-03-20
RE/0066-SGE-SF-AD -01 | House Keeping Expenses | 2010 |  | 2010 | SMARTWORLD THE EDITION | Updater Services limited | 9110000199 | 150 |  |  | 2023-07-18 | ODONIL 50 GMS 1770 | NO | 35 | 42.26 | 1479.1 | 1745.34 | 1479.07 | 1745.3 | 0.03 | 1479.1 | 1745.3 | ZMAT | 2025-01-20 | 2025-03-20
RE/0066-SGE-SF-AD -01 | House Keeping Expenses | 2010 |  | 2010 | SMARTWORLD THE EDITION | Updater Services limited | 9110000199 | 160 |  |  | 2023-07-18 | FEM HAND WASH 5 LITS 1770 | NO | 1 | 760.73 | 760.73 | 897.66 | 760.79 | 897.73 | 0.06 | 760.73 | 897.73 | ZMAT | 2025-01-20 | 2025-03-20
RE/0066-SGE-SF-AD -01 | House Keeping Expenses | 2010 |  | 2010 | SMARTWORLD THE EDITION | Updater Services limited | 9110000199 | 170 |  |  | 2023-07-18 | Vim Bar 300 grm Small 1770 | NO | 2 | 21 | 42 | 49.56 | 42.03 | 49.6 | 0.03 | 42 | 49.6 | ZMAT | 2025-01-20 | 2025-03-20
RE/0066-SGE-SF-AD -01 | House Keeping Expenses | 2010 |  | 2010 | SMARTWORLD THE EDITION | Updater Services limited | 9110000199 | 180 |  |  | 2023-07-18 | HARD BROOM BEST QLTY 1770 | NO | 8 | 72.45 | 579.6 | 579.6 | 579.6 | 579.6 | 0 | 579.6 | 579.6 | ZMAT | 2025-01-20 | 2025-03-20
RE/0066-SGE-SF-AD -01 | House Keeping Expenses | 2010 |  | 2010 | SMARTWORLD THE EDITION | Updater Services limited | 9110000199 | 190 |  |  | 2023-07-18 | NAPTHOLIN BALLS (1 KG) 1770 | NO | 1 | 217.35 | 217.35 | 256.47 | 217.42 | 256.55 | 0.07 | 217.35 | 256.55 | ZMAT | 2025-01-20 | 2025-03-20
RE/0066-SGE-SF-AD -01 | House Keeping Expenses | 2010 |  | 2010 | SMARTWORLD THE EDITION | Updater Services limited | 9110000199 | 200 |  |  | 2023-07-18 | ROOM FRESHNER-PREMIUM VENNILA 1770 | NO | 8 | 132.83 | 1062.64 | 1253.92 | 1062.58 | 1253.84 | 0.06 | 1062.64 | 1253.84 | ZMAT | 2025-01-20 | 2025-03-20
RE/0066-SGE-SF-AD -01 | House Keeping Expenses | 2010 |  | 2010 | SMARTWORLD THE EDITION | Updater Services limited | 9110000199 | 210 |  |  | 2023-07-18 | DISPOSABLE BAG SMALL BLACK 1770 | NO | 5 | 114.71 | 573.55 | 676.79 | 573.52 | 676.75 | 0.03 | 573.55 | 676.75 | ZMAT | 2025-01-20 | 2025-03-20
RE/0066-SGE-SF-AD -01 | House Keeping Expenses | 2010 |  | 2010 | SMARTWORLD THE EDITION | Updater Services limited | 9110000199 | 220 |  |  | 2023-07-18 | DISPOSABLE BAG BIG BLACK (45-50) 1770 | NO | 20 | 114.71 | 2294.2 | 2707.16 | 2294.24 | 2707.2 | 0.04 | 2294.2 | 2707.2 | ZMAT | 2025-01-20 | 2025-03-20
RE/0066-SGE-SF-AD -01 | House Keeping Expenses | 2010 |  | 2010 | SMARTWORLD THE EDITION | Updater Services limited | 9110000199 | 230 |  |  | 2023-07-18 | FLOOR CLEANING CLOTH MEDIUM 1770 | NO | 24 | 35.02 | 840.48 | 882.5 | 840.46 | 882.48 | 0.02 | 840.48 | 882.48 | ZMAT | 2025-01-20 | 2025-03-20
RE/0066-SGE-SF-AD -01 | House Keeping Expenses | 2010 |  | 2010 | SMARTWORLD THE EDITION | Updater Services limited | 9110000199 | 240 |  |  | 2023-07-18 | HARPIC 500 ML 1770 | NO | 2 | 84 | 168 | 198.24 | 167.97 | 198.2 | 0.03 | 168 | 198.2 | ZMAT | 2025-01-20 | 2025-03-20
RE/0066-SGE-SF-AD -01 | House Keeping Expenses | 2010 |  | 2010 | SMARTWORLD THE EDITION | Updater Services limited | 9110000199 | 250 |  |  | 2023-07-18 | PRILL 425 ML 1770 | NO | 2 | 99.02 | 198.04 | 233.69 | 198 | 233.64 | 0.04 | 198.04 | 233.64 | ZMAT | 2025-01-20 | 2025-03-20
RE/0066-SGE-SF-AD -01 | House Keeping Expenses | 2010 |  | 2010 | SMARTWORLD THE EDITION | Updater Services limited | 9110000199 | 260 |  |  | 2023-07-18 | SOFTBROOM BIG PIPE 1770 | NO | 4 | 108.68 | 434.72 | 434.72 | 434.72 | 434.72 | 0 | 434.72 | 434.72 | ZMAT | 2025-01-20 | 2025-03-20
RE/0066-SGE-SF-AD -01 | House Keeping Expenses | 2010 |  | 2010 | SMARTWORLD THE EDITION | Updater Services limited | 9110000199 | 270 |  |  | 2023-07-18 | TASKI - R1 1770 | NO | 5 | 270.9 | 1354.5 | 1598.31 | 1354.49 | 1598.3 | 0.01 | 1354.5 | 1598.3 | ZMAT | 2025-01-20 | 2025-03-20
RE/0066-SGE-SF-AD -01 | House Keeping Expenses | 2010 |  | 2010 | SMARTWORLD THE EDITION | Updater Services limited | 9110000199 | 280 |  |  | 2023-07-18 | TASKI - R2 1770 | NO | 5 | 236.25 | 1181.25 | 1393.88 | 1181.23 | 1393.85 | 0.02 | 1181.25 | 1393.85 | ZMAT | 2025-01-20 | 2025-03-20
RE/0066-SGE-SF-AD -01 | House Keeping Expenses | 2010 |  | 2010 | SMARTWORLD THE EDITION | Updater Services limited | 9110000199 | 290 |  |  | 2023-07-18 | TASKI - R3 1770 | NO | 5 | 315 | 1575 | 1858.5 | 1575.08 | 1858.6 | 0.08 | 1575 | 1858.6 | ZMAT | 2025-01-20 | 2025-03-20
RE/0066-SGE-SF-AD -01 | House Keeping Expenses | 2010 |  | 2010 | SMARTWORLD THE EDITION | Updater Services limited | 9110000199 | 300 |  |  | 2023-07-18 | TASKI - R5 1770 | NO | 5 | 236.25 | 1181.25 | 1393.88 | 1181.23 | 1393.85 | 0.02 | 1181.25 | 1393.85 | ZMAT | 2025-01-20 | 2025-03-20
RE/0066-SGE-SF-AD -01 | House Keeping Expenses | 2010 |  | 2010 | SMARTWORLD THE EDITION | Updater Services limited | 9110000199 | 310 |  |  | 2023-07-18 | TASKI - R6 1770 | NO | 5 | 168 | 840 | 991.2 | 840 | 991.2 | 0 | 840 | 991.2 | ZMAT | 2025-01-20 | 2025-03-20
RE/0066-SGE-SF-AD -01 | House Keeping Expenses | 2010 |  | 2010 | SMARTWORLD THE EDITION | Updater Services limited | 9110000199 | 320 |  |  | 2023-07-18 | TASKI - R9 1770 | NO | 5 | 241.5 | 1207.5 | 1424.85 | 1207.54 | 1424.9 | 0.04 | 1207.5 | 1424.9 | ZMAT | 2025-01-20 | 2025-03-20
RE/0066-SGE-SF-AD -01 | House Keeping Expenses | 2010 |  | 2010 | SMARTWORLD THE EDITION | Updater Services limited | 9110000199 | 330 |  |  | 2023-07-18 | HIT SPRAY (M) BLACK/ 200ML 1770 | NO | 6 | 100.22 | 601.32 | 709.56 | 601.29 | 709.52 | 0.03 | 601.32 | 709.52 | ZMAT | 2025-01-20 | 2025-03-20
RE/0066-SGE-SF-AD -01 | House Keeping Expenses | 2010 |  | 2010 | SMARTWORLD THE EDITION | Updater Services limited | 9110000199 | 340 |  |  | 2023-07-18 | BIO URINAL SCREEN 1770 | NO | 12 | 144.9 | 1738.8 | 2051.78 | 1738.81 | 2051.8 | 0.01 | 1738.8 | 2051.8 | ZMAT | 2025-01-20 | 2025-03-20
RE/0066-SGE-SF-AD -01 | House Keeping Expenses | 2010 |  | 2010 | SMARTWORLD THE EDITION | Updater Services limited | 9110000199 | 350 |  |  | 2023-07-18 | SQUEZE GLASS CLEANER RUBBER 1770 | NO | 4 | 265.65 | 1062.6 | 1253.87 | 1062.54 | 1253.8 | 0.06 | 1062.6 | 1253.8 | ZMAT | 2025-01-20 | 2025-03-20
RE/0066-SGE-SF-AD -01 | House Keeping Expenses | 2010 |  | 2010 | SMARTWORLD THE EDITION | Updater Services limited | 9110000199 | 360 |  |  | 2023-07-18 | HIT SPRAY (M) RED 200ML 1770 | NO | 5 | 102.64 | 513.2 | 605.58 | 513.22 | 605.6 | 0.02 | 513.2 | 605.6 | ZMAT | 2025-01-20 | 2025-03-20
RE/0066-SGE-SF-AD -01 | House Keeping Expenses | 2010 |  | 2010 | SMARTWORLD THE EDITION | Updater Services limited | 9110000199 | 370 |  |  | 2023-07-18 | BIO URINAL SCREEN | NO | 8 | 144.9 | 1159.2 | 1367.86 | 0 | 0 | 1159.2 | 0 | 0 | ZMAT | 2025-01-20 | 2025-03-20
RE/0066-SGE-SF-AD -01 | House Keeping Expenses | 2010 |  | 2010 | SMARTWORLD THE EDITION | Updater Services limited | 9110000199 | 380 |  |  | 2023-07-18 | Urinal Cubes | NO | 5 | 84 | 420 | 495.6 | 0 | 0 | 420 | 0 | 0 | ZMAT | 2025-01-20 | 2025-03-20
RE/0066-SGE-SF-AD -01 | House Keeping Expenses | 2010 |  | 2010 | SMARTWORLD THE EDITION | Updater Services limited | 9110000199 | 390 |  |  | 2023-07-18 | MICRO FIBER CLOTH Blue | NO | 4 | 144.9 | 579.6 | 608.58 | 0 | 0 | 579.6 | 0 | 0 | ZMAT | 2025-01-20 | 2025-03-20
RE/0066-SGE-SF-AD -01 | House Keeping Expenses | 2010 |  | 2010 | SMARTWORLD THE EDITION | Updater Services limited | 9110000199 | 400 |  |  | 2023-07-18 | MICRO FIBER CLOTH Yellow | NO | 4 | 144.9 | 579.6 | 608.58 | 0 | 0 | 579.6 | 0 | 0 | ZMAT | 2025-01-20 | 2025-03-20
RE/0066-SGE-SF-AD -01 | House Keeping Expenses | 2010 |  | 2010 | SMARTWORLD THE EDITION | Updater Services limited | 9110000199 | 410 |  |  | 2023-07-18 | CHECK DUSTER MEDIUM 20X20 (BLUE) | NO | 8 | 23.1 | 184.8 | 194.04 | 0 | 0 | 184.8 | 0 | 0 | ZMAT | 2025-01-20 | 2025-03-20
RE/0066-SGE-SF-AD -01 | House Keeping Expenses | 2010 |  | 2010 | SMARTWORLD THE EDITION | Updater Services limited | 9110000199 | 420 |  |  | 2023-07-18 | PATTI PLATE | NO | 10 | 15.75 | 157.5 | 185.85 | 0 | 0 | 157.5 | 0 | 0 | ZMAT | 2025-01-20 | 2025-03-20
RE/0066-SGE-SF-AD -01 | House Keeping Expenses | 2010 |  | 2010 | SMARTWORLD THE EDITION | Updater Services limited | 9110000199 | 430 |  |  | 2023-07-18 | RUBBER GLOVES RED | NO | 5 | 54.34 | 271.7 | 320.61 | 0 | 0 | 271.7 | 0 | 0 | ZMAT | 2025-01-20 | 2025-03-20
RE/0066-SGE-SF-AD -01 | House Keeping Expenses | 2010 |  | 2010 | SMARTWORLD THE EDITION | Updater Services limited | 9110000199 | 440 |  |  | 2023-07-18 | TOILET ROUND BRUSH NYLON | NO | 2 | 54.34 | 108.68 | 128.24 | 0 | 0 | 108.68 | 0 | 0 | ZMAT | 2025-01-20 | 2025-03-20
RE/0066-SGE-SF-AD -01 | House Keeping Expenses | 2010 |  | 2010 | SMARTWORLD THE EDITION | Updater Services limited | 9110000199 | 450 |  |  | 2023-07-18 | VIM BAR 200 GMS | NO | 2 | 26.57 | 53.14 | 62.71 | 0 | 0 | 53.14 | 0 | 0 | ZMAT | 2025-01-20 | 2025-03-20
RE/0066-SGE-SF-AD -01 | House Keeping Expenses | 2010 |  | 2010 | SMARTWORLD THE EDITION | Updater Services limited | 9110000199 | 460 |  |  | 2023-07-18 | ODONIL 50 GMS | NO | 15 | 42.26 | 633.9 | 748 | 0 | 0 | 633.9 | 0 | 0 | ZMAT | 2025-01-20 | 2025-03-20
RE/0066-SGE-SF-AD -01 | House Keeping Expenses | 2010 |  | 2010 | SMARTWORLD THE EDITION | Updater Services limited | 9110000199 | 470 |  |  | 2023-07-18 | GLASS CLEANING SCRAPPER | NO | 3 | 392.44 | 1177.32 | 1389.24 | 0 | 0 | 1177.32 | 0 | 0 | ZMAT | 2025-01-20 | 2025-03-20
RE/0066-SGE-SF-AD -01 | House Keeping Expenses | 2010 |  | 2010 | SMARTWORLD THE EDITION | Updater Services limited | 9110000199 | 480 |  |  | 2023-07-18 | SCOTCH BRIGHT 3M | NO | 4 | 27.77 | 111.08 | 131.07 | 0 | 0 | 111.08 | 0 | 0 | ZMAT | 2025-01-20 | 2025-03-20
RE/0066-SGE-SF-AD -01 | House Keeping Expenses | 2010 |  | 2010 | SMARTWORLD THE EDITION | Updater Services limited | 9110000199 | 490 |  |  | 2023-07-18 | GLASS SCRAPER BLADE | NO | 1 | 784.88 | 784.88 | 926.16 | 0 | 0 | 784.88 | 0 | 0 | ZMAT | 2025-01-20 | 2025-03-20
RE/0066-SGE-SF-AD -01 | House Keeping Expenses | 2010 |  | 2010 | SMARTWORLD THE EDITION | Updater Services limited | 9110000199 | 500 |  |  | 2023-07-18 | HARD BROOM (BIG) | NO | 10 | 54.34 | 543.4 | 543.4 | 0 | 0 | 543.4 | 0 | 0 | ZMAT | 2025-01-20 | 2025-03-20
RE/0066-SGE-SF-AD -01 | House Keeping Expenses | 2010 |  | 2010 | SMARTWORLD THE EDITION | Updater Services limited | 9110000199 | 510 |  |  | 2023-07-18 | Toilet Pump | NO | 2 | 54.34 | 108.68 | 128.24 | 0 | 0 | 108.68 | 0 | 0 | ZMAT | 2025-01-20 | 2025-03-20
RE/0066-SGE-SF-AD -01 | House Keeping Expenses | 2010 |  | 2010 | SMARTWORLD THE EDITION | Updater Services limited | 9110000199 | 520 |  |  | 2023-07-18 | CARPET BRUSH | NO | 2 | 60.38 | 120.76 | 142.5 | 0 | 0 | 120.76 | 0 | 0 | ZMAT | 2025-01-20 | 2025-03-20
RE/0066-SGE-SF-AD -01 | House Keeping Expenses | 2010 |  | 2010 | SMARTWORLD THE EDITION | Updater Services limited | 9110000199 | 530 |  |  | 2023-07-18 | FEM HAND WASH 5 LITS | NO | 2 | 760.73 | 1521.46 | 1795.32 | 0 | 0 | 1521.46 | 0 | 0 | ZMAT | 2025-01-20 | 2025-03-20
RE/0066-SGE-SF-AD -01 | House Keeping Expenses | 2010 |  | 2010 | SMARTWORLD THE EDITION | Updater Services limited | 9110000199 | 540 |  |  | 2023-07-18 | NAPTHOLIN BALLS (1 KG) | NO | 1 | 217.35 | 217.35 | 256.47 | 0 | 0 | 217.35 | 0 | 0 | ZMAT | 2025-01-20 | 2025-03-20
RE/0066-SGE-SF-AD -01 | House Keeping Expenses | 2010 |  | 2010 | SMARTWORLD THE EDITION | Updater Services limited | 9110000199 | 550 |  |  | 2023-07-18 | ROOM FRESHNER-PREMIUM VENNILA | NO | 8 | 132.83 | 1062.64 | 1253.92 | 0 | 0 | 1062.64 | 0 | 0 | ZMAT | 2025-01-20 | 2025-03-20
RE/0066-SGE-SF-AD -01 | House Keeping Expenses | 2010 |  | 2010 | SMARTWORLD THE EDITION | Updater Services limited | 9110000199 | 560 |  |  | 2023-07-18 | DISPOSABLE BAG SMALL BLACK | NO | 5 | 114.71 | 573.55 | 676.79 | 0 | 0 | 573.55 | 0 | 0 | ZMAT | 2025-01-20 | 2025-03-20
RE/0066-SGE-SF-AD -01 | House Keeping Expenses | 2010 |  | 2010 | SMARTWORLD THE EDITION | Updater Services limited | 9110000199 | 570 |  |  | 2023-07-18 | DISPOSABLE BAG BIG BLACK (45-50) | NO | 15 | 114.71 | 1720.65 | 2030.37 | 0 | 0 | 1720.65 | 0 | 0 | ZMAT | 2025-01-20 | 2025-03-20
RE/0066-SGE-SF-AD -01 | House Keeping Expenses | 2010 |  | 2010 | SMARTWORLD THE EDITION | Updater Services limited | 9110000199 | 580 |  |  | 2023-07-18 | FLOOR CLEANING CLOTH MEDIUM | NO | 18 | 35.02 | 630.36 | 661.88 | 0 | 0 | 630.36 | 0 | 0 | ZMAT | 2025-01-20 | 2025-03-20
RE/0066-SGE-SF-AD -01 | House Keeping Expenses | 2010 |  | 2010 | SMARTWORLD THE EDITION | Updater Services limited | 9110000199 | 590 |  |  | 2023-07-18 | PRILL 425 ML | NO | 2 | 99.02 | 198.04 | 233.69 | 0 | 0 | 198.04 | 0 | 0 | ZMAT | 2025-01-20 | 2025-03-20
RE/0066-SGE-SF-AD -01 | House Keeping Expenses | 2010 |  | 2010 | SMARTWORLD THE EDITION | Updater Services limited | 9110000199 | 600 |  |  | 2023-07-18 | SOFTBROOM BIG PIPE | NO | 4 | 108.68 | 434.72 | 434.72 | 0 | 0 | 434.72 | 0 | 0 | ZMAT | 2025-01-20 | 2025-03-20
RE/0066-SGE-SF-AD -01 | House Keeping Expenses | 2010 |  | 2010 | SMARTWORLD THE EDITION | Updater Services limited | 9110000199 | 610 |  |  | 2023-07-18 | TASKI - R2 | NO | 5 | 236.25 | 1181.25 | 1393.88 | 0 | 0 | 1181.25 | 0 | 0 | ZMAT | 2025-01-20 | 2025-03-20
RE/0066-SGE-SF-AD -01 | House Keeping Expenses | 2010 |  | 2010 | SMARTWORLD THE EDITION | Updater Services limited | 9110000199 | 620 |  |  | 2023-07-18 | TASKI - R3 | NO | 5 | 315 | 1575 | 1858.5 | 0 | 0 | 1575 | 0 | 0 | ZMAT | 2025-01-20 | 2025-03-20
RE/0066-SGE-SF-AD -01 | House Keeping Expenses | 2010 |  | 2010 | SMARTWORLD THE EDITION | Updater Services limited | 9110000199 | 630 |  |  | 2023-07-18 | TASKI - R5 | NO | 5 | 236.25 | 1181.25 | 1393.88 | 0 | 0 | 1181.25 | 0 | 0 | ZMAT | 2025-01-20 | 2025-03-20
RE/0066-SGE-SF-AD -01 | House Keeping Expenses | 2010 |  | 2010 | SMARTWORLD THE EDITION | Updater Services limited | 9110000199 | 640 |  |  | 2023-07-18 | TASKI - R6 | NO | 10 | 168 | 1680 | 1982.4 | 0 | 0 | 1680 | 0 | 0 | ZMAT | 2025-01-20 | 2025-03-20
RE/0066-SGE-SF-AD -01 | House Keeping Expenses | 2010 |  | 2010 | SMARTWORLD THE EDITION | Updater Services limited | 9110000199 | 650 |  |  | 2023-07-18 | WHITE PHENYLE CANE 5 LTR CLEANO 1781 | NO | 2 | 120.75 | 241.5 | 284.97 | 241.44 | 284.9 | 0.06 | 241.5 | 284.9 | ZMAT | 2025-01-20 | 2025-03-20
RE/0066-SGE-SF-AD -01 | House Keeping Expenses | 2010 |  | 2010 | SMARTWORLD THE EDITION | Updater Services limited | 9110000199 | 660 |  |  | 2023-07-18 | BIO URINAL SCREEN 1781 | NO | 12 | 126 | 1512 | 1784.16 | 1512.03 | 1784.2 | 0.03 | 1512 | 1784.2 | ZMAT | 2025-01-20 | 2025-03-20
RE/0066-SGE-SF-AD -01 | House Keeping Expenses | 2010 |  | 2010 | SMARTWORLD THE EDITION | Updater Services limited | 9110000199 | 670 |  |  | 2023-07-18 | Trinal Urinal Cubes 400gms 1781 | NO | 5 | 84 | 420 | 495.6 | 420 | 495.6 | 0 | 420 | 495.6 | ZMAT | 2025-01-20 | 2025-03-20
RE/0066-SGE-SF-AD -01 | House Keeping Expenses | 2010 |  | 2010 | SMARTWORLD THE EDITION | Updater Services limited | 9110000199 | 680 |  |  | 2023-07-18 | MICRO FIBER CLOTH Blue & Yellow 1781 | NO | 5 | 126 | 630 | 661.5 | 630.1 | 661.6 | 0.1 | 630 | 661.6 | ZMAT | 2025-01-20 | 2025-03-20
RE/0066-SGE-SF-AD -01 | House Keeping Expenses | 2010 |  | 2010 | SMARTWORLD THE EDITION | Updater Services limited | 9110000199 | 690 |  |  | 2023-07-18 | CHECK DUSTER MEDIUM 20X20 1781 | NO | 12 | 14.7 | 176.4 | 185.22 | 176.38 | 185.2 | 0.02 | 176.4 | 185.2 | ZMAT | 2025-01-20 | 2025-03-20
RE/0066-SGE-SF-AD -01 | House Keeping Expenses | 2010 |  | 2010 | SMARTWORLD THE EDITION | Updater Services limited | 9110000199 | 700 |  |  | 2023-07-18 | YELLOW DUSTER LARGE 1781 | NO | 12 | 21 | 252 | 264.6 | 252 | 264.6 | 0 | 252 | 264.6 | ZMAT | 2025-01-20 | 2025-03-20
RE/0066-SGE-SF-AD -01 | House Keeping Expenses | 2010 |  | 2010 | SMARTWORLD THE EDITION | Updater Services limited | 9110000199 | 710 |  |  | 2023-07-18 | COLIN 500 ML 1781 | NO | 3 | 71.4 | 214.2 | 252.76 | 214.24 | 252.8 | 0.04 | 214.2 | 252.8 | ZMAT | 2025-01-20 | 2025-03-20
RE/0066-SGE-SF-AD -01 | House Keeping Expenses | 2010 |  | 2010 | SMARTWORLD THE EDITION | Updater Services limited | 9110000199 | 720 |  |  | 2023-07-18 | DUST PAN IPS 1781 | NO | 5 | 21 | 105 | 123.9 | 105.08 | 124 | 0.08 | 105 | 124 | ZMAT | 2025-01-20 | 2025-03-20
RE/0066-SGE-SF-AD -01 | House Keeping Expenses | 2010 |  | 2010 | SMARTWORLD THE EDITION | Updater Services limited | 9110000199 | 730 |  |  | 2023-07-18 | RUBBER GLOVES RED & BLUE 1781 | NO | 5 | 47.25 | 236.25 | 278.78 | 236.31 | 278.85 | 0.06 | 236.25 | 278.85 | ZMAT | 2025-01-20 | 2025-03-20
RE/0066-SGE-SF-AD -01 | House Keeping Expenses | 2010 |  | 2010 | SMARTWORLD THE EDITION | Updater Services limited | 9110000199 | 740 |  |  | 2023-07-18 | SPONGE 1781 | NO | 5 | 15.75 | 78.75 | 92.93 | 78.77 | 92.95 | 0.02 | 78.75 | 92.95 | ZMAT | 2025-01-20 | 2025-03-20
RE/0066-SGE-SF-AD -01 | House Keeping Expenses | 2010 |  | 2010 | SMARTWORLD THE EDITION | Updater Services limited | 9110000199 | 750 |  |  | 2023-07-18 | VIM BAR 200 GMS 1781 | NO | 10 | 23.1 | 231 | 272.58 | 231.02 | 272.6 | 0.02 | 231 | 272.6 | ZMAT | 2025-01-20 | 2025-03-20
RE/0066-SGE-SF-AD -01 | House Keeping Expenses | 2010 |  | 2010 | SMARTWORLD THE EDITION | Updater Services limited | 9110000199 | 760 |  |  | 2023-07-18 | DRAINEX 1781 | NO | 5 | 23.1 | 115.5 | 136.29 | 115.51 | 136.3 | 0.01 | 115.5 | 136.3 | ZMAT | 2025-01-20 | 2025-03-20
RE/0066-SGE-SF-AD -01 | House Keeping Expenses | 2010 |  | 2010 | SMARTWORLD THE EDITION | Updater Services limited | 9110000199 | 770 |  |  | 2023-07-18 | ODONIL 50 GMS 1781 | NO | 50 | 36.75 | 1837.5 | 2168.25 | 1837.54 | 2168.3 | 0.04 | 1837.5 | 2168.3 | ZMAT | 2025-01-20 | 2025-03-20
RE/0066-SGE-SF-AD -01 | House Keeping Expenses | 2010 |  | 2010 | SMARTWORLD THE EDITION | Updater Services limited | 9110000199 | 780 |  |  | 2023-07-18 | SCOTCH BRIGHT 3M 1781 | NO | 12 | 24.15 | 289.8 | 341.96 | 289.83 | 342 | 0.03 | 289.8 | 342 | ZMAT | 2025-01-20 | 2025-03-20
RE/0066-SGE-SF-AD -01 | House Keeping Expenses | 2010 |  | 2010 | SMARTWORLD THE EDITION | Updater Services limited | 9110000199 | 790 |  |  | 2023-07-18 | HARD BROOM (BIG) 1781 | NO | 10 | 47.25 | 472.5 | 472.5 | 472.5 | 472.5 | 0 | 472.5 | 472.5 | ZMAT | 2025-01-20 | 2025-03-20
RE/0066-SGE-SF-AD -01 | House Keeping Expenses | 2010 |  | 2010 | SMARTWORLD THE EDITION | Updater Services limited | 9110000199 | 800 |  |  | 2023-07-18 | NIRMA POWDER 1KG 1781 | NO | 1 | 42 | 42 | 49.56 | 42.03 | 49.6 | 0.03 | 42 | 49.6 | ZMAT | 2025-01-20 | 2025-03-20
RE/0066-SGE-SF-AD -01 | House Keeping Expenses | 2010 |  | 2010 | SMARTWORLD THE EDITION | Updater Services limited | 9110000199 | 810 |  |  | 2023-07-18 | Shoe Polish Cherry 40 gm 1781 | NO | 2 | 52.5 | 105 | 123.9 | 105.08 | 124 | 0.08 | 105 | 124 | ZMAT | 2025-01-20 | 2025-03-20
RE/0066-SGE-SF-AD -01 | House Keeping Expenses | 2010 |  | 2010 | SMARTWORLD THE EDITION | Updater Services limited | 9110000199 | 820 |  |  | 2023-07-18 | NAPTHLIN BALLS METROPOL ( 200 GRM ) 178 | NO | 2 | 63 | 126 | 148.68 | 125.93 | 148.6 | 0.07 | 126 | 148.6 | ZMAT | 2025-01-20 | 2025-03-20
RE/0066-SGE-SF-AD -01 | House Keeping Expenses | 2010 |  | 2010 | SMARTWORLD THE EDITION | Updater Services limited | 9110000199 | 830 |  |  | 2023-07-18 | ROOM FRESHNER-PREMIUM 1781 | NO | 15 | 115.5 | 1732.5 | 2044.35 | 1732.46 | 2044.3 | 0.04 | 1732.5 | 2044.3 | ZMAT | 2025-01-20 | 2025-03-20
RE/0066-SGE-SF-AD -01 | House Keeping Expenses | 2010 |  | 2010 | SMARTWORLD THE EDITION | Updater Services limited | 9110000199 | 840 |  |  | 2023-07-18 | DISPOSABLE BAG SMALL BLACK 1781 | NO | 10 | 99.75 | 997.5 | 1177.05 | 997.54 | 1177.1 | 0.04 | 997.5 | 1177.1 | ZMAT | 2025-01-20 | 2025-03-20
RE/0066-SGE-SF-AD -01 | House Keeping Expenses | 2010 |  | 2010 | SMARTWORLD THE EDITION | Updater Services limited | 9110000199 | 850 |  |  | 2023-07-18 | DISPOSABLE BAG BIG BLACK (45-50) 1781 | NO | 15 | 99.75 | 1496.25 | 1765.58 | 1496.31 | 1765.65 | 0.06 | 1496.25 | 1765.65 | ZMAT | 2025-01-20 | 2025-03-20
RE/0066-SGE-SF-AD -01 | House Keeping Expenses | 2010 |  | 2010 | SMARTWORLD THE EDITION | Updater Services limited | 9110000199 | 860 |  |  | 2023-07-18 | FLOOR CLEANING CLOTH MEDIUM 1781 | NO | 24 | 21 | 504 | 529.2 | 504 | 529.2 | 0 | 504 | 529.2 | ZMAT | 2025-01-20 | 2025-03-20
RE/0066-SGE-SF-AD -01 | House Keeping Expenses | 2010 |  | 2010 | SMARTWORLD THE EDITION | Updater Services limited | 9110000199 | 870 |  |  | 2023-07-18 | FEM HAND WASH 5 LITS 1781 | NO | 1 | 661.5 | 661.5 | 780.57 | 661.44 | 780.5 | 0.06 | 661.5 | 780.5 | ZMAT | 2025-01-20 | 2025-03-20
RE/0066-SGE-SF-AD -01 | House Keeping Expenses | 2010 |  | 2010 | SMARTWORLD THE EDITION | Updater Services limited | 9110000199 | 880 |  |  | 2023-07-18 | PRILL 425 ML 1781 | NO | 4 | 86.1 | 344.4 | 406.39 | 344.41 | 406.4 | 0.01 | 344.4 | 406.4 | ZMAT | 2025-01-20 | 2025-03-20
RE/0066-SGE-SF-AD -01 | House Keeping Expenses | 2010 |  | 2010 | SMARTWORLD THE EDITION | Updater Services limited | 9110000199 | 890 |  |  | 2023-07-18 | SOFTBROOM BIG PIPE 1781 | NO | 2 | 94.5 | 189 | 189 | 189 | 189 | 0 | 189 | 189 | ZMAT | 2025-01-20 | 2025-03-20
RE/0066-SGE-SF-AD -01 | House Keeping Expenses | 2010 |  | 2010 | SMARTWORLD THE EDITION | Updater Services limited | 9110000199 | 900 |  |  | 2023-07-18 | TASKI - D7 1781 | NO | 5 | 309.26 | 1546.3 | 1824.63 | 1546.36 | 1824.7 | 0.06 | 1546.3 | 1824.7 | ZMAT | 2025-01-20 | 2025-03-20
RE/0066-SGE-SF-AD -01 | House Keeping Expenses | 2010 |  | 2010 | SMARTWORLD THE EDITION | Updater Services limited | 9110000199 | 910 |  |  | 2023-07-18 | TASKI - R1 1781 | NO | 5 | 233.53 | 1167.65 | 1377.83 | 1167.67 | 1377.85 | 0.02 | 1167.65 | 1377.85 | ZMAT | 2025-01-20 | 2025-03-20
RE/0066-SGE-SF-AD -01 | House Keeping Expenses | 2010 |  | 2010 | SMARTWORLD THE EDITION | Updater Services limited | 9110000199 | 920 |  |  | 2023-07-18 | TASKI - R2 1781 | NO | 5 | 202.62 | 1013.1 | 1195.46 | 1013.14 | 1195.5 | 0.04 | 1013.1 | 1195.5 | ZMAT | 2025-01-20 | 2025-03-20
RE/0066-SGE-SF-AD -01 | House Keeping Expenses | 2010 |  | 2010 | SMARTWORLD THE EDITION | Updater Services limited | 9110000199 | 930 |  |  | 2023-07-18 | TASKI - R5 1781 | NO | 10 | 204.06 | 2040.6 | 2407.91 | 2040.68 | 2408 | 0.08 | 2040.6 | 2408 | ZMAT | 2025-01-20 | 2025-03-20
RE/0066-SGE-SF-AD -01 | House Keeping Expenses | 2010 |  | 2010 | SMARTWORLD THE EDITION | Updater Services limited | 9110000199 | 940 |  |  | 2023-07-18 | TASKI - R6 1781 | NO | 10 | 145.31 | 1453.1 | 1714.66 | 1453.14 | 1714.7 | 0.04 | 1453.1 | 1714.7 | ZMAT | 2025-01-20 | 2025-03-20
RE/0066-SGE-SF-AD -01 | House Keeping Expenses | 2010 |  | 2010 | SMARTWORLD THE EDITION | Updater Services limited | 9110000199 | 950 |  |  | 2023-07-18 | SQUEZE GLASS CLEANER RUBBER 1781 | NO | 2 | 265.65 | 531.3 | 626.93 | 531.27 | 626.9 | 0.03 | 531.3 | 626.9 | ZMAT | 2025-01-20 | 2025-03-20
RE/0066-SGE-SF-AD -01 | House Keeping Expenses | 2010 |  | 2010 | SMARTWORLD THE EDITION | Updater Services limited | 9110000199 | 960 |  |  | 2023-07-18 | PHYENYLE WHITE 1 LTR 1767 | NO | 5 | 27.77 | 138.85 | 163.84 | 138.86 | 163.85 | 0.01 | 138.85 | 163.85 | ZMAT | 2025-01-20 | 2025-03-20
RE/0066-SGE-SF-AD -01 | House Keeping Expenses | 2010 |  | 2010 | SMARTWORLD THE EDITION | Updater Services limited | 9110000199 | 970 |  |  | 2023-07-18 | BIO URINAL SCREEN 1767 | NO | 6 | 144.9 | 869.4 | 1025.89 | 869.49 | 1026 | 0.09 | 869.4 | 1026 | ZMAT | 2025-01-20 | 2025-03-20
RE/0066-SGE-SF-AD -01 | House Keeping Expenses | 2010 |  | 2010 | SMARTWORLD THE EDITION | Updater Services limited | 9110000199 | 980 |  |  | 2023-07-18 | Urinal Cubes 1767 | NO | 5 | 72.45 | 362.25 | 427.46 | 362.25 | 427.45 | 0 | 362.03 | 427.23 | ZMAT | 2025-01-20 | 2025-03-20
RE/0066-SGE-SF-AD -01 | House Keeping Expenses | 2010 |  | 2010 | SMARTWORLD THE EDITION | Updater Services limited | 9110000199 | 990 |  |  | 2023-07-18 | MICRO FIBER CLOTH Blue 1767 | NO | 5 | 144.9 | 724.5 | 760.73 | 724.48 | 760.7 | 0.02 | 724.5 | 760.7 | ZMAT | 2025-01-20 | 2025-03-20
RE/0066-SGE-SF-AD -01 | House Keeping Expenses | 2010 |  | 2010 | SMARTWORLD THE EDITION | Updater Services limited | 9110000199 | 1000 |  |  | 2023-07-18 | CHECK DUSTER MEDIUM 20X20 (BLUE) 1767 | NO | 12 | 23.1 | 277.2 | 291.06 | 277.14 | 291 | 0.06 | 277.2 | 291 | ZMAT | 2025-01-20 | 2025-03-20
RE/0066-SGE-SF-AD -01 | House Keeping Expenses | 2010 |  | 2010 | SMARTWORLD THE EDITION | Updater Services limited | 9110000199 | 1010 |  |  | 2023-07-18 | FEATHER BRUSH 1767 | NO | 2 | 73.5 | 147 | 173.46 | 146.95 | 173.4 | 0.05 | 147 | 173.4 | ZMAT | 2025-01-20 | 2025-03-20
RE/0066-SGE-SF-AD -01 | House Keeping Expenses | 2010 |  | 2010 | SMARTWORLD THE EDITION | Updater Services limited | 9110000199 | 1020 |  |  | 2023-07-18 | COLIN 500 ML 1767 | NO | 4 | 100.8 | 403.2 | 475.78 | 403.22 | 475.8 | 0.02 | 403.2 | 475.8 | ZMAT | 2025-01-20 | 2025-03-20
RE/0066-SGE-SF-AD -01 | House Keeping Expenses | 2010 |  | 2010 | SMARTWORLD THE EDITION | Updater Services limited | 9110000199 | 1030 |  |  | 2023-07-18 | NYLON SCRUBBER 1767 | NO | 2 | 18.9 | 37.8 | 44.6 | 37.8 | 44.6 | 0 | 37.8 | 44.6 | ZMAT | 2025-01-20 | 2025-03-20
RE/0066-SGE-SF-AD -01 | House Keeping Expenses | 2010 |  | 2010 | SMARTWORLD THE EDITION | Updater Services limited | 9110000199 | 1040 |  |  | 2023-07-18 | ODONIL 75 GMS 1767 | NO | 25 | 71.4 | 1785 | 2106.3 | 1785.08 | 2106.4 | 0.08 | 1785 | 2106.4 | ZMAT | 2025-01-20 | 2025-03-20
RE/0066-SGE-SF-AD -01 | House Keeping Expenses | 2010 |  | 2010 | SMARTWORLD THE EDITION | Updater Services limited | 9110000199 | 1050 |  |  | 2023-07-18 | RUBBER GLOVES RED 1767 | NO | 4 | 54.34 | 217.36 | 256.48 | 217.42 | 256.56 | 0.06 | 217.36 | 256.56 | ZMAT | 2025-01-20 | 2025-03-20
RE/0066-SGE-SF-AD -01 | House Keeping Expenses | 2010 |  | 2010 | SMARTWORLD THE EDITION | Updater Services limited | 9110000199 | 1060 |  |  | 2023-07-18 | VIM BAR 145 GM 1767 | NO | 10 | 15.75 | 157.5 | 185.85 | 157.54 | 185.9 | 0.04 | 157.5 | 185.9 | ZMAT | 2025-01-20 | 2025-03-20
RE/0066-SGE-SF-AD -01 | House Keeping Expenses | 2010 |  | 2010 | SMARTWORLD THE EDITION | Updater Services limited | 9110000199 | 1070 |  |  | 2023-07-18 | SCOTCH BRIGHT 3M 1767 | NO | 12 | 27.77 | 333.24 | 393.22 | 333.25 | 393.24 | 0.01 | 333.24 | 393.24 | ZMAT | 2025-01-20 | 2025-03-20
RE/0066-SGE-SF-AD -01 | House Keeping Expenses | 2010 |  | 2010 | SMARTWORLD THE EDITION | Updater Services limited | 9110000199 | 1080 |  |  | 2023-07-18 | HARD BROOM (BIG) 1767 | NO | 6 | 54.34 | 326.04 | 326.04 | 326.04 | 326.04 | 0 | 326.04 | 326.04 | ZMAT | 2025-01-20 | 2025-03-20
RE/0066-SGE-SF-AD -01 | House Keeping Expenses | 2010 |  | 2010 | SMARTWORLD THE EDITION | Updater Services limited | 9110000199 | 1090 |  |  | 2023-07-18 | FEM HAND WASH 5 LITS 1767 | NO | 1 | 760.73 | 760.73 | 897.66 | 760.79 | 897.73 | 0.06 | 760.73 | 897.73 | ZMAT | 2025-01-20 | 2025-03-20
RE/0066-SGE-SF-AD -01 | House Keeping Expenses | 2010 |  | 2010 | SMARTWORLD THE EDITION | Updater Services limited | 9110000199 | 1100 |  |  | 2023-07-18 | Nepthelene Ball ( M ) (Superior ) White | NO | 4 | 144.9 | 579.6 | 683.93 | 579.66 | 684 | 0.06 | 579.6 | 684 | ZMAT | 2025-01-20 | 2025-03-20
RE/0066-SGE-SF-AD -01 | House Keeping Expenses | 2010 |  | 2010 | SMARTWORLD THE EDITION | Updater Services limited | 9110000199 | 1110 |  |  | 2023-07-18 | WIPER MEDIUM 1767 | NO | 3 | 144.9 | 434.7 | 512.95 | 434.66 | 512.9 | 0.04 | 434.7 | 512.9 | ZMAT | 2025-01-20 | 2025-03-20
RE/0066-SGE-SF-AD -01 | House Keeping Expenses | 2010 |  | 2010 | SMARTWORLD THE EDITION | Updater Services limited | 9110000199 | 1120 |  |  | 2023-07-18 | DUST CONTROL BLUE RIFFIL 1767 | NO | 2 | 217.35 | 434.7 | 512.95 | 434.66 | 512.9 | 0.04 | 434.7 | 512.9 | ZMAT | 2025-01-20 | 2025-03-20
RE/0066-SGE-SF-AD -01 | House Keeping Expenses | 2010 |  | 2010 | SMARTWORLD THE EDITION | Updater Services limited | 9110000199 | 1130 |  |  | 2023-07-18 | ROOM FRESHNER-PREMIUM VENNILA 1767 | NO | 10 | 132.83 | 1328.3 | 1567.39 | 1328.39 | 1567.5 | 0.09 | 1328.3 | 1567.5 | ZMAT | 2025-01-20 | 2025-03-20
RE/0066-SGE-SF-AD -01 | House Keeping Expenses | 2010 |  | 2010 | SMARTWORLD THE EDITION | Updater Services limited | 9110000199 | 1140 |  |  | 2023-07-18 | DISPOSABLE BAG SMALL BLACK 1767 | NO | 10 | 114.71 | 1147.1 | 1353.58 | 1147.03 | 1353.5 | 0.07 | 1147.1 | 1353.5 | ZMAT | 2025-01-20 | 2025-03-20
RE/0066-SGE-SF-AD -01 | House Keeping Expenses | 2010 |  | 2010 | SMARTWORLD THE EDITION | Updater Services limited | 9110000199 | 1150 |  |  | 2023-07-18 | DISPOSABLE BAG BIG BLACK (45-50) 1767 | NO | 15 | 114.71 | 1720.65 | 2030.37 | 1720.72 | 2030.45 | 0.07 | 1720.65 | 2030.45 | ZMAT | 2025-01-20 | 2025-03-20
RE/0066-SGE-SF-AD -01 | House Keeping Expenses | 2010 |  | 2010 | SMARTWORLD THE EDITION | Updater Services limited | 9110000199 | 1160 |  |  | 2023-07-18 | FLOOR CLEANING CLOTH MEDIUM 1767 | NO | 24 | 35.02 | 840.48 | 882.5 | 840.46 | 882.48 | 0.02 | 840.48 | 882.48 | ZMAT | 2025-01-20 | 2025-03-20
RE/0066-SGE-SF-AD -01 | House Keeping Expenses | 2010 |  | 2010 | SMARTWORLD THE EDITION | Updater Services limited | 9110000199 | 1170 |  |  | 2023-07-18 | PRILL 425 ML 1767 | NO | 4 | 99.02 | 396.08 | 467.37 | 396.17 | 467.48 | 0.09 | 396.08 | 467.48 | ZMAT | 2025-01-20 | 2025-03-20
RE/0066-SGE-SF-AD -01 | House Keeping Expenses | 2010 |  | 2010 | SMARTWORLD THE EDITION | Updater Services limited | 9110000199 | 1180 |  |  | 2023-07-18 | SOFTBROOM BIG PIPE 1767 | NO | 3 | 108.68 | 326.04 | 326.04 | 326.04 | 326.04 | 0 | 326.04 | 326.04 | ZMAT | 2025-01-20 | 2025-03-20
RE/0066-SGE-SF-AD -01 | House Keeping Expenses | 2010 |  | 2010 | SMARTWORLD THE EDITION | Updater Services limited | 9110000199 | 1190 |  |  | 2023-07-18 | TASKI - R1 1767 | NO | 5 | 270.9 | 1354.5 | 1598.31 | 1354.49 | 1598.3 | 0.01 | 1354.5 | 1598.3 | ZMAT | 2025-01-20 | 2025-03-20
RE/0066-SGE-SF-AD -01 | House Keeping Expenses | 2010 |  | 2010 | SMARTWORLD THE EDITION | Updater Services limited | 9110000199 | 1200 |  |  | 2023-07-18 | TASKI - R2 1767 | NO | 5 | 236.25 | 1181.25 | 1393.88 | 1181.23 | 1393.85 | 0.02 | 1181.25 | 1393.85 | ZMAT | 2025-01-20 | 2025-03-20
RE/0066-SGE-SF-AD -01 | House Keeping Expenses | 2010 |  | 2010 | SMARTWORLD THE EDITION | Updater Services limited | 9110000199 | 1210 |  |  | 2023-07-18 | TASKI - R5 1767 | NO | 5 | 236.25 | 1181.25 | 1393.88 | 1181.23 | 1393.85 | 0.02 | 1181.25 | 1393.85 | ZMAT | 2025-01-20 | 2025-03-20
RE/0066-SGE-SF-AD -01 | House Keeping Expenses | 2010 |  | 2010 | SMARTWORLD THE EDITION | Updater Services limited | 9110000199 | 1220 |  |  | 2023-07-18 | TASKI - R6 1767 | NO | 10 | 168 | 1680 | 1982.4 | 1680 | 1982.4 | 0 | 1680 | 1982.4 | ZMAT | 2025-01-20 | 2025-03-20
RE/0066-SGE-SF-AD -01 | House Keeping Expenses | 2010 |  | 2010 | SMARTWORLD THE EDITION | Updater Services limited | 9110000199 | 1230 |  |  | 2023-07-18 | SQUEZE GLASS CLEANER RUBBER 1767 | NO | 2 | 265.65 | 531.3 | 626.93 | 531.27 | 626.9 | 0.03 | 531.3 | 626.9 | ZMAT | 2025-01-20 | 2025-03-20
RE/0066-SGE-SF-AD -01 | House Keeping Expenses | 2010 |  | 2010 | SMARTWORLD THE EDITION | Updater Services limited | 9110000199 | 1240 |  |  | 2023-07-18 | TASKI - R9 | NO | 5 | 100.22 | 501.1 | 591.3 | 0 | 0 | 501.1 | 0 | 0 | ZMAT | 2025-01-20 | 2025-03-20
RE/0066-SGE-SF-AD -01 | House Keeping Expenses | 2010 |  | 2010 | SMARTWORLD THE EDITION | Updater Services limited | 9110000199 | 1250 |  |  | 2023-07-18 | HIT SPRAY (M) BLACK/ 200ML | NO | 3 | 100.22 | 300.66 | 354.78 | 0 | 0 | 300.66 | 0 | 0 | ZMAT | 2025-01-20 | 2025-03-20
RE/0066-SGE-SF-AD -01 | House Keeping Expenses | 2010 |  | 2010 | SMARTWORLD THE EDITION | Updater Services limited | 9110000199 | 1260 |  |  | 2023-07-18 | HIT SPRAY (M) BLACK/ 200ML | NO | 1 | 167566.47 | 167566.47 | 167566.47 | 0 | 0 | 167566.47 | 0 | 0 | ZMAT | 2025-01-20 | 2025-03-20
RE/0066-SGE-SF-AD -01 | House Keeping Expenses | 2010 |  | 2010 | SMARTWORLD THE EDITION | Merino International | 9110000382 | 10 |  |  | 2024-02-14 | shoes cover for sample flat | PC | 100 | 430 | 43000 | 50740 | 43000 | 50740 | 0 | 43000 | 50740 | ZMAT | 2025-01-20 | 2025-03-20
RE/0066-SGE-SF-AD -01 | House Keeping Expenses | 2010 |  | 2010 | SMARTWORLD THE EDITION | Merino International | 9110000382 | 20 |  |  | 2024-02-14 | Delivery charge | PC | 1 | 1500 | 1500 | 1770 | 1500 | 1770 | 0 | 1500 | 1770 | ZMAT | 2025-01-20 | 2025-03-20
RE/0066-SGE-SF-AD -01 | House Keeping Expenses | 2010 |  | 2010 | Sales Gallery-62 | Deskbasket office SuppliesVandana | 9110000562 | 10 |  |  | 2024-05-29 | ALLOUT REFILL WITH MACHINE 1770 | NO | 10 | 1.5 | 15 | 17.7 | 0 | 0 | 15 | 0 | 0 | ZMAT | 2024-04-01 | 2025-03-31
RE/0066-SGE-SF-AD -01 | House Keeping Expenses | 2010 |  | 2010 | SMARTWORLD THE EDITION | Yadav Pest Control ServiceYogendra Yadav | 9160000205 | 10 |  |  | 2023-07-06 | Pest Control Service | AU | 1 | 68250 | 68250 | 80535 | 68250 | 80535 | 0 | 68250 | 80535 | ZGEN | 2023-04-01 | 2024-03-31
RE/0066-SGE-SF-AD -01 | House Keeping Expenses | 2010 |  | 2010 | SMARTWORLD THE EDITION | Updater Services limited | 9160000241 | 10 |  |  | 2023-07-18 | MANPOWER (JULY'23 – MARCH’24) | AU | 1 | 2333649.7 | 2333649.7 | 2753706.65 | 2333724.17 | 2753794.52 | 74.47 | 2333647.63 | 2753704.2 | ZGEN | 2023-04-01 | 2024-03-31
RE/0066-SGE-SF-AD -01 | House Keeping Expenses | 2010 |  | 2010 | SMARTWORLD THE EDITION | Updater Services limited | 9160000241 | 20 |  |  | 2023-07-18 | MANPOWER(APRIL'23 – JUNE’23) | AU | 1 | 880983.46 | 880983.46 | 1039560.48 | 881815.76 | 1040542.6 | 832.3 | 880979.21 | 1039555.47 | ZGEN | 2023-04-01 | 2024-03-31
RE/0066-SGE-SF-AD -01 | House Keeping Expenses | 2010 |  | 2010 | SMARTWORLD THE EDITION | Tecknomen Facility Services Pvt. LtDwarka | 9160000268 | 10 |  |  | 2023-07-28 | Support manpower | AU | 1 | 1634304.66 | 1634304.66 | 1928479.5 | 2806078.27 | 3311172.36 | 1171773.61 | 2806072.99 | 3311166.13 | ZGEN | 2023-04-01 | 2024-03-31
RE/0066-SGE-SF-AD -01 | House Keeping Expenses | 2010 |  | 2010 | SMARTWORLD THE EDITION | Landscaperz IndiaVikram | 9160000297 | 20 |  |  | 2023-08-04 | Horticulture Maintenance work for 62 SG | AU | 1 | 296555.37 | 296555.37 | 349935.34 | 296547.46 | 349926 | 7.91 | 296555.75 | 349935.78 | ZGEN | 2023-04-01 | 2024-03-31
RE/0066-SGE-SF-AD -01 | House Keeping Expenses | 2010 |  | 2010 | SMARTWORLD THE EDITION | Updater Services limited | 9160000304 | 20 |  |  | 2023-08-05 | Rider Conveyance | AU | 1 | 45241.01 | 45241.01 | 53384.39 | 45240.78 | 53384.12 | 0.23 | 45241.03 | 53384.41 | ZGEN | 2023-04-01 | 2024-04-01
RE/0066-SGE-SF-AD -01 | House Keeping Expenses | 2010 |  | 2010 | SMARTWORLD THE EDITION | Manone India Private Limited | 9160000532 | 20 |  |  | 2024-01-02 | F&B manpower | AU | 1 | 740957.38 | 740957.38 | 874329.71 | 740896.83 | 874258.26 | 60.55 | 740957.44 | 874329.78 | ZGEN | 2023-10-24 | 2024-03-31
RE/0066-SGE-SF-AD -01 | House Keeping Expenses | 2010 |  | 2010 | SMARTWORLD THE EDITION | Raj Enterprises | 9160000605 | 20 |  |  | 2024-02-05 | Manpower | AU | 1 | 5400 | 5400 | 5670 | 5400 | 5670 | 0 | 5400 | 5670 | ZGEN | 2023-11-16 | 2023-11-16
RE/0066-SGE-SF-AD -02 | Pantry Expenses | 2010 |  | 2010 | SMARTWORLD THE EDITION | SMS CommercialRakesh | 9110000151 | 30 |  |  | 2023-06-17 | 750ML PET PEPSI COLA 24*40MRP | NO | 1600 | 22.86 | 36576 | 51206.4 | 5016.21 | 7022.7 | 31559.79 | 5486.4 | 7681.01 | ZMAT | 2025-01-20 | 2025-03-20
RE/0066-SGE-SF-AD -02 | Pantry Expenses | 2010 |  | 2010 | SMARTWORLD THE EDITION | SMS CommercialRakesh | 9110000151 | 40 |  |  | 2023-06-17 | 750ML PET MIRINDA 24*40MRP | NO | 1506 | 22.86 | 34427.16 | 48198.02 | 5016.18 | 7022.65 | 29410.98 | 5486.4 | 7681.01 | ZMAT | 2025-01-20 | 2025-03-20
RE/0066-SGE-SF-AD -02 | Pantry Expenses | 2010 |  | 2010 | SMARTWORLD THE EDITION | SMS CommercialRakesh | 9110000151 | 50 |  |  | 2023-06-17 | 750ML PET MOUNTAIN DEW 24*40MR | NO | 1500 | 22.86 | 34290 | 48006 | 5016.23 | 7022.72 | 29273.77 | 5484.27 | 7677.98 | ZMAT | 2025-01-20 | 2025-03-20
RE/0066-SGE-SF-AD -02 | Pantry Expenses | 2010 |  | 2010 | SMARTWORLD THE EDITION | Bright Star Hospitality Services PvManoj | 9110000182 | 20 |  |  | 2023-06-28 | Pantry_Food Items_Chips | NO | 15400 | 15.62 | 240548 | 269413.76 | 54670.04 | 61230.45 | 185877.96 | 54687.5 | 61250 | ZMAT | 2025-01-20 | 2025-03-20
RE/0066-SGE-SF-AD -02 | Pantry Expenses | 2010 |  | 2010 | SMARTWORLD THE EDITION | D D EnterprisesSushil Bajaj | 9110000188 | 20 |  |  | 2023-07-10 | Drinking water | NO | 15072 | 4.89 | 73702.08 | 86968.45 | 70416.03 | 83090.91 | 3286.05 | 70416.04 | 83091 | ZMAT | 2025-01-20 | 2025-03-20
RE/0066-SGE-SF-AD -02 | Pantry Expenses | 2010 |  | 2010 | SMARTWORLD THE EDITION | D D EnterprisesSushil Bajaj | 9110000188 | 30 |  |  | 2023-07-10 | 300 ML DRINKING WATR | NO | 96000 | 4.89 | 469440 | 553939.2 | 311004 | 366984.72 | 158436 | 311004.28 | 366985 | ZMAT | 2025-01-20 | 2025-03-20
RE/0066-SGE-SF-AD -02 | Pantry Expenses | 2010 |  | 2010 | SMARTWORLD THE EDITION | Luck Aqua | 9110000189 | 20 |  |  | 2023-07-10 | Drinking water 20 Ltr Jar | NO | 352 | 15 | 5280 | 5913.6 | 3390 | 3796.8 | 1890 | 3390 | 3797 | ZMAT | 2025-01-20 | 2025-03-20
RE/0066-SGE-SF-AD -02 | Pantry Expenses | 2010 |  | 2010 | SMARTWORLD THE EDITION | Luck Aqua | 9110000189 | 30 |  |  | 2023-07-10 | Drinking water 20 Ltr Jar | NO | 939 | 15 | 14085 | 15775.2 | 13740 | 15388.8 | 345 | 13740.2 | 15389 | ZMAT | 2025-01-20 | 2025-03-20
RE/0066-SGE-SF-AD -02 | Pantry Expenses | 2010 |  | 2010 | SMARTWORLD THE EDITION | PalbisRahul | 9110000211 | 10 |  |  | 2023-07-24 | Cookies | KG | 120 | 150 | 18000 | 21240 | 0 | 0 | 18000 | 0 | 0 | ZMAT | 2025-01-20 | 2025-03-20
RE/0066-SGE-SF-AD -02 | Pantry Expenses | 2010 |  | 2010 | SMARTWORLD THE EDITION | PalbisRahul | 9110000211 | 20 |  |  | 2023-07-24 | Cookies | KG | 120 | 205 | 24600 | 29028 | 0 | 0 | 24600 | 0 | 0 | ZMAT | 2025-01-20 | 2025-03-20
RE/0066-SGE-SF-AD -02 | Pantry Expenses | 2010 |  | 2010 | SMARTWORLD THE EDITION | PalbisRahul | 9110000211 | 30 |  |  | 2023-07-24 | Cookies | KG | 80 | 235 | 18800 | 22184 | 0 | 0 | 18800 | 0 | 0 | ZMAT | 2025-01-20 | 2025-03-20
RE/0066-SGE-SF-AD -02 | Pantry Expenses | 2010 |  | 2010 | SMARTWORLD THE EDITION | PalbisRahul | 9110000211 | 40 |  |  | 2023-07-24 | Cookies | KG | 64 | 290 | 18560 | 21900.8 | 0 | 0 | 18560 | 0 | 0 | ZMAT | 2025-01-20 | 2025-03-20
RE/0066-SGE-SF-AD -02 | Pantry Expenses | 2010 |  | 2010 | SMARTWORLD THE EDITION | PalbisRahul | 9110000211 | 50 |  |  | 2023-07-24 | Cookies | KG | 80 | 250 | 20000 | 23600 | 0 | 0 | 20000 | 0 | 0 | ZMAT | 2025-01-20 | 2025-03-20
RE/0066-SGE-SF-AD -02 | Pantry Expenses | 2010 |  | 2010 | SMARTWORLD THE EDITION | PalbisRahul | 9110000242 | 10 |  |  | 2023-08-04 | Zeera Cookies | KG | 336 | 150 | 50400 | 59472 | 45000 | 53100 | 5400 | 45000 | 53100 | ZMAT | 2025-01-20 | 2025-03-20
RE/0066-SGE-SF-AD -02 | Pantry Expenses | 2010 |  | 2010 | SMARTWORLD THE EDITION | PalbisRahul | 9110000242 | 20 |  |  | 2023-08-04 | Almond Cookies | KG | 335 | 290 | 97150 | 114637 | 87000 | 102660 | 10150 | 87000 | 102660 | ZMAT | 2025-01-20 | 2025-03-20
RE/0066-SGE-SF-AD -02 | Pantry Expenses | 2010 |  | 2010 | SMARTWORLD THE EDITION | PalbisRahul | 9110000242 | 30 |  |  | 2023-08-04 | Coconut Cookies | KG | 335 | 205 | 68675 | 81036.5 | 61500.38 | 72570.45 | 7174.62 | 61500 | 72570 | ZMAT | 2025-01-20 | 2025-03-20
RE/0066-SGE-SF-AD -02 | Pantry Expenses | 2010 |  | 2010 | SMARTWORLD THE EDITION | PalbisRahul | 9110000242 | 40 |  |  | 2023-08-04 | Musli Cookies | KG | 335 | 300 | 100500 | 118590 | 57000 | 67260 | 43500 | 57000 | 67260 | ZMAT | 2025-01-20 | 2025-03-20
RE/0066-SGE-SF-AD -02 | Pantry Expenses | 2010 |  | 2010 | SMARTWORLD THE EDITION | PalbisRahul | 9110000242 | 50 |  |  | 2023-08-04 | Jam Cookies | KG | 331 | 215 | 71165 | 83974.7 | 38700.15 | 45666.18 | 32464.85 | 38700 | 45666 | ZMAT | 2025-01-20 | 2025-03-20
RE/0066-SGE-SF-AD -02 | Pantry Expenses | 2010 |  | 2010 | Sales Gallery-62 | Wings BeveragesCharanpreet | 9110000456 | 140 |  |  | 2024-04-06 | Milk | L | 1475 | 66 | 97350 | 97350 | 65340 | 65340 | 32010 | 65340 | 65340 | ZMAT | 2024-04-01 | 2025-03-31
RE/0066-SGE-SF-AD -02 | Pantry Expenses | 2010 |  | 2010 | Sales Gallery-62 | Wings BeveragesCharanpreet | 9110000456 | 150 |  |  | 2024-04-06 | Milk | L | 1410 | 66 | 93060 | 93060 | 79530 | 79530 | 13530 | 79530 | 79530 | ZMAT | 2024-04-01 | 2025-03-31
RE/0066-SGE-SF-AD -02 | Pantry Expenses | 2010 |  | 2010 | Sales Gallery-62 | Wings BeveragesCharanpreet | 9110000456 | 380 |  |  | 2024-04-06 | Roosh Dip Tea green Lemon Bags | PC | 9340 | 5 | 46700 | 49035 | 9000 | 9450 | 37700 | 9000.3 | 9450.3 | ZMAT | 2024-04-01 | 2025-03-31
RE/0066-SGE-SF-AD -02 | Pantry Expenses | 2010 |  | 2010 | Sales Gallery-62 | Wings BeveragesCharanpreet | 9110000456 | 400 |  |  | 2024-04-06 | Milk | L | 1205 | 66 | 79530 | 79530 | 79530 | 79530 | 0 | 79530 | 79530 | ZMAT | 2024-04-01 | 2025-03-31
RE/0066-SGE-SF-AD -02 | Pantry Expenses | 2010 |  | 2010 | Sales Gallery-62 | Wings BeveragesCharanpreet | 9110000456 | 500 |  |  | 2024-04-06 | Coffee Beans | KG | 370 | 623 | 230510 | 242035.5 | 230510.1 | 242035.6 | 0.1 | 230510 | 242035.67 | ZMAT | 2024-04-01 | 2025-03-31
RE/0066-SGE-SF-AD -02 | Pantry Expenses | 2010 |  | 2010 | Sales Gallery-62 | Wings BeveragesCharanpreet | 9110000456 | 510 |  |  | 2024-04-06 | Tea | PC | 2075 | 4.5 | 9337.5 | 9804.38 | 9337.43 | 9804.3 | 0.07 | 9337.5 | 9804.31 | ZMAT | 2024-04-01 | 2025-03-31
RE/0066-SGE-SF-AD -02 | Pantry Expenses | 2010 |  | 2010 | Sales Gallery-62 | Wings BeveragesCharanpreet | 9110000456 | 520 |  |  | 2024-04-06 | Roosh Dip Tea Green Bags | PC | 2650 | 4.5 | 11925 | 12521.25 | 11924.95 | 12521.2 | 0.05 | 11925 | 12521.4 | ZMAT | 2024-04-01 | 2025-03-31
RE/0066-SGE-SF-AD -02 | Pantry Expenses | 2010 |  | 2010 | Sales Gallery-62 | Wings BeveragesCharanpreet | 9110000456 | 530 |  |  | 2024-04-06 | Tea | BOX | 173 | 248 | 42904 | 45049.2 | 42904 | 45049.2 | 0 | 42904 | 45049.23 | ZMAT | 2024-04-01 | 2025-03-31
RE/0066-SGE-SF-AD -02 | Pantry Expenses | 2010 |  | 2010 | Sales Gallery-62 | Wings BeveragesCharanpreet | 9110000456 | 540 |  |  | 2024-04-06 | Roosh Dip Tea Ginger | BOX | 173 | 248 | 42904 | 45049.2 | 42904 | 45049.2 | 0 | 42904 | 45049.23 | ZMAT | 2024-04-01 | 2025-03-31
RE/0066-SGE-SF-AD -02 | Pantry Expenses | 2010 |  | 2010 | Sales Gallery-62 | Wings BeveragesCharanpreet | 9110000456 | 550 |  |  | 2024-04-06 | Roosh Dip Tea Masala | BOX | 173 | 248 | 42904 | 45049.2 | 42904 | 45049.2 | 0 | 42904 | 45049.23 | ZMAT | 2024-04-01 | 2025-03-31
RE/0066-SGE-SF-AD -02 | Pantry Expenses | 2010 |  | 2010 | Sales Gallery-62 | Wings BeveragesCharanpreet | 9110000456 | 560 |  |  | 2024-04-06 | Sugar Cube | KG | 480 | 90 | 43200 | 48384 | 43200 | 48384 | 0 | 43200 | 48384 | ZMAT | 2024-04-01 | 2025-03-31
RE/0066-SGE-SF-AD -02 | Pantry Expenses | 2010 |  | 2010 | Sales Gallery-62 | Wings BeveragesCharanpreet | 9110000456 | 570 |  |  | 2024-04-06 | Sugar Crystal | KG | 525 | 58 | 30450 | 31972.5 | 30450.1 | 31972.6 | 0.1 | 30450 | 31972.62 | ZMAT | 2024-04-01 | 2025-03-31
RE/0066-SGE-SF-AD -02 | Pantry Expenses | 2010 |  | 2010 | Sales Gallery-62 | Wings BeveragesCharanpreet | 9110000456 | 580 |  |  | 2024-04-06 | Tea | BOX | 84 | 150 | 12600 | 13230 | 12600 | 13230 | 0 | 12600 | 13230.01 | ZMAT | 2024-04-01 | 2025-03-31
RE/0066-SGE-SF-AD -02 | Pantry Expenses | 2010 |  | 2010 | SMARTWORLD THE EDITION | Wings BeveragesCharanpreet | 9160000265 | 20 |  |  | 2023-07-27 | CCD coffee Machine on Rental Basis 2 Nos | AU | 1 | 9400 | 9400 | 11092 | 9400 | 11092 | 0 | 9400 | 11092 | ZGEN | 2023-04-01 | 2024-03-31
RE/0066-SGE-SF-AD -02 | Pantry Expenses | 2010 |  | 2010 | SMARTWORLD THE EDITION | Updater Services limited | 9160000285 | 10 |  |  | 2023-08-01 | House Keeping MANPOWER | AU | 1 | 254299.75 | 254299.75 | 300073.71 | 254609.46 | 300439.16 | 309.71 | 254299.62 | 300073.55 | ZGEN | 2023-07-12 | 2024-03-31
RE/0066-SGE-SF-AD -02 | Pantry Expenses | 2010 |  | 2010 | SMARTWORLD THE EDITION | Manone India Private Limited | 9160000532 | 10 |  |  | 2024-01-02 | Cafe at 62 Gallery | NO | 1 | 1 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | ZGEN | 2023-10-24 | 2024-03-31
RE/0066-SGE-SF-AD -02 | Pantry Expenses | 2010 |  | 2010 | SMARTWORLD THE EDITION | Manone India Private Limited | 9160000532 | 30 |  |  | 2024-01-02 | Food and beverage services | AU | 1 | 894150 | 894150 | 938857.5 | 894150.48 | 938858 | 0.48 | 894150 | 938857.5 | ZGEN | 2023-10-24 | 2024-03-31
RE/0066-SGE-SF-AD -02 | Pantry Expenses | 2010 |  | 2010 | SMARTWORLD THE EDITION | Raj Enterprises | 9160000605 | 10 |  |  | 2024-02-05 | Food and beverage services | AU | 1 | 87600 | 87600 | 91980 | 87600 | 91980 | 0 | 87600 | 91980 | ZGEN | 2023-11-16 | 2023-11-16
RE/0066-SGE-SF-AD -03 | Electricity Expenses | 2010 |  | 2010 | SMARTWORLD THE EDITION | SMS CommercialRakesh | 9110000151 | 10 |  |  | 2023-06-17 | Soft Drink | NO | 70063.36 | 1 | 70063.36 | 89681.1 | 54737 | 70063.36 | 15326.36 | 54733.5 | 70058.94 | ZMAT | 2025-01-20 | 2025-03-20
RE/0066-SGE-SF-AD -03 | Electricity Expenses | 2010 |  | 2010 | SMARTWORLD THE EDITION | SMS CommercialRakesh | 9110000151 | 20 |  |  | 2023-06-17 | Soft Drink | NO | 6736.8 | 1 | 6736.8 | 7545.22 | 6015 | 6736.8 | 721.8 | 6371.4 | 6529.44 | ZMAT | 2025-01-20 | 2025-03-20
RE/0066-SGE-SF-AD -03 | Electricity Expenses | 2010 |  | 2010 | SMARTWORLD THE EDITION | Bright Star Hospitality Services PvManoj | 9110000182 | 10 |  |  | 2023-06-28 | Pantry_Food Items_Chips | NO | 5600 | 15.62 | 87472 | 97968.64 | 87472 | 97968.64 | 0 | 87482 | 97980.28 | ZMAT | 2025-01-20 | 2025-03-20
RE/0066-SGE-SF-AD -03 | Electricity Expenses | 2010 |  | 2010 | SMARTWORLD THE EDITION | D D EnterprisesSushil Bajaj | 9110000188 | 10 |  |  | 2023-07-10 | Drinking water | NO | 71328 | 4.89 | 348793.92 | 411576.83 | 348793.92 | 411576.83 | 0 | 348793.92 | 411577 | ZMAT | 2025-01-20 | 2025-03-20
RE/0066-SGE-SF-AD -03 | Electricity Expenses | 2010 |  | 2010 | SMARTWORLD THE EDITION | Luck Aqua | 9110000189 | 10 |  |  | 2023-07-10 | Drinking water 20 Ltr Jar | NO | 1961 | 15 | 29415 | 32944.8 | 29415 | 32944.8 | 0 | 29415 | 32945.6 | ZMAT | 2025-01-20 | 2025-03-20
RE/0066-SGE-SF-AD -03 | Electricity Expenses | 2010 |  | 2010 | SMARTWORLD THE EDITION | Wings BeveragesCharanpreet | 9110000208 | 30 |  |  | 2023-07-24 | Lemon Tea (Dip)- CCD | PC | 450 | 4.5 | 2025 | 2126.25 | 675.24 | 709 | 1349.76 | 675 | 709.02 | ZMAT | 2025-01-20 | 2025-03-20
RE/0066-SGE-SF-AD -03 | Electricity Expenses | 2010 |  | 2010 | SMARTWORLD THE EDITION | Wings BeveragesCharanpreet | 9110000208 | 40 |  |  | 2023-07-24 | Masala Tea -CCD (100 Dip) | PC | 84 | 248 | 20832 | 21873.6 | 2975.88 | 3124.67 | 17856.12 | 2976 | 3124.09 | ZMAT | 2025-01-20 | 2025-03-20
RE/0066-SGE-SF-AD -03 | Electricity Expenses | 2010 |  | 2010 | SMARTWORLD THE EDITION | Wings BeveragesCharanpreet | 9110000208 | 50 |  |  | 2023-07-24 | Ginger Tea - CCD (100 Dip) | BOX | 12 | 248 | 2976 | 3124.8 | 2976.19 | 3125 | 0.19 | 2976 | 3124.09 | ZMAT | 2025-01-20 | 2025-03-20
RE/0066-SGE-SF-AD -03 | Electricity Expenses | 2010 |  | 2010 | SMARTWORLD THE EDITION | Wings BeveragesCharanpreet | 9110000208 | 60 |  |  | 2023-07-24 | Elaichi Tea - CCD (100 Dip) | BOX | 48 | 248 | 11904 | 12499.2 | 2975.99 | 3124.79 | 8928.01 | 2976 | 3124.09 | ZMAT | 2025-01-20 | 2025-03-20
RE/0066-SGE-SF-AD -03 | Electricity Expenses | 2010 |  | 2010 | SMARTWORLD THE EDITION | Wings BeveragesCharanpreet | 9110000208 | 70 |  |  | 2023-07-24 | Green Tea - CCD | PC | 1000 | 4.5 | 4500 | 4725 | 1125.05 | 1181.3 | 3374.95 | 1125 | 1181.04 | ZMAT | 2025-01-20 | 2025-03-20
RE/0066-SGE-SF-AD -03 | Electricity Expenses | 2010 |  | 2010 | SMARTWORLD THE EDITION | Wings BeveragesCharanpreet | 9110000208 | 80 |  |  | 2023-07-24 | Coffee Beans - CCD | KG | 130 | 623 | 80990 | 85039.5 | 18690.11 | 19624.62 | 62299.89 | 18690 | 19624.58 | ZMAT | 2025-01-20 | 2025-03-20
RE/0066-SGE-SF-AD -03 | Electricity Expenses | 2010 |  | 2010 | SMARTWORLD THE EDITION | Wings BeveragesCharanpreet | 9110000208 | 110 |  |  | 2023-07-24 | Sugar Crystal Branded | KG | 150 | 58 | 8700 | 9135 | 2900.31 | 3045.33 | 5799.69 | 2900 | 3046.09 | ZMAT | 2025-01-20 | 2025-03-20
RE/0066-SGE-SF-AD -03 | Electricity Expenses | 2010 |  | 2010 | SMARTWORLD THE EDITION | Wings BeveragesCharanpreet | 9110000208 | 120 |  |  | 2023-07-24 | Sugar Cube branded | KG | 160 | 90 | 14400 | 16128 | 3600 | 4032 | 10800 | 3600 | 4033 | ZMAT | 2025-01-20 | 2025-03-20
RE/0066-SGE-SF-AD -03 | Electricity Expenses | 2010 |  | 2010 | SMARTWORLD THE EDITION | Wings BeveragesCharanpreet | 9110000208 | 160 |  |  | 2023-07-24 | Milk | L | 11248.576 | 66 | 742406.02 | 742406.02 | 719070 | 719070 | 23336.02 | 719070 | 719070 | ZMAT | 2025-01-20 | 2025-03-20
RE/0066-SGE-SF-AD -03 | Electricity Expenses | 2010 |  | 2010 | SMARTWORLD THE EDITION | Wings BeveragesCharanpreet | 9160000265 | 10 |  |  | 2023-07-27 | CCD coffee Machine on Rental Basis 2 Nos | AU | 1 | 47000 | 47000 | 55460 | 47000 | 55460 | 0 | 47000 | 55460 | ZGEN | 2023-04-01 | 2024-03-31
RE/0066-SGE-SF-AD -03 | Electricity Expenses | 2010 |  | 2010 | SMARTWORLD THE EDITION | Tecknomen Facility Services Pvt. LtDwarka | 9160000314 | 10 |  |  | 2023-08-09 | Rider Conveyance | AU | 1 | 19652 | 19652 | 23189.36 | 19652.1 | 23189.48 | 0.1 | 19652.03 | 23189.4 | ZGEN | 2023-04-01 | 2024-03-31
RE/0066-SGE-SF-AD -03 | Electricity Expenses | 2010 |  | 2010 | SMARTWORLD THE EDITION | Tecknomen Facility Services Pvt. LtDwarka | 9160000314 | 20 |  |  | 2023-08-09 | Management Fees( 4.5%) | AU | 1 | 885.6 | 885.6 | 1045.01 | 883.49 | 1042.52 | 2.11 | 885.59 | 1045 | ZGEN | 2023-04-01 | 2024-03-31
RE/0066-SGE-SF-AD -04 | Office Expenses | 2010 |  | 2010 | SMARTWORLD THE EDITION | Aqsa Marketing Pvt Ltd | 9110000312 | 20 |  |  | 2023-12-08 | AQSA Premium Aromatic Oils 10 Ltr | L | 10 | 1850 | 18500 | 21830 | 18500 | 21830 | 0 | 18500 | 21830 | ZMAT | 2025-01-20 | 2025-03-20
RE/0066-SGE-SF-AD -04 | Office Expenses | 2010 |  | 2010 | SMARTWORLD THE EDITION | Aqsa Marketing Pvt Ltd | 9110000312 | 30 |  |  | 2023-12-08 | AIR freshener cum neutralizer AQSA | PC | 10 | 1900 | 19000 | 22420 | 19000 | 22420 | 0 | 19000 | 22420 | ZMAT | 2025-01-20 | 2025-03-20
RE/0066-SGE-SF-AD -04 | Office Expenses | 2010 |  | 2010 | SMARTWORLD THE EDITION | New Era Electric Co. | 9110000411 | 10 |  |  | 2024-03-07 | 2*2 led panel light | NO | 2 | 1740 | 3480 | 4106.4 | 0 | 0 | 3480 | 0 | 0 | ZMAT | 2025-01-20 | 2025-03-20
RE/0066-SGE-SF-AD -04 | Office Expenses | 2010 |  | 2010 | SMARTWORLD THE EDITION | Max ComMayank | 9160000365 | 10 |  |  | 2023-09-08 | Walky Talky on Rent (Sep'23 to Mar'24) | AU | 1 | 6960 | 6960 | 8212.8 | 6961.02 | 8214 | 1.02 | 6960.68 | 8213.6 | ZGEN | 2023-09-01 | 2024-03-31
RE/0066-SGE-SF-AD -05 | Power & Fuel Expenses | 2010 | GR01 | 2010 |  |  |  | 0 | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
RE/0066-SGE-SF-AD -06 | Asset | 2010 | GR01 | 2010 |  |  |  | 0 | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
RE/0066-SGE-SF-AD -07 | Vehicle repair & Maintenance | 2010 | GR01 | 2010 |  |  |  | 0 | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
RE/0066-SGE-SF-AD -08 | Printing & Stationery Expenses | 2010 |  | 2010 | SMARTWORLD THE EDITION | Book Mark Office AutomationPreeti Shivhare | 9110000180 | 10 |  |  | 2023-06-28 | Pencil | NO | 400 | 3.3 | 1320 | 1557.6 | 1320.34 | 1558 | 0.34 | 1320 | 1557.64 | ZMAT | 2025-01-20 | 2025-03-20
RE/0066-SGE-SF-AD -08 | Printing & Stationery Expenses | 2010 |  | 2010 | SMARTWORLD THE EDITION | Book Mark Office AutomationPreeti Shivhare | 9110000180 | 20 |  |  | 2023-06-28 | Use & Through Pen | NO | 400 | 2.45 | 980 | 1156.4 | 979.66 | 1156 | 0.34 | 980 | 1156.43 | ZMAT | 2025-01-20 | 2025-03-20
RE/0066-SGE-SF-AD -08 | Printing & Stationery Expenses | 2010 |  | 2010 | SMARTWORLD THE EDITION | Book Mark Office AutomationPreeti Shivhare | 9110000180 | 30 |  |  | 2023-06-28 | Enevelope 10.5 Inch X4.5 Inch | NO | 1000 | 1.1 | 1100 | 1298 | 1100 | 1298 | 0 | 1100 | 1298.03 | ZMAT | 2025-01-20 | 2025-03-20
RE/0066-SGE-SF-AD -08 | Printing & Stationery Expenses | 2010 |  | 2010 | SMARTWORLD THE EDITION | Book Mark Office AutomationPreeti Shivhare | 9110000180 | 40 |  |  | 2023-06-28 | Ball Pen Black | NO | 41 | 7 | 287 | 338.66 | 280.28 | 330.73 | 6.72 | 280 | 330.41 | ZMAT | 2025-01-20 | 2025-03-20
RE/0066-SGE-SF-AD -08 | Printing & Stationery Expenses | 2010 |  | 2010 | SMARTWORLD THE EDITION | Book Mark Office AutomationPreeti Shivhare | 9110000180 | 50 |  |  | 2023-06-28 | Envelope A4 Yellow | NO | 400 | 3.25 | 1300 | 1534 | 650 | 767 | 650 | 640 | 755.22 | ZMAT | 2025-01-20 | 2025-03-20
RE/0066-SGE-SF-AD -08 | Printing & Stationery Expenses | 2010 |  | 2010 | SMARTWORLD THE EDITION | Book Mark Office AutomationPreeti Shivhare | 9110000180 | 60 |  |  | 2023-06-28 | Envelope A3 Yellow | NO | 402 | 4.88 | 1961.76 | 2314.88 | 976.37 | 1152.12 | 985.39 | 976 | 1151.62 | ZMAT | 2025-01-20 | 2025-03-20
RE/0066-SGE-SF-AD -08 | Printing & Stationery Expenses | 2010 |  | 2010 | SMARTWORLD THE EDITION | Book Mark Office AutomationPreeti Shivhare | 9110000180 | 70 |  |  | 2023-06-28 | Register | NO | 20 | 274 | 5480 | 6466.4 | 5479.66 | 6466 | 0.34 | 5480 | 6466.54 | ZMAT | 2025-01-20 | 2025-03-20
RE/0066-SGE-SF-AD -08 | Printing & Stationery Expenses | 2010 |  | 2010 | SMARTWORLD THE EDITION | Book Mark Office AutomationPreeti Shivhare | 9110000180 | 80 |  |  | 2023-06-28 | Enevelope A4 White | NO | 200 | 3.2 | 640 | 755.2 | 0 | 0 | 640 | 0 | 0 | ZMAT | 2025-01-20 | 2025-03-20
RE/0066-SGE-SF-AD -08 | Printing & Stationery Expenses | 2010 |  | 2010 | SMARTWORLD THE EDITION | Book Mark Office AutomationPreeti Shivhare | 9110000180 | 90 |  |  | 2023-06-28 | Cello Tape 1 Inch | NO | 12 | 14 | 168 | 198.24 | 0 | 0 | 168 | 0 | 0 | ZMAT | 2025-01-20 | 2025-03-20
RE/0066-SGE-SF-AD -08 | Printing & Stationery Expenses | 2010 |  | 2010 | SMARTWORLD THE EDITION | Book Mark Office AutomationPreeti Shivhare | 9110000180 | 100 |  |  | 2023-06-28 | Inward Register | NO | 2 | 274 | 548 | 646.64 | 0 | 0 | 548 | 0 | 0 | ZMAT | 2025-01-20 | 2025-03-20
RE/0066-SGE-SF-AD -08 | Printing & Stationery Expenses | 2010 |  | 2010 | SMARTWORLD THE EDITION | Book Mark Office AutomationPreeti Shivhare | 9110000180 | 110 |  |  | 2023-06-28 | Brown Tape | NO | 12 | 32 | 384 | 453.12 | 0 | 0 | 384 | 0 | 0 | ZMAT | 2025-01-20 | 2025-03-20
RE/0066-SGE-SF-AD -08 | Printing & Stationery Expenses | 2010 |  | 2010 | SMARTWORLD THE EDITION | Book Mark Office AutomationPreeti Shivhare | 9110000180 | 120 |  |  | 2023-06-28 | Paper Cutter | NO | 18235.679 | 20.2 | 368360.72 | 434665.65 | 101 | 119.18 | 368259.72 | 101 | 119.2 | ZMAT | 2025-01-20 | 2025-03-20
RE/0066-SGE-SF-AD -08 | Printing & Stationery Expenses | 2010 |  | 2010 | SMARTWORLD THE EDITION | Book Mark Office AutomationPreeti Shivhare | 9110000180 | 130 |  |  | 2023-06-28 | Notice Board 4*3 Inch | NO | 2 | 685 | 1370 | 1616.6 | 0 | 0 | 1370 | 0 | 0 | ZMAT | 2025-01-20 | 2025-03-20
RE/0066-SGE-SF-AD -08 | Printing & Stationery Expenses | 2010 |  | 2010 | SMARTWORLD THE EDITION | Book Mark Office AutomationPreeti Shivhare | 9110000180 | 140 |  |  | 2023-06-28 | Box File | NO | 100 | 110 | 11000 | 12980 | 0 | 0 | 11000 | 0 | 0 | ZMAT | 2025-01-20 | 2025-03-20
RE/0066-SGE-SF-AD -08 | Printing & Stationery Expenses | 2010 |  | 2010 | SMARTWORLD THE EDITION | Book Mark Office AutomationPreeti Shivhare | 9110000180 | 150 |  |  | 2023-06-28 | Sketch Pen | NO | 6 | 15.5 | 93 | 109.74 | 0 | 0 | 93 | 0 | 0 | ZMAT | 2025-01-20 | 2025-03-20
RE/0066-SGE-SF-AD -08 | Printing & Stationery Expenses | 2010 |  | 2010 | SMARTWORLD THE EDITION | Book Mark Office AutomationPreeti Shivhare | 9110000180 | 160 |  |  | 2023-06-28 | Note Pad | NO | 50 | 39.25 | 1962.5 | 2315.75 | 0 | 0 | 1962.5 | 0 | 0 | ZMAT | 2025-01-20 | 2025-03-20
RE/0066-SGE-SF-AD -08 | Printing & Stationery Expenses | 2010 |  | 2010 | SMARTWORLD THE EDITION | Book Mark Office AutomationPreeti Shivhare | 9110000180 | 170 |  |  | 2023-06-28 | Stationery Items | NO | 400 | 3.3 | 1320 | 1557.6 | 0 | 0 | 1320 | 0 | 0 | ZMAT | 2025-01-20 | 2025-03-20
RE/0066-SGE-SF-AD -08 | Printing & Stationery Expenses | 2010 |  | 2010 | SMARTWORLD THE EDITION | Book Mark Office AutomationPreeti Shivhare | 9110000180 | 180 |  |  | 2023-06-28 | Use & Through Pen | NO | 400 | 2.45 | 980 | 1156.4 | 0 | 0 | 980 | 0 | 0 | ZMAT | 2025-01-20 | 2025-03-20
RE/0066-SGE-SF-AD -08 | Printing & Stationery Expenses | 2010 |  | 2010 | SMARTWORLD THE EDITION | Book Mark Office AutomationPreeti Shivhare | 9110000180 | 190 |  |  | 2023-06-28 | Enevelope 10.5 * 4.5 | NO | 1000 | 1.1 | 1100 | 1298 | 0 | 0 | 1100 | 0 | 0 | ZMAT | 2025-01-20 | 2025-03-20
RE/0066-SGE-SF-AD -08 | Printing & Stationery Expenses | 2010 |  | 2010 | SMARTWORLD THE EDITION | Book Mark Office AutomationPreeti Shivhare | 9110000180 | 200 |  |  | 2023-06-28 | Yellow Envelope A/4 | NO | 200 | 3.2 | 640 | 755.2 | 0 | 0 | 640 | 0 | 0 | ZMAT | 2025-01-20 | 2025-03-20
RE/0066-SGE-SF-AD -08 | Printing & Stationery Expenses | 2010 |  | 2010 | SMARTWORLD THE EDITION | Book Mark Office AutomationPreeti Shivhare | 9110000180 | 210 |  |  | 2023-06-28 | Ball Pen Black | NO | 40 | 7 | 280 | 330.4 | 0 | 0 | 280 | 0 | 0 | ZMAT | 2025-01-20 | 2025-03-20
RE/0066-SGE-SF-AD -08 | Printing & Stationery Expenses | 2010 |  | 2010 | SMARTWORLD THE EDITION | Book Mark Office AutomationPreeti Shivhare | 9110000180 | 220 |  |  | 2023-06-28 | Envelope A3 Yellow | NO | 200 | 4.88 | 976 | 1151.68 | 0 | 0 | 976 | 0 | 0 | ZMAT | 2025-01-20 | 2025-03-20
RE/0066-SGE-SF-AD -08 | Printing & Stationery Expenses | 2010 |  | 2010 | SMARTWORLD THE EDITION | Book Mark Office AutomationPreeti Shivhare | 9110000180 | 230 |  |  | 2023-06-28 | Register | NO | 20 | 274 | 5480 | 6466.4 | 0 | 0 | 5480 | 0 | 0 | ZMAT | 2025-01-20 | 2025-03-20
RE/0066-SGE-SF-AD -08 | Printing & Stationery Expenses | 2010 |  | 2010 | SMARTWORLD THE EDITION | Book Mark Office AutomationPreeti Shivhare | 9110000180 | 240 |  |  | 2023-06-28 | Paper Cutter | NO | 5 | 20.2 | 101 | 119.18 | 0 | 0 | 101 | 0 | 0 | ZMAT | 2025-01-20 | 2025-03-20
RE/0066-SGE-SF-AD -08 | Printing & Stationery Expenses | 2010 |  | 2010 | SMARTWORLD THE EDITION | Book Mark Office AutomationPreeti Shivhare | 9110000180 | 250 |  |  | 2023-06-28 | Dura Cell AA | NO | 40 | 33.5 | 1340 | 1581.2 | 1340.68 | 1582 | 0.68 | 1340 | 1581.24 | ZMAT | 2025-01-20 | 2025-03-20
RE/0066-SGE-SF-AD -08 | Printing & Stationery Expenses | 2010 |  | 2010 | SMARTWORLD THE EDITION | Book Mark Office AutomationPreeti Shivhare | 9110000180 | 260 |  |  | 2023-06-28 | Dura Cell AAA | NO | 20 | 33.5 | 670 | 790.6 | 669.49 | 790 | 0.51 | 670 | 790.62 | ZMAT | 2025-01-20 | 2025-03-20
RE/0066-SGE-SF-AD -08 | Printing & Stationery Expenses | 2010 |  | 2010 | SMARTWORLD THE EDITION | Book Mark Office AutomationPreeti Shivhare | 9110000180 | 270 |  |  | 2023-06-28 | CD Marker | NO | 20 | 7.5 | 150 | 177 | 150.85 | 178 | 0.85 | 150 | 177 | ZMAT | 2025-01-20 | 2025-03-20
RE/0066-SGE-SF-AD -08 | Printing & Stationery Expenses | 2010 |  | 2010 | SMARTWORLD THE EDITION | Book Mark Office AutomationPreeti Shivhare | 9110000180 | 280 |  |  | 2023-06-28 | White Board Marker Black | NO | 20 | 18.5 | 370 | 436.6 | 369.49 | 436 | 0.51 | 370 | 436.61 | ZMAT | 2025-01-20 | 2025-03-20
RE/0066-SGE-SF-AD -08 | Printing & Stationery Expenses | 2010 |  | 2010 | SMARTWORLD THE EDITION | Book Mark Office AutomationPreeti Shivhare | 9110000180 | 290 |  |  | 2023-06-28 | Conference Pad | NO | 200 | 7.9 | 1580 | 1864.4 | 1579.66 | 1864 | 0.34 | 1580 | 1864.44 | ZMAT | 2025-01-20 | 2025-03-20
RE/0066-SGE-SF-AD -08 | Printing & Stationery Expenses | 2010 |  | 2010 | SMARTWORLD THE EDITION | Book Mark Office AutomationPreeti Shivhare | 9110000180 | 300 |  |  | 2023-06-28 | Pencil | NO | 400 | 3.3 | 1320 | 1557.6 | 1320 | 1557.6 | 0 | 1320.28 | 1557.87 | ZMAT | 2025-01-20 | 2025-03-20
RE/0066-SGE-SF-AD -08 | Printing & Stationery Expenses | 2010 |  | 2010 | SMARTWORLD THE EDITION | Book Mark Office AutomationPreeti Shivhare | 9110000180 | 310 |  |  | 2023-06-28 | Use & Through Pen | NO | 400 | 2.45 | 980 | 1156.4 | 980 | 1156.4 | 0 | 980 | 1156.39 | ZMAT | 2025-01-20 | 2025-03-20
RE/0066-SGE-SF-AD -08 | Printing & Stationery Expenses | 2010 |  | 2010 | SMARTWORLD THE EDITION | Book Mark Office AutomationPreeti Shivhare | 9110000180 | 320 |  |  | 2023-06-28 | Enevelope 10.5 Inch X4.5 Inch | NO | 1000 | 1.1 | 1100 | 1298 | 1100 | 1298 | 0 | 1100 | 1297.99 | ZMAT | 2025-01-20 | 2025-03-20
RE/0066-SGE-SF-AD -08 | Printing & Stationery Expenses | 2010 |  | 2010 | SMARTWORLD THE EDITION | Book Mark Office AutomationPreeti Shivhare | 9110000180 | 330 |  |  | 2023-06-28 | Ball Pen Black | NO | 40 | 7 | 280 | 330.4 | 280 | 330.4 | 0 | 280 | 330.4 | ZMAT | 2025-01-20 | 2025-03-20
RE/0066-SGE-SF-AD -08 | Printing & Stationery Expenses | 2010 |  | 2010 | SMARTWORLD THE EDITION | Book Mark Office AutomationPreeti Shivhare | 9110000180 | 340 |  |  | 2023-06-28 | Envelope A4 Yellow | NO | 400 | 3.25 | 1300 | 1534 | 1300 | 1534 | 0 | 1300 | 1533.99 | ZMAT | 2025-01-20 | 2025-03-20
RE/0066-SGE-SF-AD -08 | Printing & Stationery Expenses | 2010 |  | 2010 | SMARTWORLD THE EDITION | Book Mark Office AutomationPreeti Shivhare | 9110000180 | 350 |  |  | 2023-06-28 | Envelope A3 Yellow | NO | 400 | 4.88 | 1952 | 2303.36 | 1952.03 | 2303.4 | 0.03 | 1952 | 2303.39 | ZMAT | 2025-01-20 | 2025-03-20
RE/0066-SGE-SF-AD -08 | Printing & Stationery Expenses | 2010 |  | 2010 | SMARTWORLD THE EDITION | Book Mark Office AutomationPreeti Shivhare | 9110000180 | 360 |  |  | 2023-06-28 | Register | NO | 20 | 274 | 5480 | 6466.4 | 5480 | 6466.4 | 0 | 5480 | 6466.38 | ZMAT | 2025-01-20 | 2025-03-20
RE/0066-SGE-SF-AD -08 | Printing & Stationery Expenses | 2010 |  | 2010 | SMARTWORLD THE EDITION | Book Mark Office AutomationPreeti Shivhare | 9110000180 | 370 |  |  | 2023-06-28 | Enevelope A4 White | NO | 200 | 3.2 | 640 | 755.2 | 640 | 755.2 | 0 | 640 | 755.2 | ZMAT | 2025-01-20 | 2025-03-20
RE/0066-SGE-SF-AD -08 | Printing & Stationery Expenses | 2010 |  | 2010 | SMARTWORLD THE EDITION | Book Mark Office AutomationPreeti Shivhare | 9110000180 | 380 |  |  | 2023-06-28 | Cello Tape 1 Inch | NO | 12 | 14 | 168 | 198.24 | 167.97 | 198.2 | 0.03 | 168 | 198.2 | ZMAT | 2025-01-20 | 2025-03-20
RE/0066-SGE-SF-AD -08 | Printing & Stationery Expenses | 2010 |  | 2010 | SMARTWORLD THE EDITION | Book Mark Office AutomationPreeti Shivhare | 9110000180 | 390 |  |  | 2023-06-28 | Inward Register | NO | 2 | 274 | 548 | 646.64 | 547.97 | 646.6 | 0.03 | 548 | 646.6 | ZMAT | 2025-01-20 | 2025-03-20
RE/0066-SGE-SF-AD -08 | Printing & Stationery Expenses | 2010 |  | 2010 | SMARTWORLD THE EDITION | Book Mark Office AutomationPreeti Shivhare | 9110000180 | 400 |  |  | 2023-06-28 | Brown Tape | NO | 12 | 32 | 384 | 453.12 | 384.07 | 453.2 | 0.07 | 384 | 453.19 | ZMAT | 2025-01-20 | 2025-03-20
RE/0066-SGE-SF-AD -08 | Printing & Stationery Expenses | 2010 |  | 2010 | SMARTWORLD THE EDITION | Book Mark Office AutomationPreeti Shivhare | 9110000180 | 410 |  |  | 2023-06-28 | Paper Cutter | NO | 10 | 20.2 | 202 | 238.36 | 202.03 | 238.4 | 0.03 | 202 | 238.4 | ZMAT | 2025-01-20 | 2025-03-20
RE/0066-SGE-SF-AD -08 | Printing & Stationery Expenses | 2010 |  | 2010 | SMARTWORLD THE EDITION | Book Mark Office AutomationPreeti Shivhare | 9110000180 | 420 |  |  | 2023-06-28 | Stationery Items | NO | 400 | 3.3 | 1320 | 1557.6 | 1320 | 1557.6 | 0 | 1320 | 1557.6 | ZMAT | 2025-01-20 | 2025-03-20
RE/0066-SGE-SF-AD -08 | Printing & Stationery Expenses | 2010 |  | 2010 | SMARTWORLD THE EDITION | Book Mark Office AutomationPreeti Shivhare | 9110000180 | 430 |  |  | 2023-06-28 | Use & Through Pen | NO | 400 | 2.45 | 980 | 1156.4 | 980 | 1156.4 | 0 | 980 | 1156.4 | ZMAT | 2025-01-20 | 2025-03-20
RE/0066-SGE-SF-AD -08 | Printing & Stationery Expenses | 2010 |  | 2010 | SMARTWORLD THE EDITION | Book Mark Office AutomationPreeti Shivhare | 9110000180 | 440 |  |  | 2023-06-28 | White Envelope A/4 | NO | 1000 | 3.2 | 3200 | 3776 | 3200 | 3776 | 0 | 3200 | 3776 | ZMAT | 2025-01-20 | 2025-03-20
RE/0066-SGE-SF-AD -08 | Printing & Stationery Expenses | 2010 |  | 2010 | SMARTWORLD THE EDITION | Book Mark Office AutomationPreeti Shivhare | 9110000180 | 450 |  |  | 2023-06-28 | Envelope A4 Yellow | NO | 200 | 3.25 | 650 | 767 | 650 | 767 | 0 | 650 | 767 | ZMAT | 2025-01-20 | 2025-03-20
RE/0066-SGE-SF-AD -08 | Printing & Stationery Expenses | 2010 |  | 2010 | SMARTWORLD THE EDITION | Book Mark Office AutomationPreeti Shivhare | 9110000180 | 460 |  |  | 2023-06-28 | Stationery Items | NO | 40 | 6 | 240 | 283.2 | 240 | 283.2 | 0 | 240 | 283.2 | ZMAT | 2025-01-20 | 2025-03-20
RE/0066-SGE-SF-AD -08 | Printing & Stationery Expenses | 2010 |  | 2010 | SMARTWORLD THE EDITION | Book Mark Office AutomationPreeti Shivhare | 9110000180 | 470 |  |  | 2023-06-28 | Envelope A3 Yellow | NO | 200 | 4.88 | 976 | 1151.68 | 975.93 | 1151.6 | 0.07 | 976 | 1151.6 | ZMAT | 2025-01-20 | 2025-03-20
RE/0066-SGE-SF-AD -08 | Printing & Stationery Expenses | 2010 |  | 2010 | SMARTWORLD THE EDITION | Book Mark Office AutomationPreeti Shivhare | 9110000180 | 480 |  |  | 2023-06-28 | Register | NO | 20 | 274 | 5480 | 6466.4 | 5480 | 6466.4 | 0 | 5480 | 6466.4 | ZMAT | 2025-01-20 | 2025-03-20
RE/0066-SGE-SF-AD -08 | Printing & Stationery Expenses | 2010 |  | 2010 | SMARTWORLD THE EDITION | Book Mark Office AutomationPreeti Shivhare | 9110000180 | 490 |  |  | 2023-06-28 | Paper Cutter | NO | 5 | 20.2 | 101 | 119.18 | 101.02 | 119.2 | 0.02 | 101 | 119.2 | ZMAT | 2025-01-20 | 2025-03-20
RE/0066-SGE-SF-AD -08 | Printing & Stationery Expenses | 2010 |  | 2010 | SMARTWORLD THE EDITION | Book Mark Office AutomationPreeti Shivhare | 9110000180 | 500 |  |  | 2023-06-28 | Dura Cell AA | NO | 40 | 33.5 | 1340 | 1581.2 | 1340 | 1581.2 | 0 | 1340 | 1581.2 | ZMAT | 2025-01-20 | 2025-03-20
RE/0066-SGE-SF-AD -08 | Printing & Stationery Expenses | 2010 |  | 2010 | SMARTWORLD THE EDITION | Book Mark Office AutomationPreeti Shivhare | 9110000180 | 510 |  |  | 2023-06-28 | Dura Cell AAA | NO | 40 | 33.5 | 1340 | 1581.2 | 1340 | 1581.2 | 0 | 1340 | 1581.2 | ZMAT | 2025-01-20 | 2025-03-20
RE/0066-SGE-SF-AD -08 | Printing & Stationery Expenses | 2010 |  | 2010 | SMARTWORLD THE EDITION | Book Mark Office AutomationPreeti Shivhare | 9110000180 | 520 |  |  | 2023-06-28 | Note Pad | NO | 200 | 23.9 | 4780 | 5640.4 | 4780 | 5640.4 | 0 | 4780 | 5640.4 | ZMAT | 2025-01-20 | 2025-03-20
RE/0066-SGE-SF-AD -08 | Printing & Stationery Expenses | 2010 |  | 2010 | SMARTWORLD THE EDITION | Book Mark Office AutomationPreeti Shivhare | 9110000180 | 530 |  |  | 2023-06-28 | White Board Marker Blue | NO | 20 | 18.5 | 370 | 436.6 | 370 | 436.6 | 0 | 370 | 436.6 | ZMAT | 2025-01-20 | 2025-03-20
RE/0066-SGE-SF-AD -08 | Printing & Stationery Expenses | 2010 |  | 2010 | SMARTWORLD THE EDITION | Book Mark Office AutomationPreeti Shivhare | 9110000180 | 540 |  |  | 2023-06-28 | White Board Marker Black | NO | 10 | 18.5 | 185 | 218.3 | 185.08 | 218.4 | 0.08 | 185 | 218.4 | ZMAT | 2025-01-20 | 2025-03-20
RE/0066-SGE-SF-AD -08 | Printing & Stationery Expenses | 2010 |  | 2010 | SMARTWORLD THE EDITION | Book Mark Office AutomationPreeti Shivhare | 9110000180 | 550 |  |  | 2023-06-28 | Correction Pen | NO | 10 | 17.6 | 176 | 207.68 | 175.93 | 207.6 | 0.07 | 175.6 | 207.2 | ZMAT | 2025-01-20 | 2025-03-20
RE/0066-SGE-SF-AD -08 | Printing & Stationery Expenses | 2010 |  | 2010 | SMARTWORLD THE EDITION | Book Mark Office AutomationPreeti Shivhare | 9110000180 | 560 |  |  | 2023-06-28 | Cello Tape 2 Inch | NO | 20 | 32 | 640 | 755.2 | 640 | 755.2 | 0 | 640 | 755.2 | ZMAT | 2025-01-20 | 2025-03-20
RE/0066-SGE-SF-AD -08 | Printing & Stationery Expenses | 2010 |  | 2010 | SMARTWORLD THE EDITION | Book Mark Office AutomationPreeti Shivhare | 9110000180 | 570 |  |  | 2023-06-28 | Glue Stick | NO | 10 | 27 | 270 | 318.6 | 270 | 318.6 | 0 | 270 | 318.6 | ZMAT | 2025-01-20 | 2025-03-20
RE/0066-SGE-SF-AD -08 | Printing & Stationery Expenses | 2010 |  | 2010 | SMARTWORLD THE EDITION | Book Mark Office AutomationPreeti Shivhare | 9110000180 | 580 |  |  | 2023-06-28 | Copier Paper A/4 75GSM | NO | 30 | 238 | 7140 | 7996.8 | 7140 | 7996.8 | 0 | 7140 | 7996.8 | ZMAT | 2025-01-20 | 2025-03-20
RE/0066-SGE-SF-AD -08 | Printing & Stationery Expenses | 2010 |  | 2010 | SMARTWORLD THE EDITION | Book Mark Office AutomationPreeti Shivhare | 9110000180 | 590 |  |  | 2023-06-28 | Pencil | NO | 400 | 3.3 | 1320 | 1557.6 | 1320 | 1557.6 | 0 | 1320 | 1557.6 | ZMAT | 2025-01-20 | 2025-03-20
RE/0066-SGE-SF-AD -08 | Printing & Stationery Expenses | 2010 |  | 2010 | SMARTWORLD THE EDITION | Book Mark Office AutomationPreeti Shivhare | 9110000180 | 600 |  |  | 2023-06-28 | Use & Through Pen | NO | 400 | 2.45 | 980 | 1156.4 | 980 | 1156.4 | 0 | 980 | 1156.4 | ZMAT | 2025-01-20 | 2025-03-20
RE/0066-SGE-SF-AD -08 | Printing & Stationery Expenses | 2010 |  | 2010 | SMARTWORLD THE EDITION | Book Mark Office AutomationPreeti Shivhare | 9110000180 | 610 |  |  | 2023-06-28 | Enevelope 10.5 Inch X4.5 Inch | NO | 1000 | 1.1 | 1100 | 1298 | 1100 | 1298 | 0 | 1100 | 1298 | ZMAT | 2025-01-20 | 2025-03-20
RE/0066-SGE-SF-AD -08 | Printing & Stationery Expenses | 2010 |  | 2010 | SMARTWORLD THE EDITION | Book Mark Office AutomationPreeti Shivhare | 9110000180 | 620 |  |  | 2023-06-28 | Envelope A4 Yellow | NO | 400 | 3.25 | 1300 | 1534 | 1300 | 1534 | 0 | 1300 | 1534 | ZMAT | 2025-01-20 | 2025-03-20
RE/0066-SGE-SF-AD -08 | Printing & Stationery Expenses | 2010 |  | 2010 | SMARTWORLD THE EDITION | Book Mark Office AutomationPreeti Shivhare | 9110000180 | 630 |  |  | 2023-06-28 | Ball Pen Black | NO | 13 | 7 | 91 | 107.38 | 91.02 | 107.4 | 0.02 | 91 | 107.4 | ZMAT | 2025-01-20 | 2025-03-20
RE/0066-SGE-SF-AD -08 | Printing & Stationery Expenses | 2010 |  | 2010 | SMARTWORLD THE EDITION | Book Mark Office AutomationPreeti Shivhare | 9110000180 | 640 |  |  | 2023-06-28 | Envelope A3 Yellow | NO | 200 | 4.88 | 976 | 1151.68 | 975.93 | 1151.6 | 0.07 | 976 | 1151.6 | ZMAT | 2025-01-20 | 2025-03-20
RE/0066-SGE-SF-AD -08 | Printing & Stationery Expenses | 2010 |  | 2010 | SMARTWORLD THE EDITION | Book Mark Office AutomationPreeti Shivhare | 9110000180 | 650 |  |  | 2023-06-28 | Register | NO | 20 | 274 | 5480 | 6466.4 | 5480 | 6466.4 | 0 | 5480 | 6466.4 | ZMAT | 2025-01-20 | 2025-03-20
RE/0066-SGE-SF-AD -08 | Printing & Stationery Expenses | 2010 |  | 2010 | SMARTWORLD THE EDITION | Book Mark Office AutomationPreeti Shivhare | 9110000180 | 660 |  |  | 2023-06-28 | Paper Cutter | NO | 10 | 20.2 | 202 | 238.36 | 202.03 | 238.4 | 0.03 | 202 | 238.4 | ZMAT | 2025-01-20 | 2025-03-20
RE/0066-SGE-SF-AD -08 | Printing & Stationery Expenses | 2010 |  | 2010 | SMARTWORLD THE EDITION | Book Mark Office AutomationPreeti Shivhare | 9110000180 | 670 |  |  | 2023-06-28 | Cello Tape 1 Inch | NO | 12 | 14 | 168 | 198.24 | 167.97 | 198.2 | 0.03 | 168 | 198.2 | ZMAT | 2025-01-20 | 2025-03-20
RE/0066-SGE-SF-AD -08 | Printing & Stationery Expenses | 2010 |  | 2010 | SMARTWORLD THE EDITION | Book Mark Office AutomationPreeti Shivhare | 9110000180 | 680 |  |  | 2023-06-28 | Inward Register | NO | 2 | 274 | 548 | 646.64 | 547.97 | 646.6 | 0.03 | 548 | 646.6 | ZMAT | 2025-01-20 | 2025-03-20
RE/0066-SGE-SF-AD -08 | Printing & Stationery Expenses | 2010 |  | 2010 | SMARTWORLD THE EDITION | Book Mark Office AutomationPreeti Shivhare | 9110000180 | 690 |  |  | 2023-06-28 | Brown Tape | NO | 12 | 32 | 384 | 453.12 | 384.07 | 453.2 | 0.07 | 384 | 453.2 | ZMAT | 2025-01-20 | 2025-03-20
RE/0066-SGE-SF-AD -08 | Printing & Stationery Expenses | 2010 |  | 2010 | SMARTWORLD THE EDITION | Book Mark Office AutomationPreeti Shivhare | 9110000180 | 700 |  |  | 2023-06-28 | Dura Cell AA | NO | 20 | 33.5 | 670 | 790.6 | 670 | 790.6 | 0 | 670 | 790.6 | ZMAT | 2025-01-20 | 2025-03-20
RE/0066-SGE-SF-AD -08 | Printing & Stationery Expenses | 2010 |  | 2010 | SMARTWORLD THE EDITION | Book Mark Office AutomationPreeti Shivhare | 9110000180 | 710 |  |  | 2023-06-28 | Dura Cell AAA | NO | 10 | 33.5 | 335 | 395.3 | 335.08 | 395.4 | 0.08 | 335 | 395.4 | ZMAT | 2025-01-20 | 2025-03-20
RE/0066-SGE-SF-AD -08 | Printing & Stationery Expenses | 2010 |  | 2010 | SMARTWORLD THE EDITION | Book Mark Office AutomationPreeti Shivhare | 9110000180 | 720 |  |  | 2023-06-28 | Note Pad | NO | 200 | 23.9 | 4780 | 5640.4 | 4780 | 5640.4 | 0 | 4780 | 5640.4 | ZMAT | 2025-01-20 | 2025-03-20
RE/0066-SGE-SF-AD -08 | Printing & Stationery Expenses | 2010 |  | 2010 | SMARTWORLD THE EDITION | Book Mark Office AutomationPreeti Shivhare | 9110000180 | 730 |  |  | 2023-06-28 | Whitener | NO | 10 | 17.6 | 176 | 207.68 | 175.93 | 207.6 | 0.07 | 176 | 207.6 | ZMAT | 2025-01-20 | 2025-03-20
RE/0066-SGE-SF-AD -08 | Printing & Stationery Expenses | 2010 |  | 2010 | SMARTWORLD THE EDITION | Book Mark Office AutomationPreeti Shivhare | 9110000180 | 740 |  |  | 2023-06-28 | White Board Duster | NO | 10 | 42 | 420 | 495.6 | 420 | 495.6 | 0 | 420 | 495.6 | ZMAT | 2025-01-20 | 2025-03-20
RE/0066-SGE-SF-AD -08 | Printing & Stationery Expenses | 2010 |  | 2010 | SMARTWORLD THE EDITION | Book Mark Office AutomationPreeti Shivhare | 9110000180 | 750 |  |  | 2023-06-28 | CD Marker | NO | 20 | 7.5 | 150 | 177 | 150 | 177 | 0 | 150 | 177 | ZMAT | 2025-01-20 | 2025-03-20
RE/0066-SGE-SF-AD -08 | Printing & Stationery Expenses | 2010 |  | 2010 | SMARTWORLD THE EDITION | Book Mark Office AutomationPreeti Shivhare | 9110000180 | 760 |  |  | 2023-06-28 | White Board Marker Black | NO | 20 | 18.5 | 370 | 436.6 | 370 | 436.6 | 0 | 370 | 436.6 | ZMAT | 2025-01-20 | 2025-03-20
RE/0066-SGE-SF-AD -08 | Printing & Stationery Expenses | 2010 |  | 2010 | SMARTWORLD THE EDITION | Book Mark Office AutomationPreeti Shivhare | 9110000180 | 770 |  |  | 2023-06-28 | Pencil | NO | 400 | 3.3 | 1320 | 1557.6 | 1320 | 1557.6 | 0 | 1319.6 | 1557.2 | ZMAT | 2025-01-20 | 2025-03-20
RE/0066-SGE-SF-AD -08 | Printing & Stationery Expenses | 2010 |  | 2010 | SMARTWORLD THE EDITION | Book Mark Office AutomationPreeti Shivhare | 9110000180 | 780 |  |  | 2023-06-28 | Use & Through Pen | NO | 400 | 2.45 | 980 | 1156.4 | 980 | 1156.4 | 0 | 980 | 1156.4 | ZMAT | 2025-01-20 | 2025-03-20
RE/0066-SGE-SF-AD -08 | Printing & Stationery Expenses | 2010 |  | 2010 | SMARTWORLD THE EDITION | Book Mark Office AutomationPreeti Shivhare | 9110000180 | 790 |  |  | 2023-06-28 | Envelope A/3 White | NO | 500 | 4.88 | 2440 | 2879.2 | 2440 | 2879.2 | 0 | 2440 | 2879.2 | ZMAT | 2025-01-20 | 2025-03-20
RE/0066-SGE-SF-AD -08 | Printing & Stationery Expenses | 2010 |  | 2010 | SMARTWORLD THE EDITION | Book Mark Office AutomationPreeti Shivhare | 9110000180 | 800 |  |  | 2023-06-28 | Envelope A4 Yellow | NO | 400 | 3.25 | 1300 | 1534 | 1300 | 1534 | 0 | 1300 | 1534 | ZMAT | 2025-01-20 | 2025-03-20
RE/0066-SGE-SF-AD -08 | Printing & Stationery Expenses | 2010 |  | 2010 | SMARTWORLD THE EDITION | Book Mark Office AutomationPreeti Shivhare | 9110000180 | 810 |  |  | 2023-06-28 | Ball Pen Blue | NO | 20 | 6 | 120 | 141.6 | 120 | 141.6 | 0 | 120 | 141.6 | ZMAT | 2025-01-20 | 2025-03-20
RE/0066-SGE-SF-AD -08 | Printing & Stationery Expenses | 2010 |  | 2010 | SMARTWORLD THE EDITION | Book Mark Office AutomationPreeti Shivhare | 9110000180 | 820 |  |  | 2023-06-28 | Envelope A3 Yellow | NO | 200 | 4.88 | 976 | 1151.68 | 975.93 | 1151.6 | 0.07 | 976 | 1151.6 | ZMAT | 2025-01-20 | 2025-03-20
RE/0066-SGE-SF-AD -08 | Printing & Stationery Expenses | 2010 |  | 2010 | SMARTWORLD THE EDITION | Book Mark Office AutomationPreeti Shivhare | 9110000180 | 830 |  |  | 2023-06-28 | Register 144pgs | NO | 20 | 79 | 1580 | 1769.6 | 1580 | 1769.6 | 0 | 1580 | 1769.6 | ZMAT | 2025-01-20 | 2025-03-20
RE/0066-SGE-SF-AD -08 | Printing & Stationery Expenses | 2010 |  | 2010 | SMARTWORLD THE EDITION | Book Mark Office AutomationPreeti Shivhare | 9110000180 | 840 |  |  | 2023-06-28 | Paper Cutter | NO | 10 | 20.2 | 202 | 238.36 | 202.03 | 238.4 | 0.03 | 202 | 238.4 | ZMAT | 2025-01-20 | 2025-03-20
RE/0066-SGE-SF-AD -08 | Printing & Stationery Expenses | 2010 |  | 2010 | SMARTWORLD THE EDITION | Book Mark Office AutomationPreeti Shivhare | 9110000180 | 850 |  |  | 2023-06-28 | Duracell AA | NO | 40 | 33.5 | 1340 | 1581.2 | 1340 | 1581.2 | 0 | 1340 | 1581.2 | ZMAT | 2025-01-20 | 2025-03-20
RE/0066-SGE-SF-AD -08 | Printing & Stationery Expenses | 2010 |  | 2010 | SMARTWORLD THE EDITION | Book Mark Office AutomationPreeti Shivhare | 9110000180 | 860 |  |  | 2023-06-28 | Dura Cell AAA | NO | 40 | 33.5 | 1340 | 1581.2 | 1340 | 1581.2 | 0 | 1340 | 1581.2 | ZMAT | 2025-01-20 | 2025-03-20
RE/0066-SGE-SF-AD -08 | Printing & Stationery Expenses | 2010 |  | 2010 | SMARTWORLD THE EDITION | Book Mark Office AutomationPreeti Shivhare | 9110000180 | 870 |  |  | 2023-06-28 | Note Pad | NO | 200 | 23.9 | 4780 | 5640.4 | 4780 | 5640.4 | 0 | 4780 | 5640.4 | ZMAT | 2025-01-20 | 2025-03-20
RE/0066-SGE-SF-AD -08 | Printing & Stationery Expenses | 2010 |  | 2010 | SMARTWORLD THE EDITION | Book Mark Office AutomationPreeti Shivhare | 9110000180 | 880 |  |  | 2023-06-28 | White Board Marker Blue | NO | 20 | 18.5 | 370 | 436.6 | 370 | 436.6 | 0 | 370 | 436.6 | ZMAT | 2025-01-20 | 2025-03-20
RE/0066-SGE-SF-AD -08 | Printing & Stationery Expenses | 2010 |  | 2010 | SMARTWORLD THE EDITION | Book Mark Office AutomationPreeti Shivhare | 9110000180 | 890 |  |  | 2023-06-28 | White Board Marker Black | NO | 20 | 18.5 | 370 | 436.6 | 370 | 436.6 | 0 | 370 | 436.6 | ZMAT | 2025-01-20 | 2025-03-20
RE/0066-SGE-SF-AD -08 | Printing & Stationery Expenses | 2010 |  | 2010 | SMARTWORLD THE EDITION | Book Mark Office AutomationPreeti Shivhare | 9110000180 | 900 |  |  | 2023-06-28 | Whitener | NO | 10 | 17.6 | 176 | 207.68 | 175.93 | 207.6 | 0.07 | 176 | 207.6 | ZMAT | 2025-01-20 | 2025-03-20
RE/0066-SGE-SF-AD -08 | Printing & Stationery Expenses | 2010 |  | 2010 | SMARTWORLD THE EDITION | Book Mark Office AutomationPreeti Shivhare | 9110000180 | 910 |  |  | 2023-06-28 | Cello Tape 1 Inch | NO | 20 | 14 | 280 | 330.4 | 280 | 330.4 | 0 | 280 | 330.4 | ZMAT | 2025-01-20 | 2025-03-20
RE/0066-SGE-SF-AD -08 | Printing & Stationery Expenses | 2010 |  | 2010 | SMARTWORLD THE EDITION | Book Mark Office AutomationPreeti Shivhare | 9110000180 | 920 |  |  | 2023-06-28 | Glue Stick | NO | 20 | 27 | 540 | 637.2 | 540 | 637.2 | 0 | 540 | 637.2 | ZMAT | 2025-01-20 | 2025-03-20
RE/0066-SGE-SF-AD -08 | Printing & Stationery Expenses | 2010 |  | 2010 | SMARTWORLD THE EDITION | Book Mark Office AutomationPreeti Shivhare | 9110000180 | 930 |  |  | 2023-06-28 | Scissors | NO | 20 | 72.6 | 1452 | 1713.36 | 1452.03 | 1713.4 | 0.03 | 1452 | 1713.4 | ZMAT | 2025-01-20 | 2025-03-20
RE/0066-SGE-SF-AD -08 | Printing & Stationery Expenses | 2010 |  | 2010 | SMARTWORLD THE EDITION | Book Mark Office AutomationPreeti Shivhare | 9110000180 | 940 |  |  | 2023-06-28 | Board Pin | NO | 10 | 18 | 180 | 212.4 | 180 | 212.4 | 0 | 180 | 212.4 | ZMAT | 2025-01-20 | 2025-03-20
RE/0066-SGE-SF-AD -08 | Printing & Stationery Expenses | 2010 |  | 2010 | SMARTWORLD THE EDITION | Book Mark Office AutomationPreeti Shivhare | 9110000180 | 950 |  |  | 2023-06-28 | Copier Paper A/4 75GSM | NO | 20 | 238 | 4760 | 5331.2 | 4760 | 5331.2 | 0 | 4760 | 5331.2 | ZMAT | 2025-01-20 | 2025-03-20
RE/0066-SGE-SF-AD -08 | Printing & Stationery Expenses | 2010 |  | 2010 | SMARTWORLD THE EDITION | Book Mark Office AutomationPreeti Shivhare | 9110000180 | 960 |  |  | 2023-06-28 | Cello Tape 2 Inch | NO | 10 | 32 | 320 | 377.6 | 320 | 377.6 | 0 | 320 | 377.6 | ZMAT | 2025-01-20 | 2025-03-20
RE/0066-SGE-SF-AD -08 | Printing & Stationery Expenses | 2010 |  | 2010 | SMARTWORLD THE EDITION | Book Mark Office AutomationPreeti Shivhare | 9110000180 | 970 |  |  | 2023-06-28 | Stapler Pin No 10 | NO | 40 | 6 | 240 | 283.2 | 240 | 283.2 | 0 | 240 | 283.2 | ZMAT | 2025-01-20 | 2025-03-20
RE/0066-SGE-SF-AD -09 | Repair & Maintenance Expenses | 2010 |  | 2010 | SMARTWORLD THE EDITION | Landscaperz IndiaVikram | 9160000297 | 10 |  |  | 2023-08-04 | Horticulture Maintenance work for 62 SG | AU | 1 | 53849.74 | 53849.74 | 63542.69 | 53844.92 | 63537 | 4.82 | 53849.78 | 63542.74 | ZGEN | 2023-04-01 | 2024-03-31
RE/0066-SGE-SF-AD -09 | Repair & Maintenance Expenses | 2010 |  | 2010 | SMARTWORLD THE EDITION | New Sign Grafix | 9160000522 | 10 |  |  | 2023-12-27 | Repairing and AMC Signage Board light | AU | 1 | 145000 | 145000 | 171100 | 144952 | 171043.36 | 48 | 145000.25 | 171100.3 | ZGEN | 2023-10-20 | 2024-09-30
RE/0066-SGE-SF-AD -10 | Travel Expenses | 2010 |  | 2010 | SMARTWORLD THE EDITION | Updater Services limited | 9160000304 | 10 |  |  | 2023-08-05 | Rider Conveyance | AU | 1 | 42645.9 | 42645.9 | 50322.16 | 42639.83 | 50315 | 6.07 | 42645.68 | 50321.9 | ZGEN | 2023-04-01 | 2024-04-01
RE/0066-SGE-SF-AD -11 | Security Manpower Expenses | 2010 |  | 2010 | SMARTWORLD THE EDITION | G4S SECURE SOLUTIONS (INDIA) PVT LT | 9160000267 | 30 |  |  | 2023-07-28 | Hiring of Manpower for Security | AU | 1 | 1843908.66 | 1843908.66 | 2175812.22 | 1906615.81 | 2249806.66 | 62707.15 | 1843910.29 | 2175814.14 | ZGEN | 2023-06-29 | 2024-06-30
RE/0066-SGE-SF-AD -11 | Security Manpower Expenses | 2010 |  | 2010 | SMARTWORLD THE EDITION | SIS Limited | 9160000318 | 10 |  |  | 2023-08-10 | 24x7 QRT (01 Vehicle, 02 Driver (02 shif | AU | 1 | 3315437.97 | 3315437.97 | 3912216.8 | 3280372.73 | 3870839.82 | 35065.24 | 3315438.39 | 3912217.3 | ZGEN | 2023-04-01 | 2024-03-31
RE/0066-SGE-SF-AD -11 | Security Manpower Expenses | 2010 |  | 2010 | SMARTWORLD THE EDITION | Max ComMayank | 9160000365 | 20 |  |  | 2023-09-08 | Walky Talky on Rent (Sep'23 to Mar'24) | AU | 1 | 6960 | 6960 | 8212.8 | 6961.02 | 8214 | 1.02 | 6960 | 8212.8 | ZGEN | 2023-09-01 | 2024-03-31
RE/0066-SGE-SF-AD -11 | Security Manpower Expenses | 2010 |  | 2010 | SMARTWORLD THE EDITION | Peregrine Guarding Private LimitedSiddharth Dahiya | 9160000389 | 10 |  |  | 2023-09-26 | Security Manpower | AU | 1 | 139522.4 | 139522.4 | 164636.43 | 139522.03 | 164636 | 0.37 | 139522.37 | 164636.4 | ZGEN | 2023-07-01 | 2023-07-16
RE/0066-SGE-SF-AD -11 | Security Manpower Expenses | 2010 |  | 2010 | Sales Gallery-62 | G4S SECURE SOLUTIONS (INDIA) PVT LT | 9160000826 | 10 |  |  | 2024-05-07 | Deployment of security Manpower | AU | 1 | 390029.19 | 390029.19 | 460234.44 | 390950.35 | 461321.41 | 921.16 | 390029.23 | 460234.49 | ZGEN | 2023-11-01 | 2024-03-31
RE/0066-SGE-SF-IT -01 | Internet Lease Line - SGE | 2010 |  | 2010 | SMARTWORLD THE EDITION | Tripleplay Interactive Network PvtMr. Dhananjay | 9160000234 | 10 |  |  | 2023-07-13 | Lease Line_50 mbps | AU | 1 | 189000.65 | 189000.65 | 223020.77 | 184275.35 | 217444.91 | 4725.3 | 175876.1 | 207533.8 | ZGEN | 2023-07-03 | 2024-07-02
RE/0066-SGE-SF-IT -02 | Rental Charges - SGE | 2010 |  | 2010 | SMARTWORLD THE EDITION | Nuways Creation Pvt. Ltd.Ravinder | 9160000299 | 10 |  |  | 2023-08-04 | Printer SHARP (Model No. BP-50C31 | AU | 1 | 61200 | 61200 | 72216 | 61199.26 | 72215.13 | 0.74 | 61200 | 72216 | ZGEN | 2023-04-01 | 2024-03-31
RE/0066-SGE-SF-IT -02 | Rental Charges - SGE | 2010 |  | 2010 | SMARTWORLD THE EDITION | Nuways Creation Pvt. Ltd.Ravinder | 9160000299 | 20 |  |  | 2023-08-04 | Rental A4_MFP Printer-1 Printer | AU | 1 | 25110 | 25110 | 29629.8 | 6000 | 7080 | 19110 | 6000 | 7080 | ZGEN | 2023-04-01 | 2024-03-31
RE/0066-SGE-SF-IT -02 | Rental Charges - SGE | 2010 |  | 2010 | SMARTWORLD THE EDITION | Nuways Creation Pvt. Ltd.Ravinder | 9160000299 | 30 |  |  | 2023-08-04 | Extra Pages_Black/Color | AU | 1 | 31891 | 31891 | 37631.38 | 31890.57 | 37630.87 | 0.43 | 31891.02 | 37631.4 | ZGEN | 2023-04-01 | 2024-03-31
RE/0066-SGE-SF-IT -02 | Rental Charges - SGE | 2010 |  | 2010 | SMARTWORLD THE EDITION | Bharti Airtel LimitedMr. Sourabh | 9160000554 | 10 |  |  | 2024-01-10 | Business Broadband 1 GBPS For Warehouse | AU | 1 | 47988 | 47988 | 56625.84 | 0 | 0 | 47988 | 0 | 0 | ZGEN | 2024-01-10 | 2025-01-09
RE/0066-SGE-SF-IT -03 | IT Miscellaneous Expenses | 2010 |  | 2010 | SMARTWORLD THE EDITION | Knowlarity Communication Pvt Ltd.Mr. Narendar | 9160000342 | 10 |  |  | 2023-08-25 | Knowlarity call center solution - S&M | AU | 1 | 698500 | 698500 | 824230 | 698500 | 824230 | 0 | 698500 | 824230 | ZGEN | 2023-09-01 | 2024-07-31
RE/0066-SGE-SF-IT -03 | IT Miscellaneous Expenses | 2010 |  | 2010 | SMARTWORLD THE EDITION | Knowlarity Communication Pvt Ltd.Mr. Narendar | 9160000680 | 10 |  |  | 2024-03-07 | SMS service for one year | AU | 1 | 14000 | 14000 | 16520 | 0 | 0 | 14000 | 0 | 0 | ZGEN | 2024-03-04 | 2025-03-05
RE/0066-SGE-SF-IT -04 | Computer & IT Expenses | 2010 |  | 2010 | SMARTWORLD THE EDITION | Nuways Creation Pvt. Ltd.Ravinder | 9110000267 | 10 |  |  | 2023-09-14 | MAC KEY License for Printer machine | NO | 1 | 28000 | 28000 | 33040 | 28000 | 33040 | 0 | 28000 | 33040 | ZMAT | 2025-01-20 | 2025-03-20
RE/0066-SGE-SF-IT -05 | AMC Charges | 2010 |  | 2010 | SMARTWORLD THE EDITION | Corporate Telesystems Pvt LtdMs. Archna | 9160000523 | 10 |  |  | 2023-12-27 | AMC for Matrix EPABX System_ETSY | AU | 1 | 14848.2 | 14848.2 | 17520.88 | 14848.31 | 17521 | 0.11 | 14848.22 | 17520.9 | ZGEN | 2024-02-01 | 2025-01-31
RE/0066-SGE-SF-IT -10 | R & M - Computers & It Services | 2010 | GR01 | 2010 |  |  |  | 0 | [5 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
RE/0066-SGE-SF-SD -01 | Awards, Gifts & Staff Welfare Expenses | 2010 |  | 2010 | Sales Gallery-62 | Kridha & Company | 9160000881 | 10 |  |  | 2024-05-28 | Full Day F&B-CP & Cust -Sec 62-on26Nov23 | AU | 1 | 165000 | 165000 | 173250 | 165000 | 173250 | 0 | 165000 | 173250 | ZGEN | 2023-11-26 | 2023-11-26
RE/0066-SOE-75 | Site Office Expenses at Sec 75 | 2010 |  | 2010 | SMARTWORLD THE EDITION | N S Concrete Pvt Ltd | 9110000042 | 10 |  |  | 2023-03-04 | RMC M7.5 Grade | M3 | 5 | 3427.5 | 17137.5 | 20222.25 | 0 | 0 | 17137.5 | 0 | 0 | ZMAT | 2025-01-20 | 2025-03-20
RE/0066-SOE-75 | Site Office Expenses at Sec 75 | 2010 |  | 2010 | SMARTWORLD THE EDITION | N S Concrete Pvt Ltd | 9110000042 | 20 |  |  | 2023-03-04 | RMC M25 Grade | M3 | 70 | 3945 | 276150 | 325857 | 0 | 0 | 276150 | 0 | 0 | ZMAT | 2025-01-20 | 2025-03-20
RE/0066-SOE-75 | Site Office Expenses at Sec 75 | 2010 |  | 2010 | SMARTWORLD THE EDITION | Book Mark Office AutomationPreeti Shivhare | 9110000058 | 10 |  |  | 2023-03-31 | Stationary Items | NO | 80000 | 1 | 80000 | 89600 | 62079 | 69528.48 | 17921 | 74330 | 83249.6 | ZMAT | 2025-01-20 | 2025-03-20
RE/0066-SOE-75 | Site Office Expenses at Sec 75 | 2010 |  | 2010 | SMARTWORLD THE EDITION | Book Mark Office AutomationPreeti Shivhare | 9110000058 | 11 |  |  | 2023-03-31 | Stationary Items | NO | 215000 | 1 | 215000 | 253700 | 149622.5 | 176554.55 | 65377.5 | 137371.1 | 162097.9 | ZMAT | 2025-01-20 | 2025-03-20
RE/0066-SOE-75 | Site Office Expenses at Sec 75 | 2010 |  | 2010 | SMARTWORLD THE EDITION | Book Mark Office AutomationPreeti Shivhare | 9110000058 | 12 |  |  | 2023-03-31 | Stationary Items | NO | 5000 | 1 | 5000 | 5250 | 70 | 73.5 | 4930 | 70 | 73.5 | ZMAT | 2025-01-20 | 2025-03-20
RE/0066-SOE-75 | Site Office Expenses at Sec 75 | 2010 |  | 2010 | SMARTWORLD THE EDITION | PALCO'SSahil Chadha | 9110000063 | 1 |  |  | 2023-04-03 | Cookies Container | NO | 38380 | 1 | 38380 | 45288.4 | 38380 | 45288.4 | 0 | 38379.6 | 45287.93 | ZMAT | 2025-01-20 | 2025-03-20
RE/0066-SOE-75 | Site Office Expenses at Sec 75 | 2010 |  | 2010 | SMARTWORLD THE EDITION | Wings BeveragesCharanpreet | 9110000068 | 1 |  |  | 2023-04-10 | Pantry Items | LS | 1 | 91788 | 91788 | 96377.4 | 0 | 0 | 91788 | 0 | 0 | ZMAT | 2025-01-20 | 2025-03-20
RE/0066-SOE-75 | Site Office Expenses at Sec 75 | 2010 |  | 2010 | SMARTWORLD THE EDITION | KAP Multi Product | 9110000070 | 17 |  |  | 2023-04-13 | Freight Charges | AU | 1 | 0.1 | 0.1 | 0.12 | 0 | 0 | 0.1 | 0 | 0 | ZMAT | 2025-01-20 | 2025-03-20
RE/0066-SOE-75 | Site Office Expenses at Sec 75 | 2010 |  | 2010 | SMARTWORLD THE EDITION | KAP Multi Product | 9110000070 | 37 |  |  | 2023-04-13 | Miscellaneous Office Items CWIP-75 | NO | 10 | 6000 | 60000 | 70800 | 60000 | 70800 | 0 | 60000 | 70799.84 | ZMAT | 2025-01-20 | 2025-03-20
RE/0066-SOE-75 | Site Office Expenses at Sec 75 | 2010 |  | 2010 | SMARTWORLD THE EDITION | KAP Multi Product | 9110000070 | 47 |  |  | 2023-04-13 | Miscellaneous Office Items CWIP-75 | NO | 10 | 6500 | 65000 | 76700 | 65000 | 76700 | 0 | 65000 | 76699.82 | ZMAT | 2025-01-20 | 2025-03-20
RE/0066-SOE-75 | Site Office Expenses at Sec 75 | 2010 |  | 2010 | SMARTWORLD THE EDITION | KAP Multi Product | 9110000070 | 57 |  |  | 2023-04-13 | Miscellaneous Office Items CWIP-75 | NO | 1 | 7000 | 7000 | 8260 | 7000 | 8260 | 0 | 7000 | 8259.98 | ZMAT | 2025-01-20 | 2025-03-20
RE/0066-SOE-75 | Site Office Expenses at Sec 75 | 2010 |  | 2010 | SMARTWORLD THE EDITION | KAP Multi Product | 9110000070 | 67 |  |  | 2023-04-13 | Miscellaneous Office Items CWIP-75 | NO | 1 | 33500 | 33500 | 39530 | 33500 | 39530 | 0 | 33500 | 39529.91 | ZMAT | 2025-01-20 | 2025-03-20
RE/0066-SOE-75 | Site Office Expenses at Sec 75 | 2010 |  | 2010 | SMARTWORLD THE EDITION | KAP Multi Product | 9110000070 | 77 |  |  | 2023-04-13 | Miscellaneous Office Items CWIP-75 | NO | 21 | 3350 | 70350 | 83013 | 70350 | 83013 | 0 | 70350 | 83013.81 | ZMAT | 2025-01-20 | 2025-03-20
RE/0066-SOE-75 | Site Office Expenses at Sec 75 | 2010 |  | 2010 | SMARTWORLD THE EDITION | KAP Multi Product | 9110000070 | 87 |  |  | 2023-04-13 | Miscellaneous Office Items CWIP-75 | NO | 140 | 830 | 116200 | 137116 | 116200 | 137116 | 0 | 116200 | 137115.68 | ZMAT | 2025-01-20 | 2025-03-20
RE/0066-SOE-75 | Site Office Expenses at Sec 75 | 2010 |  | 2010 | SMARTWORLD THE EDITION | KAP Multi Product | 9110000070 | 97 |  |  | 2023-04-13 | Miscellaneous Office Items CWIP-75 | NO | 1 | 11000 | 11000 | 12980 | 11000 | 12980 | 0 | 11000 | 12979.97 | ZMAT | 2025-01-20 | 2025-03-20
RE/0066-SOE-75 | Site Office Expenses at Sec 75 | 2010 |  | 2010 | SMARTWORLD THE EDITION | KAP Multi Product | 9110000070 | 107 |  |  | 2023-04-13 | Miscellaneous Office Items CWIP-75 | NO | 1 | 5000 | 5000 | 5900 | 5000 | 5900 | 0 | 5000 | 5899.99 | ZMAT | 2025-01-20 | 2025-03-20
RE/0066-SOE-75 | Site Office Expenses at Sec 75 | 2010 |  | 2010 | SMARTWORLD THE EDITION | Shoe Point | 9110000072 | 1 |  |  | 2023-04-19 | Electrical- Kitchen Equipment | NO | 2 | 6885 | 13770 | 16248.6 | 13770 | 16248.6 | 0 | 13770 | 16248.59 | ZMAT | 2025-01-20 | 2025-03-20
RE/0066-SOE-75 | Site Office Expenses at Sec 75 | 2010 |  | 2010 | SMARTWORLD THE EDITION | Shoe Point | 9110000072 | 2 |  |  | 2023-04-19 | Electrical- Kitchen Equipment | NO | 2 | 1659.32 | 3318.64 | 3916 | 3318.64 | 3916 | 0 | 3318.64 | 3916 | ZMAT | 2025-01-20 | 2025-03-20
RE/0066-SOE-75 | Site Office Expenses at Sec 75 | 2010 |  | 2010 | SMARTWORLD THE EDITION | Shoe Point | 9110000072 | 3 |  |  | 2023-04-19 | Electrical- Kitchen Equipment | NO | 2 | 1101.69 | 2203.38 | 2599.99 | 1101.69 | 1300 | 1101.69 | 1101.69 | 1300 | ZMAT | 2025-01-20 | 2025-03-20
RE/0066-SOE-75 | Site Office Expenses at Sec 75 | 2010 |  | 2010 | SMARTWORLD THE EDITION | Shoe Point | 9110000072 | 4 |  |  | 2023-04-19 | Stationery Items (CWIP Material ) | NO | 160 | 193.22 | 30915.2 | 36479.94 | 30915.2 | 36479.94 | 0 | 30915.2 | 36479.93 | ZMAT | 2025-01-20 | 2025-03-20
RE/0066-SOE-75 | Site Office Expenses at Sec 75 | 2010 |  | 2010 | SMARTWORLD THE EDITION | Shoe Point | 9110000072 | 5 |  |  | 2023-04-19 | Housekeeping Items (CWIP) | NO | 9 | 422.88 | 3805.92 | 4490.99 | 3805.92 | 4490.99 | 0 | 3805.92 | 4490.99 | ZMAT | 2025-01-20 | 2025-03-20
RE/0066-SOE-75 | Site Office Expenses at Sec 75 | 2010 |  | 2010 | SMARTWORLD THE EDITION | Shoe Point | 9110000072 | 6 |  |  | 2023-04-19 | Housekeeping Items (CWIP) | NO | 2 | 1064.61 | 2129.22 | 2512.48 | 1064.61 | 1256.24 | 1064.61 | 1064.61 | 1256.24 | ZMAT | 2025-01-20 | 2025-03-20
RE/0066-SOE-75 | Site Office Expenses at Sec 75 | 2010 |  | 2010 | SMARTWORLD THE EDITION | Shoe Point | 9110000072 | 7 |  |  | 2023-04-19 | Housekeeping Items (CWIP) | NO | 100 | 311.22 | 31122 | 34856.64 | 31122 | 34856.64 | 0 | 31122 | 34856.63 | ZMAT | 2025-01-20 | 2025-03-20
RE/0066-SOE-75 | Site Office Expenses at Sec 75 | 2010 |  | 2010 | SMARTWORLD THE EDITION | Shoe Point | 9110000072 | 8 |  |  | 2023-04-19 | Kitchen/Crockery items | NO | 4 | 180 | 720 | 806.4 | 540 | 604.8 | 180 | 540 | 604.8 | ZMAT | 2025-01-20 | 2025-03-20
RE/0066-SOE-75 | Site Office Expenses at Sec 75 | 2010 |  | 2010 | SMARTWORLD THE EDITION | Shoe Point | 9110000072 | 9 |  |  | 2023-04-19 | Kitchen/Crockery items | NO | 200 | 155 | 31000 | 36580 | 30690 | 36214.2 | 310 | 30690 | 36214.19 | ZMAT | 2025-01-20 | 2025-03-20
RE/0066-SOE-75 | Site Office Expenses at Sec 75 | 2010 |  | 2010 | SMARTWORLD THE EDITION | Shoe Point | 9110000072 | 10 |  |  | 2023-04-19 | Kitchen/Crockery items | NO | 4 | 34.82 | 139.28 | 155.99 | 139.29 | 156 | 0.01 | 139.28 | 156 | ZMAT | 2025-01-20 | 2025-03-20
RE/0066-SOE-75 | Site Office Expenses at Sec 75 | 2010 |  | 2010 | SMARTWORLD THE EDITION | Shoe Point | 9110000072 | 11 |  |  | 2023-04-19 | Kitchen/Crockery items | NO | 2 | 31.25 | 62.5 | 70 | 62.5 | 70 | 0 | 62.5 | 70 | ZMAT | 2025-01-20 | 2025-03-20
RE/0066-SOE-75 | Site Office Expenses at Sec 75 | 2010 |  | 2010 | SMARTWORLD THE EDITION | Shoe Point | 9110000072 | 12 |  |  | 2023-04-19 | Kitchen/Crockery items | NO | 2 | 107.14 | 214.28 | 239.99 | 214.29 | 240 | 0.01 | 214.28 | 240 | ZMAT | 2025-01-20 | 2025-03-20
RE/0066-SOE-75 | Site Office Expenses at Sec 75 | 2010 |  | 2010 | SMARTWORLD THE EDITION | Shoe Point | 9110000072 | 13 |  |  | 2023-04-19 | Housekeeping Items (CWIP) | NO | 5 | 168.64 | 843.2 | 994.98 | 843.2 | 994.98 | 0 | 843.2 | 994.98 | ZMAT | 2025-01-20 | 2025-03-20
RE/0066-SOE-75 | Site Office Expenses at Sec 75 | 2010 |  | 2010 | SMARTWORLD THE EDITION | Shoe Point | 9110000072 | 14 |  |  | 2023-04-19 | Kitchen/Crockery items | NO | 5 | 238.34 | 1191.7 | 1406.21 | 1191.7 | 1406.21 | 0 | 1191.7 | 1406.21 | ZMAT | 2025-01-20 | 2025-03-20
RE/0066-SOE-75 | Site Office Expenses at Sec 75 | 2010 |  | 2010 | SMARTWORLD THE EDITION | Shoe Point | 9110000072 | 15 |  |  | 2023-04-19 | Kitchen/Crockery items | NO | 20 | 133.94 | 2678.8 | 3000.26 | 2410.92 | 2700.23 | 267.88 | 2410.92 | 2700.24 | ZMAT | 2025-01-20 | 2025-03-20
RE/0066-SOE-75 | Site Office Expenses at Sec 75 | 2010 |  | 2010 | SMARTWORLD THE EDITION | Shoe Point | 9110000072 | 16 |  |  | 2023-04-19 | Kitchen/Crockery items | NO | 20 | 133.94 | 2678.8 | 3000.26 | 2410.92 | 2700.23 | 267.88 | 2410.92 | 2700.24 | ZMAT | 2025-01-20 | 2025-03-20
RE/0066-SOE-75 | Site Office Expenses at Sec 75 | 2010 |  | 2010 | SMARTWORLD THE EDITION | Shoe Point | 9110000072 | 17 |  |  | 2023-04-19 | Kitchen/Crockery items | NO | 200 | 91.52 | 18304 | 21598.72 | 18304 | 21598.72 | 0 | 18304 | 21598.71 | ZMAT | 2025-01-20 | 2025-03-20
RE/0066-SOE-75 | Site Office Expenses at Sec 75 | 2010 |  | 2010 | SMARTWORLD THE EDITION | Shoe Point | 9110000072 | 18 |  |  | 2023-04-19 | Kitchen/Crockery items | NO | 50 | 63.55 | 3177.5 | 3749.45 | 3050.41 | 3599.48 | 127.09 | 3050.4 | 3599.48 | ZMAT | 2025-01-20 | 2025-03-20
RE/0066-SOE-75 | Site Office Expenses at Sec 75 | 2010 |  | 2010 | SMARTWORLD THE EDITION | Shoe Point | 9110000072 | 19 |  |  | 2023-04-19 | Kitchen/Crockery items | NO | 50 | 47.66 | 2383 | 2811.94 | 2287.68 | 2699.46 | 95.32 | 2287.68 | 2699.47 | ZMAT | 2025-01-20 | 2025-03-20
RE/0066-SOE-75 | Site Office Expenses at Sec 75 | 2010 |  | 2010 | SMARTWORLD THE EDITION | Shoe Point | 9110000072 | 20 |  |  | 2023-04-19 | Kitchen/Crockery items | NO | 50 | 44.49 | 2224.5 | 2624.91 | 2135.53 | 2519.92 | 88.97 | 2135.52 | 2519.92 | ZMAT | 2025-01-20 | 2025-03-20
RE/0066-SOE-75 | Site Office Expenses at Sec 75 | 2010 |  | 2010 | SMARTWORLD THE EDITION | Shoe Point | 9110000072 | 21 |  |  | 2023-04-19 | Kitchen/Crockery items | NO | 5 | 47.66 | 238.3 | 281.19 | 238.31 | 281.2 | 0.01 | 238.3 | 281.2 | ZMAT | 2025-01-20 | 2025-03-20
RE/0066-SOE-75 | Site Office Expenses at Sec 75 | 2010 |  | 2010 | SMARTWORLD THE EDITION | Shoe Point | 9110000072 | 22 |  |  | 2023-04-19 | Kitchen/Crockery items | NO | 34 | 355.93 | 12101.62 | 14279.91 | 11389.76 | 13439.92 | 711.86 | 11389.76 | 13439.92 | ZMAT | 2025-01-20 | 2025-03-20
RE/0066-SOE-75 | Site Office Expenses at Sec 75 | 2010 |  | 2010 | SMARTWORLD THE EDITION | Shoe Point | 9110000072 | 23 |  |  | 2023-04-19 | Kitchen/Crockery items | NO | 100 | 136.94 | 13694 | 15337.28 | 13146.24 | 14723.79 | 547.76 | 13146.24 | 14723.78 | ZMAT | 2025-01-20 | 2025-03-20
RE/0066-SOE-75 | Site Office Expenses at Sec 75 | 2010 |  | 2010 | SMARTWORLD THE EDITION | Shoe Point | 9110000072 | 24 |  |  | 2023-04-19 | Kitchen/Crockery items | NO | 2 | 837.05 | 1674.1 | 1874.99 | 1674.11 | 1875 | 0.01 | 1674.1 | 1875 | ZMAT | 2025-01-20 | 2025-03-20
RE/0066-SOE-75 | Site Office Expenses at Sec 75 | 2010 |  | 2010 | SMARTWORLD THE EDITION | Shoe Point | 9110000072 | 25 |  |  | 2023-04-19 | Kitchen/Crockery items | NO | 2 | 656.25 | 1312.5 | 1470 | 1312.5 | 1470 | 0 | 1312.5 | 1470 | ZMAT | 2025-01-20 | 2025-03-20
RE/0066-SOE-75 | Site Office Expenses at Sec 75 | 2010 |  | 2010 | SMARTWORLD THE EDITION | Shoe Point | 9110000072 | 26 |  |  | 2023-04-19 | Kitchen/Crockery items | NO | 2 | 194.64 | 389.28 | 435.99 | 389.29 | 436 | 0.01 | 389.28 | 436 | ZMAT | 2025-01-20 | 2025-03-20
RE/0066-SOE-75 | Site Office Expenses at Sec 75 | 2010 |  | 2010 | SMARTWORLD THE EDITION | Shoe Point | 9110000072 | 27 |  |  | 2023-04-19 | Housekeeping Items (CWIP) | NO | 2 | 1186.6 | 2373.2 | 2657.98 | 1186.61 | 1329 | 1186.59 | 1186.6 | 1329 | ZMAT | 2025-01-20 | 2025-03-20
RE/0066-SOE-75 | Site Office Expenses at Sec 75 | 2010 |  | 2010 | SMARTWORLD THE EDITION | Shoe Point | 9110000072 | 28 |  |  | 2023-04-19 | Housekeeping Items (CWIP) | NO | 1 | 1025.89 | 1025.89 | 1149 | 1025.89 | 1149 | 0 | 1025.89 | 1149 | ZMAT | 2025-01-20 | 2025-03-20
RE/0066-SOE-75 | Site Office Expenses at Sec 75 | 2010 |  | 2010 | SMARTWORLD THE EDITION | Shoe Point | 9110000072 | 29 |  |  | 2023-04-19 | Housekeeping Items (CWIP) | NO | 5 | 70.53 | 352.65 | 394.97 | 352.65 | 394.97 | 0 | 352.65 | 394.97 | ZMAT | 2025-01-20 | 2025-03-20
RE/0066-SOE-75 | Site Office Expenses at Sec 75 | 2010 |  | 2010 | SMARTWORLD THE EDITION | Shoe Point | 9110000072 | 30 |  |  | 2023-04-19 | Housekeeping Items (CWIP) | NO | 4 | 95.78 | 383.12 | 452.08 | 383.13 | 452.09 | 0.01 | 383.12 | 452.09 | ZMAT | 2025-01-20 | 2025-03-20
RE/0066-SOE-75 | Site Office Expenses at Sec 75 | 2010 |  | 2010 | SMARTWORLD THE EDITION | Shoe Point | 9110000072 | 31 |  |  | 2023-04-19 | Kitchen/Crockery items | NO | 4 | 652 | 2608 | 2920.96 | 1956 | 2190.72 | 652 | 1956 | 2190.72 | ZMAT | 2025-01-20 | 2025-03-20
RE/0066-SOE-75 | Site Office Expenses at Sec 75 | 2010 |  | 2010 | SMARTWORLD THE EDITION | Shoe Point | 9110000072 | 32 |  |  | 2023-04-19 | Housekeeping Items (CWIP) | NO | 4 | 72 | 288 | 302.4 | 288 | 302.4 | 0 | 288 | 302.4 | ZMAT | 2025-01-20 | 2025-03-20
RE/0066-SOE-75 | Site Office Expenses at Sec 75 | 2010 |  | 2010 | SMARTWORLD THE EDITION | Shoe Point | 9110000072 | 33 |  |  | 2023-04-19 | Kitchen/Crockery items | NO | 20 | 338.13 | 6762.6 | 7979.87 | 6762.6 | 7979.87 | 0 | 6762.6 | 7979.87 | ZMAT | 2025-01-20 | 2025-03-20
RE/0066-SOE-75 | Site Office Expenses at Sec 75 | 2010 |  | 2010 | SMARTWORLD THE EDITION | Shoe Point | 9110000072 | 34 |  |  | 2023-04-19 | Kitchen/Crockery items | NO | 1 | 238.34 | 238.34 | 281.24 | 238.35 | 281.25 | 0.01 | 238.34 | 281.25 | ZMAT | 2025-01-20 | 2025-03-20
RE/0066-SOE-75 | Site Office Expenses at Sec 75 | 2010 |  | 2010 | SMARTWORLD THE EDITION | Shoe Point | 9110000072 | 35 |  |  | 2023-04-19 | Housekeeping Items (CWIP) | NO | 2 | 5325 | 10650 | 12567 | 0 | 0 | 10650 | 0 | 0 | ZMAT | 2025-01-20 | 2025-03-20
RE/0066-SOE-75 | Site Office Expenses at Sec 75 | 2010 |  | 2010 | SMARTWORLD THE EDITION | Shoe Point | 9110000072 | 36 |  |  | 2023-04-19 | Housekeeping Items (CWIP) | NO | 2 | 254.23 | 508.46 | 599.98 | 508.47 | 599.99 | 0.01 | 508.46 | 599.99 | ZMAT | 2025-01-20 | 2025-03-20
RE/0066-SOE-75 | Site Office Expenses at Sec 75 | 2010 |  | 2010 | SMARTWORLD THE EDITION | Shoe Point | 9110000072 | 37 |  |  | 2023-04-19 | Kitchen/Crockery items | NO | 2 | 363.55 | 727.1 | 857.98 | 727.1 | 857.98 | 0 | 727.1 | 857.98 | ZMAT | 2025-01-20 | 2025-03-20
RE/0066-SOE-75 | Site Office Expenses at Sec 75 | 2010 |  | 2010 | SMARTWORLD THE EDITION | Shoe Point | 9110000072 | 38 |  |  | 2023-04-19 | Kitchen/Crockery items | NO | 2 | 270.33 | 540.66 | 637.98 | 540.66 | 637.98 | 0 | 540.66 | 637.98 | ZMAT | 2025-01-20 | 2025-03-20
RE/0066-SOE-75 | Site Office Expenses at Sec 75 | 2010 |  | 2010 | SMARTWORLD THE EDITION | Shoe Point | 9110000072 | 39 |  |  | 2023-04-19 | Housekeeping Items (CWIP) | NO | 2 | 549.15 | 1098.3 | 1295.99 | 1098.31 | 1296 | 0.01 | 1098.3 | 1296 | ZMAT | 2025-01-20 | 2025-03-20
RE/0066-SOE-75 | Site Office Expenses at Sec 75 | 2010 |  | 2010 | SMARTWORLD THE EDITION | Shoe Point | 9110000072 | 40 |  |  | 2023-04-19 | Housekeeping Items (CWIP) | NO | 1 | 160.15 | 160.15 | 188.98 | 160.15 | 188.98 | 0 | 160.15 | 188.98 | ZMAT | 2025-01-20 | 2025-03-20
RE/0066-SOE-75 | Site Office Expenses at Sec 75 | 2010 |  | 2010 | SMARTWORLD THE EDITION | Shoe Point | 9110000072 | 41 |  |  | 2023-04-19 | Housekeeping Items (CWIP) | NO | 50 | 5 | 250 | 295 | 250 | 295 | 0 | 250 | 295 | ZMAT | 2025-01-20 | 2025-03-20
RE/0066-SOE-75 | Site Office Expenses at Sec 75 | 2010 |  | 2010 | SMARTWORLD THE EDITION | Shoe Point | 9110000072 | 42 |  |  | 2023-04-19 | Kitchen/Crockery items | NO | 2 | 378.17 | 756.34 | 892.48 | 756.35 | 892.49 | 0.01 | 756.34 | 892.49 | ZMAT | 2025-01-20 | 2025-03-20
RE/0066-SOE-75 | Site Office Expenses at Sec 75 | 2010 |  | 2010 | SMARTWORLD THE EDITION | Shoe Point | 9110000072 | 43 |  |  | 2023-04-19 | Kitchen/Crockery items | NO | 6 | 80.76 | 484.56 | 571.78 | 484.57 | 571.79 | 0.01 | 484.56 | 571.76 | ZMAT | 2025-01-20 | 2025-03-20
RE/0066-SOE-75 | Site Office Expenses at Sec 75 | 2010 |  | 2010 | SMARTWORLD THE EDITION | Shoe Point | 9110000072 | 44 |  |  | 2023-04-19 | Housekeeping Items (CWIP) | NO | 4 | 110.16 | 440.64 | 519.96 | 0 | 0 | 440.64 | 0 | 0 | ZMAT | 2025-01-20 | 2025-03-20
RE/0066-SOE-75 | Site Office Expenses at Sec 75 | 2010 |  | 2010 | SMARTWORLD THE EDITION | Superior NetworksMr. Manoj (9911163201) | 9110000079 | 1 |  |  | 2023-04-26 | Molex Cat-6 angular jack panels-24 ports | NO | 13 | 5690 | 73970 | 87284.6 | 73970 | 87284.6 | 0 | 73970 | 87284.6 | ZMAT | 2025-01-20 | 2025-03-20
RE/0066-SOE-75 | Site Office Expenses at Sec 75 | 2010 |  | 2010 | SMARTWORLD THE EDITION | Superior NetworksMr. Manoj (9911163201) | 9110000079 | 2 |  |  | 2023-04-26 | Molex Cat-6 jack panels-24 ports loaded | NO | 2 | 5580 | 11160 | 13168.8 | 11160 | 13168.8 | 0 | 11160 | 13168.8 | ZMAT | 2025-01-20 | 2025-03-20
RE/0066-SOE-75 | Site Office Expenses at Sec 75 | 2010 |  | 2010 | SMARTWORLD THE EDITION | Superior NetworksMr. Manoj (9911163201) | 9110000079 | 3 |  |  | 2023-04-26 | Molex 50 Pair Voice Patch Panel | NO | 3 | 5520 | 16560 | 19540.8 | 16560 | 19540.8 | 0 | 16560 | 19540.8 | ZMAT | 2025-01-20 | 2025-03-20
RE/0066-SOE-75 | Site Office Expenses at Sec 75 | 2010 |  | 2010 | SMARTWORLD THE EDITION | Superior NetworksMr. Manoj (9911163201) | 9110000079 | 4 |  |  | 2023-04-26 | I/O | NO | 350 | 172 | 60200 | 71036 | 60200 | 71036 | 0 | 60200 | 71036 | ZMAT | 2025-01-20 | 2025-03-20
RE/0066-SOE-75 | Site Office Expenses at Sec 75 | 2010 |  | 2010 | SMARTWORLD THE EDITION | Superior NetworksMr. Manoj (9911163201) | 9110000079 | 5 |  |  | 2023-04-26 | Face Plate Dual | NO | 150 | 58 | 8700 | 10266 | 8700 | 10266 | 0 | 8700 | 10266 | ZMAT | 2025-01-20 | 2025-03-20
RE/0066-SOE-75 | Site Office Expenses at Sec 75 | 2010 |  | 2010 | SMARTWORLD THE EDITION | Superior NetworksMr. Manoj (9911163201) | 9110000079 | 6 |  |  | 2023-04-26 | Molex Cat-6 Patch Cord-2 Mtrs | NO | 450 | 172 | 77400 | 91332 | 77400 | 91332 | 0 | 77400 | 91332 | ZMAT | 2025-01-20 | 2025-03-20
RE/0066-SOE-75 | Site Office Expenses at Sec 75 | 2010 |  | 2010 | SMARTWORLD THE EDITION | Superior NetworksMr. Manoj (9911163201) | 9110000079 | 7 |  |  | 2023-04-26 | HDMI Cable 5 Mtrs | NO | 30 | 990 | 29700 | 35046 | 29700 | 35046 | 0 | 29700 | 35046 | ZMAT | 2025-01-20 | 2025-03-20
RE/0066-SOE-75 | Site Office Expenses at Sec 75 | 2010 |  | 2010 | SMARTWORLD THE EDITION | Superior NetworksMr. Manoj (9911163201) | 9110000079 | 8 |  |  | 2023-04-26 | PWRINJ6 POE Injector | NO | 12 | 5760 | 69120 | 81561.6 | 69120 | 81561.6 | 0 | 69120 | 81561.6 | ZMAT | 2025-01-20 | 2025-03-20
RE/0066-SOE-75 | Site Office Expenses at Sec 75 | 2010 |  | 2010 | SMARTWORLD THE EDITION | Superior NetworksMr. Manoj (9911163201) | 9110000079 | 9 |  |  | 2023-04-26 | 45U Open Rack | NO | 1 | 45240 | 45240 | 53383.2 | 45240 | 53383.2 | 0 | 45240 | 53383.2 | ZMAT | 2025-01-20 | 2025-03-20
RE/0066-SOE-75 | Site Office Expenses at Sec 75 | 2010 |  | 2010 | SMARTWORLD THE EDITION | Superior NetworksMr. Manoj (9911163201) | 9110000079 | 10 |  |  | 2023-04-26 | PDU-5/15 AMP-12Socket-with MCB | NO | 1 | 3250 | 3250 | 3835 | 3250 | 3835 | 0 | 3250 | 3835 | ZMAT | 2025-01-20 | 2025-03-20
RE/0066-SOE-75 | Site Office Expenses at Sec 75 | 2010 |  | 2010 | SMARTWORLD THE EDITION | Superior NetworksMr. Manoj (9911163201) | 9110000079 | 11 |  |  | 2023-04-26 | 24 Port L3 Switch C9300-24T-A | NO | 2 | 290200 | 580400 | 684872 | 580400 | 684872 | 0 | 580400 | 684872 | ZMAT | 2025-01-20 | 2025-03-20
RE/0066-SOE-75 | Site Office Expenses at Sec 75 | 2010 |  | 2010 | SMARTWORLD THE EDITION | Superior NetworksMr. Manoj (9911163201) | 9110000079 | 12 |  |  | 2023-04-26 | DNA of 3 years for C9300-24T-A | NO | 2 | 83700 | 167400 | 197532 | 167400 | 197532 | 0 | 167400 | 197532 | ZMAT | 2025-01-20 | 2025-03-20
RE/0066-SOE-75 | Site Office Expenses at Sec 75 | 2010 |  | 2010 | SMARTWORLD THE EDITION | Superior NetworksMr. Manoj (9911163201) | 9110000079 | 13 |  |  | 2023-04-26 | 24 Port GIGA POE Manageable Switches,CBS | NO | 2 | 34800 | 69600 | 82128 | 69600 | 82128 | 0 | 69600 | 82128 | ZMAT | 2025-01-20 | 2025-03-20
RE/0066-SOE-75 | Site Office Expenses at Sec 75 | 2010 |  | 2010 | SMARTWORLD THE EDITION | Superior NetworksMr. Manoj (9911163201) | 9110000079 | 14 |  |  | 2023-04-26 | Cisco Catalyst 9115AX Series Access Poi | NO | 12 | 55650 | 667800 | 788004 | 667800 | 788004 | 0 | 667800 | 788004 | ZMAT | 2025-01-20 | 2025-03-20
RE/0066-SOE-75 | Site Office Expenses at Sec 75 | 2010 |  | 2010 | SMARTWORLD THE EDITION | Superior NetworksMr. Manoj (9911163201) | 9110000079 | 15 |  |  | 2023-04-26 | Server Rack-27-600W x1000D,Top Cover wit | NO | 1 | 29600 | 29600 | 34928 | 29600 | 34928 | 0 | 29600 | 34928 | ZMAT | 2025-01-20 | 2025-03-20
RE/0066-SOE-75 | Site Office Expenses at Sec 75 | 2010 |  | 2010 | SMARTWORLD THE EDITION | Superior NetworksMr. Manoj (9911163201) | 9110000079 | 16 |  |  | 2023-04-26 | Closed Floor Mount Network Rack Presiden | NO | 1 | 36800 | 36800 | 43424 | 36800 | 43424 | 0 | 36800 | 43424 | ZMAT | 2025-01-20 | 2025-03-20
RE/0066-SOE-75 | Site Office Expenses at Sec 75 | 2010 |  | 2010 | SMARTWORLD THE EDITION | Superior NetworksMr. Manoj (9911163201) | 9110000079 | 17 |  |  | 2023-04-26 | 24 Port GIGAManageable Switches CBS-350- | NO | 10 | 21900 | 219000 | 258420 | 219000 | 258420 | 0 | 219000 | 258420 | ZMAT | 2025-01-20 | 2025-03-20
RE/0066-SOE-75 | Site Office Expenses at Sec 75 | 2010 |  | 2010 | SMARTWORLD THE EDITION | Gloplast Advertising Pvt. Ltd. | 9110000083 | 1 |  |  | 2023-04-28 | Machan | NO | 2 | 219500 | 439000 | 518020 | 439000 | 518020 | 0 | 439000 | 518020 | ZMAT | 2025-01-20 | 2025-03-20
RE/0066-SOE-75 | Site Office Expenses at Sec 75 | 2010 |  | 2010 | SMARTWORLD THE EDITION | PalbisRahul | 9110000087 | 2 |  |  | 2023-05-03 | Cookies | NO | 75600 | 1 | 75600 | 89208 | 75600 | 89208 | 0 | 75600 | 89208 | ZMAT | 2025-01-20 | 2025-03-20
RE/0066-SOE-75 | Site Office Expenses at Sec 75 | 2010 |  | 2010 | SMARTWORLD THE EDITION | Prime Solutions | 9110000101 | 10 |  |  | 2023-05-16 | JANITORIAL ITEMS_Tissue | NO | 90511.78 | 1 | 90511.78 | 106803.9 | 76704.9 | 90511.78 | 13806.88 | 76704.6 | 90511.45 | ZMAT | 2025-01-20 | 2025-03-20
RE/0066-SOE-75 | Site Office Expenses at Sec 75 | 2010 |  | 2010 | SMARTWORLD THE EDITION | Bright Star Hospitality Services PvManoj | 9110000105 | 10 |  |  | 2023-05-17 | Pantry_Food Items_Chips | NO | 21000 | 15.62 | 328020 | 367382.4 | 116369 | 130333.28 | 211651 | 116399.24 | 130367 | ZMAT | 2025-01-20 | 2025-03-20
RE/0066-SOE-75 | Site Office Expenses at Sec 75 | 2010 |  | 2010 | SMARTWORLD THE EDITION | D D EnterprisesSushil Bajaj | 9110000111 | 10 |  |  | 2023-05-17 | Drinking Water | NO | 28800 | 4.89 | 140832 | 166181.76 | 0 | 0 | 140832 | 0 | 0 | ZMAT | 2025-01-20 | 2025-03-20
RE/0066-SOE-75 | Site Office Expenses at Sec 75 | 2010 |  | 2010 | SMARTWORLD THE EDITION | Luck Aqua | 9110000122 | 10 |  |  | 2023-05-23 | Drinking Water | NO | 9735 | 1 | 9735 | 10903.2 | 9735 | 10903.2 | 0 | 9734.64 | 10903 | ZMAT | 2025-01-20 | 2025-03-20
RE/0066-SOE-75 | Site Office Expenses at Sec 75 | 2010 |  | 2010 | SMARTWORLD THE EDITION | Luck Aqua | 9110000124 | 10 |  |  | 2023-05-24 | 20ltr drinking water at sec-75 | NO | 15000 | 1 | 15000 | 16800 | 0 | 0 | 15000 | 0 | 0 | ZMAT | 2025-01-20 | 2025-03-20
RE/0066-SOE-75 | Site Office Expenses at Sec 75 | 2010 |  | 2010 | SMARTWORLD THE EDITION | N S Concrete Pvt Ltd | 9110000128 | 10 |  |  | 2023-05-26 | Ready Mix Concrete M - 7.5 CWIP-75 | M3 | 19 | 3427.5 | 65122.5 | 76844.55 | 47985.01 | 56622.31 | 17137.49 | 47985 | 56622.3 | ZMAT | 2025-01-20 | 2025-03-20
RE/0066-SOE-75 | Site Office Expenses at Sec 75 | 2010 |  | 2010 | SMARTWORLD THE EDITION | N S Concrete Pvt Ltd | 9110000128 | 20 |  |  | 2023-05-26 | Ready Mix Concrete M - 25 CWIP-75 | M3 | 68 | 3945 | 268260 | 316546.8 | 0 | 0 | 268260 | 0 | 0 | ZMAT | 2025-01-20 | 2025-03-20
RE/0066-SOE-75 | Site Office Expenses at Sec 75 | 2010 |  | 2010 | SMARTWORLD THE EDITION | Treis Solutions LLP | 9110000139 | 10 |  |  | 2023-06-08 | Diesel | L | 13376 | 89.71 | 1199960.96 | 1199960.96 | 731136.5 | 731136.5 | 468824.46 | 703925.88 | 703925.88 | ZMAT | 2025-01-20 | 2025-03-20
RE/0066-SOE-75 | Site Office Expenses at Sec 75 | 2010 |  | 2010 | SMARTWORLD THE EDITION | Treis Solutions LLP | 9110000139 | 20 |  |  | 2023-06-08 | Diesel | L | 83 | 199 | 16517 | 19490.06 | 3383 | 3991.94 | 13134 | 3184 | 3757.12 | ZMAT | 2025-01-20 | 2025-03-20
RE/0066-SOE-75 | Site Office Expenses at Sec 75 | 2010 |  | 2010 | SMARTWORLD THE EDITION | Treis Solutions LLP | 9110000141 | 10 |  |  | 2023-06-08 | Diesel | L | 30000 | 90.21 | 2706300 | 2706300 | 1982003.91 | 1982003.91 | 724296.09 | 1969248.41 | 1969248.59 | ZMAT | 2025-01-20 | 2025-03-20
RE/0066-SOE-75 | Site Office Expenses at Sec 75 | 2010 |  | 2010 | SMARTWORLD THE EDITION | Treis Solutions LLP | 9110000141 | 30 |  |  | 2023-06-08 | Freight | L | 30 | 199 | 5970 | 7044.6 | 3781 | 4461.58 | 2189 | 3781 | 4461.7 | ZMAT | 2025-01-20 | 2025-03-20
RE/0066-SOE-75 | Site Office Expenses at Sec 75 | 2010 |  | 2010 | SMARTWORLD THE EDITION | Euronics Industries Private Limited | 9110000143 | 30 |  |  | 2023-06-08 | Paper Dispensar | NO | 9 | 2912.7 | 26214.3 | 30932.87 | 26214.31 | 30932.88 | 0.01 | 26214.3 | 30932.3 | ZMAT | 2025-01-20 | 2025-03-20
RE/0066-SOE-75 | Site Office Expenses at Sec 75 | 2010 |  | 2010 | SMARTWORLD THE EDITION | Shree Balaji RMC | 9110000146 | 10 |  |  | 2023-06-12 | Ready Mix Concrete M - 7.5 CWIP-75 | M3 | 171 | 3427.5 | 586102.5 | 691600.95 | 568965.01 | 671378.71 | 17137.49 | 568965 | 671379 | ZMAT | 2025-01-20 | 2025-03-20
RE/0066-SOE-75 | Site Office Expenses at Sec 75 | 2010 |  | 2010 | SMARTWORLD THE EDITION | Shree Balaji RMC | 9110000146 | 20 |  |  | 2023-06-12 | Ready Mix Concrete M - 25 CWIP-75 | M3 | 322 | 3945 | 1270290 | 1498942.2 | 1234785 | 1457046.3 | 35505 | 1234785 | 1457047 | ZMAT | 2025-01-20 | 2025-03-20
RE/0066-SOE-75 | Site Office Expenses at Sec 75 | 2010 |  | 2010 | SMARTWORLD THE EDITION | Shree Balaji RMC | 9110000146 | 30 |  |  | 2023-06-12 | Ready Mix Concrete M-30 CWIP-75 | M3 | 55 | 4125 | 226875 | 267712.5 | 220687.5 | 260411.25 | 6187.5 | 220687.5 | 260411.5 | ZMAT | 2025-01-20 | 2025-03-20
RE/0066-SOE-75 | Site Office Expenses at Sec 75 | 2010 |  | 2010 | SMARTWORLD THE EDITION | Venus Sales Corporation | 9110000173 | 10 |  |  | 2023-06-26 | Ripple Glass 12 month | NO | 100000 | 2 | 200000 | 236000 | 180000 | 212400 | 20000 | 180000 | 212400 | ZMAT | 2025-01-20 | 2025-03-20
RE/0066-SOE-75 | Site Office Expenses at Sec 75 | 2010 |  | 2010 | SMARTWORLD THE EDITION | Venus Sales Corporation | 9110000174 | 10 |  |  | 2023-06-26 | Ripple Glass 12 month | NO | 60000 | 2 | 120000 | 141600 | 0 | 0 | 120000 | 0 | 0 | ZMAT | 2025-01-20 | 2025-03-20
RE/0066-SOE-75 | Site Office Expenses at Sec 75 | 2010 |  | 2010 | SMARTWORLD THE EDITION | Book Mark Office AutomationPreeti Shivhare | 9110000175 | 10 |  |  | 2023-06-26 | Stationery Items | NO | 44501.69 | 1 | 44501.69 | 52511.99 | 44501.69 | 52511.99 | 0 | 44501.69 | 52511.97 | ZMAT | 2025-01-20 | 2025-03-20
RE/0066-SOE-75 | Site Office Expenses at Sec 75 | 2010 |  | 2010 | SMARTWORLD THE EDITION | Book Mark Office AutomationPreeti Shivhare | 9110000175 | 20 |  |  | 2023-06-26 | Stationery Items | NO | 22076 | 1 | 22076 | 24725.12 | 22076 | 24725.12 | 0 | 22076 | 24725.12 | ZMAT | 2025-01-20 | 2025-03-20
RE/0066-SOE-75 | Site Office Expenses at Sec 75 | 2010 |  | 2010 | SMARTWORLD THE EDITION | Book Mark Office AutomationPreeti Shivhare | 9110000175 | 30 |  |  | 2023-06-26 | Stationery Items | NO | 70 | 1 | 70 | 73.5 | 70 | 73.5 | 0 | 70 | 73.6 | ZMAT | 2025-01-20 | 2025-03-20
RE/0066-SOE-75 | Site Office Expenses at Sec 75 | 2010 |  | 2010 | SMARTWORLD THE EDITION | Treis Solutions LLP | 9110000183 | 10 |  |  | 2023-06-29 | Diesel | L | 13376 | 90.21 | 1206648.96 | 1206648.96 | 0 | 0 | 1206648.96 | 0 | 0 | ZMAT | 2025-01-20 | 2025-03-20
RE/0066-SOE-75 | Site Office Expenses at Sec 75 | 2010 |  | 2010 | SMARTWORLD THE EDITION | Treis Solutions LLP | 9110000183 | 20 |  |  | 2023-06-29 | freight | L | 4 | 199 | 796 | 939.28 | 0 | 0 | 796 | 0 | 0 | ZMAT | 2025-01-20 | 2025-03-20
RE/0066-SOE-75 | Site Office Expenses at Sec 75 | 2010 |  | 2010 | SMARTWORLD THE EDITION | Shoe Point | 9110000195 | 10 |  |  | 2023-07-12 | Coffee Mug | NO | 6 | 155 | 930 | 1097.4 | 930 | 1097.4 | 0 | 930 | 1098 | ZMAT | 2025-01-20 | 2025-03-20
RE/0066-SOE-75 | Site Office Expenses at Sec 75 | 2010 |  | 2010 | SMARTWORLD THE EDITION | Shoe Point | 9110000195 | 20 |  |  | 2023-07-12 | Water Glass | NO | 6 | 355.93 | 2135.58 | 2519.98 | 2135.58 | 2519.99 | 0 | 2135.58 | 2519.58 | ZMAT | 2025-01-20 | 2025-03-20
RE/0066-SOE-75 | Site Office Expenses at Sec 75 | 2010 |  | 2010 | SMARTWORLD THE EDITION | Shoe Point | 9110000195 | 30 |  |  | 2023-07-12 | Juice Glass | NO | 6 | 253.38 | 1520.28 | 1793.93 | 1520.29 | 1793.94 | 0.01 | 1520.28 | 1794.28 | ZMAT | 2025-01-20 | 2025-03-20
RE/0066-SOE-75 | Site Office Expenses at Sec 75 | 2010 |  | 2010 | SMARTWORLD THE EDITION | Shoe Point | 9110000195 | 40 |  |  | 2023-07-12 | Tea Mug With soccer Plates | NO | 6 | 973.72 | 5842.32 | 6893.94 | 0 | 0 | 5842.32 | 0 | 0 | ZMAT | 2025-01-20 | 2025-03-20
RE/0066-SOE-75 | Site Office Expenses at Sec 75 | 2010 |  | 2010 | SMARTWORLD THE EDITION | Shoe Point | 9110000195 | 50 |  |  | 2023-07-12 | Dinner Plates | NO | 6 | 66.73 | 400.38 | 472.45 | 400.38 | 472.45 | 0 | 400.38 | 472.38 | ZMAT | 2025-01-20 | 2025-03-20
RE/0066-SOE-75 | Site Office Expenses at Sec 75 | 2010 |  | 2010 | SMARTWORLD THE EDITION | Shoe Point | 9110000195 | 60 |  |  | 2023-07-12 | Vegetables Bowl | NO | 6 | 44.49 | 266.94 | 314.99 | 266.94 | 314.99 | 0 | 266.94 | 314.94 | ZMAT | 2025-01-20 | 2025-03-20
RE/0066-SOE-75 | Site Office Expenses at Sec 75 | 2010 |  | 2010 | SMARTWORLD THE EDITION | Shoe Point | 9110000195 | 70 |  |  | 2023-07-12 | Soup Bowl | NO | 6 | 47.66 | 285.96 | 337.43 | 285.97 | 337.44 | 0.01 | 285.96 | 337.96 | ZMAT | 2025-01-20 | 2025-03-20
RE/0066-SOE-75 | Site Office Expenses at Sec 75 | 2010 |  | 2010 | SMARTWORLD THE EDITION | Shoe Point | 9110000195 | 80 |  |  | 2023-07-12 | Fruit Bowl | NO | 6 | 100.84 | 605.04 | 713.95 | 605.04 | 713.95 | 0 | 605.04 | 713.04 | ZMAT | 2025-01-20 | 2025-03-20
RE/0066-SOE-75 | Site Office Expenses at Sec 75 | 2010 |  | 2010 | SMARTWORLD THE EDITION | Shoe Point | 9110000195 | 90 |  |  | 2023-07-12 | Dinner Mates | NO | 3 | 363.55 | 1090.65 | 1286.97 | 1090.65 | 1286.97 | 0 | 1090.65 | 1286.65 | ZMAT | 2025-01-20 | 2025-03-20
RE/0066-SOE-75 | Site Office Expenses at Sec 75 | 2010 |  | 2010 | SMARTWORLD THE EDITION | Shoe Point | 9110000195 | 100 |  |  | 2023-07-12 | Cloth Napkins | NO | 6 | 72 | 432 | 453.6 | 432 | 453.6 | 0 | 432 | 454 | ZMAT | 2025-01-20 | 2025-03-20
RE/0066-SOE-75 | Site Office Expenses at Sec 75 | 2010 |  | 2010 | SMARTWORLD THE EDITION | Shoe Point | 9110000195 | 110 |  |  | 2023-07-12 | Candle for dining table | NO | 6 | 642.37 | 3854.22 | 4547.98 | 1284.74 | 1515.99 | 2569.48 | 1284.74 | 1516.74 | ZMAT | 2025-01-20 | 2025-03-20
RE/0066-SOE-75 | Site Office Expenses at Sec 75 | 2010 |  | 2010 | SMARTWORLD THE EDITION | Shoe Point | 9110000195 | 120 |  |  | 2023-07-12 | Mug Coaster leather | NO | 6 | 338.13 | 2028.78 | 2393.96 | 0 | 0 | 2028.78 | 0 | 0 | ZMAT | 2025-01-20 | 2025-03-20
RE/0066-SOE-75 | Site Office Expenses at Sec 75 | 2010 |  | 2010 | SMARTWORLD THE EDITION | Shoe Point | 9110000195 | 130 |  |  | 2023-07-12 | Food serving tray leather | NO | 6 | 2481.35 | 14888.1 | 17567.96 | 2481.35 | 2927.99 | 12406.75 | 2481.35 | 2927.35 | ZMAT | 2025-01-20 | 2025-03-20
RE/0066-SOE-75 | Site Office Expenses at Sec 75 | 2010 |  | 2010 | SMARTWORLD THE EDITION | Shoe Point | 9110000195 | 140 |  |  | 2023-07-12 | Hand Towel For washroom | NO | 6 | 72 | 432 | 453.6 | 432 | 453.6 | 0 | 432 | 454 | ZMAT | 2025-01-20 | 2025-03-20
RE/0066-SOE-75 | Site Office Expenses at Sec 75 | 2010 |  | 2010 | SMARTWORLD THE EDITION | Shoe Point | 9110000195 | 150 |  |  | 2023-07-12 | Napkins Holder | NO | 2 | 422.88 | 845.76 | 998 | 845.76 | 998 | 0 | 845.76 | 997.76 | ZMAT | 2025-01-20 | 2025-03-20
RE/0066-SOE-75 | Site Office Expenses at Sec 75 | 2010 |  | 2010 | SMARTWORLD THE EDITION | Shoe Point | 9110000195 | 160 |  |  | 2023-07-12 | Toothpick | NO | 2 | 101.22 | 202.44 | 238.88 | 0 | 0 | 202.44 | 0 | 0 | ZMAT | 2025-01-20 | 2025-03-20
RE/0066-SOE-75 | Site Office Expenses at Sec 75 | 2010 |  | 2010 | SMARTWORLD THE EDITION | Shoe Point | 9110000195 | 170 |  |  | 2023-07-12 | Pepper pot | NO | 4 | 158.26 | 633.04 | 746.99 | 0 | 0 | 633.04 | 0 | 0 | ZMAT | 2025-01-20 | 2025-03-20
RE/0066-SOE-75 | Site Office Expenses at Sec 75 | 2010 |  | 2010 | SMARTWORLD THE EDITION | Shoe Point | 9110000195 | 180 |  |  | 2023-07-12 | Sugar Bowl | NO | 2 | 238.34 | 476.68 | 562.48 | 476.69 | 562.49 | 0.01 | 476.68 | 562.68 | ZMAT | 2025-01-20 | 2025-03-20
RE/0066-SOE-75 | Site Office Expenses at Sec 75 | 2010 |  | 2010 | SMARTWORLD THE EDITION | Shoe Point | 9110000195 | 190 |  |  | 2023-07-12 | Cream jug | NO | 2 | 378.17 | 756.34 | 892.48 | 756.35 | 892.49 | 0.01 | 756.34 | 892.34 | ZMAT | 2025-01-20 | 2025-03-20
RE/0066-SOE-75 | Site Office Expenses at Sec 75 | 2010 |  | 2010 | SMARTWORLD THE EDITION | Shoe Point | 9110000195 | 200 |  |  | 2023-07-12 | salt Cellar | NO | 2 | 158.26 | 316.52 | 373.49 | 316.53 | 373.5 | 0.01 | 474.78 | 560.78 | ZMAT | 2025-01-20 | 2025-03-20
RE/0066-SOE-75 | Site Office Expenses at Sec 75 | 2010 |  | 2010 | SMARTWORLD THE EDITION | Shoe Point | 9110000195 | 210 |  |  | 2023-07-12 | Dinner Knife | NO | 3 | 169 | 507 | 598.26 | 169 | 199.42 | 338 | 169 | 199 | ZMAT | 2025-01-20 | 2025-03-20
RE/0066-SOE-75 | Site Office Expenses at Sec 75 | 2010 |  | 2010 | SMARTWORLD THE EDITION | Shoe Point | 9110000195 | 220 |  |  | 2023-07-12 | Chips Bowl | NO | 6 | 94.7 | 568.2 | 670.48 | 568.2 | 670.48 | 0 | 568.2 | 670.2 | ZMAT | 2025-01-20 | 2025-03-20
RE/0066-SOE-75 | Site Office Expenses at Sec 75 | 2010 |  | 2010 | SMARTWORLD THE EDITION | Shoe Point | 9110000195 | 230 |  |  | 2023-07-12 | Sugar Pot | NO | 3 | 238.34 | 715.02 | 843.72 | 715.03 | 843.73 | 0.01 | 715.02 | 843.02 | ZMAT | 2025-01-20 | 2025-03-20
RE/0066-SOE-75 | Site Office Expenses at Sec 75 | 2010 |  | 2010 | SMARTWORLD THE EDITION | Shoe Point | 9110000195 | 240 |  |  | 2023-07-12 | Sugar Tong | NO | 3 | 77 | 231 | 272.58 | 154 | 181.72 | 77 | 154 | 182 | ZMAT | 2025-01-20 | 2025-03-20
RE/0066-SOE-75 | Site Office Expenses at Sec 75 | 2010 |  | 2010 | SMARTWORLD THE EDITION | Shoe Point | 9110000195 | 250 |  |  | 2023-07-12 | Tea spoon | NO | 6 | 133.94 | 803.64 | 948.3 | 803.64 | 948.3 | 0 | 803.64 | 947.64 | ZMAT | 2025-01-20 | 2025-03-20
RE/0066-SOE-75 | Site Office Expenses at Sec 75 | 2010 |  | 2010 | SMARTWORLD THE EDITION | Shoe Point | 9110000195 | 260 |  |  | 2023-07-12 | AP spoon | NO | 6 | 136.94 | 821.64 | 969.54 | 821.64 | 969.54 | 0 | 821.64 | 969.64 | ZMAT | 2025-01-20 | 2025-03-20
RE/0066-SOE-75 | Site Office Expenses at Sec 75 | 2010 |  | 2010 | SMARTWORLD THE EDITION | Shoe Point | 9110000195 | 270 |  |  | 2023-07-12 | Ap Fork | NO | 6 | 136.91 | 821.46 | 969.32 | 821.47 | 969.33 | 0.01 | 821.46 | 969.46 | ZMAT | 2025-01-20 | 2025-03-20
RE/0066-SOE-75 | Site Office Expenses at Sec 75 | 2010 |  | 2010 | SMARTWORLD THE EDITION | Shoe Point | 9110000195 | 280 |  |  | 2023-07-12 | Chopping Knife | NO | 3 | 103.38 | 310.14 | 365.97 | 310.14 | 365.97 | 0 | 310.14 | 366.14 | ZMAT | 2025-01-20 | 2025-03-20
RE/0066-SOE-75 | Site Office Expenses at Sec 75 | 2010 |  | 2010 | SMARTWORLD THE EDITION | Ceasefire Industries Private LimiteRahul Kumar | 9110000202 | 10 |  |  | 2023-07-19 | FIRE EXTINGUISHER ABC TYPE 4 KG CWIP-75 | NO | 8 | 6187.5 | 49500 | 58410 | 49500 | 58410 | 0 | 49500 | 58410 | ZMAT | 2025-01-20 | 2025-03-20
RE/0066-SOE-75 | Site Office Expenses at Sec 75 | 2010 |  | 2010 | SMARTWORLD THE EDITION | Ceasefire Industries Private LimiteRahul Kumar | 9110000202 | 20 |  |  | 2023-07-19 | FIRE EXTINGUISHER ABC TYPE 2 KG CWIP-75 | NO | 4 | 4500 | 18000 | 21240 | 18000 | 21240 | 0 | 18000 | 21240 | ZMAT | 2025-01-20 | 2025-03-20
RE/0066-SOE-75 | Site Office Expenses at Sec 75 | 2010 |  | 2010 | SMARTWORLD THE EDITION | Ceasefire Industries Private LimiteRahul Kumar | 9110000202 | 30 |  |  | 2023-07-19 | FIRE EXTINGUISHER CO2 TYPE 2 KG CWIP-75 | NO | 5 | 7807.5 | 39037.5 | 46064.25 | 39037.5 | 46064.25 | 0 | 39037.5 | 46064.3 | ZMAT | 2025-01-20 | 2025-03-20
RE/0066-SOE-75 | Site Office Expenses at Sec 75 | 2010 |  | 2010 | SMARTWORLD THE EDITION | Ceasefire Industries Private LimiteRahul Kumar | 9110000202 | 40 |  |  | 2023-07-19 | Freight | NO | 1 | 1275 | 1275 | 1504.5 | 1275 | 1504.5 | 0 | 1275 | 1504.5 | ZMAT | 2025-01-20 | 2025-03-20
RE/0066-SOE-75 | Site Office Expenses at Sec 75 | 2010 |  | 2010 | SMARTWORLD THE EDITION | Corporate Telesystems Pvt LtdMs. Archna | 9110000205 | 80 |  |  | 2023-07-21 | Rack Mount Kit | NO | 1 | 1250 | 1250 | 1475 | 1250 | 1475 | 0 | 1250 | 1475 | ZMAT | 2025-01-20 | 2025-03-20
RE/0066-SOE-75 | Site Office Expenses at Sec 75 | 2010 |  | 2010 | SMARTWORLD THE EDITION | Corporate Telesystems Pvt LtdMs. Archna | 9110000205 | 90 |  |  | 2023-07-21 | Panasonic KX-T7703SX Landline Telephone | NO | 135 | 825 | 111375 | 131422.5 | 111375.42 | 131423 | 0.42 | 111375 | 131422.5 | ZMAT | 2025-01-20 | 2025-03-20
RE/0066-SOE-75 | Site Office Expenses at Sec 75 | 2010 |  | 2010 | SMARTWORLD THE EDITION | Commercial Equipment | 9110000206 | 10 |  |  | 2023-07-24 | CTM 500 kN | NO | 1 | 320900 | 320900 | 378662 | 320900 | 378662 | 0 | 320900 | 378662 | ZMAT | 2025-01-20 | 2025-03-20
RE/0066-SOE-75 | Site Office Expenses at Sec 75 | 2010 |  | 2010 | SMARTWORLD THE EDITION | Commercial Equipment | 9110000206 | 20 |  |  | 2023-07-24 | Humidity Chamber | NO | 1 | 260689.6 | 260689.6 | 307613.73 | 260689.49 | 307613.6 | 0.11 | 260689.3 | 307613.4 | ZMAT | 2025-01-20 | 2025-03-20
RE/0066-SOE-75 | Site Office Expenses at Sec 75 | 2010 |  | 2010 | SMARTWORLD THE EDITION | Commercial Equipment | 9110000206 | 30 |  |  | 2023-07-24 | Curing Tank , Coolin and heating | NO | 1 | 195517.56 | 195517.56 | 230710.72 | 195517.42 | 230710.56 | 0.14 | 195517.56 | 230710.56 | ZMAT | 2025-01-20 | 2025-03-20
RE/0066-SOE-75 | Site Office Expenses at Sec 75 | 2010 |  | 2010 | SMARTWORLD THE EDITION | Commercial Equipment | 9110000206 | 40 |  |  | 2023-07-24 | Vicate Apparatus with mould and 3 needle | NO | 1 | 3780 | 3780 | 4460.4 | 3779.66 | 4460 | 0.34 | 3780 | 4460 | ZMAT | 2025-01-20 | 2025-03-20
RE/0066-SOE-75 | Site Office Expenses at Sec 75 | 2010 |  | 2010 | SMARTWORLD THE EDITION | Commercial Equipment | 9110000206 | 50 |  |  | 2023-07-24 | Constant Temp Water bath 27 degree | NO | 1 | 86800 | 86800 | 102424 | 86800 | 102424 | 0 | 86800 | 102424 | ZMAT | 2025-01-20 | 2025-03-20
RE/0066-SOE-75 | Site Office Expenses at Sec 75 | 2010 |  | 2010 | SMARTWORLD THE EDITION | Commercial Equipment | 9110000206 | 60 |  |  | 2023-07-24 | Cube mould 70.0x70.6mm | NO | 36 | 940.77 | 33867.72 | 39963.91 | 33867.56 | 39963.72 | 0.16 | 33867.72 | 39963.72 | ZMAT | 2025-01-20 | 2025-03-20
RE/0066-SOE-75 | Site Office Expenses at Sec 75 | 2010 |  | 2010 | SMARTWORLD THE EDITION | Commercial Equipment | 9110000206 | 70 |  |  | 2023-07-24 | Humidity fire | NO | 1 | 21200 | 21200 | 25016 | 21200 | 25016 | 0 | 21200 | 25016 | ZMAT | 2025-01-20 | 2025-03-20
RE/0066-SOE-75 | Site Office Expenses at Sec 75 | 2010 |  | 2010 | SMARTWORLD THE EDITION | Commercial Equipment | 9110000206 | 80 |  |  | 2023-07-24 | De-humidity fire small | NO | 1 | 38800 | 38800 | 45784 | 38800 | 45784 | 0 | 38800 | 45783.96 | ZMAT | 2025-01-20 | 2025-03-20
RE/0066-SOE-75 | Site Office Expenses at Sec 75 | 2010 |  | 2010 | SMARTWORLD THE EDITION | Commercial Equipment | 9110000206 | 90 |  |  | 2023-07-24 | Weighing Balance 320gm. | NO | 1 | 11840 | 11840 | 13971.2 | 11839.83 | 13971 | 0.17 | 11840 | 13971 | ZMAT | 2025-01-20 | 2025-03-20
RE/0066-SOE-75 | Site Office Expenses at Sec 75 | 2010 |  | 2010 | SMARTWORLD THE EDITION | Commercial Equipment | 9110000206 | 100 |  |  | 2023-07-24 | Blaine Fineness app. With Mercury and D | NO | 1 | 4464.8 | 4464.8 | 5268.46 | 4465.08 | 5268.8 | 0.28 | 4464.8 | 5268.8 | ZMAT | 2025-01-20 | 2025-03-20
RE/0066-SOE-75 | Site Office Expenses at Sec 75 | 2010 |  | 2010 | SMARTWORLD THE EDITION | Commercial Equipment | 9110000206 | 110 |  |  | 2023-07-24 | Sieve90 micron,45 micron and shaker | NO | 1 | 44515.8 | 44515.8 | 52528.64 | 44515.93 | 52528.8 | 0.13 | 44515.8 | 52528.8 | ZMAT | 2025-01-20 | 2025-03-20
RE/0066-SOE-75 | Site Office Expenses at Sec 75 | 2010 |  | 2010 | SMARTWORLD THE EDITION | Commercial Equipment | 9110000206 | 120 |  |  | 2023-07-24 | Vibration Machine with Tachometer | NO | 1 | 59938.2 | 59938.2 | 70727.08 | 59938.31 | 70727.2 | 0.11 | 59938.2 | 70727.2 | ZMAT | 2025-01-20 | 2025-03-20
RE/0066-SOE-75 | Site Office Expenses at Sec 75 | 2010 |  | 2010 | SMARTWORLD THE EDITION | Commercial Equipment | 9110000206 | 130 |  |  | 2023-07-24 | Autoclave Machine | NO | 1 | 101715.6 | 101715.6 | 120024.41 | 101715.76 | 120024.6 | 0.16 | 101715.6 | 120024.6 | ZMAT | 2025-01-20 | 2025-03-20
RE/0066-SOE-75 | Site Office Expenses at Sec 75 | 2010 |  | 2010 | SMARTWORLD THE EDITION | Commercial Equipment | 9110000206 | 140 |  |  | 2023-07-24 | Auto clave Mould | NO | 6 | 2250.35 | 13502.1 | 15932.48 | 13501.78 | 15932.1 | 0.32 | 13502.1 | 15932.1 | ZMAT | 2025-01-20 | 2025-03-20
RE/0066-SOE-75 | Site Office Expenses at Sec 75 | 2010 |  | 2010 | SMARTWORLD THE EDITION | Commercial Equipment | 9110000206 | 150 |  |  | 2023-07-24 | Lenth Comparator with Referance Rod | NO | 1 | 16464 | 16464 | 19427.52 | 16464.41 | 19428 | 0.41 | 16464 | 19428 | ZMAT | 2025-01-20 | 2025-03-20
RE/0066-SOE-75 | Site Office Expenses at Sec 75 | 2010 |  | 2010 | SMARTWORLD THE EDITION | Commercial Equipment | 9110000206 | 160 |  |  | 2023-07-24 | Le chatelier mould | NO | 2 | 2797.16 | 5594.32 | 6601.3 | 5594.34 | 6601.32 | 0.02 | 5594.32 | 6601.32 | ZMAT | 2025-01-20 | 2025-03-20
RE/0066-SOE-75 | Site Office Expenses at Sec 75 | 2010 |  | 2010 | SMARTWORLD THE EDITION | Commercial Equipment | 9110000206 | 170 |  |  | 2023-07-24 | Le-chatelier Water Bath | NO | 1 | 15840 | 15840 | 18691.2 | 15839.83 | 18691 | 0.17 | 15840 | 18691.2 | ZMAT | 2025-01-20 | 2025-03-20
RE/0066-SOE-75 | Site Office Expenses at Sec 75 | 2010 |  | 2010 | SMARTWORLD THE EDITION | Commercial Equipment | 9110000206 | 180 |  |  | 2023-07-24 | Gauing Trowel set | NO | 2 | 386.4 | 772.8 | 911.9 | 772.71 | 911.8 | 0.09 | 772.8 | 911.8 | ZMAT | 2025-01-20 | 2025-03-20
RE/0066-SOE-75 | Site Office Expenses at Sec 75 | 2010 |  | 2010 | SMARTWORLD THE EDITION | Commercial Equipment | 9110000206 | 190 |  |  | 2023-07-24 | Hygrometer (1 Nos Each lab) | NO | 2 | 1480 | 2960 | 3492.8 | 2960.17 | 3493 | 0.17 | 2960 | 3493 | ZMAT | 2025-01-20 | 2025-03-20
RE/0066-SOE-75 | Site Office Expenses at Sec 75 | 2010 |  | 2010 | SMARTWORLD THE EDITION | Commercial Equipment | 9110000206 | 200 |  |  | 2023-07-24 | Standard sand ( 1st, 2nd & 3rd Grade) S | NO | 25 | 8280 | 207000 | 244260 | 207000 | 244260 | 0 | 207000 | 244260 | ZMAT | 2025-01-20 | 2025-03-20
RE/0066-SOE-75 | Site Office Expenses at Sec 75 | 2010 |  | 2010 | SMARTWORLD THE EDITION | Commercial Equipment | 9110000206 | 210 |  |  | 2023-07-24 | Crushing mould , CTM , Balance | NO | 1 | 16867.2 | 16867.2 | 19903.3 | 16867.12 | 19903.2 | 0.08 | 16867.2 | 19903.2 | ZMAT | 2025-01-20 | 2025-03-20
RE/0066-SOE-75 | Site Office Expenses at Sec 75 | 2010 |  | 2010 | SMARTWORLD THE EDITION | Commercial Equipment | 9110000206 | 220 |  |  | 2023-07-24 | Impact Appartus | NO | 1 | 17917.2 | 17917.2 | 21142.3 | 17917.12 | 21142.2 | 0.08 | 17917.2 | 21142.2 | ZMAT | 2025-01-20 | 2025-03-20
RE/0066-SOE-75 | Site Office Expenses at Sec 75 | 2010 |  | 2010 | SMARTWORLD THE EDITION | Commercial Equipment | 9110000206 | 230 |  |  | 2023-07-24 | Water bath | NO | 1 | 62800 | 62800 | 74104 | 62800 | 74104 | 0 | 62800 | 74104 | ZMAT | 2025-01-20 | 2025-03-20
RE/0066-SOE-75 | Site Office Expenses at Sec 75 | 2010 |  | 2010 | SMARTWORLD THE EDITION | Commercial Equipment | 9110000206 | 240 |  |  | 2023-07-24 | Bucket 3,10,15 Liter | NO | 1 | 11986.8 | 11986.8 | 14144.42 | 11987.12 | 14144.8 | 0.32 | 11986.8 | 14144.8 | ZMAT | 2025-01-20 | 2025-03-20
RE/0066-SOE-75 | Site Office Expenses at Sec 75 | 2010 |  | 2010 | SMARTWORLD THE EDITION | Commercial Equipment | 9110000206 | 250 |  |  | 2023-07-24 | 100Kg Balance | NO | 1 | 10560 | 10560 | 12460.8 | 10560.17 | 12461 | 0.17 | 10560 | 12461 | ZMAT | 2025-01-20 | 2025-03-20
RE/0066-SOE-75 | Site Office Expenses at Sec 75 | 2010 |  | 2010 | SMARTWORLD THE EDITION | Commercial Equipment | 9110000206 | 260 |  |  | 2023-07-24 | 6kg 0.1 g | NO | 1 | 10800 | 10800 | 12744 | 10800 | 12744 | 0 | 10800 | 12744 | ZMAT | 2025-01-20 | 2025-03-20
RE/0066-SOE-75 | Site Office Expenses at Sec 75 | 2010 |  | 2010 | SMARTWORLD THE EDITION | Commercial Equipment | 9110000206 | 270 |  |  | 2023-07-24 | Elongated gauge | NO | 1 | 2646 | 2646 | 3122.28 | 2645.76 | 3122 | 0.24 | 2646 | 3122 | ZMAT | 2025-01-20 | 2025-03-20
RE/0066-SOE-75 | Site Office Expenses at Sec 75 | 2010 |  | 2010 | SMARTWORLD THE EDITION | Commercial Equipment | 9110000206 | 280 |  |  | 2023-07-24 | Flakiness gauge | NO | 1 | 3099.6 | 3099.6 | 3657.53 | 3099.66 | 3657.6 | 0.06 | 3099.6 | 3657.6 | ZMAT | 2025-01-20 | 2025-03-20
RE/0066-SOE-75 | Site Office Expenses at Sec 75 | 2010 |  | 2010 | SMARTWORLD THE EDITION | Commercial Equipment | 9110000206 | 290 |  |  | 2023-07-24 | Oven big size | NO | 1 | 32960 | 32960 | 38892.8 | 32960.17 | 38893 | 0.17 | 32960 | 38893 | ZMAT | 2025-01-20 | 2025-03-20
RE/0066-SOE-75 | Site Office Expenses at Sec 75 | 2010 |  | 2010 | SMARTWORLD THE EDITION | Commercial Equipment | 9110000206 | 300 |  |  | 2023-07-24 | Sieve | NO | 1 | 1155 | 1155 | 1362.9 | 1155.08 | 1363 | 0.08 | 1155 | 1363 | ZMAT | 2025-01-20 | 2025-03-20
RE/0066-SOE-75 | Site Office Expenses at Sec 75 | 2010 |  | 2010 | SMARTWORLD THE EDITION | Commercial Equipment | 9110000206 | 310 |  |  | 2023-07-24 | sieve 63,40,20,10,4.75,2.36,1.18.600mic | NO | 1 | 65020.2 | 65020.2 | 76723.84 | 65020.51 | 76724.2 | 0.31 | 65020.2 | 76724.2 | ZMAT | 2025-01-20 | 2025-03-20
RE/0066-SOE-75 | Site Office Expenses at Sec 75 | 2010 |  | 2010 | SMARTWORLD THE EDITION | Commercial Equipment | 9110000206 | 320 |  |  | 2023-07-24 | Bioncey Balance with basket, | NO | 1 | 57200 | 57200 | 67496 | 57200 | 67496 | 0 | 57200 | 67496 | ZMAT | 2025-01-20 | 2025-03-20
RE/0066-SOE-75 | Site Office Expenses at Sec 75 | 2010 |  | 2010 | SMARTWORLD THE EDITION | Commercial Equipment | 9110000206 | 330 |  |  | 2023-07-24 | Pycknometer bottle 1000 ml | NO | 2 | 508 | 1016 | 1198.88 | 1016.1 | 1199 | 0.1 | 1016 | 1199 | ZMAT | 2025-01-20 | 2025-03-20
RE/0066-SOE-75 | Site Office Expenses at Sec 75 | 2010 |  | 2010 | SMARTWORLD THE EDITION | Commercial Equipment | 9110000206 | 340 |  |  | 2023-07-24 | Core-cutter and hammer | NO | 6 | 2511.5 | 15069 | 17781.42 | 15068.64 | 17781 | 0.36 | 15069 | 17781 | ZMAT | 2025-01-20 | 2025-03-20
RE/0066-SOE-75 | Site Office Expenses at Sec 75 | 2010 |  | 2010 | SMARTWORLD THE EDITION | Commercial Equipment | 9110000206 | 350 |  |  | 2023-07-24 | Sand Replacement app. | NO | 2 | 4804.5 | 9609 | 11338.62 | 9609.32 | 11339 | 0.32 | 9609 | 11339 | ZMAT | 2025-01-20 | 2025-03-20
RE/0066-SOE-75 | Site Office Expenses at Sec 75 | 2010 |  | 2010 | SMARTWORLD THE EDITION | Commercial Equipment | 9110000206 | 360 |  |  | 2023-07-24 | Light Compaction | NO | 1 | 5317.2 | 5317.2 | 6274.3 | 5317.12 | 6274.2 | 0.08 | 5317.2 | 6274.2 | ZMAT | 2025-01-20 | 2025-03-20
RE/0066-SOE-75 | Site Office Expenses at Sec 75 | 2010 |  | 2010 | SMARTWORLD THE EDITION | Commercial Equipment | 9110000206 | 370 |  |  | 2023-07-24 | Heavy Compaction | NO | 1 | 6837.6 | 6837.6 | 8068.37 | 6837.8 | 8068.6 | 0.2 | 6837.6 | 8068.6 | ZMAT | 2025-01-20 | 2025-03-20
RE/0066-SOE-75 | Site Office Expenses at Sec 75 | 2010 |  | 2010 | SMARTWORLD THE EDITION | Commercial Equipment | 9110000206 | 380 |  |  | 2023-07-24 | UTM Machine 1000KN | NO | 1 | 1397928 | 1397928 | 1649555.04 | 1397927.97 | 1649555 | 0.03 | 1397928 | 1649555 | ZMAT | 2025-01-20 | 2025-03-20
RE/0066-SOE-75 | Site Office Expenses at Sec 75 | 2010 |  | 2010 | SMARTWORLD THE EDITION | Commercial Equipment | 9110000206 | 390 |  |  | 2023-07-24 | Manderal for up 32m,m dia of bars | NO | 1 | 67032 | 67032 | 79097.76 | 67032.2 | 79098 | 0.2 | 67032 | 79098 | ZMAT | 2025-01-20 | 2025-03-20
RE/0066-SOE-75 | Site Office Expenses at Sec 75 | 2010 |  | 2010 | SMARTWORLD THE EDITION | Commercial Equipment | 9110000206 | 400 |  |  | 2023-07-24 | Measuring Tape 5meter | NO | 2 | 1160 | 2320 | 2737.6 | 2320.34 | 2738 | 0.34 | 2320 | 2738 | ZMAT | 2025-01-20 | 2025-03-20
RE/0066-SOE-75 | Site Office Expenses at Sec 75 | 2010 |  | 2010 | SMARTWORLD THE EDITION | Commercial Equipment | 9110000206 | 420 |  |  | 2023-07-24 | Micrometer 25mm | NO | 1 | 8460 | 8460 | 9982.8 | 8460.17 | 9983 | 0.17 | 8460 | 9983 | ZMAT | 2025-01-20 | 2025-03-20
RE/0066-SOE-75 | Site Office Expenses at Sec 75 | 2010 |  | 2010 | SMARTWORLD THE EDITION | Commercial Equipment | 9110000206 | 430 |  |  | 2023-07-24 | Rebend Test | NO | 1 | 65436 | 65436 | 77214.48 | 65435.59 | 77214 | 0.41 | 65436 | 77214 | ZMAT | 2025-01-20 | 2025-03-20
RE/0066-SOE-75 | Site Office Expenses at Sec 75 | 2010 |  | 2010 | SMARTWORLD THE EDITION | Commercial Equipment | 9110000206 | 440 |  |  | 2023-07-24 | Balance, 30 kg | NO | 1 | 10240 | 10240 | 12083.2 | 10239.83 | 12083 | 0.17 | 10240 | 12083 | ZMAT | 2025-01-20 | 2025-03-20
RE/0066-SOE-75 | Site Office Expenses at Sec 75 | 2010 |  | 2010 | SMARTWORLD THE EDITION | Commercial Equipment | 9110000206 | 460 |  |  | 2023-07-24 | Water bath | NO | 1 | 22800 | 22800 | 26904 | 22800 | 26904 | 0 | 22800 | 26904 | ZMAT | 2025-01-20 | 2025-03-20
RE/0066-SOE-75 | Site Office Expenses at Sec 75 | 2010 |  | 2010 | SMARTWORLD THE EDITION | Commercial Equipment | 9110000206 | 470 |  |  | 2023-07-24 | Efflorence app. | NO | 10 | 10013.6 | 100136 | 118160.48 | 100135.59 | 118160 | 0.41 | 100135.7 | 118160.2 | ZMAT | 2025-01-20 | 2025-03-20
RE/0066-SOE-75 | Site Office Expenses at Sec 75 | 2010 |  | 2010 | SMARTWORLD THE EDITION | Commercial Equipment | 9110000206 | 480 |  |  | 2023-07-24 | Measuring Tape | NO | 1 | 1517.6 | 1517.6 | 1790.77 | 1517.46 | 1790.6 | 0.14 | 1517.6 | 1790.6 | ZMAT | 2025-01-20 | 2025-03-20
RE/0066-SOE-75 | Site Office Expenses at Sec 75 | 2010 |  | 2010 | SMARTWORLD THE EDITION | Commercial Equipment | 9110000206 | 490 |  |  | 2023-07-24 | Centrifuge | NO | 1 | 42214.2 | 42214.2 | 49812.76 | 42214.58 | 49813.2 | 0.38 | 42214.2 | 49813.2 | ZMAT | 2025-01-20 | 2025-03-20
RE/0066-SOE-75 | Site Office Expenses at Sec 75 | 2010 |  | 2010 | SMARTWORLD THE EDITION | Commercial Equipment | 9110000206 | 500 |  |  | 2023-07-24 | Asphalt Mixture Density Meter | NO | 1 | 54192.6 | 54192.6 | 63947.27 | 54192.88 | 63947.6 | 0.28 | 54192.6 | 63947.6 | ZMAT | 2025-01-20 | 2025-03-20
RE/0066-SOE-75 | Site Office Expenses at Sec 75 | 2010 |  | 2010 | SMARTWORLD THE EDITION | Commercial Equipment | 9110000206 | 510 |  |  | 2023-07-24 | Oven big size 250deg | NO | 1 | 118160 | 118160 | 139428.8 | 118160.17 | 139429 | 0.17 | 118160 | 139428.68 | ZMAT | 2025-01-20 | 2025-03-20
RE/0066-SOE-75 | Site Office Expenses at Sec 75 | 2010 |  | 2010 | SMARTWORLD THE EDITION | Commercial Equipment | 9110000206 | 520 |  |  | 2023-07-24 | CTM 100KN | NO | 1 | 319314.24 | 319314.24 | 376790.8 | 0 | 0 | 319314.24 | 0 | 0 | ZMAT | 2025-01-20 | 2025-03-20
RE/0066-SOE-75 | Site Office Expenses at Sec 75 | 2010 |  | 2010 | SMARTWORLD THE EDITION | Commercial Equipment | 9110000206 | 530 |  |  | 2023-07-24 | Vernier 1000 mm | NO | 1 | 50000 | 50000 | 59000 | 50000 | 59000 | 0 | 50000 | 59000 | ZMAT | 2025-01-20 | 2025-03-20
RE/0066-SOE-75 | Site Office Expenses at Sec 75 | 2010 |  | 2010 | SMARTWORLD THE EDITION | Commercial Equipment | 9110000206 | 540 |  |  | 2023-07-24 | Block Cutting Maqchine | NO | 1 | 187600 | 187600 | 221368 | 187600 | 221368 | 0 | 187600 | 221368 | ZMAT | 2025-01-20 | 2025-03-20
RE/0066-SOE-75 | Site Office Expenses at Sec 75 | 2010 |  | 2010 | SMARTWORLD THE EDITION | Commercial Equipment | 9110000206 | 550 |  |  | 2023-07-24 | Tile abrasion Machine,oven | NO | 1 | 162500 | 162500 | 191750 | 162500 | 191750 | 0 | 162500 | 191750 | ZMAT | 2025-01-20 | 2025-03-20
RE/0066-SOE-75 | Site Office Expenses at Sec 75 | 2010 |  | 2010 | SMARTWORLD THE EDITION | Commercial Equipment | 9110000206 | 560 |  |  | 2023-07-24 | Thickness Gauge AIM-48101 | NO | 1 | 11499.6 | 11499.6 | 13569.53 | 11499.66 | 13569.6 | 0.06 | 11499.6 | 13569.6 | ZMAT | 2025-01-20 | 2025-03-20
RE/0066-SOE-75 | Site Office Expenses at Sec 75 | 2010 |  | 2010 | SMARTWORLD THE EDITION | Commercial Equipment | 9110000206 | 570 |  |  | 2023-07-24 | CTM 3000kN | NO | 1 | 465958.08 | 465958.08 | 549830.53 | 465957.69 | 549830.08 | 0.39 | 465958.04 | 549830.54 | ZMAT | 2025-01-20 | 2025-03-20
RE/0066-SOE-75 | Site Office Expenses at Sec 75 | 2010 |  | 2010 | SMARTWORLD THE EDITION | Commercial Equipment | 9110000206 | 580 |  |  | 2023-07-24 | Flexural Machine | NO | 1 | 261172.8 | 261172.8 | 308183.9 | 261172.71 | 308183.8 | 0.09 | 261172.8 | 308183.8 | ZMAT | 2025-01-20 | 2025-03-20
RE/0066-SOE-75 | Site Office Expenses at Sec 75 | 2010 |  | 2010 | SMARTWORLD THE EDITION | Commercial Equipment | 9110000206 | 590 |  |  | 2023-07-24 | Split Machine | NO | 1 | 57540 | 57540 | 67897.2 | 0 | 0 | 57540 | 0 | 0 | ZMAT | 2025-01-20 | 2025-03-20
RE/0066-SOE-75 | Site Office Expenses at Sec 75 | 2010 |  | 2010 | SMARTWORLD THE EDITION | Commercial Equipment | 9110000206 | 600 |  |  | 2023-07-24 | Water bath | NO | 1 | 62800 | 62800 | 74104 | 0 | 0 | 62800 | 0 | 0 | ZMAT | 2025-01-20 | 2025-03-20
RE/0066-SOE-75 | Site Office Expenses at Sec 75 | 2010 |  | 2010 | SMARTWORLD THE EDITION | Commercial Equipment | 9110000206 | 610 |  |  | 2023-07-24 | Mortar mixer( CTM lower range) | NO | 1 | 89310.48 | 89310.48 | 105386.37 | 89310.58 | 105386.48 | 0.1 | 89310.48 | 105386.38 | ZMAT | 2025-01-20 | 2025-03-20
RE/0066-SOE-75 | Site Office Expenses at Sec 75 | 2010 |  | 2010 | SMARTWORLD THE EDITION | Commercial Equipment | 9110000206 | 620 |  |  | 2023-07-24 | Cube mould 50x50x50 | NO | 25 | 583.8 | 14595 | 17222.1 | 14594.92 | 17222 | 0.08 | 14595 | 17222 | ZMAT | 2025-01-20 | 2025-03-20
RE/0066-SOE-75 | Site Office Expenses at Sec 75 | 2010 |  | 2010 | SMARTWORLD THE EDITION | Commercial Equipment | 9110000206 | 630 |  |  | 2023-07-24 | Blaine Fineness app. With Mercury and D | NO | 1 | 4464.6 | 4464.6 | 5268.23 | 4464.92 | 5268.6 | 0.32 | 4464.6 | 5268.6 | ZMAT | 2025-01-20 | 2025-03-20
RE/0066-SOE-75 | Site Office Expenses at Sec 75 | 2010 |  | 2010 | SMARTWORLD THE EDITION | Commercial Equipment | 9110000206 | 650 |  |  | 2023-07-24 | Hot air Oven CE-HC090 | NO | 1 | 32960 | 32960 | 38892.8 | 32960.17 | 38893 | 0.17 | 32960 | 38892.77 | ZMAT | 2025-01-20 | 2025-03-20
RE/0066-SOE-75 | Site Office Expenses at Sec 75 | 2010 |  | 2010 | SMARTWORLD THE EDITION | Commercial Equipment | 9110000206 | 660 |  |  | 2023-07-24 | Sieve | NO | 2 | 1890 | 3780 | 4460.4 | 3779.66 | 4460 | 0.34 | 3780 | 4460 | ZMAT | 2025-01-20 | 2025-03-20
RE/0066-SOE-75 | Site Office Expenses at Sec 75 | 2010 |  | 2010 | SMARTWORLD THE EDITION | Commercial Equipment | 9110000206 | 680 |  |  | 2023-07-24 | Lechatelier flask | NO | 2 | 1982.4 | 3964.8 | 4678.46 | 3965.08 | 4678.8 | 0.28 | 3964.8 | 4678.8 | ZMAT | 2025-01-20 | 2025-03-20
RE/0066-SOE-75 | Site Office Expenses at Sec 75 | 2010 |  | 2010 | SMARTWORLD THE EDITION | Commercial Equipment | 9110000206 | 700 |  |  | 2023-07-24 | Autoclave Machine | NO | 1 | 325500 | 325500 | 384090 | 0 | 0 | 325500 | 0 | 0 | ZMAT | 2025-01-20 | 2025-03-20
RE/0066-SOE-75 | Site Office Expenses at Sec 75 | 2010 |  | 2010 | SMARTWORLD THE EDITION | Commercial Equipment | 9110000206 | 710 |  |  | 2023-07-24 | Mohs Hardness standard stone CE-GL064 | NO | 1 | 39532 | 39532 | 46647.76 | 39532.2 | 46648 | 0.2 | 39532 | 46648 | ZMAT | 2025-01-20 | 2025-03-20
RE/0066-SOE-75 | Site Office Expenses at Sec 75 | 2010 |  | 2010 | SMARTWORLD THE EDITION | Commercial Equipment | 9110000206 | 720 |  |  | 2023-07-24 | Warpage machine | NO | 1 | 575448.8 | 575448.8 | 679029.58 | 0 | 0 | 575448.8 | 0 | 0 | ZMAT | 2025-01-20 | 2025-03-20
RE/0066-SOE-75 | Site Office Expenses at Sec 75 | 2010 |  | 2010 | SMARTWORLD THE EDITION | Commercial Equipment | 9110000206 | 730 |  |  | 2023-07-24 | Water bath CE-SP024 | NO | 1 | 31600 | 31600 | 37288 | 31600 | 37288 | 0 | 31600 | 37288 | ZMAT | 2025-01-20 | 2025-03-20
RE/0066-SOE-75 | Site Office Expenses at Sec 75 | 2010 |  | 2010 | SMARTWORLD THE EDITION | Commercial Equipment | 9110000206 | 740 |  |  | 2023-07-24 | Tile MOR Machine AIM-430 | NO | 1 | 282200 | 282200 | 332996 | 0 | 0 | 282200 | 0 | 0 | ZMAT | 2025-01-20 | 2025-03-20
RE/0066-SOE-75 | Site Office Expenses at Sec 75 | 2010 |  | 2010 | SMARTWORLD THE EDITION | Commercial Equipment | 9110000206 | 830 |  |  | 2023-07-24 | Concrete pan Type baby mixer, | NO | 1 | 149994.6 | 149994.6 | 176993.63 | 149994.58 | 176993.6 | 0.02 | 149994.6 | 176993.6 | ZMAT | 2025-01-20 | 2025-03-20
RE/0066-SOE-75 | Site Office Expenses at Sec 75 | 2010 |  | 2010 | SMARTWORLD THE EDITION | Commercial Equipment | 9110000206 | 840 |  |  | 2023-07-24 | Vibrating Table | NO | 1 | 52281.6 | 52281.6 | 61692.29 | 52281.86 | 61692.6 | 0.26 | 52281.6 | 61692.6 | ZMAT | 2025-01-20 | 2025-03-20
RE/0066-SOE-75 | Site Office Expenses at Sec 75 | 2010 |  | 2010 | SMARTWORLD THE EDITION | Commercial Equipment | 9110000206 | 850 |  |  | 2023-07-24 | Cube mould 150x150mm | NO | 24 | 2948.37 | 70760.88 | 83497.84 | 70760.92 | 83497.88 | 0.04 | 70760.88 | 83497.88 | ZMAT | 2025-01-20 | 2025-03-20
RE/0066-SOE-75 | Site Office Expenses at Sec 75 | 2010 |  | 2010 | SMARTWORLD THE EDITION | Commercial Equipment | 9110000206 | 860 |  |  | 2023-07-24 | Flexural Mould 150x150x700 mm | NO | 6 | 10378.16 | 62268.96 | 73477.37 | 62268.61 | 73476.96 | 0.35 | 62268.96 | 73476.96 | ZMAT | 2025-01-20 | 2025-03-20
RE/0066-SOE-75 | Site Office Expenses at Sec 75 | 2010 |  | 2010 | SMARTWORLD THE EDITION | Commercial Equipment | 9110000206 | 870 |  |  | 2023-07-24 | Prism Mould 75x75x250 | NO | 6 | 6228.5 | 37371 | 44097.78 | 37371.19 | 44098 | 0.19 | 37371 | 44098 | ZMAT | 2025-01-20 | 2025-03-20
RE/0066-SOE-75 | Site Office Expenses at Sec 75 | 2010 |  | 2010 | SMARTWORLD THE EDITION | Commercial Equipment | 9110000206 | 890 |  |  | 2023-07-24 | Slump cone | NO | 1 | 3347.4 | 3347.4 | 3949.93 | 3347.8 | 3950.4 | 0.4 | 3347.4 | 3950.4 | ZMAT | 2025-01-20 | 2025-03-20
RE/0066-SOE-75 | Site Office Expenses at Sec 75 | 2010 |  | 2010 | SMARTWORLD THE EDITION | Commercial Equipment | 9110000206 | 900 |  |  | 2023-07-24 | flow table | NO | 1 | 24622.08 | 24622.08 | 29054.05 | 24622.1 | 29054.08 | 0.02 | 24622.08 | 29054.08 | ZMAT | 2025-01-20 | 2025-03-20
RE/0066-SOE-75 | Site Office Expenses at Sec 75 | 2010 |  | 2010 | SMARTWORLD THE EDITION | Commercial Equipment | 9110000206 | 910 |  |  | 2023-07-24 | Y funnel | NO | 1 | 7064.4 | 7064.4 | 8335.99 | 7064.75 | 8336.4 | 0.35 | 7064.4 | 8336.4 | ZMAT | 2025-01-20 | 2025-03-20
RE/0066-SOE-75 | Site Office Expenses at Sec 75 | 2010 |  | 2010 | SMARTWORLD THE EDITION | Commercial Equipment | 9110000206 | 920 |  |  | 2023-07-24 | U box | NO | 1 | 8492.4 | 8492.4 | 10021.03 | 8492.71 | 10021.4 | 0.31 | 8492.4 | 10021.4 | ZMAT | 2025-01-20 | 2025-03-20
RE/0066-SOE-75 | Site Office Expenses at Sec 75 | 2010 |  | 2010 | SMARTWORLD THE EDITION | Commercial Equipment | 9110000206 | 930 |  |  | 2023-07-24 | Hygrometer | NO | 1 | 1480 | 1480 | 1746.4 | 1479.66 | 1746 | 0.34 | 1480 | 1746 | ZMAT | 2025-01-20 | 2025-03-20
RE/0066-SOE-75 | Site Office Expenses at Sec 75 | 2010 |  | 2010 | SMARTWORLD THE EDITION | Commercial Equipment | 9110000206 | 940 |  |  | 2023-07-24 | L box | NO | 1 | 10357.2 | 10357.2 | 12221.5 | 10356.95 | 12221.2 | 0.25 | 10357.2 | 12221.2 | ZMAT | 2025-01-20 | 2025-03-20
RE/0066-SOE-75 | Site Office Expenses at Sec 75 | 2010 |  | 2010 | SMARTWORLD THE EDITION | Commercial Equipment | 9110000206 | 950 |  |  | 2023-07-24 | Mixing Tray 1x1 meter | NO | 1 | 4200 | 4200 | 4956 | 4200 | 4956 | 0 | 4200 | 4956 | ZMAT | 2025-01-20 | 2025-03-20
RE/0066-SOE-75 | Site Office Expenses at Sec 75 | 2010 |  | 2010 | SMARTWORLD THE EDITION | Commercial Equipment | 9110000206 | 980 |  |  | 2023-07-24 | Vernier 300MM | NO | 1 | 9200 | 9200 | 10856 | 9200 | 10856 | 0 | 9200 | 10856 | ZMAT | 2025-01-20 | 2025-03-20
RE/0066-SOE-75 | Site Office Expenses at Sec 75 | 2010 |  | 2010 | SMARTWORLD THE EDITION | Commercial Equipment | 9110000206 | 990 |  |  | 2023-07-24 | Balance 0.01 gm-600gm | NO | 1 | 10300.8 | 10300.8 | 12154.94 | 10300.68 | 12154.8 | 0.12 | 10300.8 | 12154.8 | ZMAT | 2025-01-20 | 2025-03-20
RE/0066-SOE-75 | Site Office Expenses at Sec 75 | 2010 |  | 2010 | SMARTWORLD THE EDITION | Commercial Equipment | 9110000206 | 1000 |  |  | 2023-07-24 | Balance 0.1gm-3kg | NO | 1 | 9396 | 9396 | 11087.28 | 9395.76 | 11087 | 0.24 | 9396 | 11087 | ZMAT | 2025-01-20 | 2025-03-20
RE/0066-SOE-75 | Site Office Expenses at Sec 75 | 2010 |  | 2010 | SMARTWORLD THE EDITION | Commercial Equipment | 9110000206 | 1010 |  |  | 2023-07-24 | Balance 0.1gm-5kg | NO | 1 | 9396 | 9396 | 11087.28 | 9395.76 | 11087 | 0.24 | 9396 | 11087 | ZMAT | 2025-01-20 | 2025-03-20
RE/0066-SOE-75 | Site Office Expenses at Sec 75 | 2010 |  | 2010 | SMARTWORLD THE EDITION | Commercial Equipment | 9110000206 | 1020 |  |  | 2023-07-24 | Analytical Balance 0.1 mg to 220 gm | NO | 1 | 90132 | 90132 | 106355.76 | 90132.2 | 106356 | 0.2 | 90132 | 106355.8 | ZMAT | 2025-01-20 | 2025-03-20
RE/0066-SOE-75 | Site Office Expenses at Sec 75 | 2010 |  | 2010 | SMARTWORLD THE EDITION | Commercial Equipment | 9110000206 | 1040 |  |  | 2023-07-24 | MUFFLE FURNACE | NO | 1 | 47676 | 47676 | 56257.68 | 47676.27 | 56258 | 0.27 | 47676 | 56257.65 | ZMAT | 2025-01-20 | 2025-03-20
RE/0066-SOE-75 | Site Office Expenses at Sec 75 | 2010 |  | 2010 | SMARTWORLD THE EDITION | Commercial Equipment | 9110000206 | 1050 |  |  | 2023-07-24 | WATER BATH SS Up to 1200 degree | NO | 1 | 19836 | 19836 | 23406.48 | 0 | 0 | 19836 | 0 | 0 | ZMAT | 2025-01-20 | 2025-03-20
RE/0066-SOE-75 | Site Office Expenses at Sec 75 | 2010 |  | 2010 | SMARTWORLD THE EDITION | Commercial Equipment | 9110000206 | 1060 |  |  | 2023-07-24 | NEPTHELO METER 0 to 1000 NTU | NO | 1 | 13572 | 13572 | 16014.96 | 13572.03 | 16015 | 0.03 | 13572 | 16015 | ZMAT | 2025-01-20 | 2025-03-20
RE/0066-SOE-75 | Site Office Expenses at Sec 75 | 2010 |  | 2010 | SMARTWORLD THE EDITION | Commercial Equipment | 9110000206 | 1070 |  |  | 2023-07-24 | PH METER 0 to 14 | NO | 1 | 6612 | 6612 | 7802.16 | 6611.86 | 7802 | 0.14 | 6612 | 7802 | ZMAT | 2025-01-20 | 2025-03-20
RE/0066-SOE-75 | Site Office Expenses at Sec 75 | 2010 |  | 2010 | SMARTWORLD THE EDITION | Commercial Equipment | 9110000206 | 1080 |  |  | 2023-07-24 | CONDUCTIVITY METER 0 ms to 200 ms | NO | 1 | 11762.4 | 11762.4 | 13879.63 | 11762.2 | 13879.4 | 0.2 | 11762.4 | 13879.4 | ZMAT | 2025-01-20 | 2025-03-20
RE/0066-SOE-75 | Site Office Expenses at Sec 75 | 2010 |  | 2010 | SMARTWORLD THE EDITION | Commercial Equipment | 9110000206 | 1090 |  |  | 2023-07-24 | STROHLEIN UP to 4% | NO | 1 | 82476 | 82476 | 97321.68 | 82476.27 | 97322 | 0.27 | 82476 | 97321.61 | ZMAT | 2025-01-20 | 2025-03-20
RE/0066-SOE-75 | Site Office Expenses at Sec 75 | 2010 |  | 2010 | SMARTWORLD THE EDITION | Commercial Equipment | 9110000206 | 1100 |  |  | 2023-07-24 | FLAME PHOTO METER 0 to 100 ppm | NO | 1 | 64380 | 64380 | 75968.4 | 64379.66 | 75968 | 0.34 | 64380 | 75968.33 | ZMAT | 2025-01-20 | 2025-03-20
RE/0066-SOE-75 | Site Office Expenses at Sec 75 | 2010 |  | 2010 | SMARTWORLD THE EDITION | Commercial Equipment | 9110000206 | 1110 |  |  | 2023-07-24 | Fume hood | NO | 1 | 157226.4 | 157226.4 | 185527.15 | 157226.61 | 185527.4 | 0.21 | 157226.3 | 185527 | ZMAT | 2025-01-20 | 2025-03-20
RE/0066-SOE-75 | Site Office Expenses at Sec 75 | 2010 |  | 2010 | SMARTWORLD THE EDITION | Commercial Equipment | 9110000206 | 1120 |  |  | 2023-07-24 | Heating Plate Up to 100 degree | NO | 1 | 2540 | 2540 | 2997.2 | 2539.83 | 2997 | 0.17 | 2540 | 2997 | ZMAT | 2025-01-20 | 2025-03-20
RE/0066-SOE-75 | Site Office Expenses at Sec 75 | 2010 |  | 2010 | SMARTWORLD THE EDITION | Commercial Equipment | 9110000206 | 1140 |  |  | 2023-07-24 | Glass Beaker, Cap.: 25ml | NO | 1 | 83.52 | 83.52 | 98.55 | 83.49 | 98.52 | 0.03 | 83.52 | 98.52 | ZMAT | 2025-01-20 | 2025-03-20
RE/0066-SOE-75 | Site Office Expenses at Sec 75 | 2010 |  | 2010 | SMARTWORLD THE EDITION | Commercial Equipment | 9110000206 | 1150 |  |  | 2023-07-24 | Glass Beaker, Cap.: 50ml | NO | 1 | 87 | 87 | 102.66 | 87.29 | 103 | 0.29 | 87 | 103 | ZMAT | 2025-01-20 | 2025-03-20
RE/0066-SOE-75 | Site Office Expenses at Sec 75 | 2010 |  | 2010 | SMARTWORLD THE EDITION | Commercial Equipment | 9110000206 | 1160 |  |  | 2023-07-24 | Glass Beaker, Cap.: 100ml | NO | 1 | 100.92 | 100.92 | 119.09 | 100.78 | 118.92 | 0.14 | 100.92 | 118.92 | ZMAT | 2025-01-20 | 2025-03-20
RE/0066-SOE-75 | Site Office Expenses at Sec 75 | 2010 |  | 2010 | SMARTWORLD THE EDITION | Commercial Equipment | 9110000206 | 1170 |  |  | 2023-07-24 | Glass Beaker, Cap.: 250ml | NO | 1 | 111.36 | 111.36 | 131.4 | 111.32 | 131.36 | 0.04 | 111.36 | 131.36 | ZMAT | 2025-01-20 | 2025-03-20
RE/0066-SOE-75 | Site Office Expenses at Sec 75 | 2010 |  | 2010 | SMARTWORLD THE EDITION | Commercial Equipment | 9110000206 | 1180 |  |  | 2023-07-24 | Glass Beaker, Cap.: 500ml | NO | 1 | 184.44 | 184.44 | 217.64 | 184.27 | 217.44 | 0.17 | 184.44 | 217.44 | ZMAT | 2025-01-20 | 2025-03-20
RE/0066-SOE-75 | Site Office Expenses at Sec 75 | 2010 |  | 2010 | SMARTWORLD THE EDITION | Commercial Equipment | 9110000206 | 1190 |  |  | 2023-07-24 | Glass Beaker, Cap.: 1000ml | NO | 1 | 341.04 | 341.04 | 402.43 | 340.71 | 402.04 | 0.33 | 341.04 | 402.04 | ZMAT | 2025-01-20 | 2025-03-20
RE/0066-SOE-75 | Site Office Expenses at Sec 75 | 2010 |  | 2010 | SMARTWORLD THE EDITION | Commercial Equipment | 9110000206 | 1200 |  |  | 2023-07-24 | Glass Beaker, Cap.: 2000ml | NO | 1 | 542.88 | 542.88 | 640.6 | 543.12 | 640.88 | 0.24 | 542.88 | 640.88 | ZMAT | 2025-01-20 | 2025-03-20
RE/0066-SOE-75 | Site Office Expenses at Sec 75 | 2010 |  | 2010 | SMARTWORLD THE EDITION | Commercial Equipment | 9110000206 | 1210 |  |  | 2023-07-24 | Glass Pipette, Cap.: 5ml | NO | 1 | 174.08 | 174.08 | 205.41 | 173.8 | 205.08 | 0.28 | 174.08 | 205.08 | ZMAT | 2025-01-20 | 2025-03-20
RE/0066-SOE-75 | Site Office Expenses at Sec 75 | 2010 |  | 2010 | SMARTWORLD THE EDITION | Commercial Equipment | 9110000206 | 1220 |  |  | 2023-07-24 | Glass Pipette, Cap.: 10ml | NO | 1 | 191.2 | 191.2 | 225.62 | 190.85 | 225.2 | 0.35 | 191.2 | 225.2 | ZMAT | 2025-01-20 | 2025-03-20
RE/0066-SOE-75 | Site Office Expenses at Sec 75 | 2010 |  | 2010 | SMARTWORLD THE EDITION | Commercial Equipment | 9110000206 | 1230 |  |  | 2023-07-24 | Glass Pipette, Cap.: 25ml | NO | 1 | 243.2 | 243.2 | 286.98 | 243.39 | 287.2 | 0.19 | 243.2 | 287.2 | ZMAT | 2025-01-20 | 2025-03-20
RE/0066-SOE-75 | Site Office Expenses at Sec 75 | 2010 |  | 2010 | SMARTWORLD THE EDITION | Commercial Equipment | 9110000206 | 1240 |  |  | 2023-07-24 | Glass Measuring Cylinder, Cap.: 10ml | NO | 1 | 330.4 | 330.4 | 389.87 | 330 | 389.4 | 0.4 | 330.4 | 389.4 | ZMAT | 2025-01-20 | 2025-03-20
RE/0066-SOE-75 | Site Office Expenses at Sec 75 | 2010 |  | 2010 | SMARTWORLD THE EDITION | Commercial Equipment | 9110000206 | 1250 |  |  | 2023-07-24 | Glass Measuring Cylinder, Cap.: 50ml | NO | 1 | 444.8 | 444.8 | 524.86 | 444.75 | 524.8 | 0.05 | 444.8 | 524.8 | ZMAT | 2025-01-20 | 2025-03-20
RE/0066-SOE-75 | Site Office Expenses at Sec 75 | 2010 |  | 2010 | SMARTWORLD THE EDITION | Commercial Equipment | 9110000206 | 1260 |  |  | 2023-07-24 | Glass Measuring Cylinder, Cap.: 100ml | NO | 1 | 480 | 480 | 566.4 | 479.66 | 566 | 0.34 | 480 | 566 | ZMAT | 2025-01-20 | 2025-03-20
RE/0066-SOE-75 | Site Office Expenses at Sec 75 | 2010 |  | 2010 | SMARTWORLD THE EDITION | Commercial Equipment | 9110000206 | 1270 |  |  | 2023-07-24 | Glass Measuring Cylinder, Cap.: 250ml | NO | 1 | 820.8 | 820.8 | 968.54 | 821.02 | 968.8 | 0.22 | 820.8 | 968.8 | ZMAT | 2025-01-20 | 2025-03-20
RE/0066-SOE-75 | Site Office Expenses at Sec 75 | 2010 |  | 2010 | SMARTWORLD THE EDITION | Commercial Equipment | 9110000206 | 1280 |  |  | 2023-07-24 | Glass Measuring Cylinder, Cap.: 500ml | NO | 1 | 1078.4 | 1078.4 | 1272.51 | 1078.31 | 1272.4 | 0.09 | 1078.4 | 1272.4 | ZMAT | 2025-01-20 | 2025-03-20
RE/0066-SOE-75 | Site Office Expenses at Sec 75 | 2010 |  | 2010 | SMARTWORLD THE EDITION | Commercial Equipment | 9110000206 | 1290 |  |  | 2023-07-24 | Glass Measuring Cylinder, Cap.: 1000ml | NO | 1 | 1461.6 | 1461.6 | 1724.69 | 1461.53 | 1724.6 | 0.07 | 1461.6 | 1724.6 | ZMAT | 2025-01-20 | 2025-03-20
RE/0066-SOE-75 | Site Office Expenses at Sec 75 | 2010 |  | 2010 | SMARTWORLD THE EDITION | Commercial Equipment | 9110000206 | 1300 |  |  | 2023-07-24 | Glass Measuring Cylinder, Cap.: 2000ml | NO | 1 | 2769.6 | 2769.6 | 3268.13 | 2770 | 3268.6 | 0.4 | 2769.6 | 3268.6 | ZMAT | 2025-01-20 | 2025-03-20
RE/0066-SOE-75 | Site Office Expenses at Sec 75 | 2010 |  | 2010 | SMARTWORLD THE EDITION | Commercial Equipment | 9110000206 | 1310 |  |  | 2023-07-24 | Glass Funnel, Size: 35mm x 30mm | NO | 1 | 264 | 264 | 311.52 | 264.41 | 312 | 0.41 | 264 | 312 | ZMAT | 2025-01-20 | 2025-03-20
RE/0066-SOE-75 | Site Office Expenses at Sec 75 | 2010 |  | 2010 | SMARTWORLD THE EDITION | Commercial Equipment | 9110000206 | 1320 |  |  | 2023-07-24 | Glass Funnel, Size: 80mm x 40mm | NO | 1 | 452 | 452 | 533.36 | 451.69 | 533 | 0.31 | 452 | 533 | ZMAT | 2025-01-20 | 2025-03-20
RE/0066-SOE-75 | Site Office Expenses at Sec 75 | 2010 |  | 2010 | SMARTWORLD THE EDITION | Commercial Equipment | 9110000206 | 1330 |  |  | 2023-07-24 | HYDROCHLORIC ACID 500gms | NO | 1 | 344 | 344 | 405.92 | 344.07 | 406 | 0.07 | 344 | 406 | ZMAT | 2025-01-20 | 2025-03-20
RE/0066-SOE-75 | Site Office Expenses at Sec 75 | 2010 |  | 2010 | SMARTWORLD THE EDITION | Commercial Equipment | 9110000206 | 1340 |  |  | 2023-07-24 | NITRIC ACID 500ml | NO | 1 | 624 | 624 | 736.32 | 623.73 | 736 | 0.27 | 624 | 736 | ZMAT | 2025-01-20 | 2025-03-20
RE/0066-SOE-75 | Site Office Expenses at Sec 75 | 2010 |  | 2010 | SMARTWORLD THE EDITION | Commercial Equipment | 9110000206 | 1350 |  |  | 2023-07-24 | SULPHURIC ACID 500ml | NO | 1 | 480 | 480 | 566.4 | 479.66 | 566 | 0.34 | 480 | 566 | ZMAT | 2025-01-20 | 2025-03-20
RE/0066-SOE-75 | Site Office Expenses at Sec 75 | 2010 |  | 2010 | SMARTWORLD THE EDITION | Commercial Equipment | 9110000206 | 1360 |  |  | 2023-07-24 | ORTHO PHOPHOSPHORIC ACID 500gm | NO | 1 | 1040 | 1040 | 1227.2 | 1039.83 | 1227 | 0.17 | 1040 | 1227 | ZMAT | 2025-01-20 | 2025-03-20
RE/0066-SOE-75 | Site Office Expenses at Sec 75 | 2010 |  | 2010 | SMARTWORLD THE EDITION | Commercial Equipment | 9110000206 | 1370 |  |  | 2023-07-24 | HYDROFLORIC ACID 500ml | NO | 1 | 1888 | 1888 | 2227.84 | 1888.14 | 2228 | 0.14 | 1888 | 2228 | ZMAT | 2025-01-20 | 2025-03-20
RE/0066-SOE-75 | Site Office Expenses at Sec 75 | 2010 |  | 2010 | SMARTWORLD THE EDITION | Commercial Equipment | 9110000206 | 1380 |  |  | 2023-07-24 | SODIUM HYDROXIDE 500ml | NO | 1 | 440 | 440 | 519.2 | 439.83 | 519 | 0.17 | 440 | 519 | ZMAT | 2025-01-20 | 2025-03-20
RE/0066-SOE-75 | Site Office Expenses at Sec 75 | 2010 |  | 2010 | SMARTWORLD THE EDITION | Commercial Equipment | 9110000206 | 1390 |  |  | 2023-07-24 | GLYCEROL 500ml | NO | 1 | 944 | 944 | 1113.92 | 944.07 | 1114 | 0.07 | 944 | 1114 | ZMAT | 2025-01-20 | 2025-03-20
RE/0066-SOE-75 | Site Office Expenses at Sec 75 | 2010 |  | 2010 | SMARTWORLD THE EDITION | Commercial Equipment | 9110000206 | 1400 |  |  | 2023-07-24 | DIETHYLAMINE 500ml | NO | 1 | 768 | 768 | 906.24 | 767.8 | 906 | 0.2 | 768 | 906 | ZMAT | 2025-01-20 | 2025-03-20
RE/0066-SOE-75 | Site Office Expenses at Sec 75 | 2010 |  | 2010 | SMARTWORLD THE EDITION | Commercial Equipment | 9110000206 | 1410 |  |  | 2023-07-24 | TRIETHYLAMINE 500ml | NO | 1 | 1360 | 1360 | 1604.8 | 1360.17 | 1605 | 0.17 | 1360 | 1605 | ZMAT | 2025-01-20 | 2025-03-20
RE/0066-SOE-75 | Site Office Expenses at Sec 75 | 2010 |  | 2010 | SMARTWORLD THE EDITION | Commercial Equipment | 9110000206 | 1420 |  |  | 2023-07-24 | AMMONIUM HYDROXIDE 500ml | NO | 1 | 384 | 384 | 453.12 | 383.9 | 453 | 0.1 | 384 | 453 | ZMAT | 2025-01-20 | 2025-03-20
RE/0066-SOE-75 | Site Office Expenses at Sec 75 | 2010 |  | 2010 | SMARTWORLD THE EDITION | Commercial Equipment | 9110000206 | 1430 |  |  | 2023-07-24 | SULPHOSYLIC ACID 100gm | NO | 1 | 944 | 944 | 1113.92 | 944.07 | 1114 | 0.07 | 944 | 1114 | ZMAT | 2025-01-20 | 2025-03-20
RE/0066-SOE-75 | Site Office Expenses at Sec 75 | 2010 |  | 2010 | SMARTWORLD THE EDITION | Commercial Equipment | 9110000206 | 1440 |  |  | 2023-07-24 | PATTON AND READER 5gm | NO | 1 | 392 | 392 | 462.56 | 392.37 | 463 | 0.37 | 392 | 463 | ZMAT | 2025-01-20 | 2025-03-20
RE/0066-SOE-75 | Site Office Expenses at Sec 75 | 2010 |  | 2010 | SMARTWORLD THE EDITION | Commercial Equipment | 9110000206 | 1450 |  |  | 2023-07-24 | SILVER NITRATE 25gm | NO | 1 | 8000 | 8000 | 9440 | 8000 | 9440 | 0 | 8000 | 9440 | ZMAT | 2025-01-20 | 2025-03-20
RE/0066-SOE-75 | Site Office Expenses at Sec 75 | 2010 |  | 2010 | SMARTWORLD THE EDITION | Commercial Equipment | 9110000206 | 1460 |  |  | 2023-07-24 | AMMONIUM CHLORIDE 500gm | NO | 1 | 2048 | 2048 | 2416.64 | 2048.31 | 2417 | 0.31 | 2048 | 2417 | ZMAT | 2025-01-20 | 2025-03-20
RE/0066-SOE-75 | Site Office Expenses at Sec 75 | 2010 |  | 2010 | SMARTWORLD THE EDITION | Commercial Equipment | 9110000206 | 1470 |  |  | 2023-07-24 | POTTASIUM HYDROXIDE 500gm | NO | 1 | 976 | 976 | 1151.68 | 976.27 | 1152 | 0.27 | 976 | 1152 | ZMAT | 2025-01-20 | 2025-03-20
RE/0066-SOE-75 | Site Office Expenses at Sec 75 | 2010 |  | 2010 | SMARTWORLD THE EDITION | Commercial Equipment | 9110000206 | 1480 |  |  | 2023-07-24 | AMMONIUM THICYANATE 500gm | NO | 1 | 1144 | 1144 | 1349.92 | 1144.07 | 1350 | 0.07 | 1144 | 1350 | ZMAT | 2025-01-20 | 2025-03-20
RE/0066-SOE-75 | Site Office Expenses at Sec 75 | 2010 |  | 2010 | SMARTWORLD THE EDITION | Commercial Equipment | 9110000206 | 1490 |  |  | 2023-07-24 | SODIUM THIOSULPHATE 500gm | NO | 1 | 440 | 440 | 519.2 | 439.83 | 519 | 0.17 | 440 | 519 | ZMAT | 2025-01-20 | 2025-03-20
RE/0066-SOE-75 | Site Office Expenses at Sec 75 | 2010 |  | 2010 | SMARTWORLD THE EDITION | Commercial Equipment | 9110000206 | 1500 |  |  | 2023-07-24 | E.D.T.A 100gm | NO | 1 | 672 | 672 | 792.96 | 672.03 | 793 | 0.03 | 672 | 793 | ZMAT | 2025-01-20 | 2025-03-20
RE/0066-SOE-75 | Site Office Expenses at Sec 75 | 2010 |  | 2010 | SMARTWORLD THE EDITION | Commercial Equipment | 9110000206 | 1510 |  |  | 2023-07-24 | NITRO BENZEN 25gm | NO | 1 | 1440 | 1440 | 1699.2 | 1439.83 | 1699 | 0.17 | 1440 | 1699 | ZMAT | 2025-01-20 | 2025-03-20
RE/0066-SOE-75 | Site Office Expenses at Sec 75 | 2010 |  | 2010 | SMARTWORLD THE EDITION | Commercial Equipment | 9110000206 | 1520 |  |  | 2023-07-24 | FERIC ALUM 100gm | NO | 1 | 320 | 320 | 377.6 | 320.34 | 378 | 0.34 | 320 | 378 | ZMAT | 2025-01-20 | 2025-03-20
RE/0066-SOE-75 | Site Office Expenses at Sec 75 | 2010 |  | 2010 | SMARTWORLD THE EDITION | Commercial Equipment | 9110000206 | 1530 |  |  | 2023-07-24 | FEROUS AMMONIUM SULPHATE 500gm | NO | 1 | 464 | 464 | 547.52 | 464.41 | 548 | 0.41 | 464 | 548 | ZMAT | 2025-01-20 | 2025-03-20
RE/0066-SOE-75 | Site Office Expenses at Sec 75 | 2010 |  | 2010 | SMARTWORLD THE EDITION | Commercial Equipment | 9110000206 | 1540 |  |  | 2023-07-24 | Machine oil 500ml | NO | 1 | 320 | 320 | 377.6 | 320.34 | 378 | 0.34 | 320 | 378 | ZMAT | 2025-01-20 | 2025-03-20
RE/0066-SOE-75 | Site Office Expenses at Sec 75 | 2010 |  | 2010 | SMARTWORLD THE EDITION | Commercial Equipment | 9110000206 | 1550 |  |  | 2023-07-24 | Propanol 500ml | NO | 1 | 1000 | 1000 | 1180 | 1000 | 1180 | 0 | 1000 | 1180 | ZMAT | 2025-01-20 | 2025-03-20
RE/0066-SOE-75 | Site Office Expenses at Sec 75 | 2010 |  | 2010 | SMARTWORLD THE EDITION | Commercial Equipment | 9110000206 | 1570 |  |  | 2023-07-24 | Lab Equipment | NO | 3 | 6150 | 18450 | 21771 | 0 | 0 | 18450 | 0 | 0 | ZMAT | 2025-01-20 | 2025-03-20
RE/0066-SOE-75 | Site Office Expenses at Sec 75 | 2010 |  | 2010 | SMARTWORLD THE EDITION | Commercial Equipment | 9110000206 | 1580 |  |  | 2023-07-24 | Lab Equipment | NO | 1 | 17300 | 17300 | 20414 | 0 | 0 | 17300 | 0 | 0 | ZMAT | 2025-01-20 | 2025-03-20
RE/0066-SOE-75 | Site Office Expenses at Sec 75 | 2010 |  | 2010 | SMARTWORLD THE EDITION | Commercial Equipment | 9110000206 | 1590 |  |  | 2023-07-24 | Lab Equipment | NO | 1 | 15100 | 15100 | 17818 | 15100 | 17818 | 0 | 15100 | 17818 | ZMAT | 2025-01-20 | 2025-03-20
RE/0066-SOE-75 | Site Office Expenses at Sec 75 | 2010 |  | 2010 | SMARTWORLD THE EDITION | Commercial Equipment | 9110000206 | 1600 |  |  | 2023-07-24 | Lab Equipment | NO | 4 | 850 | 3400 | 4012 | 3400 | 4012 | 0 | 3400 | 4012 | ZMAT | 2025-01-20 | 2025-03-20
RE/0066-SOE-75 | Site Office Expenses at Sec 75 | 2010 |  | 2010 | SMARTWORLD THE EDITION | Commercial Equipment | 9110000206 | 1610 |  |  | 2023-07-24 | Lab Equipment | NO | 6 | 7750 | 46500 | 54870 | 0 | 0 | 46500 | 0 | 0 | ZMAT | 2025-01-20 | 2025-03-20
RE/0066-SOE-75 | Site Office Expenses at Sec 75 | 2010 |  | 2010 | SMARTWORLD THE EDITION | Commercial Equipment | 9110000206 | 1620 |  |  | 2023-07-24 | Lab Equipment | NO | 1 | 30950 | 30950 | 36521 | 0 | 0 | 30950 | 0 | 0 | ZMAT | 2025-01-20 | 2025-03-20
RE/0066-SOE-75 | Site Office Expenses at Sec 75 | 2010 |  | 2010 | SMARTWORLD THE EDITION | Commercial Equipment | 9110000206 | 1630 |  |  | 2023-07-24 | Lab Equipment | NO | 1 | 18600 | 18600 | 21948 | 0 | 0 | 18600 | 0 | 0 | ZMAT | 2025-01-20 | 2025-03-20
RE/0066-SOE-75 | Site Office Expenses at Sec 75 | 2010 |  | 2010 | SMARTWORLD THE EDITION | Commercial Equipment | 9110000206 | 1640 |  |  | 2023-07-24 | Lab Equipment | NO | 6 | 6750 | 40500 | 47790 | 0 | 0 | 40500 | 0 | 0 | ZMAT | 2025-01-20 | 2025-03-20
RE/0066-SOE-75 | Site Office Expenses at Sec 75 | 2010 |  | 2010 | SMARTWORLD THE EDITION | Commercial Equipment | 9110000206 | 1650 |  |  | 2023-07-24 | Lab Equipment | NO | 2 | 4200 | 8400 | 9912 | 0 | 0 | 8400 | 0 | 0 | ZMAT | 2025-01-20 | 2025-03-20
RE/0066-SOE-75 | Site Office Expenses at Sec 75 | 2010 |  | 2010 | SMARTWORLD THE EDITION | Commercial Equipment | 9110000206 | 1660 |  |  | 2023-07-24 | Lab Equipment | NO | 2 | 580 | 1160 | 1368.8 | 1160.17 | 1369 | 0.17 | 1160 | 1368.8 | ZMAT | 2025-01-20 | 2025-03-20
RE/0066-SOE-75 | Site Office Expenses at Sec 75 | 2010 |  | 2010 | SMARTWORLD THE EDITION | Commercial Equipment | 9110000206 | 1670 |  |  | 2023-07-24 | Lab Equipment | NO | 2 | 580 | 1160 | 1368.8 | 1160.17 | 1369 | 0.17 | 1160 | 1368.8 | ZMAT | 2025-01-20 | 2025-03-20
RE/0066-SOE-75 | Site Office Expenses at Sec 75 | 2010 |  | 2010 | SMARTWORLD THE EDITION | Commercial Equipment | 9110000206 | 1680 |  |  | 2023-07-24 | Lab Equipment | NO | 1 | 554500 | 554500 | 654310 | 554500 | 654310 | 0 | 554500 | 654310 | ZMAT | 2025-01-20 | 2025-03-20
RE/0066-SOE-75 | Site Office Expenses at Sec 75 | 2010 |  | 2010 | SMARTWORLD THE EDITION | Commercial Equipment | 9110000206 | 1690 |  |  | 2023-07-24 | Lab Equipment | NO | 1 | 9800 | 9800 | 11564 | 9800 | 11564 | 0 | 9800 | 11564 | ZMAT | 2025-01-20 | 2025-03-20
RE/0066-SOE-75 | Site Office Expenses at Sec 75 | 2010 |  | 2010 | SMARTWORLD THE EDITION | Commercial Equipment | 9110000206 | 1700 |  |  | 2023-07-24 | Lab Equipment | NO | 1 | 9800 | 9800 | 11564 | 0 | 0 | 9800 | 0 | 0 | ZMAT | 2025-01-20 | 2025-03-20
RE/0066-SOE-75 | Site Office Expenses at Sec 75 | 2010 |  | 2010 | SMARTWORLD THE EDITION | Commercial Equipment | 9110000206 | 1710 |  |  | 2023-07-24 | Lab Equipment | NO | 1 | 10500 | 10500 | 12390 | 0 | 0 | 10500 | 0 | 0 | ZMAT | 2025-01-20 | 2025-03-20
RE/0066-SOE-75 | Site Office Expenses at Sec 75 | 2010 |  | 2010 | SMARTWORLD THE EDITION | Commercial Equipment | 9110000206 | 1720 |  |  | 2023-07-24 | Lab Equipment | NO | 1 | 6500 | 6500 | 7670 | 6500 | 7670 | 0 | 6500 | 7670 | ZMAT | 2025-01-20 | 2025-03-20
RE/0066-SOE-75 | Site Office Expenses at Sec 75 | 2010 |  | 2010 | SMARTWORLD THE EDITION | Commercial Equipment | 9110000206 | 1730 |  |  | 2023-07-24 | Lab Equipment | NO | 1 | 1250 | 1250 | 1475 | 1250 | 1475 | 0 | 1250 | 1475 | ZMAT | 2025-01-20 | 2025-03-20
RE/0066-SOE-75 | Site Office Expenses at Sec 75 | 2010 |  | 2010 | SMARTWORLD THE EDITION | Commercial Equipment | 9110000206 | 1740 |  |  | 2023-07-24 | Lab Equipment | NO | 1 | 1850 | 1850 | 2183 | 1850 | 2183 | 0 | 1850 | 2183 | ZMAT | 2025-01-20 | 2025-03-20
RE/0066-SOE-75 | Site Office Expenses at Sec 75 | 2010 |  | 2010 | SMARTWORLD THE EDITION | Commercial Equipment | 9110000206 | 1750 |  |  | 2023-07-24 | Lab Equipment | NO | 1 | 232500 | 232500 | 274350 | 232500 | 274350 | 0 | 232500 | 274350 | ZMAT | 2025-01-20 | 2025-03-20
RE/0066-SOE-75 | Site Office Expenses at Sec 75 | 2010 |  | 2010 | SMARTWORLD THE EDITION | Commercial Equipment | 9110000206 | 1760 |  |  | 2023-07-24 | Lab Equipment | NO | 1 | 4500 | 4500 | 5310 | 4500 | 5310 | 0 | 4500 | 5310 | ZMAT | 2025-01-20 | 2025-03-20
RE/0066-SOE-75 | Site Office Expenses at Sec 75 | 2010 |  | 2010 | SMARTWORLD THE EDITION | Commercial Equipment | 9110000206 | 1770 |  |  | 2023-07-24 | Lab Equipment | NO | 1 | 4500 | 4500 | 5310 | 4500 | 5310 | 0 | 4500 | 5310 | ZMAT | 2025-01-20 | 2025-03-20
RE/0066-SOE-75 | Site Office Expenses at Sec 75 | 2010 |  | 2010 | SMARTWORLD THE EDITION | Commercial Equipment | 9110000206 | 1780 |  |  | 2023-07-24 | Lab Equipment | NO | 1 | 2800 | 2800 | 3304 | 2800 | 3304 | 0 | 2800 | 3304 | ZMAT | 2025-01-20 | 2025-03-20
RE/0066-SOE-75 | Site Office Expenses at Sec 75 | 2010 |  | 2010 | SMARTWORLD THE EDITION | Commercial Equipment | 9110000206 | 1790 |  |  | 2023-07-24 | Lab Equipment | NO | 1 | 52000 | 52000 | 61360 | 52000 | 61360 | 0 | 52000 | 61360 | ZMAT | 2025-01-20 | 2025-03-20
RE/0066-SOE-75 | Site Office Expenses at Sec 75 | 2010 |  | 2010 | SMARTWORLD THE EDITION | Commercial Equipment | 9110000206 | 1800 |  |  | 2023-07-24 | Lab Equipment | NO | 1 | 2600 | 2600 | 3068 | 0 | 0 | 2600 | 0 | 0 | ZMAT | 2025-01-20 | 2025-03-20
RE/0066-SOE-75 | Site Office Expenses at Sec 75 | 2010 |  | 2010 | SMARTWORLD THE EDITION | Commercial Equipment | 9110000206 | 1810 |  |  | 2023-07-24 | Lab Equipment | NO | 1 | 1490 | 1490 | 1758.2 | 0 | 0 | 1490 | 0 | 0 | ZMAT | 2025-01-20 | 2025-03-20
RE/0066-SOE-75 | Site Office Expenses at Sec 75 | 2010 |  | 2010 | SMARTWORLD THE EDITION | Commercial Equipment | 9110000206 | 1820 |  |  | 2023-07-24 | Lab Equipment | NO | 11 | 1160 | 12760 | 15056.8 | 0 | 0 | 12760 | 0 | 0 | ZMAT | 2025-01-20 | 2025-03-20
RE/0066-SOE-75 | Site Office Expenses at Sec 75 | 2010 |  | 2010 | SMARTWORLD THE EDITION | Commercial Equipment | 9110000206 | 1830 |  |  | 2023-07-24 | Lab Equipment | NO | 1 | 35700 | 35700 | 42126 | 35700 | 42126 | 0 | 35700 | 42126 | ZMAT | 2025-01-20 | 2025-03-20
RE/0066-SOE-75 | Site Office Expenses at Sec 75 | 2010 |  | 2010 | SMARTWORLD THE EDITION | Wings BeveragesCharanpreet | 9110000215 | 30 |  |  | 2023-07-25 | Lemon Tea (Dip)- CCD | PC | 3600 | 4.5 | 16200 | 17010 | 8100 | 8505 | 8100 | 8100 | 8505 | ZMAT | 2025-01-20 | 2025-03-20
RE/0066-SOE-75 | Site Office Expenses at Sec 75 | 2010 |  | 2010 | SMARTWORLD THE EDITION | Wings BeveragesCharanpreet | 9110000215 | 40 |  |  | 2023-07-25 | Masala Tea -CCD (100 Dip) | PC | 244 | 248 | 60512 | 63537.6 | 60512 | 63537.6 | 0 | 60584.6 | 63612.75 | ZMAT | 2025-01-20 | 2025-03-20
RE/0066-SOE-75 | Site Office Expenses at Sec 75 | 2010 |  | 2010 | SMARTWORLD THE EDITION | Wings BeveragesCharanpreet | 9110000215 | 50 |  |  | 2023-07-25 | Ginger Tea - CCD (100 Dip) | BOX | 231 | 248 | 57288 | 60152.4 | 55552 | 58329.6 | 1736 | 55552 | 58329.59 | ZMAT | 2025-01-20 | 2025-03-20
RE/0066-SOE-75 | Site Office Expenses at Sec 75 | 2010 |  | 2010 | SMARTWORLD THE EDITION | Wings BeveragesCharanpreet | 9110000215 | 60 |  |  | 2023-07-25 | Elaichi Tea - CCD (100 Dip) | BOX | 317.032 | 248 | 78623.94 | 82555.14 | 46872 | 49215.6 | 31751.94 | 46872 | 49215.64 | ZMAT | 2025-01-20 | 2025-03-20
RE/0066-SOE-75 | Site Office Expenses at Sec 75 | 2010 |  | 2010 | SMARTWORLD THE EDITION | Wings BeveragesCharanpreet | 9110000215 | 70 |  |  | 2023-07-25 | Green Tea - CCD | PC | 5666.67 | 4.5 | 25500.02 | 26775.02 | 24300 | 25515 | 1200.02 | 24300 | 25515.82 | ZMAT | 2025-01-20 | 2025-03-20
RE/0066-SOE-75 | Site Office Expenses at Sec 75 | 2010 |  | 2010 | SMARTWORLD THE EDITION | Wings BeveragesCharanpreet | 9110000215 | 80 |  |  | 2023-07-25 | Coffee Beans - CCD | KG | 528.793 | 623 | 329438.04 | 345909.94 | 93450.03 | 98122.53 | 235988.01 | 93550.4 | 98228.2 | ZMAT | 2025-01-20 | 2025-03-20
RE/0066-SOE-75 | Site Office Expenses at Sec 75 | 2010 |  | 2010 | SMARTWORLD THE EDITION | Wings BeveragesCharanpreet | 9110000215 | 90 |  |  | 2023-07-25 | Premium Coffee Beans (Aroma / Intenso) | KG | 2 | 850 | 1700 | 1785 | 0 | 0 | 1700 | 0 | 0 | ZMAT | 2025-01-20 | 2025-03-20
RE/0066-SOE-75 | Site Office Expenses at Sec 75 | 2010 |  | 2010 | SMARTWORLD THE EDITION | Wings BeveragesCharanpreet | 9110000215 | 100 |  |  | 2023-07-25 | Assam/ Classic/ Plain Tea - CCD | BOX | 276 | 150 | 41400 | 43470 | 41400 | 43470 | 0 | 41400 | 43469.61 | ZMAT | 2025-01-20 | 2025-03-20
RE/0066-SOE-75 | Site Office Expenses at Sec 75 | 2010 |  | 2010 | SMARTWORLD THE EDITION | Wings BeveragesCharanpreet | 9110000215 | 110 |  |  | 2023-07-25 | Sugar Crystal Branded | KG | 425 | 58 | 24650 | 25882.5 | 18850.02 | 19792.52 | 5799.98 | 18850 | 19793.39 | ZMAT | 2025-01-20 | 2025-03-20
RE/0066-SOE-75 | Site Office Expenses at Sec 75 | 2010 |  | 2010 | SMARTWORLD THE EDITION | Wings BeveragesCharanpreet | 9110000215 | 120 |  |  | 2023-07-25 | Sugar Cube branded | KG | 24 | 90 | 2160 | 2419.2 | 0 | 0 | 2160 | 0 | 0 | ZMAT | 2025-01-20 | 2025-03-20
RE/0066-SOE-75 | Site Office Expenses at Sec 75 | 2010 |  | 2010 | SMARTWORLD THE EDITION | Wings BeveragesCharanpreet | 9110000215 | 130 |  |  | 2023-07-25 | Flavor Green Tea (Tulsi/ Mint/Honey/lemo | PC | 1620 | 5 | 8100 | 8505 | 6000 | 6300 | 2100 | 6000 | 6300 | ZMAT | 2025-01-20 | 2025-03-20
RE/0066-SOE-75 | Site Office Expenses at Sec 75 | 2010 |  | 2010 | SMARTWORLD THE EDITION | Wings BeveragesCharanpreet | 9110000215 | 140 |  |  | 2023-07-25 | Sugar Free Sachet | PC | 24 | 1.25 | 30 | 33.6 | 0 | 0 | 30 | 0 | 0 | ZMAT | 2025-01-20 | 2025-03-20
RE/0066-SOE-75 | Site Office Expenses at Sec 75 | 2010 |  | 2010 | SMARTWORLD THE EDITION | Wings BeveragesCharanpreet | 9110000215 | 150 |  |  | 2023-07-25 | Wooden Stirrer | PC | 12 | 0.24 | 2.88 | 3.02 | 0 | 0 | 2.88 | 0 | 0 | ZMAT | 2025-01-20 | 2025-03-20
RE/0066-SOE-75 | Site Office Expenses at Sec 75 | 2010 |  | 2010 | SMARTWORLD THE EDITION | Wings BeveragesCharanpreet | 9110000215 | 160 |  |  | 2023-07-25 | Milk | L | 3683.76 | 66 | 243128.16 | 243128.16 | 94710 | 94710 | 148418.16 | 94710 | 94710 | ZMAT | 2025-01-20 | 2025-03-20
RE/0066-SOE-75 | Site Office Expenses at Sec 75 | 2010 |  | 2010 | SMARTWORLD THE EDITION | M/s Jaipur Rugs Company Pvt Ltd. | 9110000219 | 20 |  |  | 2023-07-26 | HANDCRAFTED RUGS | NO | 1 | 33335.82 | 33335.82 | 35002.61 | 33335.82 | 35002.61 | 0 | 33335.82 | 35002.82 | ZMAT | 2025-01-20 | 2025-03-20
RE/0066-SOE-75 | Site Office Expenses at Sec 75 | 2010 |  | 2010 | SMARTWORLD THE EDITION | KAP Multi Product | 9110000234 | 10 |  |  | 2023-08-02 | Slotted Angle Rack CWIP-75 | RFT | 35.5 | 3650 | 129575 | 152898.5 | 129575 | 152898.5 | 0 | 129575 | 152899 | ZMAT | 2025-01-20 | 2025-03-20
RE/0066-SOE-75 | Site Office Expenses at Sec 75 | 2010 |  | 2010 | SMARTWORLD THE EDITION | KAP Multi Product | 9110000234 | 20 |  |  | 2023-08-02 | Installation Charges | RFT | 1 | 4000 | 4000 | 4720 | 4000 | 4720 | 0 | 4000 | 4720 | ZMAT | 2025-01-20 | 2025-03-20
RE/0066-SOE-75 | Site Office Expenses at Sec 75 | 2010 |  | 2010 | SWD Central office-75 | Industrial Foams Private Limited | 9110000715 | 10 |  |  | 2024-09-30 | Supply of Gutter in PPGI 0.5mm | RMT | 210 | 450 | 94500 | 111510 | 0 | 0 | 94500 | 0 | 0 | ZMAT | 2024-10-08 | 2024-11-08
RE/0066-SOE-75 | Site Office Expenses at Sec 75 | 2010 |  | 2010 | SMARTWORLD THE EDITION | Metamorphosis ConstructionsSUMIT | 9140000041 | 10 |  |  | 2023-02-10 | Fit-out work for our Project Office | AU | 1 | 20880000 | 0 | 0 | 0 | 0 | 0 | 20860000 | 24614800 | ZSER | 2022-10-29 | 2023-02-28
RE/0066-SOE-75 | Site Office Expenses at Sec 75 | 2010 |  | 2010 | SMARTWORLD THE EDITION | Metamorphosis ConstructionsSUMIT | 9140000041 | 10 |  |  | 2023-02-10 | Fit-out work for our Project Office | AU | 1 | 0 | 20880000 | 24638400 | 0 | 0 | 20880000 | 17677966.1 | 20860000 | ZSER | 2022-10-29 | 2023-02-28
RE/0066-SOE-75 | Site Office Expenses at Sec 75 | 2010 |  | 2010 | SMARTWORLD THE EDITION | Metamorphosis ConstructionsSUMIT | 9140000041 | 20 |  |  | 2023-02-10 | Fit-out work for our Project Office | AU | 1 | 2320000 | 2320000 | 2737600 | 2320000 | 2737600 | 0 | 2143050.85 | 2528800 | ZSER | 2022-10-29 | 2023-02-28
RE/0066-SOE-75 | Site Office Expenses at Sec 75 | 2010 |  | 2010 | SMARTWORLD THE EDITION | Metamorphosis ConstructionsSUMIT | 9140000041 | 30 |  |  | 2023-02-10 | Amednment 2 for additional items | AU | 1 | 1003359 | 1003359 | 1183963.62 | 1003358.47 | 1183963 | 0.53 | 1003358.98 | 1183963.6 | ZSER | 2022-10-29 | 2023-02-28
RE/0066-SOE-75 | Site Office Expenses at Sec 75 | 2010 |  | 2010 | SMARTWORLD THE EDITION | GMGR Sanitary and Allied Private li | 9140000053 | 10 |  |  | 2023-03-03 | SITC OF BIO DIGESTER -5 KLD | AU | 1 | 600000 | 600000 | 600000 | 621600 | 621600 | 21600 | 600000 | 600000 | ZSER | 2023-01-30 | 2023-02-15
RE/0066-SOE-75 | Site Office Expenses at Sec 75 | 2010 |  | 2010 | SMARTWORLD THE EDITION | C. Jena & CompanyC. Jena & Company | 9140000055 | 10 |  |  | 2023-03-13 | EXTERNAL SEWERAGE & STORM WATER DRAINAGE | AU | 1 | 1085127.38 | 1085127.38 | 1280450.31 | 1085127.38 | 1280450.31 | 0 | 1085127.38 | 1280450.31 | ZSER | 2023-01-18 | 2023-02-12
RE/0066-SOE-75 | Site Office Expenses at Sec 75 | 2010 |  | 2010 | SMARTWORLD THE EDITION | C. Jena & CompanyC. Jena & Company | 9140000055 | 10 |  |  | 2023-03-13 | EXTERNAL SEWERAGE & STORM WATER DRAINAGE | AU | 1 | 0 | 1085127.38 | 1280450.31 | 1085127.38 | 1280450.31 | 0 | 1085127.38 | 1280450.31 | ZSER | 2023-01-18 | 2023-02-12
RE/0066-SOE-75 | Site Office Expenses at Sec 75 | 2010 |  | 2010 | SMARTWORLD THE EDITION | C. Jena & CompanyC. Jena & Company | 9140000055 | 10 |  |  | 2023-03-13 | EXTERNAL SEWERAGE & STORM WATER DRAINAGE | AU | 1 | 0 | 1085127.38 | 1280450.31 | 1085127.38 | 1280450.31 | 0 | 1085127.38 | 1280450.31 | ZSER | 2023-01-18 | 2023-02-12
RE/0066-SOE-75 | Site Office Expenses at Sec 75 | 2010 |  | 2010 | SMARTWORLD THE EDITION | C. Jena & CompanyC. Jena & Company | 9140000055 | 20 |  |  | 2023-03-13 | EXTERNAL WATER SUPPLY SYSTEM | AU | 1 | 74630 | 74630 | 88063.4 | 63245.76 | 74630 | 11384.24 | 63245.76 | 74630 | ZSER | 2023-01-18 | 2023-02-12
RE/0066-SOE-75 | Site Office Expenses at Sec 75 | 2010 |  | 2010 | SMARTWORLD THE EDITION | C. Jena & CompanyC. Jena & Company | 9140000055 | 20 |  |  | 2023-03-13 | EXTERNAL WATER SUPPLY SYSTEM | AU | 1 | 0 | 74630 | 88063.4 | 63245.76 | 74630 | 11384.24 | 63245.76 | 74630 | ZSER | 2023-01-18 | 2023-02-12
RE/0066-SOE-75 | Site Office Expenses at Sec 75 | 2010 |  | 2010 | SMARTWORLD THE EDITION | C. Jena & CompanyC. Jena & Company | 9140000055 | 30 |  |  | 2023-03-13 | GARDEN HYDRANT | AU | 1 | 110062.7 | 110062.7 | 129873.99 | 93273.47 | 110062.7 | 16789.23 | 93273.47 | 110062.7 | ZSER | 2023-01-18 | 2023-02-12
RE/0066-SOE-75 | Site Office Expenses at Sec 75 | 2010 |  | 2010 | SMARTWORLD THE EDITION | C. Jena & CompanyC. Jena & Company | 9140000055 | 30 |  |  | 2023-03-13 | GARDEN HYDRANT | AU | 1 | 0 | 110062.7 | 129873.99 | 93273.47 | 110062.7 | 16789.23 | 93273.47 | 110062.7 | ZSER | 2023-01-18 | 2023-02-12
RE/0066-SOE-75 | Site Office Expenses at Sec 75 | 2010 |  | 2010 | SMARTWORLD THE EDITION | C. Jena & CompanyC. Jena & Company | 9140000055 | 40 |  |  | 2023-03-13 | PUMPS & ALLIED EQUIPMENT | AU | 1 | 294950 | 294950 | 348041 | 249957.63 | 294950 | 44992.37 | 249957.63 | 294950 | ZSER | 2023-01-18 | 2023-02-12
RE/0066-SOE-75 | Site Office Expenses at Sec 75 | 2010 |  | 2010 | SMARTWORLD THE EDITION | C. Jena & CompanyC. Jena & Company | 9140000055 | 40 |  |  | 2023-03-13 | PUMPS & ALLIED EQUIPMENT | AU | 1 | 0 | 294950 | 348041 | 249957.63 | 294950 | 44992.37 | 249957.63 | 294950 | ZSER | 2023-01-18 | 2023-02-12
RE/0066-SOE-75 | Site Office Expenses at Sec 75 | 2010 |  | 2010 | SMARTWORLD THE EDITION | C. Jena & CompanyC. Jena & Company | 9140000055 | 50 |  |  | 2023-03-13 | EXTERNAL SEWERAGE & STORM WATER DRg work | AU | 1 | 259774.64 | 259774.64 | 306534.08 | 224615.44 | 265046.22 | 35159.2 | 224616.3 | 265047.23 | ZSER | 2023-01-18 | 2023-02-12
RE/0066-SOE-75 | Site Office Expenses at Sec 75 | 2010 |  | 2010 | SMARTWORLD THE EDITION | C. Jena & CompanyC. Jena & Company | 9140000055 | 50 |  |  | 2023-03-13 | EXTERNAL SEWERAGE & STORM WATER DRg work | AU | 1 | 0 | 259774.64 | 306534.08 | 224615.44 | 265046.22 | 35159.2 | 224616.3 | 265047.23 | ZSER | 2023-01-18 | 2023-02-12
RE/0066-SOE-75 | Site Office Expenses at Sec 75 | 2010 |  | 2010 | SMARTWORLD THE EDITION | C. Jena & CompanyC. Jena & Company | 9140000055 | 50 |  |  | 2023-03-13 | EXTERNAL SEWERAGE & STORM WATER DRg work | AU | 1 | 0 | 259774.64 | 306534.08 | 224615.44 | 265046.22 | 35159.2 | 224616.3 | 265047.23 | ZSER | 2023-01-18 | 2023-02-12
RE/0066-SOE-75 | Site Office Expenses at Sec 75 | 2010 |  | 2010 | SMARTWORLD THE EDITION | C. Jena & CompanyC. Jena & Company | 9140000055 | 60 |  |  | 2023-03-13 | EXTERNAL WATER SUPPLY SYSTEM | AU | 1 | 87910 | 87910 | 103733.8 | 68182.64 | 80455.52 | 19727.36 | 68182.19 | 80454.98 | ZSER | 2023-01-18 | 2023-02-12
RE/0066-SOE-75 | Site Office Expenses at Sec 75 | 2010 |  | 2010 | SMARTWORLD THE EDITION | C. Jena & CompanyC. Jena & Company | 9140000055 | 60 |  |  | 2023-03-13 | EXTERNAL WATER SUPPLY SYSTEM | AU | 1 | 0 | 87910 | 103733.8 | 68182.64 | 80455.52 | 19727.36 | 68182.19 | 80454.98 | ZSER | 2023-01-18 | 2023-02-12
RE/0066-SOE-75 | Site Office Expenses at Sec 75 | 2010 |  | 2010 | SMARTWORLD THE EDITION | C. Jena & CompanyC. Jena & Company | 9140000055 | 60 |  |  | 2023-03-13 | EXTERNAL WATER SUPPLY SYSTEM | AU | 1 | 0 | 87910 | 103733.8 | 68182.64 | 80455.52 | 19727.36 | 68182.19 | 80454.98 | ZSER | 2023-01-18 | 2023-02-12
RE/0066-SOE-75 | Site Office Expenses at Sec 75 | 2010 |  | 2010 | SMARTWORLD THE EDITION | C. Jena & CompanyC. Jena & Company | 9140000055 | 70 |  |  | 2023-03-13 | GARDEN HYDRANT | AU | 1 | 113037.3 | 113037.3 | 133384.01 | 92662.35 | 109341.57 | 20374.95 | 92662.16 | 109341.35 | ZSER | 2023-01-18 | 2023-02-12
RE/0066-SOE-75 | Site Office Expenses at Sec 75 | 2010 |  | 2010 | SMARTWORLD THE EDITION | C. Jena & CompanyC. Jena & Company | 9140000055 | 70 |  |  | 2023-03-13 | GARDEN HYDRANT | AU | 1 | 0 | 113037.3 | 133384.01 | 92662.35 | 109341.57 | 20374.95 | 92662.16 | 109341.35 | ZSER | 2023-01-18 | 2023-02-12
RE/0066-SOE-75 | Site Office Expenses at Sec 75 | 2010 |  | 2010 | SMARTWORLD THE EDITION | C. Jena & CompanyC. Jena & Company | 9140000055 | 70 |  |  | 2023-03-13 | GARDEN HYDRANT | AU | 1 | 0 | 113037.3 | 133384.01 | 92662.35 | 109341.57 | 20374.95 | 92662.16 | 109341.35 | ZSER | 2023-01-18 | 2023-02-12
RE/0066-SOE-75 | Site Office Expenses at Sec 75 | 2010 |  | 2010 | SMARTWORLD THE EDITION | C. Jena & CompanyC. Jena & Company | 9140000055 | 80 |  |  | 2023-03-13 | PUMPS & ALLIED EQUIPMENT | AU | 1 | 63250 | 63250 | 74635 | 63249.83 | 74634.8 | 0.17 | 63250 | 74635 | ZSER | 2023-01-18 | 2023-02-12
RE/0066-SOE-75 | Site Office Expenses at Sec 75 | 2010 |  | 2010 | SMARTWORLD THE EDITION | C. Jena & CompanyC. Jena & Company | 9140000055 | 80 |  |  | 2023-03-13 | PUMPS & ALLIED EQUIPMENT | AU | 1 | 0 | 63250 | 74635 | 63249.83 | 74634.8 | 0.17 | 63250 | 74635 | ZSER | 2023-01-18 | 2023-02-12
RE/0066-SOE-75 | Site Office Expenses at Sec 75 | 2010 |  | 2010 | SMARTWORLD THE EDITION | C. Jena & CompanyC. Jena & Company | 9140000055 | 80 |  |  | 2023-03-13 | PUMPS & ALLIED EQUIPMENT | AU | 1 | 0 | 63250 | 74635 | 63249.83 | 74634.8 | 0.17 | 63250 | 74635 | ZSER | 2023-01-18 | 2023-02-12
RE/0066-SOE-75 | Site Office Expenses at Sec 75 | 2010 |  | 2010 | SMARTWORLD THE EDITION | C. Jena & CompanyC. Jena & Company | 9140000055 | 90 |  |  | 2023-03-13 | Additional Items | AU | 1 | 566022 | 566022 | 667905.96 | 511248.92 | 603273.72 | 54773.08 | 511249.15 | 603274 | ZSER | 2023-01-18 | 2023-02-12
RE/0066-SOE-75 | Site Office Expenses at Sec 75 | 2010 |  | 2010 | SMARTWORLD THE EDITION | C. Jena & CompanyC. Jena & Company | 9140000055 | 90 |  |  | 2023-03-13 | Additional Items | AU | 1 | 0 | 566022 | 667905.96 | 511248.92 | 603273.72 | 54773.08 | 511249.15 | 603274 | ZSER | 2023-01-18 | 2023-02-12
RE/0066-SOE-75 | Site Office Expenses at Sec 75 | 2010 |  | 2010 | SMARTWORLD THE EDITION | C. Jena & CompanyC. Jena & Company | 9140000055 | 90 |  |  | 2023-03-13 | Additional Items | AU | 1 | 0 | 566022 | 667905.96 | 511248.92 | 603273.72 | 54773.08 | 511249.15 | 603274 | ZSER | 2023-01-18 | 2023-02-12
RE/0066-SOE-75 | Site Office Expenses at Sec 75 | 2010 |  | 2010 | SMARTWORLD THE EDITION | Swastik Enterprises | 9140000071 | 10 |  |  | 2023-03-28 | Design & Build Turnkey Porta Cabin Works | AU | 1 | 2167296 | 2167296 | 2557409.28 | 1946893.22 | 2297334 | 220402.78 | 1946893.22 | 2297334 | ZSER | 2022-08-20 | 2022-10-04
RE/0066-SOE-75 | Site Office Expenses at Sec 75 | 2010 |  | 2010 | SMARTWORLD THE EDITION | Uniline Energy Systems Pvt Ltd | 9140000072 | 10 |  |  | 2023-03-31 | SITC UPS SYSTEM | AU | 1 | 170500 | 170500 | 170500 | 0 | 0 | 170500 | 0 | 0 | ZSER | 2023-02-02 | 2023-04-01
RE/0066-SOE-75 | Site Office Expenses at Sec 75 | 2010 |  | 2010 | SMARTWORLD THE EDITION | Trifle Sane | 9140000082 | 10 |  |  | 2023-04-12 | MS Structural Works | AU | 1 | 3291151.24 | 3291151.24 | 3291151.24 | 0 | 0 | 3291151.24 | 0 | 0 | ZSER | 2022-08-20 | 2022-09-19
RE/0066-SOE-75 | Site Office Expenses at Sec 75 | 2010 |  | 2010 | SMARTWORLD THE EDITION | Aelius Infrastructure Private Limit | 9140000085 | 10 |  |  | 2023-04-15 | Landscape Civil Works Sector-75 | AU | 1 | 4700509.11 | 4700509.11 | 5546600.75 | 4700508.56 | 5546600.1 | 0.55 | 4700509.05 | 5546600.68 | ZSER | 2023-02-09 | 2023-04-24
RE/0066-SOE-75 | Site Office Expenses at Sec 75 | 2010 |  | 2010 | SMARTWORLD THE EDITION | Aditya Electro Projects | 9140000086 | 10 |  |  | 2023-04-15 | Supply of Light Poles & Light Fixtures | AU | 1 | 209950.2 | 209950.2 | 247741.24 | 209950.42 | 247741.49 | 0.22 | 209950.2 | 247741.24 | ZSER | 2023-02-03 | 2023-03-18
RE/0066-SOE-75 | Site Office Expenses at Sec 75 | 2010 |  | 2010 | SMARTWORLD THE EDITION | Aditya Electro Projects | 9140000086 | 20 |  |  | 2023-04-15 | Electrical Works | AU | 1 | 410406 | 410406 | 484279.08 | 410406 | 484279.08 | 0 | 410405.76 | 484278.8 | ZSER | 2023-02-03 | 2023-03-18
RE/0066-SOE-75 | Site Office Expenses at Sec 75 | 2010 |  | 2010 | SMARTWORLD THE EDITION | Aditya Electro Projects | 9140000086 | 30 |  |  | 2023-04-15 | Electrical Works amend-2 | AU | 1 | 176000 | 176000 | 207680 | 175999.86 | 207679.83 | 0.14 | 176000 | 207680 | ZSER | 2023-02-03 | 2023-03-18
RE/0066-SOE-75 | Site Office Expenses at Sec 75 | 2010 |  | 2010 | SMARTWORLD THE EDITION | Aditya Electro Projects | 9140000093 | 10 |  |  | 2023-04-21 | SITC OF Cables and Pipes | AU | 1 | 1099732 | 1099732 | 1297683.76 | 905948.88 | 1069019.68 | 193783.12 | 905948.43 | 1069019.15 | ZSER | 2023-01-02 | 2023-02-01
RE/0066-SOE-75 | Site Office Expenses at Sec 75 | 2010 |  | 2010 | SMARTWORLD THE EDITION | Aditya Electro Projects | 9140000093 | 20 |  |  | 2023-04-21 | SITC OF HT,TRANSFORMER AND LT PANELS | AU | 1 | 2128220 | 2128220 | 2511299.6 | 2065220.55 | 2436960.25 | 62999.45 | 2065221.21 | 2436961.03 | ZSER | 2023-01-02 | 2023-02-01
RE/0066-SOE-75 | Site Office Expenses at Sec 75 | 2010 |  | 2010 | SMARTWORLD THE EDITION | Aditya Electro Projects | 9140000093 | 30 |  |  | 2023-04-21 | SITC OF MISCELLANEOUS WORKS | AU | 1 | 300830 | 300830 | 354979.4 | 206830.86 | 244060.42 | 93999.14 | 206831.36 | 244061 | ZSER | 2023-01-02 | 2023-02-01
RE/0066-SOE-75 | Site Office Expenses at Sec 75 | 2010 |  | 2010 | SMARTWORLD THE EDITION | Aditya Electro Projects | 9140000093 | 40 |  |  | 2023-04-21 | SITC OF DG SETS | AU | 1 | 303350 | 303350 | 357953 | 239110.73 | 282150.66 | 64239.27 | 239111 | 282150.98 | ZSER | 2023-01-02 | 2023-02-01
RE/0066-SOE-75 | Site Office Expenses at Sec 75 | 2010 |  | 2010 | SMARTWORLD THE EDITION | Aditya Electro Projects | 9140000093 | 50 |  |  | 2023-04-21 | SITC OF EARTHING | AU | 1 | 484900 | 484900 | 572182 | 381419.46 | 450074.96 | 103480.54 | 381420.07 | 450075.68 | ZSER | 2023-01-02 | 2023-02-01
RE/0066-SOE-75 | Site Office Expenses at Sec 75 | 2010 |  | 2010 | SMARTWORLD THE EDITION | Aditya Electro Projects | 9140000093 | 60 |  |  | 2023-04-21 | SITC OF EXTERNAL LIGHTING | AU | 1 | 426466 | 426466 | 503229.88 | 279805.84 | 330170.89 | 146660.16 | 279806.65 | 330171.85 | ZSER | 2023-01-02 | 2023-02-01
RE/0066-SOE-75 | Site Office Expenses at Sec 75 | 2010 |  | 2010 | SMARTWORLD THE EDITION | Aditya Electro Projects | 9140000093 | 80 |  |  | 2023-04-21 | SITC OF POINT WIRING FOR GUARD ROOM | AU | 1 | 419115 | 419115 | 494555.7 | 419114.76 | 494555.42 | 0.24 | 419113.89 | 494554.39 | ZSER | 2023-01-02 | 2023-02-01
RE/0066-SOE-75 | Site Office Expenses at Sec 75 | 2010 |  | 2010 | SMARTWORLD THE EDITION | Aditya Electro Projects | 9140000093 | 90 |  |  | 2023-04-21 | SITC OF CCTV SYSTEM | AU | 1 | 262910 | 262910 | 310233.8 | 168580.06 | 198924.47 | 94329.94 | 168580.64 | 198925.16 | ZSER | 2023-01-02 | 2023-02-01
RE/0066-SOE-75 | Site Office Expenses at Sec 75 | 2010 |  | 2010 | SMARTWORLD THE EDITION | Aditya Electro Projects | 9140000093 | 100 |  |  | 2023-04-21 | EXTRA ITEM | AU | 1 | 30000 | 30000 | 35400 | 26400.04 | 31152.05 | 3599.96 | 26400 | 31152 | ZSER | 2023-01-02 | 2023-02-01
RE/0066-SOE-75 | Site Office Expenses at Sec 75 | 2010 |  | 2010 | SMARTWORLD THE EDITION | Aditya Electro Projects | 9140000093 | 110 |  |  | 2023-04-21 | SITC OF MISCELLANEOUS Amendt -2 | AU | 1 | 22118.92 | 22118.92 | 26100.33 | 22118.92 | 26100.32 | 0 | 22118.92 | 26100.32 | ZSER | 2023-01-02 | 2023-02-01
RE/0066-SOE-75 | Site Office Expenses at Sec 75 | 2010 |  | 2010 | SMARTWORLD THE EDITION | Subha Nursery | 9140000105 | 10 |  |  | 2023-05-02 | Green Area Development at Sec-75 | AU | 1 | 510640 | 510640 | 602555.2 | 452259 | 533665.62 | 58381 | 452259 | 533665.62 | ZSER | 2023-04-20 | 2023-05-05
RE/0066-SOE-75 | Site Office Expenses at Sec 75 | 2010 |  | 2010 | SMARTWORLD THE EDITION | Go Goonj Event & Travel Hub | 9140000111 | 20 |  |  | 2023-05-06 | External Signage Sector-75 office | AU | 1 | 71250 | 0 | 0 | 71250 | 84075 | 71250 | 71250 | 84075 | ZSER | 2025-01-20 | 2025-03-20
RE/0066-SOE-75 | Site Office Expenses at Sec 75 | 2010 |  | 2010 | SMARTWORLD THE EDITION | Quasar Events | 9140000112 | 10 |  |  | 2023-05-08 | External TOTEM Sector-75 office | AU | 1 | 125000 | 0 | 0 | 125000 | 147500 | 125000 | 125000 | 147500 | ZSER | 2023-05-08 | 2023-05-13
RE/0066-SOE-75 | Site Office Expenses at Sec 75 | 2010 |  | 2010 | SMARTWORLD THE EDITION | Adbrands. OOH | 9140000114 | 20 |  |  | 2023-05-09 | Barricading Art work | AU | 1 | 269100 | 0 | 0 | 269100 | 317538 | 269100 | 269100 | 317538 | ZSER | 2023-05-08 | 2023-05-15
RE/0066-SOE-75 | Site Office Expenses at Sec 75 | 2010 |  | 2010 | SMARTWORLD THE EDITION | Rahul Earth Movers | 9140000116 | 10 |  |  | 2023-05-09 | Earth Filling Front of Sector 75 Office | AU | 1 | 769500 | 769500 | 908010 | 342805.6 | 404510.61 | 426694.4 | 342805.6 | 404510.61 | ZSER | 2023-04-20 | 2023-05-19
RE/0066-SOE-75 | Site Office Expenses at Sec 75 | 2010 |  | 2010 | SMARTWORLD THE EDITION | Pahuja Aircon Pvt LtdVinay Malik | 9140000153 | 10 |  |  | 2023-06-07 | Installation AC’s Central Quality Lab | AU | 1 | 327266.5 | 327266.5 | 386174.47 | 434748.7 | 513003.47 | 107482.2 | 317346.33 | 374468.67 | ZSER | 2023-06-05 | 2023-07-05
RE/0066-SOE-75 | Site Office Expenses at Sec 75 | 2010 |  | 2010 | SMARTWORLD THE EDITION | Frontline Construction | 9140000157 | 10 |  |  | 2023-06-09 | Chain Link Fence Fixing Work | AU | 1 | 297488.6 | 297488.6 | 351036.55 | 253725.42 | 299396 | 43763.18 | 253725.06 | 299395.57 | ZSER | 2023-06-05 | 2023-06-15
RE/0066-SOE-75 | Site Office Expenses at Sec 75 | 2010 |  | 2010 | SMARTWORLD THE EDITION | Ard Infra Project | 9140000160 | 10 |  |  | 2023-06-14 | Water proofing work slab | AU | 1 | 321220 | 321220 | 379039.6 | 0 | 0 | 321220 | 0 | 0 | ZSER | 2023-06-14 | 2023-06-21
RE/0066-SOE-75 | Site Office Expenses at Sec 75 | 2010 |  | 2010 | SMARTWORLD THE EDITION | Ard Infra Project | 9140000160 | 20 |  |  | 2023-06-14 | Trasport Charges | AU | 1 | 4000 | 4000 | 4720 | 0 | 0 | 4000 | 0 | 0 | ZSER | 2023-06-14 | 2023-06-21
RE/0066-SOE-75 | Site Office Expenses at Sec 75 | 2010 |  | 2010 | SMARTWORLD THE EDITION | Sps Construction | 9140000165 | 10 |  |  | 2023-06-21 | Backfilling work at sector 79 | AU | 1 | 793316 | 793316 | 936112.88 | 793315.25 | 936112 | 0.75 | 793316 | 936112.88 | ZSER | 2023-01-12 | 2023-02-12
RE/0066-SOE-75 | Site Office Expenses at Sec 75 | 2010 |  | 2010 | SMARTWORLD THE EDITION | Frontline Construction | 9140000184 | 10 |  |  | 2023-07-21 | Civil & Foundation works sector 75 | AU | 1 | 2006863.67 | 2006863.67 | 2368099.13 | 1952022.33 | 2303386.35 | 54841.34 | 1952023.18 | 2303387.35 | ZSER | 2023-07-19 | 2023-08-03
RE/0066-SOE-75 | Site Office Expenses at Sec 75 | 2010 |  | 2010 | SMARTWORLD THE EDITION | Optimas Energy And Services | 9140000234 | 10 |  |  | 2023-12-05 | SITC WORK OF DUEL FUEL KIT | AU | 1 | 375000 | 375000 | 442500 | 375000 | 442500 | 0 | 375000 | 442500 | ZSER | 2023-11-16 | 2023-11-26
RE/0066-SOE-75 | Site Office Expenses at Sec 75 | 2010 |  | 2010 | SMARTWORLD THE EDITION | Shri baba Construction | 9140000247 | 10 |  |  | 2024-01-24 | IPS flooring in Quality Lab | AU | 1 | 292500 | 292500 | 345150 | 194641.53 | 229677 | 97858.47 | 194641.74 | 229677.25 | ZSER | 2024-01-16 | 2024-02-16
RE/0066-SOE-75 | Site Office Expenses at Sec 75 | 2010 |  | 2010 | SMARTWORLD THE EDITION | Haarish Electric vehicles | 9140000256 | 10 |  |  | 2024-02-20 | Miscellaneous MS Works | AU | 1 | 27000 | 27000 | 31860 | 27000 | 31860 | 0 | 27000 | 31860 | ZSER | 2024-02-03 | 2024-02-18
RE/0066-SOE-75 | Site Office Expenses at Sec 75 | 2010 |  | 2010 | SMARTWORLD THE EDITION | SSS Services Private Limited | 9140000263 | 10 |  |  | 2024-03-13 | Rental Of Vehicle for Quality lab | AU | 1 | 420000 | 420000 | 470400 | 316128.57 | 354064 | 103871.43 | 316120 | 354054.4 | ZSER | 2024-02-26 | 2024-07-26
RE/0066-SOE-75 | Site Office Expenses at Sec 75 | 2010 |  | 2010 | SWD Central office-75 | Gautam Techno Sanitation Private Li | 9140000298 | 20 |  |  | 2024-06-10 | Plumbing works for office sec-75 | AU | 1 | 70000 | 70000 | 82600 | 0 | 0 | 70000 | 0 | 0 | ZSER | 2024-05-31 | 2024-07-31
RE/0066-SOE-75 | Site Office Expenses at Sec 75 | 2010 |  | 2010 | SMARTWORLD THE EDITION | KD ELECTRICALS PROJECT PRIVATE LIMI | 9140000501 | 10 |  |  | 2025-09-20 | Modification of Electrical Panel at Cent | AU | 1 | 351359.7 | 351359.7 | 414604.45 | 297698.69 | 351284.45 | 53661.01 | 297698.69 | 351284.45 | ZSER | 2025-09-16 | 2025-10-16
RE/0066-SOE-75 | Site Office Expenses at Sec 75 | 2010 |  | 2010 | SMARTWORLD THE EDITION | Yadav Pest Control ServiceYogendra Yadav | 9160000033 | 10 |  |  | 2023-04-05 | 04 Months- 01st Dec to 31st March'2023) | AU | 1 | 31200 | 0 | 0 | 31200 | 36816 | 31200 | 31200 | 36816 | ZGEN | 2022-12-01 | 2023-03-31
RE/0066-SOE-75 | Site Office Expenses at Sec 75 | 2010 |  | 2010 | SMARTWORLD THE EDITION | Wings BeveragesCharanpreet | 9160000039 | 10 |  |  | 2023-04-07 | Coffee Machine on rental basis 4 month | AU | 1 | 9400 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | ZGEN | 2025-01-20 | 2025-03-20
RE/0066-SOE-75 | Site Office Expenses at Sec 75 | 2010 |  | 2010 | SMARTWORLD THE EDITION | Superior NetworksMr. Manoj (9911163201) | 9160000051 | 10 |  |  | 2023-04-26 | Sitc work for wifi & Switches | AU | 1 | 344354 | 0 | 0 | 344354 | 406337.72 | 344354 | 344354 | 406337.72 | ZGEN | 2023-04-26 | 2023-04-30
RE/0066-SOE-75 | Site Office Expenses at Sec 75 | 2010 |  | 2010 | SMARTWORLD THE EDITION | Fusionnet Web Services LimitedMs. Palak | 9160000055 | 10 |  |  | 2023-04-29 | ILL Recurring Charges_200 Mbps | AU | 1 | 455000 | 455000 | 455000 | 526575 | 526575 | 71575 | 526575 | 526575 | ZGEN | 2023-02-07 | 2024-02-06
RE/0066-SOE-75 | Site Office Expenses at Sec 75 | 2010 |  | 2010 | SMARTWORLD THE EDITION | Five Force Security Solutions PrivaLimited | 9160000068 | 20 |  |  | 2023-05-04 | Deployment of Security Manpower Sec-66 | AU | 1 | 475051 | 475051 | 560560.18 | 0 | 0 | 475051 | 0 | 0 | ZGEN | 2025-01-20 | 2025-03-20
RE/0066-SOE-75 | Site Office Expenses at Sec 75 | 2010 |  | 2010 | SMARTWORLD THE EDITION | Yadav Pest Control ServiceYogendra Yadav | 9160000084 | 10 |  |  | 2023-05-17 | Pest Control at Sec 75 Project site Offc | AU | 1 | 64050 | 64050 | 75579 | 64050.85 | 75580 | 0.85 | 64050.85 | 75580 | ZGEN | 2023-04-01 | 2024-03-31
RE/0066-SOE-75 | Site Office Expenses at Sec 75 | 2010 |  | 2010 | SMARTWORLD THE EDITION | Nuways Creation Pvt. Ltd.Ravinder | 9160000134 | 10 |  |  | 2023-06-09 | Printer | AU | 1 | 196000 | 196000 | 231280 | 190169.41 | 224399.9 | 5830.59 | 190170.86 | 224401.62 | ZGEN | 2023-04-01 | 2024-03-31
RE/0066-SOE-75 | Site Office Expenses at Sec 75 | 2010 |  | 2010 | SMARTWORLD THE EDITION | Rush EnterprisesSanjay | 9160000154 | 10 |  |  | 2023-06-16 | 500 KVA DG set | AU | 1 | 1044000 | 1044000 | 1231920 | 1044000 | 1231920 | 0 | 1044000 | 1231920 | ZGEN | 2023-03-31 | 2024-03-31
RE/0066-SOE-75 | Site Office Expenses at Sec 75 | 2010 |  | 2010 | SMARTWORLD THE EDITION | Wings BeveragesCharanpreet | 9160000160 | 10 |  |  | 2023-06-16 | CCD coffee Machine on Rental Basis | AU | 1 | 23500 | 23500 | 27730 | 25851.69 | 30505 | 2351.69 | 25853.39 | 30507 | ZGEN | 2023-04-01 | 2024-03-31
RE/0066-SOE-75 | Site Office Expenses at Sec 75 | 2010 |  | 2010 | SMARTWORLD THE EDITION | Global HR Solution ServicesV Akhilesh | 9160000169 | 10 |  |  | 2023-06-20 | Consultancy charges for HR Compliance | AU | 1 | 427500 | 427500 | 504450 | 0 | 0 | 427500 | 0 | 0 | ZGEN | 2023-03-31 | 2024-03-01
RE/0066-SOE-75 | Site Office Expenses at Sec 75 | 2010 |  | 2010 | SMARTWORLD THE EDITION | Nuways Creation Pvt. Ltd.Ravinder | 9160000192 | 10 |  |  | 2023-06-29 | Printer SHARP (Model No-BP50C26) | AU | 1 | 55000 | 55000 | 64900 | 35000 | 41300 | 20000 | 35000 | 41300 | ZGEN | 2023-05-01 | 2024-03-31
RE/0066-SOE-75 | Site Office Expenses at Sec 75 | 2010 |  | 2010 | SMARTWORLD THE EDITION | Peregrine Guarding Private LimitedSiddharth Dahiya | 9160000210 | 10 |  |  | 2023-07-10 | Man power | AU | 1 | 611780.68 | 611780.68 | 721901.2 | 611867.04 | 722003.11 | 86.36 | 611782.12 | 721902.9 | ZGEN | 2023-04-01 | 2023-06-30
RE/0066-SOE-75 | Site Office Expenses at Sec 75 | 2010 |  | 2010 | SMARTWORLD THE EDITION | Peregrine Guarding Private LimitedSiddharth Dahiya | 9160000211 | 10 |  |  | 2023-07-10 | Man power | AU | 1 | 144614.08 | 144614.08 | 170644.61 | 144614.14 | 170644.68 | 0.06 | 144614.14 | 170644.68 | ZGEN | 2023-04-01 | 2023-06-30
RE/0066-SOE-75 | Site Office Expenses at Sec 75 | 2010 |  | 2010 | SMARTWORLD THE EDITION | Safecure Services Pvt. LtdShalander | 9160000217 | 10 |  |  | 2023-07-11 | Manpower (May'23 - June'23) | AU | 1 | 313526.04 | 313526.04 | 369960.73 | 313529.64 | 369964.97 | 3.6 | 313526.4 | 369961.15 | ZGEN | 2023-05-01 | 2023-06-30
RE/0066-SOE-75 | Site Office Expenses at Sec 75 | 2010 |  | 2010 | SMARTWORLD THE EDITION | K MART BUSINESS SOLUTIONSSunny | 9160000220 | 10 |  |  | 2023-07-11 | Support manpower | AU | 1 | 4020456 | 4020456 | 4744138.08 | 0 | 0 | 4020456 | 0 | 0 | ZGEN | 2025-01-20 | 2025-03-20
RE/0066-SOE-75 | Site Office Expenses at Sec 75 | 2010 |  | 2010 | SMARTWORLD THE EDITION | Wings BeveragesCharanpreet | 9160000221 | 10 |  |  | 2023-07-11 | CCD machine on rental for 01 Year | AU | 1 | 24127.45 | 24127.45 | 28470.39 | 24127.97 | 28471 | 0.52 | 24129.19 | 28472.45 | ZGEN | 2023-04-01 | 2024-03-31
RE/0066-SOE-75 | Site Office Expenses at Sec 75 | 2010 |  | 2010 | SMARTWORLD THE EDITION | K MART BUSINESS SOLUTIONSSunny | 9160000222 | 10 |  |  | 2023-07-11 | Support manpower | AU | 1 | 3087900 | 3087900 | 3643722 | 0 | 0 | 3087900 | 0 | 0 | ZGEN | 2023-04-01 | 2024-03-31
RE/0066-SOE-75 | Site Office Expenses at Sec 75 | 2010 |  | 2010 | SMARTWORLD THE EDITION | K MART BUSINESS SOLUTIONSSunny | 9160000228 | 10 |  |  | 2023-07-12 | Rider Conveyance | AU | 1 | 360000 | 360000 | 424800 | 0 | 0 | 360000 | 0 | 0 | ZGEN | 2023-04-01 | 2024-03-31
RE/0066-SOE-75 | Site Office Expenses at Sec 75 | 2010 |  | 2010 | SMARTWORLD THE EDITION | K MART BUSINESS SOLUTIONSSunny | 9160000228 | 20 |  |  | 2023-07-12 | Management Fees( 4.5%) | AU | 1 | 16200 | 16200 | 19116 | 0 | 0 | 16200 | 0 | 0 | ZGEN | 2023-04-01 | 2024-03-31
RE/0066-SOE-75 | Site Office Expenses at Sec 75 | 2010 |  | 2010 | SMARTWORLD THE EDITION | Updater Services limited | 9160000250 | 10 |  |  | 2023-07-18 | MANPOWER (JULY'23 – MARCH’24) | AU | 1 | 1852993.8 | 1852993.8 | 2186532.68 | 2061617.39 | 2432708.52 | 208623.59 | 2046635.85 | 2415030.3 | ZGEN | 2025-01-20 | 2025-03-20
RE/0066-SOE-75 | Site Office Expenses at Sec 75 | 2010 |  | 2010 | SMARTWORLD THE EDITION | Updater Services limited | 9160000250 | 20 |  |  | 2023-07-18 | MANPOWER(APRIL'23 – JUNE’23) | AU | 1 | 582368.85 | 582368.85 | 687195.24 | 180649.15 | 213166 | 401719.7 | 180614.71 | 213125.36 | ZGEN | 2025-01-20 | 2025-03-20
RE/0066-SOE-75 | Site Office Expenses at Sec 75 | 2010 |  | 2010 | SMARTWORLD THE EDITION | Dagar Power Projects Pvt. ltd. | 9160000254 | 10 |  |  | 2023-07-20 | DG Service at 75 Office | AU | 1 | 9548.3 | 9494.75 | 11203.81 | 9542.29 | 11259.9 | 47.54 | 9542.29 | 11259.9 | ZGEN | 2023-07-20 | 2023-07-20
RE/0066-SOE-75 | Site Office Expenses at Sec 75 | 2010 |  | 2010 | SMARTWORLD THE EDITION | Dagar Power Projects Pvt. ltd. | 9160000254 | 10 |  |  | 2023-07-20 | DG Service at 75 Office | AU | 1 | 0 | 53.55 | 56.23 | 10723.71 | 11259.9 | 10670.16 | 10723.71 | 11259.9 | ZGEN | 2023-07-20 | 2023-07-20
RE/0066-SOE-75 | Site Office Expenses at Sec 75 | 2010 |  | 2010 | SMARTWORLD THE EDITION | G4S SECURE SOLUTIONS (INDIA) PVT LT | 9160000267 | 10 |  |  | 2023-07-28 | Hiring of Manpower for Security | AU | 1 | 2042911.42 | 2042911.42 | 2410635.48 | 2032892.86 | 2398813.58 | 10018.56 | 2042912.92 | 2410637.25 | ZGEN | 2023-06-29 | 2024-06-30
RE/0066-SOE-75 | Site Office Expenses at Sec 75 | 2010 |  | 2010 | SMARTWORLD THE EDITION | Tecknomen Facility Services Pvt. LtDwarka | 9160000269 | 10 |  |  | 2023-07-28 | Support manpower | AU | 1 | 2725046.42 | 2725046.42 | 3215554.78 | 2725044.35 | 3215552.33 | 2.07 | 2725037.8 | 3215544.6 | ZGEN | 2023-04-01 | 2024-03-31
RE/0066-SOE-75 | Site Office Expenses at Sec 75 | 2010 |  | 2010 | SMARTWORLD THE EDITION | Tecknomen Facility Services Pvt. LtDwarka | 9160000315 | 10 |  |  | 2023-08-09 | Rider Conveyance | AU | 1 | 192980 | 192980 | 227716.4 | 192979.69 | 227716.04 | 0.31 | 192978.81 | 227715 | ZGEN | 2023-04-01 | 2024-03-31
RE/0066-SOE-75 | Site Office Expenses at Sec 75 | 2010 |  | 2010 | SMARTWORLD THE EDITION | Tecknomen Facility Services Pvt. LtDwarka | 9160000315 | 20 |  |  | 2023-08-09 | Management Fees( 4.5%) | AU | 1 | 8665 | 8665 | 10224.7 | 8682.49 | 10245.34 | 17.49 | 8665.27 | 10225.02 | ZGEN | 2023-04-01 | 2024-03-31
RE/0066-SOE-75 | Site Office Expenses at Sec 75 | 2010 |  | 2010 | SMARTWORLD THE EDITION | Anand Kumar Electrical | 9160000317 | 20 |  |  | 2023-08-10 | DHBVN Temporary connection Works | AU | 1 | 401755 | 401755 | 474070.9 | 351229.48 | 414450.79 | 50525.52 | 351261.1 | 414488.1 | ZGEN | 2023-08-09 | 2023-09-15
RE/0066-SOE-75 | Site Office Expenses at Sec 75 | 2010 |  | 2010 | SMARTWORLD THE EDITION | Anand Kumar Electrical | 9160000317 | 30 |  |  | 2023-08-10 | Amend -1 Extra Item | AU | 1 | 46200 | 46200 | 54516 | 46200.18 | 54516.21 | 0.18 | 46200 | 54516 | ZGEN | 2023-08-09 | 2023-09-15
RE/0066-SOE-75 | Site Office Expenses at Sec 75 | 2010 |  | 2010 | SMARTWORLD THE EDITION | SHIVATMIKA PROJECTSBIJENDER SINGH | 9160003064 | 10 |  |  | 2026-05-04 | Developement of Green Belt-Office -75 | AU | 1 | 1104100 | 1104100 | 1302838 | 464279.66 | 547850 | 639820.34 | 464280.48 | 547850.97 | ZGEN | 2026-03-31 | 2026-04-01
[16 empty] | 11113635607.07 | 13058762937.48